Version control

| Document number | Comments |
| --- | --- |
| Version 1 | Issued by Sport England at initial stage of consultation (May 2012). |
| Version 2 | Updated following consultation feedback and reissued to consultation groups (April 2013). |
| Version 3 | Updated following further consultation and issued on Sport England website (May 2013). |
| This version | Updated following further consultation and issued on Sport England website (May 2016) |

DATED	20[   ]

[NAME OF LOCAL AUTHORITY]

and

[CONTRACTOR] LIMITED

DESIGN BUILD OPERATE AND MAINTAIN CONTRACT

in respect of [describe the leisure facilities]

CONTENTS

Clause	Subject matter	Page

PART 1 – PRELIMINARY	1

1	Definitions and Interpretation	1

2	Exclusion of Legislation	50

3	Commencement and Duration	51

4	Collateral Warranties [and Surveys] [and Guarantees]	51

5	General Warranties	52

6	Authority Warranties	55

7	Documents and Co-Operation	56

PART 2 – LAND ISSUES	58

8	Nature of Land Interests	58

PART 3 – TRANSITIONAL ARRANGEMENTS	61

9	[Initial Services]	61

10	The Works	61

11	Construction Programme	66

12	Representatives	68

13	Site Meetings and Risk Management	69

14	Design Development	71

15	Changes to the Construction Proposals and the Construction Programme	72

16	Extensions Of Time	72

17	CDM Regulations	77

18	The Site[s]	78

19	Monitoring and Inspection	91

20	Notification of Services Availability [and/or Acceptance of Post Completion Works]	93

21	Delay And Supervening Unavailability	98

PART 4 – THE SERVICES	100

22	Principal Obligations	100

23	Condition of the [Facility/Facilities]	101

24	Hazardous Substances	107

25	Emergencies	107

26	Performance Monitoring	108

27	Benchmarking	109

28	Use Of The [Facility/Facilities] [and Surplus Share]	109

29	TUPE and Employees	110

30	Pensions	125

31	Employees – General	135

32	Operating Manual	139

33	Quality Assurance	139

34	Co-operation For Investigation And Security	141

35	Service Delivery Proposals	141

PART 5 - PAYMENT	142

36	Payment during the Works Period	142

37	Payment during the Services Period	145

38	Continuous Improvement	150

PART 6 - TERMINATION	153

39	Termination of this Agreement	153

40	Termination for Persistent Breach by the Contractor	155

41	Termination on Corrupt Gifts and Fraud	156

42	Termination On Force Majeure	158

43	Consequences of Termination	160

44	Surveys on Expiry and Retention Fund	161

45	Transition To Another Contractor	163

PART 7 - COMPENSATION ON TERMINATION	165

46	Compensation on Termination for Authority Default/Voluntary Termination	165

47	Compensation on Termination for Contractor Default and Corrupt Gifts and Fraud	166

48	Not used	167

49	Compensation on Termination for Force Majeure	167

50	Assets	167

51	Retendering Process	168

52	Miscellaneous Compensation Provisions	169

53	Method of Payment	170

PART 8 - GENERAL	172

54	Liaison	172

55	Relief Events	172

56	Change in Law	175

57	Authority and Contractor Changes	177

58	Authority Step-In	177

59	Freedom of Information and Confidentiality	179

60	Indemnities, Guarantees and Contractual Claims	185

61	Insurance	187

62	Reinstatement and Change of Requirement after Insured Event	194

63	Risks that Become Uninsurable	197

64	Dispute Resolution	202

65	Ordering of Goods and Services	207

66	Intellectual Property	207

67	Assignment and Sub-Contracting	209

68	Change In Ownership	213

69	Financial Adjustments	213

70	Audit Access	217

71	No Agency	217

72	Entire Agreement	217

73	Notices	218

74	Severability	219

75	Waiver	219

76	Public Relations and Publicity	219

77	Advertisements	220

78	Contractor's Records	220

79	Data Protection	222

80	Interest on Late Payment	223

81	Governing Law and Jurisdiction	223

82	Sole Remedy	223

83	No Double Recovery	224

84	Counterparts	224

85	Construction Industry Scheme	225

86	Capacity	225

SCHEDULE 1 AUTHORITY'S REQUIREMENTS	226

Part 1A – Facilities Requirements	226

Part 1B – Technical Specification	226

Part 2 – [Initial Services Specification]	226

Part 3 – Services Specification	226

SCHEDULE 2 CONTRACTOR'S PROPOSALS	227

Part 1 – Construction Proposals	227

Part 2 – Service Delivery Proposals	227

Part 3 – Construction Programme	227

SCHEDULE 3 NOT USED	228

SCHEDULE 4 [FACILITY/FACILITIES]	229

SCHEDULE 5 COMPLETION REQUIREMENTS	230

Part 1 – Services Availability Requirements	230

Part 2 – [Post Completion Works Acceptance Requirements]	232

SCHEDULE 6 PAYMENT AND PERFORMANCE MONITORING SYSTEM	233

SCHEDULE 7 COLLATERAL WARRANTIES	284

Part 1  Warranty from the Contractor's Building Contractor	285

Part 2  Warranty from Principal Building Sub-Contractors	301

Part 3  Warranty from members of the Professional Team	317

Part 4  Warranty from the Contractor's FM Contractor	331

Part 5  Warranty from the Contractor's Leisure Operator	343

SCHEDULE 8 REVIEW PROCEDURE	355

SCHEDULE 9	363

Part 1 – Prohibited Materials	363

Part 1 – Works Stipulations	363

SCHEDULE 10 LIAISON PROCEDURE	365

SCHEDULE 11 [WARRANTED] DATA	370

Part 1 – Authority Data	371

Part 2 – Contractor Warranted Data	373

Part 3 – Proposed Workforce Information	374

SCHEDULE 12 INDICATIVE PAYMENT SCHEDULE	375

SCHEDULE 13 TITLE MATTERS	376

Part 1 – Title Warranties	376

Part 2 – Disclosed Title Matters	377

Part 3 – Replies to Enquiries	378

Part 4 – Disclosed Searches	379

Insurances	381

SCHEDULE 14 Insurances	381

Part 1	382

Part 2	387

Part 3	392

Part 4	395

Part 5	409

SCHEDULE 15 AUTHORITY'S POLICIES	410

SCHEDULE 16 [AUTHORITY PLANNING CONDITIONS]	411

SCHEDULE 17 PROJECT DOCUMENTS AND ANCILLARY DOCUMENTS	412

Part 1 Project Documents	412

Part 2 Ancillary Documents	412

SCHEDULE 18 BENCHMARKING	413

SCHEDULE 19 SURPLUS SHARE	462

SCHEDULE 20 EQUALITY REQUIREMENTS	468

SCHEDULE 21 CONFIDENTIAL INFORMATION	470

Part 1 – Commercially Sensitive Contractual Provisions	470

Part 2 – Commercially Sensitive Material	470

SCHEDULE 22 BULK TRANSFER TERMS	471

SCHEDULE 23 LOSS OF REVENUE	477

SCHEDULE 24 CHANGE PROTOCOL	482

Part 1 – Definitions	482

Part 2 – Small Value Changes	486

Part 3 – Medium Value Changes	490

Part 4 – High Value Changes	497

Part 5 – Contractor Changes	512

Part 6 – Partial Termination	514

SCHEDULE 25 BASE CASE	517

SCHEDULE 26 LOBTA	518

SCHEDULE 27 NNDR	519

SCHEDULE 28 SITE PLAN[S]	527

SCHEDULE 29 HEADLEASE[S]	528

SCHEDULE 30 HANDBACK	539

This Agreement is made on [                                     ]

Between

      - [Name of Local Authority] of [Address of Local Authority] (the Authority); and

      - [Contractor] Limited (company registration number [                         ]) whose registered office is at [                                                      ] (the Contractor).

Background

        - By an advertisement dated [                         ] in the Supplement to the Official Journal of the European Union, the Authority sought proposals for the provision of leisure and associated services.

        - The Authority has selected the Contractor to carry out the Project.

        - The Authority is a Best Value Authority under the Local Government Act 1999 and the functions in respect of which the Authority wishes to procure the delivery of the Project are Best Value functions.

Part 1 – Preliminary

- Definitions and Interpretation

  - Definitions

In this Agreement and in the Background unless the context otherwise requires the following terms shall have the meanings given to them below:

1999 Act

the Local Government Act 1999;

Abandon`

not to carry out any Works contemplated by the Construction Programme at a Site for twenty (20) consecutive Business Days or during sixty (60) Business Days (whether consecutive or not) in any Contract Year;

Acceptance Certificate

the certificate issued by the Independent Certifier confirming the Services Availability Requirements have been met;

Actual Relevant Insurance Cost

the aggregate of the [annual] insurance premiums reasonably incurred by the Contractor to maintain the Relevant Insurance during the Insurance Review Period but excluding insurance premium tax and all broker's fees and commissions;

Adjoining Property

any land and/or property adjoining or in the neighbourhood of the Site[s] and each and every part thereof including all conduits, roads, footpaths, walls, fences, buildings and other erections and all service media and other apparatus on, under or within such land and/or property;

Adjudicator

has the meaning given to it in clause 64.4 (Adjudication);

Adjusted Amount

has the meaning given to it in clause 63.5.4 (Unavailability of terms or conditions)

Admission Body

means an admission body for the purposes of paragraph 1 of Part 3 of Schedule 2 of the LGPS Regulations;

Administering Authority

[name of administering authority] Council of [address] acting in its capacity as the administering authority of the [name of relevant LGPS fund] for the purposes of the LGPS Regulations;

Adverse Rights

any interests, rights, covenants, restrictions, stipulations, easements, customary or public rights, local land charges, mining or mineral rights, franchise, manorial rights and any other rights or interests in or over land, in each case whether or not registered that would, if exercised, prevent or disrupt the carrying out of the Works and/or the provision of the Services;

Affected Party

has the meaning given to it in the definition of Force Majeure Event in this clause 1.1 (Definitions and Interpretation);

Affiliate

in relation to any person, any holding company or subsidiary of that person or any subsidiary of such holding company, and holding company and subsidiary shall have the meaning given to them in Section 1159 of the Companies Act 2006;

Agreed Form

in relation to any document, the form of the document agreed between the parties and initialled by or on behalf of the parties for the purpose of identification;

Agreement

this agreement (including its Schedules);

Amended Reinstatement Outline

has the meaning given to it in clause 62.3.3 (Obligations);

Ancillary Documents

the documents listed in Part 2 of Schedule 17 (Project Documents and Ancillary Documents);

Ancillary Rights

- a non-exclusive licence to enter and remain upon those parts of the Sites that the Contractor and/or any Contractor Related Party requires access to in order to carry out the Works or provide the Services;

- such rights of access to and egress from the Sites as are necessary for the Contractor and any Contractor Related Party to perform their obligations and exercise their rights under this Agreement and in particular for the purposes of implementing the Works and providing the Services including those highlighted [  ] on the Site Plans provided that such rights may be varied by the Authority and such variation will be deemed to be a [Medium Value Change];

- rights of free and uninterrupted passage and running of water soil gas electricity telephone and other services including those highlighted [   ] on the Site Plans provided that such rights of passage may be varied by the Authority to such alternative routes as the Authority may reasonably specify from time to time and such variation will be deemed to be a [Medium Value Change]; and

- the right where necessary to inspect repair maintain or renew the Services Media and the right (at the cost of the Contractor) to connect into the Services Media and to construct such new Services Media as may from time to time be necessary to serve the Sites provided that the prior written consent of the Authority is obtained (such consent not to be unreasonably withheld or delayed);

provided that

- the rights are granted insofar as the Authority is capable of granting them and such rights are subject to the Disclosed Title Matters, Disclosed Searches and Replies to Enquiries; and

- the rights shall not in any circumstances entitle the Contractor or any Contractor Related Party to exclusive occupancy or exclusive possession of any part of the Sites (save as may be required by the Contractor and approved by the Authority (such approval not to be unreasonably withheld or delayed) in order to comply with relevant health and safety legislation) on a temporary basis;

Annual Payment

the fee payable under this Agreement calculated in accordance with Schedule 6 (Payment and Performance Monitoring System);

Annual Service Plan

has the meaning given to it in clause 38.2.4 (Annual Service Report and Service Plan);

Annual Service Report

has the meaning given to it in clause 38.2.1 (Annual Service Report and Annual Service Plan);

Annual Service Report Date

the date on which the Annual Service Report is required to be submitted pursuant to the Services Specification;

Approved Purposes

has the meaning given to it in clause 66.1 (Project Data);

Approved RDD Item

an item of Reviewable Design Data which has been returned or deemed to have been returned marked "no comment" or "proceed subject to amendment" under the Review Procedure;

Asbestos

has the meaning given to it in the Control of Asbestos Regulations 2006;

Asbestos Survey[s]

the [surveys];

Asbo

an injunction or criminal behaviour order issued in accordance with the Anti-Social Behaviour Crime and Policing Act 2014;

As-built Drawings

drawings, technical information, models, operation and maintenance manuals and technical information of a like nature to encompass the method of construction, manufacture, operation and maintenance of each element of [the/each] Facility in sufficient detail to allow a competent person to understand all material elements of the construction of [the/each] Facility and to maintain, dismantle, reassemble, adjust and operate all plant, equipment, fixtures, structures and construction elements thereof;

Assets

all assets and rights to enable the Authority or a successor contractor to own, operate and maintain [the/each] Facility in accordance with this Agreement including:

- any land or buildings;

- any equipment;

- any books and records (including operating and maintenance manuals, health and safety manuals and other know how);

- any spare parts, tools and other assets (together with any warranties in respect of assets being transferred);

- any revenues and any other contractual rights; [and]

- any Intellectual Property Rights subject to and in accordance with clause 66 (Intellectual Property)[; and

- [additional Project specific requirements, such as maintenance records, membership details/bulk transfer of direct debit details]],

but excluding any assets and rights in respect of which the Authority is full legal and beneficial owner;

Assigned Employees

has the meaning given to it in clause 29.8 (Retendering);

Authority Change

has the meaning given to it in the Change Protocol;

Authority Default

one of the following events:

- an expropriation, sequestration or requisition of a material part of the Assets and/or shares of the Contractor [or Holdco] by the Authority or other Relevant Authority;

- a failure by the Authority to make payment(s) of an amount of money exceeding (in aggregate) [                         ] (from time to time) that is due and payable by the Authority under this Agreement within twenty (20) Business Days of service of a formal written demand by the Contractor, where the amount fell due and payable one (1) (or more) months prior to the date of service of the written demand;

- a breach by the Authority of its obligations under this Agreement which substantially frustrates or renders it impossible for the Contractor to perform its obligations under this Agreement for a continuous period of [two (2)] months; or

- a breach by the Authority of clause 67.1 (Restrictions on Transfer of this Agreement by the Authority);

Authority Existing Employee

in relation to any service equivalent to any of the Services, all those persons employed by the Authority under a contract of employment (excluding to avoid doubt (without limitation) any person engaged by the Authority as an independent contractor or persons employed by any sub-contractor engaged by the Authority) who are wholly or substantially engaged in the provision of that service as at the Service Transfer Date;

Authority Necessary Consents

[                                                   ] ;

Authority Notice of Change

has the meaning given to it in the Change Protocol;

[Authority Planning Conditions

those conditions set out in Schedule 16 (Authority Planning Conditions]) ;

Authority Pricing Requirements

the Authority's pricing requirements, as set out in [paragraph 120 and Appendix 3] of the Services Specification;

Authority Related Party

- an officer, agent, contractor, employee or sub-contractor (of any tier) of the Authority acting in the course of his office or employment; and

- any person visiting a Facility at the invitation (express or implied) of the Authority,

but excluding in each case the Users, the Contractor and any Contractor Related Parties;

[Authority Warranted Data

the information set out or described in Part 1 of Schedule 11 ([Warranted] Data);]

Authority's Policies

the policies of the Authority referred to in Schedule 15 (Authority's Policies);

Authority's Representative

the representative appointed by the Authority pursuant to clause 12 (Representatives);

Authority's Requirements

the requirements of the Authority in respect of the Project set out in Schedule 1 (Authority's Requirements);

Barred List

the barred lists provided for under the Safeguarding Vulnerable Groups Act 2006 as amended by the Protection of Freedoms Act 2012;

Base Case

the financial model included at Schedule 25 (Base Case) and agreed between the parties prior to the date of this Agreement (as updated from time to time in accordance with the terms of this Agreement) for the purpose of, amongst other things, calculating the Annual Payment;

Base Cost

[£     ] being the amount as agreed at the [Pricing Reference Date] and set out in the Base Case which represents the insurance cost (which excludes amounts in respect of insurance premium tax and all brokers' fees and commissions) which are proposed to be incurred to maintain the Relevant Insurance in each year following the [first/final] Services Availability Date, expressed in real terms as at the [Pricing Reference Date];

Base Relevant Insurance Cost

means the aggregate of the Base Costs which were, (at the [Pricing Reference Date]) projected to be incurred to maintain the Relevant Insurance during the Insurance Review Period indexed by actual CPI from the [Pricing Reference Date] up to the dates on which the Relevant Insurance was placed or renewed either immediately before or during the Insurance Review Period (as applicable in respect of the year in question) less any Base Relevant Insurance Reduction;

Base Relevant Insurance Reduction

the reduction to be made to the Base Relevant Insurance Cost in respect of a risk which has become Uninsurable or a term or condition which is no longer available and shall be an amount that is either:

- the amount by which the Base Relevant Insurance Cost would have been a lesser amount had such a risk been Uninsurable or a term or condition been unavailable at the [Pricing Reference Date] (which amount, for the avoidance of doubt, can be £0); or

- if it is impossible to determine an amount pursuant to paragraph (a) above, an amount that is reasonable to be deducted from the Base Relevant Insurance Cost having due regard to:

  - the amount by which the Actual Relevant Insurance Cost is less than it would have been as a result of the risk becoming Uninsurable or the term or condition becoming unavailable (the Actual Reduction);

  - the size of the Actual Reduction as a percentage of the Actual Relevant Insurance Cost immediately prior to the risk becoming Uninsurable or the term or condition becoming unavailable; and

  - the effects of CPI since the [Pricing Reference Date];

Base Surplus Amount

the Annual Payment as shown in [Base Case/LOBTA] (in the form of the [Base Case/LOBTA] included at the Commencement Date without any adjustment) for a Contract Year (indexed);

Bond

[                                           ];

Building

any building or other erection at [any of] the Site[s];

Building Contract

subject to clause 7.1 (Ancillary Documents) the contract in the Agreed Form between the Contractor and the Building Contractor relating to the Works;

Building Contract Dispute

has the meaning given to it in clause 64.16.1 (Similar Disputes);

Building Contractor

[INSERT NAME AND COMPANY REGISTERED NUMBER], or such other building contractor as the Contractor may, subject to clauses 7 (Documents and Co-Operation) and 67 (Assignment and sub-contracting), appoint to carry out the Works;

Building Contractor's Site Manager

the manager to be appointed by the Building Contractor for the purposes of supervision of all day to day activities on the Site[s];

Building Contractor's Site Rules

the Building Contractor's rules, applicable on the Sites to the Authority, the Contractor, the Building Contractor and their respective sub-contractors and suppliers of every tier during the construction of the Facilities;

Building Manual

the manual for the Works containing:

Part 1

a copy of the health and safety file pursuant to the CDM Regulations (excluding those aspects of the same as fall within Part 2)

Part 2

- all As-built Drawings;

- copies of all guarantees, warranties and maintenance agreements relating to the Works;

- copies of all test certificates relating to the Works;

- copies of all manufacturers' technical literature relating to the Works; and

- copies of all operating and maintenance manuals relating to the Works;

Buildings Survey[s]

[                                                                           ];

Business Day

a day (other than a Saturday or Sunday) on which banks are open for domestic business in the City of London;

Business Interruption Insurance

has the meaning given to it in paragraph 2 of Part 2 of Schedule 14 (Insurances);

[Capital Costs

the sum the Contractor has invested or may invest in the Project as permitted in accordance with this Agreement at written down value, as shown in the Contractor's accounts [and/or (without double counting) the Leisure Operator's accounts] to the extent such capital costs have not been paid or accounted for in the [Base Case/LOBTA] when calculating the Annual Payment up to the Termination Date or via another payment pursuant to this Agreement, [subject to a cap of [(£)];]

Capital Expenditure

any expenditure which falls to be treated as capital expenditure in accordance with generally accepted accounting principles in the United Kingdom from time to time, International Financial Reporting Standards from time to time, or proper accounting practices for local authorities as defined by section 21(2) of the Local Government Act 2003 and Regulation 31 of the Local Authorities (Capital Finance and Accounting) (England) Regulations 2003;

CDM Regulations

the Construction (Design and Management) Regulations 2015;

Certificate of Making Good Defects

has the meaning given to it in clause 20.8.5 (Defects liability);

Cessation Date

any date on which the Contractor or the relevant Sub-Contractor ceases to be an Admission Body other than as a result of the termination of this Agreement or because it ceases to employ any Eligible Employees;

Change

has the meaning given to it in the Change Protocol;

Change in Costs

in respect of any Relevant Event, the effect of that Relevant Event (whether of a one-off or recurring nature, and whether positive or negative) upon the actual or anticipated costs, losses or liabilities of the Contractor and/or any Sub-Contractors (without double counting), including, as relevant, the following:

- the reasonable costs of complying with the requirements of clauses 16 (Extensions of Time), 56 (Change in Law), 58.4 (Step-In without Contractor Breach), 69 (Financial Adjustments) and the Change Protocol, including the reasonable costs of preparation of design and estimates;

- the costs of continued employment of, or making redundant, staff who are no longer required;

- the costs of employing additional staff;

- reasonable professional fees;

- the costs to the Contractor of financing any Relevant Event (and the consequences thereof) including commitment fees and capital costs interest and hedging costs, lost interest on any of the Contractor's own capital employed and any finance required pending receipt of a lump sum payment or adjustments to the Annual Payment;

- the effects of costs on implementation of any insurance reinstatement in accordance with this Agreement, including any adverse effect on the insurance proceeds payable to the Contractor (whether arising from physical damage insurance or business interruption insurance (or their equivalent)) in respect of that insurance reinstatement and any extension of the period of implementation of the insurance reinstatement;

- construction costs, operating costs, lifecycle costs, maintenance costs or replacement costs;

- Capital Expenditure (or, in the case of a Relevant Event which is a Qualifying Change in Law, Capital Expenditure for which the Authority is responsible);

- any deductible or increase in the level of deductible, or any increase in premium under or in respect of any insurance policy; and

- Direct Losses or Indirect Losses, including reasonable legal expenses on an indemnity basis;

Change in Law

the coming into effect after the date of this Agreement of:

- Legislation, other than any Legislation which on the date of this Agreement has been published:

  - in a draft Bill as part of a Government Departmental Consultation Paper;

  - in a Bill;

  - in a draft statutory instrument; or

  - as a proposal in the Official Journal of the European Communities;

- any Guidance; or

- any applicable judgment of a relevant court of law which changes a binding precedent;

Change in Ownership

- any sale, transfer or disposal of any legal, beneficial or equitable interest in any or all of the shares in the Contractor [and/or Holdco] [and/or           [    ]] (including the control over the exercise of voting rights conferred on those shares, control over the right to appoint or remove directors or the rights to dividends); and/or

- any other arrangements that have or may have or which result in the same effect as paragraph (a);

Change in Revenue

in respect of any Relevant Event, the effect of that Relevant Event (whether or a one-off or recurring nature, and whether positive or negative) upon the actual or anticipated income of the Contractor and/or any Sub-Contractor save that any Loss of Revenue shall be calculated in accordance with Schedule 23 (Loss of Revenue);

Change Protocol

means the procedure set out in Schedule 24 (Change Protocol);

Collateral Warranty

a collateral warranty executed as a deed between the Authority and (as the case may be) the Building Contractor, a Principal Building Sub-Contractor, a member of the Professional Team, the Leisure Operator or the FM Contractor in the relevant form as set out in Schedule 7 (Collateral Warranties);

Commencement Date

[the date of this Agreement];

Commercially Sensitive Information

the subset of Confidential Information listed in column 1 of Part 1 (Commercially Sensitive Contractual Provisions) and column 1 of Part 2 (Commercially Sensitive Material) of Schedule 21 (Confidential Information) in each case for the period specified in the respective columns 2 of Parts 1 and 2 of Schedule 21;

Compensation Event

- the occurrence on or before the relevant Services Availability Date [or (in relation to the Post Completion Works) on or before the date of the Post Completion Works Acceptance Certificate] of a breach by the Authority of any of its obligations or of any warranty under this Agreement;

- the occurrence during the Services Period of a breach by the Authority of the following provisions:

  - clause 8.9 (Compliance with Head Lease);

  - [clause 18.2.5.4 (Site Matters)];

  - [clause 18.3A (Authority Necessary Consents and Planning Approval)];

  - clause 18.8.7 (Fossils and antiquities);

  - clause 23.2.3 (Surveys);

  - clause 37 (Payment during the Services Period);

  - clause 44.2 (Minimisation of Disruption);

  - clause 61.3 (Obligation on Parties);

  - Schedule 8 (Review Procedure) (insofar as applicable to the Services Period); and

- any other event or circumstance identified as a Compensation Event in this Agreement;

Confidential Information

- information that ought to be considered as confidential (however it is conveyed or on whatever media it is stored) and includes information whose disclosure would, or would be likely to, prejudice the commercial interests of any person, trade secrets, Intellectual Property Rights and know-how of either party and all personal data and sensitive personal data within the meaning of the DPA 1998; and

- Commercially Sensitive Information;

Construction Panel

has the meaning given to it in clause 64.4.1 (Identity of Adjudicator);

Construction Period Insurance

the Required Insurance in respect of the period from the date of this Agreement to the Services Availability Date for [the/each] Facility;

Construction Programme

the programme for the carrying out of the Works as contained in Part 3 of Schedule 2 (Contractor's Proposals) as updated from time to time in accordance with clause 11 (Construction Programme) or Schedule 8 (Review Procedure);

Construction Proposals

the proposals for the [provision/refurbishment] of the [Facility/Facilities] to satisfy the Authority's Requirements as set out in Schedule 2 Part 1 (Construction Proposals);

Contamination

all or any pollutants or contaminants, including any chemical or industrial, radioactive, dangerous, toxic or hazardous substance, waste or residue (whether in solid, semi-solid or liquid form or a gas or vapour);

Continuation Notice

has the meaning given to it in clause 42.6 (Notice to Continue);

Continuous Improvement Duty

the duty imposed on the Authority to secure continuous improvement in the exercise of the Authority's functions, having regard to a combination of economy, efficiency and effectiveness in relation to, inter alia, the Services, pursuant to the 1999 Act;

Continuous Improvement Service Change Notice

has the meaning given to it in clause 38.2.3 (Annual Service Report and Annual Service Plan);

Contract Month

any month in a Contract Year provided that:

- the first Contract Month shall commence on the Services Availability Date and end on the last day of the month in which the Services Availability Date occurs; and

- the last Contract Month shall begin on the first day of the month in which the last day of the Services Period occurs and end on that day;

Contract Period

the period from and including the Commencement Date to the Expiry Date, or if earlier, the Termination Date;

Contract Sum

the lump sum price as identified in Schedule 12 (Indicative Payment Schedule) as adjusted (if at all) in accordance with this Agreement;

Contract Year

a period of twelve (12) months commencing on [1 April], provided that:

- the first Contract Year shall be the period commencing on the Services Availability Date and ending on the immediately following [31 March]; and

- the final Contract Year shall be the period commencing on [1 April] immediately preceding the last day of the Contract Period and ending on that day;

Contractor Admission Agreement

an admission agreement entered into in accordance with paragraph 1 of Part 3 of Schedule 2 of the LGPS Regulations by the Administering Authority, the Authority and the Contractor or a Sub-Contractor (as appropriate);

Contractor Change

has the meaning given in the Change Protocol;

Contractor Default

any one or more of the following:

- following the Services Availability Date for [a Facility/the Facility] a breach by the Contractor of any of its obligations under this Agreement which materially and adversely affects the performance of the Services;

- a Persistent Breach occurs;

- a court makes an order that the Contractor [or Holdco] be wound up or a resolution for a voluntary winding-up of the Contractor [or Holdco] is passed;

- any receiver or receiver manager in respect of the Contractor [or Holdco] is appointed or possession is taken by or on behalf of any creditor of any property of the Contractor [or Holdco] that is the subject of a charge;

- any voluntary arrangement is made for a composition of debts or a scheme of arrangement is approved under the Insolvency Act 1986 or the Companies Act 2006 in respect of the Contractor [or Holdco];

- an administration order is made or an administrator is appointed in respect of the Contractor [or Holdco];

- failure to comply with clause 67.2 (Restriction on the Contractor) or clause 68 (Change in Ownership);

- the Contractor Abandons the Works at any time;

- [the Contractor has not commenced the Works by the Start on Site Date;]

- the Acceptance Certificate [for each Facility] has not been issued by the Longstop Date;

- [in any [three (3) month] period the Contractor has incurred [            ] or more Performance Adjustment Points;]

- [in each and every month of any [six (6)] month period the Contractor has incurred [            ] or more Performance Adjustment Points;]

- not used;

- subject to clause 63 (Risks that become Uninsurable) a breach by the Contractor of its obligations to take out and maintain any of the Required Insurances;

- the Contractor committing a material breach of its obligations under this Agreement (other than as a consequence of a breach by the Authority of its obligations under this Agreement) which results in the criminal investigation, prosecution and conviction of the Contractor or any Contractor Related Party or the Authority under the Health and Safety Regime (an H&S Conviction) provided that an H&S Conviction of a Contractor Related Party or the Authority shall not constitute a Contractor Default if, within ninety (90) Business Days from the date of the H&S Conviction (whether or not the H&S Conviction is subject to an appeal or any further judicial process), the involvement in the Project of each relevant Contractor Related Party (which in the case of an individual director, officer or employee shall be deemed to include the Contractor Related Party of which that person is a director, officer or employee) is terminated and a replacement is appointed by the Contractor in accordance with clause 67.2 (Restriction on the Contractor) provided always that in determining whether to exercise any right of termination or right to require the termination of the engagement of a Contractor Related Party under this limb (o), the Authority shall:

  - act in a reasonable and proportionate manner having regard to such matters as the gravity of any offence and the identity of the person committing it; and

  - give all due consideration, where appropriate, to action other than termination of this Agreement; or

- [the Post Completion Works Acceptance Certificate has not been issued in respect of [each/the] Site by the Post Completion Works Longstop Date;]

Contractor Defects

any defect or fault in the Works, the New Buildings and/or the Facilities (not being a Snagging Item) which occurs due to a failure by the Contractor to meet the Facilities Requirements or the Construction Proposals or otherwise comply with its obligations under this Agreement;

Contractor Defects Liability Period

the period of twelve (12) months commencing on the date of issue of the Acceptance Certificate [or Post Completion Works Acceptance Certificate] for the Works [or Post Completion Works] or relevant part thereof;

Contractor IPR

any Intellectual Property Rights created by or on behalf of the Contractor, [the Building Contractor, the Leisure Operator or the FM Contractor] in respect of, in each case, their:

- brand names, trademarks, trade names, designs, logos, domain names and name;

- know-how and business systems;

- quality management procedures and customer care programme;

- sales and customer retention products and processes;

- corporate policies and training documentation;

- intranet, integrated management system and supporting documentation; and

- Service Delivery Proposals;

but excluding:

  - the Operating Manual;

  - any User or member database relevant to the [Facility/Facilities]; and

  - any booking system used at and in respect of the [Facility/Facilities];

Contractor Notice of Change

has the meaning given in the Change Protocol;

Contractor Related Party

- an officer, servant or agent of the Contractor, or any Affiliate of the Contractor and any officer, servant or agent of such a person;

- any Sub-Contractor or other sub-contractor of the Contractor of any tier and any of their officers, servants or agents; and

- any person on or at [any of] the [Facility/Facilities] at the express or implied invitation of the Contractor (other than an Authority Related Party or a User);

Contractor Termination Notice

has the meaning given to it in clause 39.2.1 (Termination on Authority Default);

Contractor's Supply Chain

the Building Contractor, the Professional Team and the Principal Building Sub-Contractors engaged in relation to the Works;

Contractor Warranted Data

the information relating to the Contractor and its Affiliates contained in Part 2 of Schedule 11 (Warranted Data);

Contractor's Proposals

the proposals of the Contractor to deliver the Project to satisfy the Authority's Requirements, as set out in Schedule 2 (Contractor's Proposals), and as amended pursuant to this Agreement;

Contractor's Representative

the person to be appointed by the Contractor pursuant to clause 12 (Representatives);

Contractor's Scheme

the occupational pension scheme(s) established or to be established under clause 30.7 (Contractor Scheme) of this Agreement;

Convictions

other than in relation to any minor road traffic offences, any previous or pending prosecutions, convictions, cautions and binding overs (including any spent convictions as contemplated by section 1(1) of the Rehabilitation of Offenders Act 1974 by virtue of the exemptions specified in Part II of Schedule 1 of the Rehabilitation of Offenders Act 1974 (Exemptions) Order 1975 (SI 1975/1023) or any replacement or amendment to that Order);

COSHH

the Control of Substances Hazardous to Health Regulations 2002;

CPI

the index published in Table 1 of the monthly Statistical Bulletin "Consumer price indices" published by the Office for National Statistics or failing such publication or in the event of a fundamental change to the index, such other index as the parties may agree, or such adjustments to the index as the parties may agree (in each case with the intention of putting the parties in no better nor worse position than they would have been in had the index not ceased to be published or the relevant fundamental change not been made) or, in the event that no such agreement is reached, as may be determined in accordance with clause 64 (Dispute Resolution) of this Agreement;

CRC Scheme

the emissions reduction scheme currently regulated by the CRC Energy Efficiency Scheme Order 2013 as amended from time to time, or such other emissions reduction scheme introduced from time to time having the same or similar effect;

Current Annual Payment

the Annual Payment that would have been payable had this Agreement not terminated as a result of Contractor Default;

Defects

any defect in any of the Buildings, or any part of them, or anything installed in the Buildings attributable to:

- defective design;

- defective workmanship or defective materials [(which, for the avoidance of doubt, shall exclude Asbestos)], plant or machinery used in such construction having regard to Good Industry Practice and to appropriate British standards and codes of practice current at the date of construction of the Building;

- the use of materials in the construction of any Building which (whether or not defective in themselves) prove to be defective in the use to which they are put in the construction of any such Building;

- defective installation of anything in or on the Buildings;

- defective preparation of the site on which the Building is constructed; or

- defects brought about by adverse ground conditions or by reason of subsidence, water table change or any other change to ground conditions;

Deficit Annual Payment

the Annual Payment where it is a negative number

Design Data

all drawings, reports, documents, plans, software, formulae, calculations and other data relating to the design, construction, testing or operation of the [Facility/Facilities] in each case that is used by or on behalf of the Contractor and/or its sub-contractors in connection with the provision of the Works or Services or the performance of the Contractor's obligations under this Agreement;

Directive

the EC Acquired Rights Directive 77/187 as amended;

Direct Losses

all damage, losses, liabilities, claims, actions, costs, expenses (including the cost of legal or professional services, legal costs being on an indemnity basis), proceedings, demands and charges whether arising under statute, contract or at common law but excluding Indirect Losses;

DISU/BI Proceeds

Delay in start up or Business Interruption Insurance proceeds;

Disclosed Data

information relating to the Project disclosed to the Contractor [and its Shareholders] and advisers before the date of this Agreement including:

- [                                           ];

- the data room located at [INSERT DETAILS]; and

- [others];

Disclosed Searches

the searches listed in Part 4 of Schedule 13 (Title Matters);

Disclosed Title Matters

the matters set out in Part 2 of Schedule 13 (Title Matters);

Disclosure and Barring Scheme

the disclosure and barring scheme operated by the Disclosure and Barring Service;

Disclosure and Barring Service

the non-departmental public body established pursuant to the Protection of Freedoms Act 2012;

Discriminatory Change in Law

a Change in Law, the terms of which apply expressly to:

- the Project and not to similar projects;

- the Contractor and not to other persons; and/or

- persons who have contracted with the Government, a Local Authority or other public or statutory body to provide services under a public private partnership arrangement and not to other persons;

Disputed Amount

has the meaning given to it in clause 37.5.3 (Disputed Amounts);

Dispute Resolution Procedure

the procedure for the resolution of disputes set out in clause 64 (Dispute Resolution);

DPA

the Data Protection Act 1998;

Elections

such local, regional or national elections or referenda that the Authority or its returning office is statutorily required to administer;

Eligible Employees

- the Transferring Employees who are active members of or eligible to join the LGPS on a Relevant Transfer Date;

- the Transferring Original Employees who are active members of or eligible to join either the LGPS or a broadly comparable scheme provided by their existing employer on a Relevant Transfer Date; and

- [any other individuals nominated by the Contractor or Sub-Contractor (as appropriate)]23,

- for so long as they are employed in connection with the provision of the Services or part of such Services;

Emergency

an event causing or, in the reasonable opinion of a party, threatening to cause death or injury to any individual, or serious disruption to the lives of a number of people or extensive damage to property, or contamination of the environment in each case on a scale beyond the capacity of the emergency services, or preventing the Services operating under normal circumstances and requiring the mobilisation and organisation of the emergency services;

Employee Liability Information

the information which a transferor is obliged to notify a transferee pursuant to Regulation 11(2) of TUPE regarding any person employed by him who is assigned to the organised grouping of resources or employees which is the subject of the Relevant Transfer and also such employees as fall within Regulation 11(4) of TUPE;

[Employment and Skills Method Statement

the method statement produced by the Contractor and forming part of the Construction Proposals and which sets out in detail how the Contractor shall implement the Employment and Skills Plan;]

[Employment and Skills Plan

the employment and skills plan produced by the Contractor and forming part of the Construction Proposals to be complied with and implemented by the Contractor in order to execute the Employment and Skills Strategy;]

[Employment and Skills Strategy

the Authority's Employment and Skills Strategy as set out in section [  ] of the Facilities Requirements;]

Energy

electricity, gas or other fuel to which the CRC Scheme applies;

Environmental Information Regulations

means the Environmental Information Regulations 2004 together with any guidance and/or codes of practice issued by the Information Commissioner or relevant Government Department in relation to such regulations;

Equalities Legislation

the Racial and Religious Hatred Act 2006, the Civil Partnership Act 2004, the Sex Discrimination (Gender Reassignment) Regulations 1999; the Gender Recognition Act 2004; the Employment Equality (Sex Discrimination) Regulations 2005; the Employment Equality (Age) Regulations 2006 and (Amendment) Regulations 2008, the Equality Act 2006; and the Equality Act 2010;

Equality Requirements

the requirements set out in Schedule 20 (Equality Requirements);

Estimated Increased Maintenance Costs

has the meaning given to it in clause 23.4.7 (Schedule of Programmed Maintenance);

European Economic Area

from time to time the European Economic Area as created by The Agreement on the European Economic Area 1992 or any successor or replacement body, association, entity or organisation which has assumed either or both the function and responsibilities of the European Economic Area;

Exceptional Cost

for an Insurance Review Period, the extent to which there is an Insurance Cost Increase which exceeds in amount [5%–30%] of the Base Relevant Insurance Cost for that Insurance Review Period;

Exceptional Saving

for an Insurance Review Period, the extent to which there is an Insurance Cost Decrease which exceeds in amount [5%–30%] of the Base Relevant Insurance Cost for that Insurance Review Period;

Existing Facility

a [facility/facilities] (listed in Schedule 4 ([Facility/Facilities]), excluding any new facilities comprising the Works);

Expiry Date

[•];

Facility

the [facility/facilities] listed in Schedule 4 ([Facility/Facilities]) being the buildings and other facilities to be provided, maintained and serviced in accordance with this Agreement located on and consisting of the Site[s];

Facilities Requirements

the requirements of the Authority in relation to the provision of the [Facility/Facilities] set out in Part 1A of Schedule 1 (Authority's Requirements);

Fees Regulations

the Freedom of Information and Data Protection (Appropriate Limit and Fees) Regulations 2004;

Final Employee List

has the meaning given to it in clause 29.4.2 (Employment Costs);

Final Warning Notice

has the meaning given to it in clause 40.2 (Final Notice);

First Contractor

the person with whom the Authority initially contracted for the provision of services which are similar to the Services;

First Employee List

has the meaning given to it in clause 29.4.1 (Employment Costs);

First Insurance Review Date

the first Business Day following the date of the first anniversary of the Relevant Insurance Inception Date;

Five Year Maintenance Plan

the five year maintenance plan provided by the Contractor to the Authority in accordance with clause 23.4.9 (Schedule of Programmed Maintenance);

FM Agreement

subject to clause 7.1 (Ancillary Documents) the agreement in the Agreed Form between the Contractor and the FM Contractor relating to the Maintenance Services;

FM Agreement Dispute

has the meaning given to it in clause 64.16.2 (Similar Disputes);

FM Contractor

[INSERT NAME AND COMPANY NUMBER], or such other facilities management contractor as the Contractor may, subject to clauses 7 (Documents and Co-Operation) and 67 (Assignment and sub-contracting), appoint to provide the Maintenance Services;

FOIA

the Freedom of Information Act 2000 and any subordinate legislation (as defined in Section 84 of the Freedom of Information Act 2000) made under the Freedom of Information Act 2000 from time to time together with any guidance and/or codes of practice issued by the Information Commissioner or relevant Government Department in relation to such Act;

FOIA Code

has the meaning given to it in clause 59.10.8 (Freedom of Information);

Force Majeure Event

the occurrence after the date of this Agreement of:

- war, civil war, armed conflict or terrorism; or

- nuclear, chemical or biological contamination unless the source or cause of the contamination is as a result of any act by the Contractor or its sub-contractors or any breach by the Contractor of the terms of this Agreement; or

- pressure waves caused by devices travelling at supersonic speeds,

which directly causes either party (the Affected Party) to be unable to comply with all or a material part of its obligations under this Agreement;

[Forward Funded Amount

means the amount profiled in Row [     ] of the [Base Case/LOBTA] up to the Termination Date (as adjusted in accordance with this Agreement) less the actual Annual Payment [paid by the Contractor] up to the Termination Date;]

Fund

the [                          ] Pension Fund;

Future Contractor

shall have the meaning given to it in clause 29.6.4 (Indemnities);

General Change in Law

a Change in Law which is not a Discriminatory Change in Law or a Specific Change in Law;

Good Industry Practice

that degree of skill, care, prudence and foresight and operating practice which would reasonably and ordinarily be expected from time to time of a skilled and experienced operator (engaged in the same type of undertaking as that of the Contractor) or facilities management contractor or building contractor or leisure operator or any sub-contractor under the same or similar circumstances;

Gross Valuation

has the meaning given to it in clause 36.3.2;

Guidance

any applicable guidance or directions with which the Contractor is bound to comply;

Handback Requirements

[the requirements relating to the condition of the [Facility/Facilities] set out in section [       ] of the Services Specification][the requirement that the [Facility/Facilities] [have/has] been maintained in accordance with the terms of this Agreement];

Head Lease

the lease[s] relating to the Site[s] to be granted by the Authority to the Contractor in the Agreed Form as set out at Schedule 29 (Headlease[s]);

Health and Safety File

has the meaning given to it in the CDM Regulations;

Health and Safety Regime

the Food Safety Act 1990 (and associated regulations), the Health & Safety at Work etc. Act 1974 (and associated regulations), the Regulatory Reform (Fire Safety) Order 2005, the Environmental Protection Act 1990, the Water Industry Act 1991, the Environment Act 1995, the Pollution Prevention and Control Act 1999 and any similar or analogous health, safety or environmental legislation in force from time to time;

HGCRA

means the Housing Grants Construction and Regeneration Act 1996 as amended by Part 8 of the Local Democracy, Economic Development and Construction Act 2009;

[Holdco]

[insert details of the Contractor's one hundred per cent (100%) holding company if any];

Holding Company

has the meaning given to it in Section 1159 of the Companies Act 2006;

Home Office Guidance

guidance issued by the Home Office relating to the level and nature of Criminal Records Bureau checks or the Disclosure and Barring Scheme (as appropriate at that time) that should be undertaken with respect to staff employed at the [Facility/Facilities];

Indemnified Party

has the meaning given to it in clause 60.4 (Notification of Claims);

Indemnifying Party

has the meaning given to it in clause 60.4 (Notification of Claims);

Independent Certifier

the person appointed jointly by the Authority and the Contractor to act as independent certifier to the Project in accordance with the Independent Certifier's Deed of Appointment;

Independent Certifier's Deed of Appointment

the deed of appointment of the Independent Certifier in the Agreed Form;

Index

has the meaning given to it in the definition of CPI in this clause 1.1 (Definitions);

Indicative Payment Schedule

means the schedule setting out details of the anticipated profile of payments due on each monthly period during which the Works are being carried out as identified in Schedule 12 (Indicative Payment Schedule) as may be adjusted in accordance with this Agreement;

Indirect Losses

loss of profits, loss of use, loss of production, loss of business, loss of business opportunity, or any claim for consequential loss or for indirect loss of any nature but excluding any of the same that relate to loss of Revenue;

Information

has the meaning given to it under Section 84 of the FOIA;

Initial Contribution Rate

[                                           ] per cent ([    ]%) of the Eligible Employees Pensionable Pay;

[Initial Phase]

[in relation to [a/the] Facility, the period from and including the Services Start Date until and excluding the Services Availability Date [for that Facility]];

[Initial Services]

[the services required to satisfy the requirements of the Initial Services Specification];

[Initial Services Specification]

[the specification contained in Part 2 of Schedule 1 (Authority's Requirements)];

Instalment Dates

has the meaning given to it in clause 53.2 (Instalments);

Insurance Cost Decrease

the Insurance Cost Differential if the value is less than zero, multiplied by minus one;

Insurance Cost Differential

shall, subject to the Insurance Review Procedure, be determined as follows:

Insurance Cost Differential = (ARIC – BRIC) – PIC

where:

ARIC is the Actual Relevant Insurance Cost;

BRIC is the Base Relevant Insurance Cost;

PIC is any Project Insurance Change;

Insurance Cost Increase

the Insurance Cost Differential if the value thereof is greater than zero;

Insurance Cost Index

any index introduced by the United Kingdom Government or the Office of National Statistics after the date of this Agreement and which is anticipated to be published annually to provide an independent and objective measure of changes in prevailing market insurance costs;

Insurance Review Date

the First Insurance Review Date and, thereafter, each date falling on the second anniversary of the previous Insurance Review Date, except where such date lies beyond the end of the Contract Period, in which case the Insurance Review Date shall be the last renewal date of the Relevant Insurances prior to the end of the Contract Period;

Insurance Review Period

a two year period from the Relevant Insurance Inception Date and each subsequent two year period commencing on the second anniversary of the Relevant Insurance Inception Date except where the end of such period lies beyond the end of the Contract Period, in which case the Insurance Review Period shall be the period from the end of the penultimate Insurance Review Period to the last day of the Contract Period;

Insurance Review Procedure

the procedure set out in clause 61.15 (Insurance Review Procedure).

Insurance Term

means any terms and/or conditions required to be in a policy of insurance by clause 61 (Insurance) and/or Schedule 14 (Insurances) but excluding any risk;

Intellectual Property Rights

any and all patents, trade marks, service marks, copyright, database rights, moral rights, rights in a design, know-how, confidential information and all or any other intellectual or industrial property rights whether or not registered or capable of registration and whether subsisting in the United Kingdom or any other part of the world together with all or any goodwill relating or attached thereto which is created, brought into existence, acquired, used or intended to be used by the Contractor or any Contractor Related Party for the purposes of carrying out the Works and/or providing the Services and/or otherwise for the purposes of this Agreement;

Intervening Contract

a contract with the Authority for the provision of services which are similar to the Services, at times after they were provided under a contract with the First Contractor and before they are to be provided by the Contractor;

Irrecoverable VAT

has the meaning given to it in clause 56.7 (Payment of Irrecoverable VAT);

Joint Insurance Account

the joint bank account in the names of both the Authority and the Contractor, having account number [INSERT NUMBER] and held with [INSERT NAME];

Joint Insurance Cost Report

has the meaning given to it in clause 61.15 (Insurance Review Procedure);

[Judicial Review Proceedings

the grant of permission for an application and any subsequent application for judicial review or related process under Part 54 of the Civil Procedure Rules in respect of the [planning permission(s);]

[Judicial Review Proceedings Action

any court order or declaration made by a relevant court (including without limitation the granting of an injunction) arising out of or in connection with any Judicial Review Proceedings that renders unlawful and/or prevents the performance of all or part of the Contractor's obligations under this Agreement;]

LAD Amount

in relation to [a/the] Facility the amount [per day] shown in the column so headed in Schedule 4 ([Facility/Facilities]) against [that/the] Facility;

Legislation

any one or more of the following:

- any Act of Parliament;

- any subordinate legislation within the meaning of Section 21(1) of the Interpretation Act 1978;

- any exercise of the Royal Prerogative; and

- any enforceable community right within the meaning of Section 2 of the European Communities Act 1972,

in each case in the United Kingdom;

Leisure Contract

subject to clause 7.1 (Documents and Co-operation), the agreement in the Agreed Form between the Contractor and the Leisure Operator relating to the Leisure Services;

Leisure Contract Dispute

has the meaning given to it in clause 64.16.3 (Similar Disputes);

Leisure Operator

[INSERT NAME AND COMPANY NUMBER] or such other leisure operator as the Contractor may, subject to clauses 7 (Documents and Co-operation) and 67 (Assignment and Sub-Contracting), appoint to provide the Leisure Services;

Leisure Operator's Base Trading Account or LOBTA

the financial model of the Leisure Operator set out at Schedule 26 (LOBTA);

Leisure Services

the services set out in the Services Specification other than the Maintenance Services;

LGPS or Local Government Pension Scheme

the Local Government Pension Scheme as established by the LGPS Regulations;

LGPS Regulations

the Local Government Pension Scheme Regulations 2013 (SI 2013/2356) as amended, re-enacted or re-instated from time to time;

Lifecycle Assets

each item of building fabric, plant and machinery, furniture, fittings and equipment to be renewed or replaced during the Services Period as identified in the Lifecycle Schedule within the Schedule of Programmed Maintenance or as may be identified by the parties applying Good Industry Practice;

Lifecycle Schedule

the detailed annual lifecycle schedule showing when the Lifecycle Assets will be renewed or replaced, and forming part of the Schedule of Programmed Maintenance;

Local Authority

a principal council (as defined in Section 270 of the Local Government Act 1972) or any body of government in England established as a successor to principal councils in relation to leisure services;

Lock-in Period

the period ending on the date that is [one (1)] year after the [final] Services Availability Date;

Longstop Date

the date [nine (9)] [twelve (12)] months after the [last] Planned Services Availability Date or such later date as may be allowed in accordance with the terms of this Agreement;

Losses

all damages, losses, liabilities, costs, expenses (including legal and other professional charges and expenses) and charges whether arising under statute, contract or at common law, or in connection with judgments, proceedings, internal costs or demands;

Loss of Revenue

the decrease in Revenue (whether of a one-off or recurring nature) arising as a direct result of a Loss of Revenue Event or Relevant Event calculated and paid in accordance with Schedule 23 (Loss of Revenue);

Loss of Revenue Event

an event occurring pursuant to one or more of the following:

- clause 23.4.7 (Schedule of Programmed Maintenance);

- clause 25.2 (Emergencies);

- clause 42.6.1 (Termination on Force Majeure); or

- clause 58.4 (Step-In without Contractor Breach);

Maintenance Services

those services set out in [paragraphs 1.16 and 1.17] of the Services Specification;

Maintenance Works

any works of maintenance or repair of the [Facility/Facilities] that are necessary to ensure that the [Facility/Facilities] are maintained in accordance with the Services Specification and Service Delivery Proposals and the [Facility/Facilities] comply with the Authority's Requirements and the Construction Proposals (including, without limitation, the renewal or replacement of any plant and equipment) throughout the Services Period;

Medium Value Change

has the meaning given to it in the Change Protocol;

Method Statement

the Contractor's method statements in relation to the Services as included in the Service Delivery Proposals;

Minimum Opening Hours

the hours of required opening of the [Facility/Facilities] to Users as set out in [paragraph 121 and Appendix 1] of the Services Specification;

Monthly Payment

has the meaning given in Schedule 6 (Payment and Performance Monitoring System);

Named Employee

has the meaning given to it in clause 31.1 (Disclosure and Barring);

Necessary Consents

all permits, licences, permissions, consents, approvals, certificates and authorisations (whether statutory or otherwise) which are required for the performance of any of the Contractor's obligations under this Agreement, whether required in order to comply with Legislation or as a result of the rights of any third party [excluding Authority Necessary Consents];

New Buildings

any Buildings constructed pursuant to the terms of this Agreement;

New Contractor

the person who has entered or who will enter into the Retendered Contract with the Authority following termination of this Agreement or the person who has entered or will enter into a new contract with the Authority following the expiry of this Agreement;

New Employer

has the meaning given to it in clause 30.13 (Transfer to another Employer);

Notice of Adjudication

has the meaning given to it in clause 64.3 (Adjudication);

Notice of Non-Completion

has the meaning given to it in clause 20.4.2 (Issue of Acceptance Certificate or notice of Non Completion);

Notified Sum

has the meaning given to it in clause 36.5.1 (Payment notice)

Operating Manual

has the meaning given to it in clause 32.1 (Maintenance of Manual);

Operational Panel

has the meaning given to it in clause 64.4.1 (Identity of Adjudicator);

Option Period

has the meaning given to it in clause 63.3.2 (Consequences)

Original Employee

those employees of the Authority who as a result of the application of TUPE in relation to what was done for the purposes of carrying out the contract between the Authority and the First Contractor became employees of someone other than the Authority;

Outstanding Work

has the meaning given to it in clause 44.4 (Maintenance Work);

Parent Company

means:

- [in the case of the Building Contractor, [                                   ] or such other person as shall guarantee the obligations of the Building Contractor as permitted by this Agreement;

- in the case of the Leisure Operator, [                                   ] or such other person as shall guarantee the obligations of the Leisure Operator as permitted by this Agreement; and

- in the case of the FM Contractor, [                                   ] or such other person as shall guarantee the obligations of the FM Contractor as permitted by this Agreement;]

[Parent Company Guarantee

the guarantee of the Parent Company in the Agreed Form;]

Partial Termination Authority Notice of Change

has the meaning given to it in the Change Protocol;

Past Service Reserve

means the actuarial value, calculated on the basis that the provisions of Section 67 of the Equality Act 2010 applies directly to the Local Government Pension Scheme or Contractor Scheme (the Transferring Scheme), of the aggregate of the benefits, whether immediate, prospective or contingent, payable under the Transferring Scheme to and in respect of each transferring member, his spouse and dependants, by reference to pensionable service in the Transferring Scheme, but making proper allowance for projected increases in the rate of pensionable salary of each transferring member from the cessation of pensionable service to the expected date of withdrawal, retirement or death and increases (whether or not pursuant to a legal obligation) in pensions in payment using demographic and actuarial assumptions which are overall no less conservative than those adopted for the most recent funding valuation of the Transferring Scheme;

Pay Less Notice

has the meaning given to it in clause 36.6 (Pay Less Notice);

Payment and Performance Monitoring System

means the payment and performance monitoring system set out in Schedule 6 (Payment and Performance Monitoring System);

Payment Period

each calendar month or (in the case of the first and final Payment Period) part thereof during the Contract Period;

Pensionable Pay

shall have the same meaning as "Pensionable Pay" as defined in the LGPS Regulations;

Performance Adjustment

has the meaning given to it in the Payment and Performance Monitoring System;

Performance Adjustment Points

has the meaning given to it in the Payment and Performance Monitoring System;

Persistent Breach

a breach for which a Final Warning Notice has been issued which has continued for more than [fourteen (14)] days or recurred in [three (3)] or more months within the [six (6)] month period after the date on which such Final Warning Notice is served on the Contractor;

Personal Data

personal data as defined in the DPA which is supplied to the Contractor by the Authority or obtained by the Contractor in the course of performing the Services;

Physical Damage Policies

has the meaning given to it in clause 62.1 (Reinstatement and Change of Requirement After Insured Event);

PI Insurance

has the meaning given to it in clause 61.13 (Professional Indemnity Insurance);

[Planned Post Completion Works Acceptance Date

in relation to [each/the] Site, the date shown as the corresponding Planned Post Completion Works Acceptance Date in Schedule 4 ([Facility/Facilities]) or such other date as may be allowed in accordance with the terms of this Agreement;]

Planned Services Availability Date

in relation to [the/each] Facility the date shown as the Planned Services Availability Date in Schedule 4 ([Facility/Facilities]) or such later date as may be allowed in accordance with the terms of this Agreement;

Portfolio Cost Saving

any insurance cost saving which arises from the Contractor changing the placement of the Required Insurances from being on a stand alone project-specific basis assumed at the [Pricing Reference Date] and reflected in the Base Cost, to being on the basis of a policy (or policies) also covering risks on other projects or other matters which are outside the scope of the Project so as to benefit from portfolio savings. A Portfolio Cost Saving is defined to be a positive sum and cannot be less than zero;

[Post Completion Works

in relation to [each/the] Site, those parts of the Works to be completed after the Services Availability Date in accordance with the Construction Programme;]

[Post Completion Works Acceptance Certificate

in respect of [a/the] Site, a certificate issued by the Independent Certifier confirming that the Post Completion Works Acceptance Requirements in respect of [that/the] Site have been met;]

[Post Completion Works Acceptance Date

in relation to any Post Completion Works in respect of [a/the] Site, the date on which the Post Completion Works Acceptance Certificate is issued;]

[Post Completion Works Acceptance Requirements

in relation to [a/the] Site, the satisfaction of the relevant tests set out in Part 2 of Schedule 5 (Completion Requirements);]

[Post Completion Works Longstop Date

the date [•] months after the Planned Post Completion Works Acceptance Date;]

Prescribed Rate

two per cent (2%) above the base rate from time to time of [INSERT NAME] Bank plc;

Pricing Reference Date

[                                                              ];

Principal Building Sub-Contractor

any sub-contractor appointed by the Building Contractor to undertake the design and/or construction of any of the following parts of the Works:

- [                                           ];

Professional Team

the architects, structural engineers, mechanical and electrical engineers, acoustic engineers and [•] employed by the Building Contractor in connection with the Works [and any employer's agent employed by the Contractor];

Profit Payment

the loss of profit suffered by the Contractor [and/or without double counting the Leisure Operator] as a result of termination of this Agreement pursuant to clause 39.1 (Voluntary termination by the Authority) or clause 39.2 (Termination on Authority Default) for the period of [          ] months from the date of termination or the period to the Expiry Date (whichever is shorter) (as shown at Schedule 25 (Base Case)), subject to a cap of [                               ];

Programmed Maintenance

the maintenance work and lifecycle replacement which the Contractor is to carry out in accordance with the Schedule of Programmed Maintenance;

Programmed Maintenance Information

has the meaning given to it in clause 23.4.3 (Schedule of Programmed Maintenance);

Prohibited Act

- offering, giving or agreeing to give to any servant of the Authority any gift or consideration of any kind as an inducement or reward:

  - for doing or not doing (or for having done or not having done) any act in relation to the obtaining or performance of this Agreement or any other contract with the Authority; or

  - for showing or not showing favour or disfavour to any person in relation to this Agreement or any other contract with the Authority;

- entering into this Agreement or any other contract with the Authority in connection with which commission has been paid or has been agreed to be paid by the Contractor or on its behalf, or to its knowledge, unless before the relevant contract is entered into particulars of any such commission and of the terms and conditions of any such contract for the payment thereof have been disclosed in writing to the Authority; or

- committing any offence:

  - under the Bribery Act 2010;

  - under Legislation creating offences in respect of fraudulent acts;

  - at common law in respect of fraudulent acts in relation to this Agreement or any other contract with the Authority; or

- defrauding or attempting to defraud or conspiring to defraud the Authority;

Project

the provision and operation of serviced accommodation to the Authority at [each and every Facility/the Facility] by the Contractor as contemplated by this Agreement including the carrying out of the Works and the provision of the Services;

Project Data

- all Design Data; and

- any other materials, documents or data acquired, brought into existence or used in relation to the Works, the Services or this Agreement,

in each case that is used by or on behalf of the Contractor and/or its sub-contractors in connection with the provision of the Works or Services or the performance of the Contractor's obligations under this Agreement;

Project Documents

the documents listed in Part 1 of Schedule 17 (Project Documents and Ancillary Documents);

Project Insurance Change

any net increase (which shall be expressed as a positive number) or net decrease (which shall be expressed as a negative number) in the Actual Relevant Insurance Cost relative to the Base Relevant Insurance Cost, arising from:

- the claims history or re-rating of the Contractor or any Contractor Related Party;

- the effect of any change in deductibles unless the following applies:-

  - such change is attributable to circumstances generally prevailing in the Relevant Insurance Market; and

  - the deductible further to such change is either greater than or equal to the maximum in Schedule 14 (Insurances);

- any other issue or factor other than circumstances generally prevailing in the Relevant Insurance Market, except for any Portfolio Cost Saving.

For the purpose of determining the Insurance Cost Differential, in the event that there is a net increase, the Project Insurance Change shall have a positive value. In the event that there is a net decrease the Project Insurance Change shall have a negative value;

Project Liaison Group

has the meaning given to it in paragraph 1.1 of Schedule 10 (Liaison Procedure);

Proposed Workforce

has the meaning given to it in clause 29.4.4.1 (Employment Costs);

Protected Characteristics

has the meaning given to it in Part 2, Chapter 1 of the Equality Act 2010;

Qualification Criteria

the criteria that the Authority requires tenderers to meet as part of the Retendering Process, which (subject to compliance with the procurement regulations) shall be:

- the Retendered Contract terms;

- tenderers should have the financial ability to deliver the Works and/or Services for the price tendered;

- the tenderer is experienced in providing the Works and/or Services or similar services;

- the technical solution proposed by the tenderers is capable of delivery and the tenderer is technically capable of delivery of the Works and/or Services; and

- any other tender criteria agreed by the Authority and the Contractor;

Qualifying Change in Law

- a Discriminatory Change in Law;

- a Specific Change in Law; or

- a General Change in Law, which comes into effect after the final Services Availability Date and which involves Capital Expenditure,

which was not foreseeable at the date of this Agreement;

Quest

the UK Quality Scheme for Sport and Leisure of the same name (supported by, inter alia, Sport England) or any successor scheme thereto that is supported by Sport England (or its successors);

Recipient

has the meaning given to it in clause 37.11.2 (VAT on Payments);

Redundancy Costs

means the statutory notice and redundancy payments, any accrued but untaken holiday pay and any contractual notice and redundancy payments that were inherited by the Contractor or Sub-Contractor as result of each Relevant Transfer pursuant to clause 29.1.1 (Relevant Transfers);

Referral Notice

has the meaning given to it in clause 64.5 (Referral of the Dispute);

Referring Party

has the meaning given to it in clause 64.3 (Adjudications);

Reinstatement Plan

has the meaning given to it in clause 62.3.5 (Obligations);

Reinstatement Outline

has the meaning given to it in clause 62.3.1 (Obligations);

Reinstatement Works

has the meaning given to it in clause 62.3.1 (Obligations);

Relevant Authority

any court with the relevant jurisdiction and any local, national or supra-national agency, inspectorate, minister, ministry, official or public or statutory person of the government of the United Kingdom or of the European Union;

Relevant Employees

the employees who are the subject of a Relevant Transfer;

Relevant Event

an Authority Change, Qualifying Change in Law, Compensation Event, step-in without Contractor breach pursuant to clause 58.4.2 (Step-In  Without Contractor Breach) or other matter as a result of which there may be an adjustment to the Annual Payment in accordance with clause 69 (Financial Adjustments);

Relevant Incident

has the meaning given to it in clause 62.3 (Obligations);

Relevant Insurance

the Required Insurance and any other insurances as may be required by law other than:

- Construction Period Insurance;

- Business Interruption Insurance except to the extent that it relates to [Unavoidable Fixed Costs/loss of Revenue]; and

- [any ancillary insurances];

Relevant Insurance Inception Date

the date on which the Relevant Insurances are first providing active insurance cover to the Contractor, being a date no earlier than the [relevant] Services Availability Date;

Relevant Insurance Market

the insurance market in the United Kingdom;

Relevant Legislation

has the meaning given to it in clause 85.4 (Construction industry scheme);

Relevant Month

has the meaning given to it in clause 36.2 (Applications for payment);

Relevant Payment

has the meaning given to it in clause 63.3.2 (Consequences);

Relevant Proceeds

any amounts standing to the credit of the Joint Insurance Account in accordance with clause 62.3.6.2;

[Relevant Service Transfer

[                                           ];]

Relevant Transfer

a relevant transfer for the purposes of TUPE;

Relevant Transfer Date

the date on which an Eligible Employee transfers to the Contractor and/or a Sub-Contractor by virtue of a Relevant Transfer;

Relief Event

any of the following:

- fire, explosion, lightning, storm, tempest, flood, bursting or overflowing of water tanks, apparatus or pipes, ionising radiation (to the extent it does not constitute a Force Majeure Event), earthquakes, riot and civil commotion;

- failure by any statutory undertaker, utility company, local authority or other like body to carry out works or provide services;

- any accidental loss or damage to the Site[s] or any roads servicing them;

- any failure or shortage of power, fuel or transport;

- any blockade or embargo which does not constitute a Force Majeure Event; or

- any:

  - official or unofficial strike;

  - lockout;

  - go-slow; or

  - other dispute,

generally affecting the construction or facilities management industry or a significant sector of the local authority leisure management industry in the United Kingdom but not including industrial action specific to the Site[s] or industrial action which affects only the employees of the Contractor or its Sub-Contractors; [or]

- [the discovery of fossils, antiquities or human remains requiring action in accordance with clause 18.8 (Fossils and Antiquities)],

unless any of the events listed in paragraphs (a) to (g) inclusive arises (directly or indirectly) as a result of any wilful default or wilful act of the Contractor or any of its Sub-Contractors;

Remuneration Costs

has the meaning given to it in clause 29.4.4.2 (Employment Costs);

Reorganisation Costs

has the meaning given to it in clause 29.4.4.3 (Employment Costs);

Replies to Enquiries

the matters set out in Part 3 of Schedule 13 (Title Matters);

Representative

the Authority's Representative or the Contractor's Representative (as appropriate);

Request for Information

shall have the meaning set out in the FOIA or the Environmental Information Regulations as relevant (where the meaning set out for the term "request" shall apply);

Required Action

has the meaning given to it in clause 58.3 (Action by Authority);

Required Insurances

the insurances specified in Schedule 14 (Insurances);

Required Standard

has the meaning given to it in clause 44.3.1 (Results of Survey);

Responding Party

has the meaning given to it in clause 64.5 (Referral of the Dispute);

Response

has the meaning given to it in clause 64.6 (Response to the Referral);

Retendered Annual Payment

has the meaning given to it in clause 51.7 (Retendering Process);

Retendered Contract

an agreement entered into following the Retendering Process with a replacement contractor on substantially similar terms and conditions as and which are no more onerous as regards the Contractor than this Agreement at the Termination Date, but with the following amendments:

- if this Agreement is terminated during the Works Period, then the [relevant] Planned Services Availability Dates shall be extended by a period to allow a New Contractor to achieve completion of the Works at the Facility [in question];

- any accrued Performance Adjustment Points and/or Performance Adjustments and/or warning notices issued pursuant to clause 40 (Termination for Persistent Breach by the Contractor) shall, for the purposes of termination only, and without prejudice to the rights of the Authority to make financial adjustments, be cancelled;

- the term of such agreement shall be equal to the term from the Termination Date to the Expiry Date;

- any other amendments which do not adversely affect the Contractor;

Retendered Works Remuneration Amount

has the meaning given to it in clause 51.7 (Retendering Process);

Retendering Costs

the reasonable and proper costs of the Authority incurred in carrying out the Retendering Process;

Retendering Information

has the meaning given to it in clause 29.8.1.1 (Retendering);

Retendering Process

shall have the meaning given in clause 51 (Retendering Process);

Retention Fund Account

has the meaning given to it in clause 44.5 (Retention Fund);

Return Date

has the meaning given to it in clause 29.9.2 (Termination of Agreement);

Returning Employees

has the meaning given to it in clause 29.9.2 (Termination of Agreement);

Revenue

the revenue or income received by the Contractor or the Leisure Operator (or where relevant would have been received but for the occurrence of a Relevant Event or Loss of Revenue Event) from Users of the relevant Facility for the provision of the Leisure Services at the relevant Facility;

Reviewable Design Data

the plans, drawings, documents and information relating to the Works listed in paragraph 7 of Schedule 8 (Review Procedure);

Review Procedure

the procedure set out in Schedule 8 (Review Procedure);

Risk Register

the register of risks identified in relation to the Works in accordance with clause 13.2.1 (Risk Assessment) as updated and amended from time to time in accordance with clause 13.2.2 (Updating the Risk Register);

Schedule of Programmed Maintenance

the Contractor's annual programme for the maintenance of [each/the] Facility to satisfy the Services Specification which, for the avoidance of doubt, includes the Lifecycle Schedule;

Scheme

has the meaning given to it in clause 85.1 (Construction Industry Scheme);

Service Delivery Proposals

the proposals for the method of providing the Services to satisfy the Services Specification set out in Part 2 of Schedule 2 (Contractor's Proposals);

Service Transfer Date

the transfer on a date agreed by the parties to the Contractor of responsibility for provision of (or procuring the provision by Sub-Contractors of) the Services in accordance with this Agreement;

Services

the services required to satisfy the Services Specification [and the Initial Services];

Services Availability

in relation to [any/the] Facility, satisfaction of the Services Availability Requirements;

Services Availability Date

in relation to [any/the] Facility, the date determined in accordance with clause 20.2 (Dates on which Services Availability may occur);

Services Availability Requirements

the requirements set out in Part 1 of Schedule 5 (Completion Requirements);

Services Media

all pipes, sewers, drains, mains, ducts, conduits, gutters, water courses, wires, cables, meters, switches, channels, flues and all other conducting media, appliances and apparatus including any fixtures, louvres, cowls and other ancillary apparatus;

Services Period

in relation to [any/the] Facility, the period from and including the Services Availability Date [for that Facility] until and including the last day of the Contract Period;

Services Specification

the specification contained in Part 3 of Schedule 1 (Authority's Requirements);

[Services Start Date]

[in relation to [each/the] Facility, the date upon which the Initial Services are to begin, shown [against that Facility] in the column headed "Services Start Date" in Schedule 4 ([Facility/Facilities])];

Shareholder

any person from time to time holding share capital in the Contractor [or Holdco];

Site Conditions

the conditions of the Site[s] including (but not limited to) climatic, hydrological, hydrogeological, ecological, environmental, geotechnical and archaeological conditions;

Site Plans

the plan[s] of the Site[s] set out in Schedule 28 (Site Plan[s]);

Site[s]

the area edged [red] on the [relevant] Site Plan [for each Facility] together with the Buildings and the service ducts and media for all utilities and services serving the Buildings;

Snagging Items

minor defects, deficiencies or omissions which do not prevent the Independent Certifier from issuing [an/the] Acceptance Certificate [or a Post Completion Works Acceptance Certificate (as the case maybe)] in relation to [a/the] Facility;

Snagging List

the list to be prepared by the Independent Certifier in accordance with clause 20.6.1 (Snagging Items) containing Snagging Items;

Snagging Programme

has the meaning given to it in clause 20.6.1 (Snagging Items);

Specific Change in Law

any Change in Law which specifically refers to the construction, operation and maintenance of premises for the provision of a service the same as or similar to the Services or to the holding of shares in companies whose main business is the construction, operation and maintenance of premises for the provision of services the same as or similar to the Services;

Sport England

means the English Sports Council (or its successors) of First Floor, 21 Bloomsbury Street, London WC1B 3HF;

[Sport England Guidance

means the guidance adopted and published by Sport England at the Commencement Date together with any changes in such guidance which were reasonably foreseeable at the Commencement Date;]

Start on Site Date

[                         ] or such later date as may be allowed in accordance with the terms of this Agreement;

Sub-Contractor

each of [the Building Contractor, the FM Contractor and the Leisure Operator] or any other person engaged by the Contractor from time to time as may be permitted by this Agreement to procure the provision of the Works and/or the Services (or any of them). References to sub-contractors means sub-contractors (of any tier) of the Contractor;

Sub-Contractor Breakage Costs

Losses that have been or will be reasonably and properly incurred by the Contractor as a direct result of the termination of this Agreement, but only to the extent that:

- the Losses are incurred in connection with the Project and in respect of the provision of Services or completion of Works, including:

  - any materials or goods ordered or sub-contracts placed that cannot be cancelled without such Losses being incurred;

  - any expenditure incurred in anticipation of the provision of Services or the completion of Works in the future;

  - the cost of demobilisation including the cost of any relocation of equipment used in connection with the Project; and

  - redundancy payments;

- the Losses are incurred under arrangements and/or agreements that are consistent with terms that have been entered into in the ordinary course of business and on reasonable commercial terms;

- the Contractor and the relevant Sub-Contractor has each used its reasonable endeavours to mitigate the Losses; and

- the Losses do not include any element of Profit Payment;

Sub-Contracts

the contracts entered into between the Contractor and the Sub-Contractors;

Submitted Item

has the meaning given to it in paragraph 1.2 of Schedule 8 (Review Procedure);

Subsidiary

has the meaning given to it in Section 1159 of the Companies Act 2006;

Suitable Third Party

any person who is not an Unsuitable Third Party;

Supplier

has the meaning given to it in clause 37.11.2 (VAT on Payments);

Surplus Annual Payment

the Annual Payment where it is a positive number;

[Suspension Notice

has the meaning given to it in clause 18.3B.2.1 (Judicial Review Proceedings);]

Tax

any kind of tax, duty, levy or other charge (other than VAT) whether or not similar to any in force at the date of this Agreement and whether imposed by a local, governmental or other Relevant Authority in the United Kingdom or elsewhere;

Technical Specification

the technical requirements of the Authority in relation to the provision of the [Facility/Facilities] set out in Part 1B of Schedule 1 (Authority's Requirements);

Termination Date

the date of early termination of this Agreement in accordance with its terms;

Termination Notice

a notice of termination issued in accordance with this Agreement;

Termination Sum

any compensation payable by the Authority to the Contractor or the Contractor to the Authority on an early termination of this Agreement under clauses 46 (Compensation on Termination for Authority Default/Voluntary Termination), 47 (Compensation on Termination for Contractor Default and Corrupt Gifts and Fraud) and 49 (Compensation on Termination for Force Majeure);

Third Party Claim

has the meaning given to it in clause 60.4 (Notification of claims);

Third Party Contractor

any sub-contractor (other than the Contractor) engaged by or on behalf of the Authority to perform any service equivalent to a Service;

Transfer Amount

the aggregate of the Transfer Values as at the Relevant Transfer Date of, respectively, those Eligible Employees who elect to transfer their benefits;

Transfer Value

the actuarial value of the benefits of each member of the Local Government Pension Scheme or Contractor's Scheme (on a secondary transfer of employees), as the case may be, who elects to transfer their benefits pursuant to the terms of this Agreement calculated on a Past Service Reserve basis and without any reduction having been applied to reflect any deficiencies in the assets relative to the liabilities of the Local Government Pension Scheme or Contractor's Scheme;

Transferring Employee

an employee of the Authority (excluding, without limitation, any person engaged by the Authority as an independent contractor) whose contract of employment becomes, by virtue of the application of TUPE in relation to what is done for the purposes of carrying out this Agreement between the Authority and the Contractor, a contract of employment with someone other than the Authority;

Transferring Original Employee

an Original Employee:

- whose contract of employment becomes, by virtue of the application of TUPE in relation to what is done for the purposes of carrying out a contract between the Authority and the Contractor, a contract of employment with someone other than his existing employer; and

- whose contract of employment on each occasion when an Intervening Contract was carried out became, by virtue of the application of TUPE in relation to what was done for the purposes of carrying out the Intervening Contract, a contract of employment with someone other than his existing employer;

TUPE

the Transfer of Undertaking (Protection of Employment) Regulations 2006 (246/2006) and/or any other Regulations enacted for the purpose of implementing the Directive into English law;

[Unavoidable Fixed Costs

the fixed costs incurred by the Contractor which first fall due for payment by the Contractor during the period of indemnity but excluding:

- costs which could have reasonably been mitigated or avoided by the Contractor;

- payments to the Contractor's Affiliates;

- payments which are not entirely at arm's length;

- Indirect Losses suffered or allegedly suffered by any person;

- fines, penalties or damages for unlawful acts, breaches of contract or other legal obligations;

- payments the Contractor can recover under contract or in respect of which the Contractor has a remedy against another person in respect of the same liability;

- payments to the extent that the Contractor has available to it payments representing any profits of the Project (to the extent not already excluded in (d) above);]

Underlease

the underlease[s] relating to the Site[s] to be granted by the Contractor to the Leisure Operator in the Agreed Form;

Uninsurable

in relation to a risk, either that:

- insurance is not available to the Contractor in respect of the Project in the worldwide insurance market with reputable insurers of good standing in respect of that risk; or

- the insurance premium payable for insuring that risk is at such a level that the risk is not generally being insured against in the worldwide insurance market with reputable insurers of good standing by contractors in the United Kingdom;

Uninsured Losses

losses arising from any risks against which the Contractor or any Contractor Related Party does not maintain insurance (where not required to maintain insurance for such risk under this Agreement or by law), provided that:

- the amount of any losses that would otherwise be recoverable under any Required Insurance but for the applicable uninsured deductible in respect of such insurance; and

- any exclusion of loss of insurance proceeds caused by or contributed to by any act or omission of the Contractor or any Contractor Related Party,

shall not be treated as Uninsured Loss;

Unsuitable Third Party

any of:

- any person who has a material interest in the production, distribution or sale of tobacco products, alcoholic drinks and/or pornography;

- any person whose activities are, in the reasonable opinion of the Authority, incompatible with the provision of leisure services in the area; or

- any person whose activities, in the reasonable opinion of the Authority, pose or could pose a threat to national security;

Users

those persons who use, or are entitled to use (whether they have done so or not) the [Facility/Facilities] and/or any or all of the Services from time to time;

Utilities

each of natural gas, fuel oil, electricity, water and other utilities that may be required in order to provide the Services and Works at the [Facility/Facilities] (which includes, for the avoidance of doubt, Energy);

Value of Completed Works

means (without double counting) the total value of:

- that part of the Works properly carried out as at the Termination Date (as such value shall have been ascertained in accordance with this Agreement prior to the Termination Date); and

- that part of the Works properly carried out as at the Termination Date (which value shall not have previously been ascertained in accordance with this Agreement (such value being ascertained as if this Agreement had not been terminated)) and not being the value of any uncompleted Works,

less any amounts previously paid to the Contractor under this Agreement in respect of the Works;

VAT

value added tax at the rate prevailing at the time of the relevant supply charged in accordance with the provisions of the Value Added Tax Act 1994;

Works

all of the works (including design and works necessary for obtaining access to the Site[s]) to be undertaken in accordance with this Agreement to satisfy the Construction Requirements [including for the avoidance of doubt the Works involved in the Post Completion Works];

Works Period

the period from the [Commencement Date] [Start on Site Date] to the later of the:

- [last] Services Availability Date [; and

- last Post Completion Works Acceptance Date].

Works Stipulations

means the works stipulations set out in Part 2 of Schedule 9;

Zone

has the meaning set out in Schedule 6 (Payment and Performance Monitoring System);

Zone Data Sheet

has the meaning set out in Schedule 6 (Payment and Performance Monitoring System).

  - Interpretation

In this Agreement except where the context otherwise requires:

    - the masculine includes the feminine and vice-versa;

    - the singular includes the plural and vice versa;

    - a reference to any clause, sub-clause, paragraph, Schedule, recital or annex is, except where expressly stated to the contrary, a reference to such clause, sub-clause, paragraph, Schedule, recital or annex of and to this Agreement;

    - save where stated to the contrary, any reference to this Agreement or to any other document shall include any permitted variation, amendment or supplement to such document;

    - any reference to any enactment, order, regulation or other similar instrument shall be construed as a reference to the enactment, order, regulation or instrument as amended, replaced, consolidated or re-enacted;

    - a reference to a person includes firms, partnerships and corporations and their successors and permitted assignees or transferees;

    - headings are for convenience of reference only; and

    - words preceding "include", "includes", "including" and "included" shall be construed without limitation by the words which follow those words.

  - Schedules

The Schedules to this Agreement form part of this Agreement.

  - Indexation

In this Agreement, references to amounts expressed to be Indexed are references to such amounts [at the Pricing Reference Date] multiplied by:

where I1 is the value of CPI most recently published prior to the relevant calculation date, and I2 is the value of CPI on [the Pricing Reference Date].

  - Precedence of Documentation

In the event of any inconsistency between the provisions of the body of this Agreement and the Schedules, or between the Schedules, the inconsistency shall be resolved according to the following descending order of priority;

    - the clauses of this Agreement and Schedule 6 (Payment and Performance Monitoring System), Schedule 8 (Review Procedure), Schedule 18 (Benchmarking), Schedule 19 (Surplus Share), Schedule 24 (Change Protocol) and Schedule 27 (NNDR);

    - Schedule 1 (Authority's Requirements);

    - the Schedules (excluding Schedule 1 (Authority's Requirements) and Schedule 2 (Contractor's Proposals));

    - Schedule 2 (Contractor's Proposals).

  - Responsibility for Related Parties

Subject to the provisions of this Agreement, the Contractor shall be responsible as against the Authority for the acts and omissions of the Contractor Related Parties as if they were the acts and omissions of the Contractor and the Authority shall be responsible as against the Contractor for the acts and omissions of the Authority Related Parties as if they were the acts and omissions of the Authority. The Contractor shall, as between itself and the Authority, be responsible for the selection of and pricing by all Contractor Related Parties.

  - Approval

Neither the giving of any approval, consent, examination, acknowledgement, knowledge of the terms of any agreement or document nor the review of any document or course of action by or on behalf of the Authority, nor the failure of the same, shall unless otherwise expressly stated in this Agreement, relieve the Contractor of any of its obligations under the Project Documents or of any duty which it may have hereunder to ensure the correctness, accuracy or suitability of the matter or thing which is the subject of the approval, consent, examination, acknowledgement or knowledge.

  - Succession

References to a public organisation (other than the Authority) shall be deemed to include a reference to any successor to such public organisation or any organisation or entity which has taken over either or both the functions and responsibilities of such public organisation. References to other persons (other than the Authority) shall include their successors and assignees.

- Exclusion of Legislation

No term of this Agreement is enforceable under the Contracts (Rights of Third Parties) Act 1999 by a person who is not a party to this Agreement.

- Commencement and Duration

  - [Subject to clause 3.2,] this Agreement and the rights and obligations of the parties shall take effect on the Commencement Date and (subject to the provisions for early termination set out in this Agreement) shall continue until the Expiry Date [provided that the obligations for the Annual Payment to be paid and for the Contractor to provide the Services shall not commence until the Services Availability Date].

  - [The Contract Period may be extended by a period of no more than [    ] years by agreement between the parties].

- Collateral Warranties [and Surveys] [and Guarantees]

  - The Contractor shall:

    - [deliver to the Authority the Collateral Warranties from the Building Contractor, each member of the Professional Team, the Leisure Operator and the FM Contractor to the Authority [on or before the date of this Agreement] [within ten/twenty (10)/(20)] Business Days of the date of this Agreement;]

    - deliver to the Authority Collateral Warranties in substantially Agreed Form (subject to amendments that each Principal Building Sub-Contractor and the Authority, the Contractor and the Building Contractor agree (acting reasonably)) from each Principal Building Sub-Contractor and copies of sub-contracts entered into between the Building Contractor and each Principal Building Sub-Contractor within [ten (10)] [twenty (20)] Business Days of appointment of such Principal Building Sub-Contractor;

    - not engage any new Building Contractor, Leisure Operator or FM Contractor (and shall procure that the Building Contractor shall not engage any Principal Building Sub-Contractor or any new member of the Professional Team) in connection with the Project unless such person has delivered to the Authority a duly executed agreement substantially in the Agreed Form of the relevant Collateral Warranty duly executed as a deed and in each case such Collateral Warranties must be delivered to the Authority before such entity enters onto [any/the] Site;

    - deliver to the Authority certified copies of the appointment of each member of the Professional Team [on or before the date of this Agreement][within ten/twenty (10/20) Business Days of the date of this Agreement]; and

    - [deliver to the Authority the Parent Company Guarantee(s)/Bond on or before the date of this Agreement].

  - The parties acknowledge that copies of the [Building Surveys and Asbestos Surveys] have been provided to the Contractor prior to the date of this Agreement and the Authority shall on the date of this Agreement deliver to the Contractor duly executed warranties in the Agreed Form from the surveyors who carried out the Building Surveys and Asbestos Surveys].

- General Warranties

  - Contractor Warranties

The Contractor warrants and represents to the Authority that on the date hereof:

    - it is properly constituted and incorporated under the laws of England and Wales and has the corporate power to own its assets and to carry on its business as it is now being conducted;

    - it has the corporate power to enter into and to exercise its rights and perform its obligations under the Project Documents;

    - all action necessary on the part of the Contractor to authorise the execution of and the performance of its obligations under the Project Documents has been taken or, in the case of any Project Document executed after the date of this Agreement, will be taken before such execution;

    - the obligations expressed to be assumed by the Contractor under the Project Documents are, or in the case of any Project Document executed after the date of this Agreement will be, legal, valid, binding and enforceable to the extent permitted by law and each Project Document is or will be in the proper form for enforcement in England;

    - the execution, delivery and performance by it of the Project Documents does not contravene any provision of:

      - any existing Legislation either in force, or enacted but not yet in force binding on the Contractor;

      - the Memorandum and Articles of Association of the Contractor;

      - any order or decree of any court or arbitrator which is binding on the Contractor; or

      - any obligation which is binding upon the Contractor or upon any of its assets or revenues;

    - the Contractor Warranted Data is true and accurate in all respects;

    - [the Contractor has not, other than in connection with the Project, traded at any time since its incorporation as a company pursuant to the Companies Act 2006;]

    - no claim is presently being assessed and no litigation, arbitration or administrative proceedings are presently in progress or, to the best of the knowledge of the Contractor, pending or threatened against it or any of its assets which will or might have a material adverse effect on the ability of the Contractor to perform its obligations under any Project Document;

    - it is not the subject of any other obligation, compliance with which will or is likely to have a material adverse effect on the ability of the Contractor to perform its obligations under any Project Document;

    - no proceedings or other steps have been taken and not discharged (nor, to the best of the knowledge of the Contractor, threatened) for its winding-up or dissolution or for the appointment of a receiver, administrative receiver, administrator, liquidator, trustee or similar officer in relation to any of its assets or revenues;

    - each of the Ancillary Documents is or, when executed, will be in full force and effect and constitutes or, when executed, will to the extent permitted by law constitute the valid, binding and enforceable obligations of the parties thereto; and

    - the copies of the Project Documents which the Contractor has delivered or, when executed, will deliver to the Authority are or, as the case may be, will be true and complete copies of such documents and there are not in existence any other agreements or documents replacing or relating to any of the Project Documents which would materially affect the interpretation or application of any of the Project Documents,

and the Authority relies upon such warranties and representations.

  - Contractor Undertakings

The Contractor undertakes with the Authority that for so long as this Agreement remains in full force:

    - it will upon becoming aware that any litigation, arbitration, administrative or adjudication or mediation proceedings before or of any court, arbitrator or Relevant Authority may be threatened or pending and immediately after the commencement thereof (or within twenty (20) Business Days of becoming aware the same may be threatened or pending or within twenty (20) Business Days after the commencement thereof where the litigation or arbitration or administrative or adjudication or mediation proceedings is against a Sub-Contractor) give the Authority notice of all such litigation, arbitration, administrative or adjudication or mediation proceedings which would adversely affect, to an extent which is material in the context of the Project, the Contractor's ability to perform its obligations under this Agreement;

    - it will not without the prior written consent of the Authority (and whether by a single transaction or by a series of transactions whether related or not) sell, transfer, lend or otherwise dispose of (other than by way of security) the whole or any part of its business or assets which would materially affect the ability of the Contractor to perform its obligations under this Agreement;

    - it will not cease to be resident in the United Kingdom or transfer in whole or in part its undertaking, business or trade outside the United Kingdom;

    - it will not undertake the performance of its obligations under this Agreement for the provision of the Services otherwise than through itself or a Sub-Contractor;

    - [it shall not without the written consent of the Authority (such consent not to be unreasonably withheld or delayed) incorporate any company or purchase or acquire or subscribe for any shares in any company save where such company is involved in the provision of the Services or Works; ]

    - [it shall not without the written consent of the Authority (such consent not to be unreasonably withheld or delayed) make any loans or grant any credit or give any guarantee or indemnity to or for the benefit of any person or otherwise voluntarily or for consideration assume any liability (whether actual or contingent) in respect of any obligation of any other person except in the ordinary course of business and/or as contemplated by the Project Documents and/or Ancillary Documents; and]

    - [it shall not change or cease its business or start any other business which is materially different from that to be carried on by it under this Agreement.]

  - Status of Warranties

All warranties, representations, undertakings, indemnities and other obligations made, given or undertaken by the Contractor in this Agreement are cumulative and none shall be given a limited construction by reference to any other.

- Authority Warranties

  - No Warranty by Authority

Subject to clause 6.3 (Fraudulent Statements), clause 6.4 (Authority Title Warranty) [and clause 6.8 (Authority Warranted Data)], the Authority does not give any warranty or undertaking as to the relevance, completeness, accuracy or fitness for any purpose of any of the Disclosed Data.

  - No Liability to Contractor

Subject to clause 6.3 (Fraudulent Statements), clause 6.4 (Authority Title Warranty) [and clause 6.8 (Authority Warranted Data)], neither the Authority nor any of its agents or employees shall be liable to the Contractor in contract, tort (including negligence or breach of statutory duty), statute or otherwise as a result of:

    - any inaccuracy, omission, unfitness for any purpose or inadequacy of any kind whatsoever in the Disclosed Data; or

    - any failure to make available to the Contractor any materials, documents, drawings, plans or other information relating to the Project.

  - Fraudulent Statements

Nothing in this clause 6 (Authority Warranties) shall exclude any liability which the Authority or any of its agents or employees would otherwise have to the Contractor in respect of any statements made fraudulently prior to the date of this Agreement.

  - Authority Title Warranty

The Authority warrants to the Contractor on the terms set out in Part 1 of Schedule 13 (Title Matters), provided that no inaccuracies or omissions in such information shall be capable of giving rise to an Authority Default.

  - Contractor's Due Diligence

The Contractor shall, subject to the terms of this Agreement, be deemed to have:

    - satisfied itself as to the assets to which it will acquire rights and the nature and extent of the risks assumed by it under this Agreement; and

    - gathered all information necessary to perform its obligations under this Agreement and other obligations assumed including:

      - information as to the nature, location and condition of the land (including hydrological, geological, geotechnical and sub-surface conditions);

      - information relating to archaeological finds, areas of archaeological scientific or natural interest, local conditions and facilities and the quality of existing structures;

      - any other contingency or risk that affects the performance of the Works and/or the Services and/or affects the performance of the Contractor's obligations under this Agreement; and

      - [other relevant information.]

  - No Relief

Subject to clause 6.3 (Fraudulent Statements), clause 6.4 (Authority Title Warranty) [and clause 6.8 (Authority Warranted Data)], the Contractor shall not in any way be relieved from any obligation under this Agreement nor shall it be entitled to claim against the Authority on grounds that any information, whether obtained from the Authority or otherwise (including information made available by the Authority), is incorrect or insufficient and shall make its own enquiries as to the accuracy and adequacy of that information.

  - Contractor acknowledgement

The Contractor hereby acknowledges and agrees that it has been provided with copies of all of the Disclosed Title Matters, Replies to Enquiries and Disclosed Searches listed in Parts 2, 3 and 4 of Schedule 13 (Title Matters) and that all such matters that are disclosed within the Disclosed Title Matters, Replies to Enquiries and Disclosed Searches are disclosed against the warranties set out in Part 1 of Schedule 13 (Title Matters).

  - [Authority Warranted Data

The Authority warrants to the Contractor that the information set out or described in Part 1 of Schedule 11 (Warranted Data) has been prepared after due and careful enquiry and is reasonably believed to be true, accurate and complete as at the date of this Agreement provided that no inaccuracies or omissions in such information shall be capable of giving rise to an Authority Default.]

- Documents and Co-Operation

  - Ancillary Documents

The Contractor shall perform its obligations under, and observe all of the provisions of, the Ancillary Documents and shall not:

    - terminate or agree to the termination of all or part of any Ancillary Document;

    - make or agree to any material variation of any Ancillary Document;

    - in any material respect depart from its obligations (or waive or allow to lapse any rights it may have in a material respect), or procure that others in any material respect depart from their obligations (or waive or allow to lapse any rights they may have in a material respect), under any Ancillary Document; or

    - enter into (or permit the entry into by any other person of) any agreement replacing all or part of (or otherwise materially and adversely affecting the interpretation of) any Ancillary Document,

unless the proposed course of action (and any relevant documentation) has been submitted to the Authority's Representative for review under the Review Procedure and there has been no objection in accordance with paragraph 3 of the Review Procedure within twenty (20) Business Days of receipt by the Authority's Representative of the submission of the proposed course of action (and any relevant documentation), or such shorter period as may be agreed by the parties, and, in the circumstances specified in clause 7.1.1 (Ancillary Documents), the Contractor has complied with clauses 67 (Assignment and Sub-Contracting) and 68 (Change in Ownership).

  - Delivery of Initial and Changed Ancillary Documents

    - The Contractor has provided to the Authority copies of the Ancillary Documents.

    - Without prejudice to the provisions of clause 7.1 (Ancillary Documents), if at any time an amendment is made to any Ancillary Document, or the Contractor enters into a new Ancillary Document (or any agreement which affects the interpretation or application of any Ancillary Document), the Contractor shall deliver to the Authority a conformed copy of each such amendment or agreement within ten (10) Business Days of the date of its execution or creation (as the case may be), certified as a true copy by an officer of the Contractor.

  - Co-operation

Each party agrees to co-operate, at its own expense (but without being compelled to incur material expenditure), with the other party in the fulfilment of the purposes and intent of this Agreement. Neither party shall be under any obligation to perform any of the other's obligations under this Agreement.

Part 2 – Land Issues

- Nature of Land Interests

  - Access during Construction

From the [Commencement Date] [Start on Site Date] until the date when the [relevant] Head Lease[s] are completed in accordance with this clause 8 (Nature of Land Interests) (or if earlier the Termination Date), the Authority will afford the Ancillary Rights to the Contractor and the Contractor Related Parties for the purpose of implementing the Works and providing the Services.

  - Grant of the Head Lease

Within twenty (20) Business Days of the [relevant] Services Availability Date the Authority shall grant to the Contractor, and the Contractor shall accept, the Head Lease for [the/each] Site[s].

  - Exclusion of Security of Tenure for the Head Lease

The Contractor hereby confirms that before it became contractually bound to enter into the tenancy created by the Head Lease pursuant to this Agreement:

    - The Authority served on the Contractor a notice dated [            ] day of [            ] in relation to the tenancy created by the Head Lease (the Head Lease Notice) in a form complying with the requirements of Schedule 1 to the Regulatory Reform (Business Tenancies) (England and Wales) Order 2003 (the Order).

    - The Contractor, or a person duly authorised by the Contractor, in relation to the Head Lease Notice made a statutory declaration (the Head Lease Declaration) dated [            ] day of [            ] in a form complying with the requirements of Schedule 2 of the Order.

    - The Contractor further confirms that, where the Head Lease Declaration was made by a person other than the Contractor, the declarant was duly authorised by the Contractor to make the Head Lease Declaration on the Contractor's behalf.

    - The Authority and the Contractor agree to exclude the provisions of sections 24 to 28 (inclusive) of the Landlord and Tenant Act 1954 in relation to the tenancy created by the Head Lease.

  - Place of Completion

The grant of the Head Lease[s] shall take place at the offices of the Authority's solicitors [DETAILS TO BE INSERTED]. The term of the Head Lease relating to the [Facility/Facilities] shall commence on the [relevant] Services Availability Date.

  - Registration

The Contractor shall apply for, and procure, registration of the Head Lease[s] at the Land Registry as soon as reasonably practicable after the [relevant] Head Lease is completed. The Authority shall use all reasonable endeavours to assist the Contractor in responding to any proper requisitions raised by the Land Registry of such documents that are in the Authority's possession relating to the freehold reversion as the Land Registry may request.

  - Early Termination

If this Agreement is terminated for any reason prior to the Expiry Date, the Head Lease[s] shall automatically cease and determine with effect from the date of termination of this Agreement (or, if not granted at the time, the obligation to grant the Head Lease[s] shall automatically cease to apply). Where the Head Lease[s] [has/have] been entered into, the Contractor shall forthwith deliver to the Authority the Head Lease[s] together with all relevant title deeds, releases from any charge and a direction to the Chief Land Registrar to cancel the registered titles relating to the Head Lease[s]. The Contractor shall take all steps as may be proper and reasonable to cancel or assist in the cancellation of all entries at the Land Registry and the Land Charges Registry in relation to the Head Lease[s].

  - No Compensation

The Contractor shall not be entitled to any compensation in respect of any variation of the terms of the Head Lease[s] or the unexpired part of its interest as tenant under the Head Lease[s] on assignment or surrender or automatic determination in accordance with this clause.

  - Compliance with Disclosed Title Matters

The Contractor shall without prejudice to clause 6.4 (Authority Title Warranty) procure that:

    - the carrying out of the Works and the provision of the Services at the Site[s] by or on behalf of the Contractor (whether before, during or after the completion of the Works) shall be carried out in a manner which does not breach any provisions of the Disclosed Title Matters relating to the Site[s] or the [Facility/Facilities]; and

    - in carrying out the Works and providing the Services at the Site[s], there shall be no action, or omission to act by the Contractor or any Contractor Related Party, which shall give rise to a right for any person to obtain title to or any right or interest over the Site[s] or any part of [it/them] (save in accordance with the terms of this Agreement);

  - Compliance with Head Lease

The Authority and the Contractor shall comply with their respective obligations in the Head Lease[s].

  - Grant of Underlease

The Authority hereby agrees to the grant by the Contractor to the Leisure Operator of the Underlease[s].

  - [Possession of the Site

    - For the avoidance of doubt, the Authority shall:

      - remain responsible for and shall retain the risk in relation to the Site[s];

      - ensure that the Site[s] [is/are] kept in a safe condition, protected from damage and kept secure against trespassers;

for the period up to the [relevant] Start on Site Date and shall hand over the Site[s] to the Contractor with vacant possession on the [relevant] Start on Site Date and in the same condition as the condition of the Site[s] as at the Commencement Date.

    - The Contractor shall take possession of the Site[s] on the [relevant] Start on Site Date on handover of the Site[s] by the Authority in accordance with clause 8.11.1 (Possession of Site).]

Part 3 – Transitional Arrangements

- [Initial Services]

  - Obligation to Provide

The Contractor shall provide to the Authority or procure the provision to the Authority of the Initial Services with effect from the relevant Services Start Date.

  - Standard of Initial Services

    - The Contractor shall provide the Initial Services so that they comply with and meet all the requirements of this Agreement, [the Initial Services Specification,] [the Service Delivery Proposals,] Good Industry Practice, Guidance and all applicable Authority's Policies and Legislation.

    - The Contractor shall ensure, and shall procure that any Contractor Related Party involved in the provision of the Initial Services shall ensure, that the Initial Services are carried out in compliance with the Equality Requirements.

  - Replacement of [FM Contractor and/or Leisure Operator]

[In circumstances where there is a material breach by the Contractor in the provision of the Initial Services the Authority shall be entitled to issue a notice to the Contractor requiring that that the Contractor removes the [FM Contractor and/or Leisure Operator] and appoints a replacement and the Contractor shall remove and replace the [FM Contractor and/or Leisure Operator]. The defaulting [FM Contractor and/or Leisure Operator] the subject of the notice shall not in such circumstances be entitled to take over the provision of the Services at the Services Availability Date without approval being given by the Authority pursuant to clause 67 (Assignment and Sub-Contracting)].

  - No Contractor Default

[Under no circumstances may any breach in respect of the performance of the Initial Services be capable of giving rise to a Contractor Default.]

- The Works

  - Obligation to Carry Out

The Contractor shall commence or shall procure the commencement of the Works no later than the Start on Site Date and shall or shall procure that the Building Contractor (and its sub-contractors and/or consultants) shall carry out the design (including the preparation of Design Data) and the construction, completion, commissioning and testing of the Works so that:

    - [each/the] Facility shall achieve Services Availability on or before the Planned Services Availability Date [for that Facility] provided that a breach of this clause 10.1.1 (Obligation to Carry Out) shall not, of itself, be capable of giving rise to a Contractor Default under either limbs (a) or (b) of that definition;

    - [the Post Completion Works Acceptance Requirements are satisfied at [the/each] Site on or before the relevant Planned Post Completion Works Acceptance Date, provided that a breach of this clause 10.1.2 shall not, of itself, be capable of giving rise to a Contractor Default under either of limbs (a) or (b) of that definition;]

    - the Works fully comply with and meet all the requirements of this Agreement, the Facilities Requirements, the Construction Proposals, Good Industry Practice, Guidance, all Necessary Consents, all applicable Authority's Policies and Legislation;

    - new materials or recycled materials that are in accordance with British Standards and/or Good Industry Practice only will be used in carrying out the Works (unless the Authority agrees otherwise in writing or the contrary is set out in the Facilities Requirements) and all goods used or included in the Works will be of satisfactory quality, and there will be used or included in the Works none of those products and materials listed in Part 1 of Schedule 9 (Prohibited Materials) nor any products or materials not in conformity with relevant British or European Union Standards or codes of practice which at the time of use are widely known to building contractors or members of the relevant design profession within the European Union to be deleterious to health or safety or to the durability of buildings and/or other structures and/or finishes and/or plant and machinery in the particular circumstances in which they are used;

    - all persons employed in connection with the performance of the Works will be skilled and experienced in their several professions, trades and callings or adequately supervised;

    - all aspects of the Works will be supervised by sufficient numbers of persons having adequate knowledge of such matters for the satisfactory and safe performance of the Works in accordance with this Agreement and having regard to the activities which are carried on at the Site[s] and to the nature of persons occupying the Site[s];

    - the Works are maintained in good order, kept in a safe condition and protected from damage, and working areas of the Site[s] are secure against trespassers and clean and tidy so far as practicable having regard to the nature of the Works;

    - adequate retaining and supporting walls are provided to support any Adjoining Property and, where appropriate, the Existing Facilities during the carrying out of the Works;

    - the Works are carried out in compliance with the Equality Requirements; and

    - the Works are carried out in compliance with the Works Stipulations.

  - Overall Responsibility

The obligations in clause 10.1 (Obligation to Carry Out) are independent obligations. In particular:

    - the fact that the Contractor has complied with the Facilities Requirements but not the Construction Proposals shall not be a defence to an allegation that the Contractor has not satisfied the Construction Proposals provided that the Facilities Requirements shall take priority over the Construction Proposals in the event of any discrepancy or inconsistency between them; and

    - the fact that the Contractor has complied with the Construction Proposals but not the Facilities Requirements shall not be a defence to an allegation that the Contractor has not satisfied the Facilities Requirements.

  - Utilities

    - The Contractor shall in relation to the services and utilities required as a result of the carrying out of the Works:

      - be responsible for determining the location of such services and utilities as may be at the Site[s] and for the maintenance of access to such services and utilities at the Site[s];

      - make and rely upon all necessary investigations and surveys as to such services and utilities at the Site[s];

      - make provision for lawfully diverting, disconnecting or otherwise dealing as may be necessary with any services and utilities not within the Site[s];

      - pay to all Relevant Authorities or undertakings all costs and expenses incurred in diverting, disconnecting or otherwise carrying out works in respect of such services and utilities within the Site[s];

      - make connection into services and utilities outside the Site[s]; and

      - otherwise do all that is required in relation to the utilities required for  the purposes of carrying out  the Works.

    - [The Contractor shall:

      - procure [or shall ensure that the Leisure Operator procures] all Utilities required for the [Facility/Facilities];

      - ensure that it [or the Leisure Operator] is the counterparty to the relevant Utility supply contracts;

      - pay [or procure payment to] the relevant Utility suppliers directly for all Utilities supplied; and

      - pay (at its own cost) [or procure payment of] all present and future rates, taxes, levies, costs, charges and other impositions (of whatever nature) payable in respect of the supply of Utilities to the [Facility/Facilities] including all liabilities under the CRC Scheme. In the event that any liability under the CRC Scheme in respect of the supply of Energy to the [Facility/Facilities] falls to the Authority, the Contractor shall reimburse the Authority and the Authority shall be entitled to set off any such liabilities against sums due under this Agreement to the Contractor.]

  - Contractor's responsibility for design

    - The Contractor accepts full responsibility for designing the Works (including the selection of materials for incorporation in the Works).

    - The Contractor shall not be relieved of its responsibility for the design of the Works by virtue of the Authority's Requirements, the Contractor's Proposals or any design documents having been prepared, reviewed, approved or commented upon by or on behalf of the Authority or any other third party, or by virtue of the incorporation of any such documents within this Agreement.

  - Contractor's duty of care

In carrying out the design of the Works, the Contractor shall exercise the level of skill and care which would reasonably and ordinarily be expected from an appropriately qualified and competent professional designer providing those services in relation to a project of a similar size and scope to the Works.

  - Discrepancies between the Facilities Requirements and the Construction Proposals

    - The Contractor has used the level of reasonable skill and care referred to in clause 10.5 (Contractor's duty of care) to check the design for the Works prior to the date of this Agreement in order to identify any discrepancies, inconsistencies, errors or inaccuracies within or between the Facilities Requirements and the Construction Proposals or between the design as so stated and any requirement of this Agreement relating to the Works.

    - Where a discrepancy is identified within the Facilities Requirements or within the Construction Proposals, or between the Facilities Requirements and/or the Construction Proposals and/or any Legislation or Necessary Consent the party discovering the discrepancy shall notify the other of the same. The Authority shall instruct the Contractor which of the discrepant provisions it wishes the Contractor to adopt subject to the terms of this Agreement, and such instruction or any such error, omission, discrepancy or inconsistency shall not give rise to an entitlement for an extension of time or the fixing of a revised Planned Services Availability Date, [Planned Post Completion Works Acceptance Date], or of any Start on Site Date nor to any adjustment to the Contract Sum or the Annual Payment and shall not be treated as an Authority Change. No instruction shall require the Contractor to act otherwise than in accordance with the Legislation or a Necessary Consent.

  - [Employment and skills

    - During the carrying out of the Works the Contractor shall comply with and implement the Employment and Skills Plan and the Employment and Skills Method Statement in accordance with the Employment and Skills Strategy.

    - The Contractor shall nominate an individual to liaise with the Authority and provide the Authority with information as reasonably required in order to demonstrate the Contractor's compliance with the Employment and Skills Plan and the Employment and Skills Method Statement.

    - The Authority shall provide to the Contractor information it has available to enable the Contractor to comply with and implement the Employment and Skills Plan and the Employment and Skills Method Statement, including the details listed in the Employment and Skills Strategy.

    - During the carrying out of the Works the Contractor shall provide to the Authority on a monthly basis in accordance with the relevant dates set out in Employment and Skills Strategy a report outlining the achievements during the previous month against the Employment and Skills Plan and the Employment and Skills Method Statement and provide details of the various employment and skills activities delivered in that month.

    - By no later than six (6) months after the [final] Services Availability Date the Parties shall meet to review the Contractor's compliance with and implementation of the Employment and Skills Plan and the Employment and Skills Method Statement.]

  - Goods and Materials not incorporated into the Works

    - Goods and materials ordered by the Contractor, the Building Contractor, the Principal Building Sub-Contractors, sub-contractors and/or the Professional Team for the Works shall become the property of the Authority upon payment by the Authority for the said goods and materials under this Agreement.

    - The Contractor shall not remove goods and materials delivered to the Site[s] which are the property of the Authority in accordance with clause 10.8.1 (Goods and materials not incorporated into the Works) without the Authority's prior written consent which shall not be unreasonably withheld or delayed.

    - The Contractor shall procure that goods and materials referred to in clause 10.8.1 (Goods and materials not incorporated into the Works) which are stored or held at any place other than the Site[s] are clearly identified as being the property of the Authority and are not moved from the place at which they are stored or held pending delivery to the Site[s].

- Construction Programme

  - Preparation of Construction Programme

The Contractor shall have prepared the Construction Programme prior to the date of this Agreement and shall be responsible for monitoring and updating it as necessary to show any amendments to the sequencing of events or the likely time for any events occurring prior to the delivery of the completed Works and, in particular, shall identify key decision events which are likely to involve the Authority or the Authority's Representative during the Works and shall co-ordinate any proposed changes to the Construction Programme with all other members of the Contractor's Supply Chain. The Contractor shall submit all proposed amendments to the Construction Programme to the Authority via the Review Procedure and shall discuss with, and if appropriate or requested, meet with the Authority to provide an explanation of any proposed changes and discuss how best to achieve any necessary reprogramming so as not to affect any relevant Planned Services Availability Date.

  - Amendments to Construction Programme

All amendments to the Construction Programme approved or not commented on by the Authority under the Review Procedure shall be circulated promptly by the Contractor to all other members of the Contractor's Supply Chain who still have obligations to carry out in respect of the Works and/or Services.

  - [Minimisation on disruption to the provision of services

Insofar as the carrying out of the Works affects or may affect the provision of any services at any Existing Facility the Contractor shall procure that (subject to the terms of this Agreement) the Works are carried out so as to minimise any disruption to the provision of those services and in compliance to the extent reasonably practicable with the Construction Programme.]

  - Notification of delays in progress of the Works

Without prejudice to the requirement of the Contractor to notify pursuant to clause 16 (Extensions of Time), if either:

    - the Contractor becomes aware at any time that the actual progress of the Works may become or has been significantly delayed or has fallen behind the Construction Programme; or

    - it appears to the Authority's Representative at any time that the actual progress of the Works has been significantly delayed or has fallen behind the Construction Programme,

the Authority's Representative shall be entitled to require that the Contractor's Representative submits to the Authority's Representative a report identifying the reasons for the delay and (where the Authority's Representative requires the Contractor's Representative to do so) the Contractor's Representative shall produce and submit to the Authority's Representative under Schedule 8 (Review Procedure) a revised Construction Programme showing the manner and the periods in which the Works will be carried out to achieve the Planned Services Availability Date and/or showing the steps which are to be taken to eliminate or reduce the delay.

  - [Authority's Obligation

The Authority shall ensure any services provided at any Existing Facility prior to the Planned Services Availability Date are provided by it in such a way and in such locations as will not prevent the Contractor from carrying out the relevant part of the Works at each such Site at the times shown in the Construction Programme and in the areas shown on the Site Plans.]

  - [Notification of Early Completion]

    - The Contractor shall notify the Authority's Representative if at any time the actual progress of the Works is significantly ahead of the Construction Programme so that the Contractor considers that the Services Availability Date [in respect of a Facility] will occur earlier than the Planned Services Availability Date [for that Facility].

    - The Authority's Representative shall be entitled to require the Contractor to produce and submit to the Authority's Representative, in accordance with the Review Procedure, a revised Construction Programme showing the manner and the periods in which the Works will be carried out and what the revised date for Services Availability would be to enable the Authority to consider (acting reasonably):

      - whether to agree a revised Planned Services Availability Date; and

      - what modifications (if any) will be required to this Agreement to accommodate such revised Planned Services Availability Date.

- Representatives

  - Representatives of the Authority

The Authority's Representative shall be [       ] or such other person appointed pursuant to this clause. The Authority's Representative shall exercise the functions and powers of the Authority in relation to the Project which are identified in this Agreement as functions or powers to be carried out by the Authority's Representative. The Authority's Representative shall also exercise such other functions and powers of the Authority under this Agreement as may be notified to the Contractor from time to time.

  - The Authority's Representative shall be entitled at any time, by notice to the Contractor, to authorise any other person to exercise the functions and powers of the Authority delegated to him pursuant to this clause, either generally or specifically. Any act of any such person shall, for the purposes of this Agreement, constitute an act of the Authority's Representative and all references to the Authority's Representative in this Agreement (apart from this clause) shall be taken as references to such person so far as they concern matters within the scope of such person's authority.

  - The Authority may by notice to the Contractor change the Authority's Representative. The Authority shall (as far as practicable) consult with the Contractor prior to the appointment of any replacement for the Authority's Representative, taking account of the need for liaison and continuity in respect of the Project. Such change shall have effect on the date specified in the written notice (which date shall, other than in the case of emergency, be such date as will not cause material inconvenience to the Contractor in the execution of its obligations under this Agreement).

  - During any period when no Authority's Representative has been appointed (or when the Authority's Representative is unable through illness, incapacity or any other reason whatsoever to carry out or exercise his functions under this Agreement) the Authority shall carry out the functions which would otherwise be performed by the Authority's Representative.

  - Save where notified in writing by the Authority before such act or instruction, the Contractor and Contractor's Representative shall be entitled to treat any act or instruction of the Authority's Representative in connection with this Agreement as being expressly authorised by the Authority and the Contractor and the Contractor's Representative shall not be required to determine whether authority has in fact been given.

  - Representative of the Contractor

The Contractor's Representative shall be [     ] or such other person appointed pursuant to this clause. The Contractor's Representative shall have full authority to act on behalf of the Contractor for all purposes of this Agreement. Except as previously notified in writing before such act by the Contractor to the Authority, the Authority and the Authority's Representative shall be entitled to treat any act of the Contractor's Representative in connection with this Agreement as being expressly authorised by the Contractor and the Authority and the Authority's Representative shall not be required to determine whether any express authority has in fact been given.

  - The Contractor may by notice to the Authority, change the Contractor's Representative. Where the Contractor wishes to do so it shall by written notice to the Authority propose a substitute for approval, taking account of the need for liaison and continuity in respect of the Project. Such appointment shall be subject to the approval of the Authority (not to be unreasonably withheld or delayed).

  - Appointment of Representatives

At any time the Authority may appoint more than one Authority's Representative and the Contractor may appoint more than one Contractor's Representative provided in each case the appointor provides written confirmation to the Contractor or Authority as appropriate of the extent of its Representative's authority.

- Site Meetings and Risk Management

  - Site Meetings

The Contractor shall procure that representatives of the Authority are afforded a reasonable opportunity to attend site meetings relating to the Works and (whether or not such representatives have attended) that a copy of the minutes of site meetings is promptly supplied to the Authority.

  - [Risk Management

    - Risk assessment

      - The Contractor shall be responsible for carrying out (with assistance from any relevant members of the Contractor's Supply Chain) risk assessments to identify:

        - potential risks relating to the performance of the Works the occurrence of which are capable of adversely affecting the time for completion, cost and/or quality of the Works;

        - the probability of these risks occurring;

        - a financial estimate of the most likely consequences of each risk occurring; and

        - those risks that are within the control of, or are best managed by, the Authority, the Contractor or another member of the Contractor's Supply Chain.

      - The results of this risk assessment shall be set out in the Risk Register.

    - Updating the Risk Register

The Contractor shall arrange regular meetings with the Authority and relevant members of the Contractor's Supply Chain to review and update the Risk Register and to consider:

      - any new risks that have arisen since the date of the last review;

      - the steps taken to prevent/mitigate previously identified risks;

      - risks which have been successfully prevented/mitigated (which can be removed from the Risk Register); and

      - the prioritisation of all continuing risks and agreement of an action plan in respect of, and risk owners for, all risks prioritised as serious risks.

    - Purpose of the Risk Register

      - The purpose of the Risk Register is to enable the parties and the Contractor's Supply Chain to identify and manage risks whose occurrence may otherwise have an adverse effect on the time taken to complete, the cost and quality of the Works.

      - The Risk Register does not allocate contractual responsibility for the consequences of the occurrence of any of the risks referred to].

- Design Development

  - Obligation to Finalise Design

The Contractor shall develop and finalise the design and specification of the Works and the Authority may review the Reviewable Design Data in accordance with the Review Procedure and the provisions of this clause 14 (Design Development).

  - Submission of Reviewable Design Data

The Contractor shall submit the Reviewable Design Data and the design of any variations developed in accordance with clause 15 (Changes to the Construction Proposals and Construction Programme) to the Authority's Representative for review under the Review Procedure.

  - No Construction prior to Review

    - Subject to clause 14.3.2 (No Construction prior to Review) the Contractor shall not commence or permit the commencement of the construction of the part or parts of the Works to which any Reviewable Design Data relates until it has submitted the relevant Reviewable Design Data for review and either it is confirmed by the Authority's Representative that the Contractor is entitled to proceed with construction in accordance with the Review Procedure or the Contractor is disputing the status of such Reviewable Design Data pursuant to paragraph 1.3 of Schedule 8 (Review Procedure).

    - If the Contractor commences or permits the commencement of construction before the Authority's Representative provides such approval or during such a dispute and it is subsequently determined that the Contractor was not entitled to proceed with construction in accordance with paragraph 4 of Schedule 8 (Review Procedure), then the Contractor shall forthwith, at its own cost, undo, remove from the Site(s) and replace (in a manner complying with this Agreement) any parts of the Works which it has been determined the Contractor was not entitled to construct.

  - Approved RDD

With effect from the date on which any item of Reviewable Design Data is or becomes an Approved RDD Item in accordance with the Review Procedure, the Contractor may proceed with the construction of the relevant part or parts of the Works (subject to the need to submit any associated Reviewable Design Data to review) in accordance with that Approved RDD Item.

  - Review of Design Data

The Contractor shall allow the Authority's Representative at any time a reasonable opportunity to view any items of Design Data, which shall be made available to the Authority's Representative as soon as reasonably practicable following receipt of any written request from the Authority's Representative.

  - Design Database

The Contractor shall procure that the Building Contractor establishes and maintains a computerised design database which the Contractor's Representative and the Authority's Representative may access remotely by computer to view drawings comprised within the Design Data (including Reviewable Design Data) and electronically store and print copies of such Design Data. If the Authority's Representative is unable to access that design database, the Contractor shall procure that the database is made available as soon as reasonably practicable for inspection by the Authority's Representative or any person authorised by the Authority's Representative.

  - Rectification of Construction Proposals

If it should be found that the Construction Proposals do not fulfil the Facilities Requirements, the Contractor shall at its own expense amend the Construction Proposals and rectify the Works or any part of the Works affected. Such amendment and rectification shall have the effect that the Construction Proposals shall satisfy the Facilities Requirements.

- Changes to the Construction Proposals and the Construction Programme

  - Proposal to Vary Construction Proposals or the Construction Programme

    - Without prejudice to clause 14.7 (Rectification of Construction Proposals), the Contractor shall be entitled to propose variations to the Construction Proposals by submitting the relevant variation to the Authority for review under the Review Procedure.

    - The Contractor shall be entitled to propose variations to the Construction Programme by submitting the relevant variation to the Authority for review under the Review Procedure.

  - Implementing a Variation to the Construction Proposals or the Construction Programme

The Contractor shall not implement any variation to the Construction Proposals or the Construction Programme (unless of a minor or non-material nature) until the Authority consents or is deemed to have consented to the variation in accordance with the Review Procedure. Once consented to, a proposed variation will form part of the Construction Proposals or the Construction Programme as the case may be.

- Extensions Of Time

  - Notice

If at any time the Contractor becomes aware that there will be or is likely to be a delay in the Works, such that the [Start on Site Date or] Planned Services Availability Date [or Planned Post Completion Works Acceptance Date] may not be achieved or (following the Planned Services Availability Date) such that there is a delay in the achievement of Services Availability, [(following the Planned Post Completion Works Acceptance Date) such that there is a delay in achievement of the Post Completion Works Acceptance Date,] the Contractor shall as soon as reasonably practicable and in any event within twenty (20) Business Days of becoming aware of the likely delay give notice to the Authority to that effect specifying:

    - the reason for the delay or likely delay; and

    - an estimate of the likely effect of the delay on the Works including the [Start on Site Date or] the Planned Services Availability Date or the Longstop Date [or any Planned Post Completion Works Acceptance Date] (taking into account any measures that the Contractor proposes to adopt to mitigate the consequences of the delay in accordance with clause 16.3 (Duty to Mitigate)).

  - Supply of Information

Following service of a notice by the Contractor pursuant to clause 16.1 (Notice), the Contractor shall promptly supply to the Authority any further information relating to the delay which:

    - is received by the Contractor; or

    - is reasonably requested by the Authority.

  - Duty to Mitigate

The Contractor shall take all reasonable steps to mitigate the delay and consequences of any delay which is the subject of a notice pursuant to clause 16.1 (Notice).

  - Time for completion of the Works

If any delay or anticipated failure to meet a [Start on Site Date or] Planned Services Availability Date [Planned Post Completion Works Acceptance Date] or, (if the delay occurs after the relevant Planned Services Availability Date), a delay in the achievement of Services Availability [or (following the Planned Post Completion Works Acceptance Date), a delay in achieving the Post Completion Works Acceptance Date] is notified to the Authority by the Contractor as being in the Contractor's reasonable opinion attributable to:

    - a Compensation Event, then the provisions of clause 16.5 (Effect of a Compensation Event) shall apply;

    - a Relief Event, then the provisions of clause 55 (Relief Events) shall apply;

    - a Force Majeure Event, then the provisions of clause 42 (Termination on force majeure) shall apply;

    - a Qualifying Change in Law, then the provisions of clause 56 (Change in Law) shall apply; or

    - an Authority Change, then the provisions of Schedule 24 (Change Protocol) shall apply.

  - Effect of a Compensation Event

If, for [any/the] Facility, as a direct result of the occurrence of a Compensation Event the Contractor will:

    - be unable to commence the Works on or before the Start on Site Date and/or;

    - be unable to achieve Services Availability on or before the Planned Services Availability Date or (following the Planned Services Availability Date but before the Longstop Date) will be delayed in achieving Services Availability; and/or

    - [be unable to fulfil the Post Completion Works Acceptance Requirements on or before the Planned Post Completion Works Acceptance Date or (following the Planned Post Completion Works Acceptance Date but before the Post Completion Works Longstop Date) will be delayed in completing the Post Completion Works; and or]

    - be unable to comply with its obligations under this Agreement; and/or

    - incur costs or lose Revenue,

then the Contractor is entitled to apply for an extension of time to the Start on Site Date and/or to the Planned Services Availability Date and/or (following the Planned Services Availability Date) to the Longstop Date [and/or to the Planned Post Completion Works Acceptance Date and/or (following the Planned Post Completion Works Acceptance Date) to the Post Completion Works Longstop Date] and/or relief from its obligations and/or to claim compensation under this Agreement.

  - Procedure for Relief and Compensation

Subject to clause 16.8 (Late Provision of Notice or Information), to obtain relief, extension and/or claim compensation the Contractor must:

    - as soon as practicable, and in any event within twenty (20) Business Days after it became aware that the Compensation Event has caused or is likely to cause delay, breach of an obligation under this Agreement and/or the Contractor to incur costs or lose Revenue, give to the Authority a notice of its claim for an extension of time to the Start on Site Date and/or to the [relevant] Planned Services Availability Date or (following the [relevant] Planned Services Availability Date) to the Longstop Date, [and/or to the Planned Post Completion Works Acceptance Date or (following the Planned Post Completion Works Acceptance Date) to the Post Completion Works Longstop Date], payment of compensation and/or relief from its obligations under this Agreement;

    - within ten (10) Business Days of receipt by the Authority of the notice referred to in clause 16.6.1 (Procedure for Relief and Compensation), give full details of the Compensation Event and the extension of time and/or relief from its obligations under this Agreement and/or any estimated Change in Costs and/or any estimated Change in Revenue claimed; and

    - demonstrate to the reasonable satisfaction of the Authority that:

      - the Compensation Event was the direct cause of:

        - the estimated Change in Costs; and/or

        - the estimated Change in Revenue and/or

        - any delay in the commencement of the Works on or before the Start on Site Date; and/or

        - any delay in achievement of Services Availability on or before the [relevant] Planned Services Availability Date or, (following the [relevant] Planned Services Availability Date but before the Longstop Date), any delay in the achievement of Services Availability; and/or

        - [any delay in the completion of the Post Completion Works on or before the [relevant] Planned Post Completion Works Acceptance Date or (following the [relevant] Planned Post Completion Works Acceptance Date) [but before the Post Completion Works Longstop Date] any delay in completing the [relevant] Post Completion Works;]

        - breach of the Contractor's obligations under this Agreement; and

      - the estimated Change in Costs, estimated Change in Revenue, time lost and/or relief from the obligations under this Agreement claimed, could not reasonably be expected to be mitigated or recovered by the Contractor acting in accordance with Good Industry Practice.

  - Giving of Relief and Compensation

In the event that the Contractor has complied with its obligations under clause 16.6 (Procedure for Relief and Compensation), then:

    - in the case of a delay, the Start on Site Date and the [relevant] Planned Services Availability Date, or following the [relevant] Planned Services Availability Date, the Longstop Date [and/or the [relevant] Planned Post Completion Works Acceptance Date or, following the Planned Post Completion Works Acceptance Date, the Post Completion Works Longstop Date], shall be postponed by such time as shall be reasonable for such a Compensation Event, taking into account the likely effect of the delay;

    - in the case of an additional cost being incurred or Change in Revenue:

      - on or before [the later of] the Services Availability Date [and the Post Completion Works Acceptance Date] for [that/the] Facility; or

      - as a result of Capital Expenditure being incurred by the Contractor at any time,

the Authority shall compensate the Contractor for the estimated Change in Costs as adjusted to reflect the actual Change in Costs reasonably incurred and/or, without double counting, for any Change in Revenue (to the extent it could not reasonably have been mitigated) within twenty (20) Business Days of its receipt of a written demand by the Contractor supported by all relevant information and shall do so by either making a lump sum payment pursuant to clause 69.2 (Financial adjustment during the Works Period) or where agreed by the parties, by staged monthly payments;

    - in the case of a payment of compensation for the estimated Change in Costs and, in the case of Change in Revenue, without double counting, for Revenue actually lost that does not result in Capital Expenditure being incurred by the Contractor referred to in clause 16.7.2.2 (Giving of Relief and Compensation) but which reflects a Change in Costs and/or, without double counting, Change in Revenue being incurred by the Contractor after the Planned Services Availability Date (to the extent it could not reasonably have been mitigated), the Authority shall compensate the Contractor in accordance with clause 16.10 (Method of Calculating Compensation) by an adjustment to the Annual Payment in accordance with clause 69 (Financial Adjustments); and/or

    - the Authority shall give the Contractor such relief from its obligations under this Agreement as is reasonable for such a Compensation Event.

  - Late Provision of Notice or Information

In the event that information is provided after the dates referred to in clause 16.6 (Procedure for Relief and Compensation), then the Contractor shall not be entitled to any extension of time, compensation or relief from its obligations under this Agreement in respect of the period for which the relevant information is delayed.

  - Failure to Agree

If the parties cannot agree the extent of any compensation, delay incurred, relief from the Contractor's obligations under this Agreement, or the Authority disagrees that a Compensation Event has occurred (or as to its consequences), or that the Contractor is entitled to relief under this clause 16 (Extensions of Time), the parties shall resolve the matter in accordance with the Dispute Resolution Procedure.

  - Method of Calculating Compensation

Any payment of compensation referred to in clauses 16.7.2 and 16.7.3 (Giving of Relief and Compensation) shall be calculated in accordance with clause 69 (Financial Adjustments), other than any Loss of Revenue which, for the avoidance of doubt, shall be calculated in accordance with Schedule 23 (Loss of Revenue) and compensated in accordance with clause 69 (Financial Adjustments).

- CDM Regulations

  - Responsibility for Design

As between the Contractor and the Authority, the Contractor shall be entirely responsible for the safety of any design which forms part of the Works or the Services and for the adequacy, stability and safety of all site operations and methods of construction.

  - The Contractor as Client

In accordance with the CDM Regulations, the Authority and the Contractor have elected that the Contractor shall be, and shall be treated as the only client in respect of the Works and the Services pursuant to Regulation 4(8) of the CDM Regulations. The Contractor shall not, prior to the completion of the Works, seek in any way to withdraw, terminate or derogate from such election.

  - Duties under the CDM Regulations

The Contractor shall observe, perform and discharge and/or shall procure the observance, performance and discharge of the obligations, requirements and duties arising under the CDM Regulations in connection with the Works and the Services (other than those that remain with the Authority pursuant to Regulation 4(8) of the CDM Regulations) and shall, prior to the Planned Services Availability Date for a Facility, provide a certified copy of the final draft Health and Safety File (as defined in the CDM Regulations) for that Facility to the Authority and, within thirty (30) Business Days of issue of the Acceptance Certificate for the Facility or the relevant parts of the Works in accordance with clause 22 (Principal Obligations), a certified copy of the full and complete Health and Safety File. The Contractor shall ensure that the Health and Safety File is revised as often as may be appropriate to incorporate any relevant new information in relation either to the Works or the Services during the Contract Period.

  - Authority to Co-operate and Provide Information

    - Upon the Contractor's reasonable request the Authority shall provide to the Contractor such information and documents as may be in the Authority's possession or which the Authority may reasonably obtain which may be required by the Contractor to fulfil its duties as client for the purposes of the CDM Regulations.

    - Notwithstanding the election made under clause 17.2 (The Contractor as Client), the Authority shall observe and continue to observe the duties that are, pursuant to Regulation 4(8) of the CDM Regulations, to remain with the Authority, notably those duties under Regulations 4(4), 8(4), and 8(6).

- The Site[s]

  - Access

Subject to the other terms of this Agreement, if at any time the Contractor requires access to the Site[s] or any interest in any land which does not form part of the Site[s] or any additional rights beyond those which the Contractor has in relation to any part of the Site[s], the responsibility and cost of securing or acquiring such access or interest shall be entirely the responsibility of the Contractor.

  - Site Matters

    - Subject to the other terms of this Agreement, the Site Conditions shall be the sole responsibility of the Contractor and accordingly (but without prejudice to any other obligation of the Contractor under this Agreement) the Contractor shall be deemed to have:

      - carried out a ground physical and geophysical investigation and to have inspected and examined the Site[s] and their surroundings and (where applicable) any existing structures or works on, over or under the Site[s];

      - satisfied itself as to the nature of the Site Conditions, the ground and the subsoil, the form and nature of the Site[s], the load-bearing and other relevant properties of the Site[s], the risk of injury or damage to property affecting the Site[s], the nature of the materials (whether natural or otherwise) to be excavated and the nature of the design, works, labour and materials necessary for the execution of the Works;

      - satisfied itself as to the adequacy of the means and rights of access to and through the Site[s] and any accommodation it may require for the purposes of fulfilling its obligations under this Agreement (such as additional land or buildings outside the Site[s]);

      - satisfied itself as to the possibility of interference by persons of any description whatsoever (other than the Authority) with access to or use of, or rights in respect of, the Site[s] with particular regard to the owners of any land adjacent to the Site[s]; and

      - satisfied itself as to the precautions, times and methods of working necessary to prevent any nuisance or interference, whether public or private, being caused to third parties.

    - Subject to the other terms of this Agreement, the Contractor accepts full responsibility for all matters referred to in clause 18.2 (Site Matters) and the Contractor shall be responsible for, and hold the Authority harmless from, cleaning up or otherwise dealing with any Contamination at the Site[s] in accordance with and so that it shall at all times comply with its obligations under this Agreement including (without limitation) complying with, at its own cost, Good Industry Practice, any applicable Legislation and any Necessary Consents, orders, notices or directions of any regulatory body (whether made against the Authority or the Contractor).

    - To the extent that unforeseen ground conditions and/or Contamination exist in any parts of the Site[s] which are under existing buildings structures or hard standing areas as at the Commencement Date and which it is not practical for the Contractor to investigate or survey, the Contractor shall not be responsible for them, [unless they were discovered by the Building Surveys/Asbestos Surveys or would have been discovered in the Building Surveys/Asbestos Surveys had that survey been carried out and with the level of skill and care reasonably to have been expected from competent professionals carrying out such survey or would have been identified had the Contractor carried out such additional surveys as it would have been reasonable to expect an experienced contractor to have carried out in the circumstances]. If the Contractor is not responsible for such ground conditions and/or Contamination under this clause 18.2.3 (Site Matters) then the Authority shall be so responsible.

    - Where pursuant to clause[s] 18.2.3 (Site Matters) [and 18.2.6 (Site Matters)] the Authority is responsible for any of the matters referred to then the following provisions shall apply:

      - where any such matter arises on or before the Services Availability Date [Post Completion Works Acceptance Date]  [for such Site] it shall be deemed to be a Compensation Event and any work which is required or instructed to be done in consequence of it shall be deemed to be an Authority Change;

      - where any such matter arises after the Services Availability Date [Post Completion Works Acceptance Date] [for such Site] it shall be deemed to be a Relief Event and no Performance Adjustment Points  will accrue and no Performance Adjustments may be made in respect of the relevant Zone pursuant to Schedule 6 (Payment and Performance Monitoring System) and any work or change to the Services or to the operation of the affected Facility or part thereof as a result or which is required or instructed to be done in consequence of it, shall be deemed to be an Authority Change;

      - where any such matter is Contamination (before or after the Services Availability Date) the Authority shall further hold the Contractor harmless from cleaning up and otherwise dealing with such Contamination and shall indemnify the Contractor in respect of all Direct Losses incurred by the Contractor resulting from such Contamination,

and the Contractor shall in carrying out any works referred to in clauses 18.2.4.1 (Site Matters) and 18.2.4.2 (Site Matters) do so in accordance with and so that it shall at all times comply with its obligations under this Agreement including (without limitation) complying with Good Industry Practice, any applicable Legislation and any Necessary Consents, orders, notices or directions of any regulatory body (whether made against the Authority or the Contractor).

    - Subject to clauses 18.2.6 (Site Matters) and 18.2.7, to the extent that any part(s) of the Site[s] suffer from or are affected by Contamination arising from a source off Site (whether or not on adjacent land) the Contractor shall be responsible for cleaning up or otherwise dealing with such Contamination and for preventing the reoccurrence of such Contamination on the Site and then the following provisions shall apply:

      - where any such matter arises on or before the Services Availability Date [for such Site] it shall be deemed to be a Relief Event for a reasonable period (to be agreed between the parties acting reasonably) for the purposes of this Agreement;

      - where any such matter arises after the Services Availability Date [for such Site] it shall be deemed to be a Relief Event and no Performance Adjustment Points will accrue and no Performance Adjustments may be made in respect of the relevant Zone pursuant to Schedule 6 (Payment and Performance Monitoring System) for a reasonable period (to be agreed between the parties acting reasonably) but any work or change to the Services required or instructed to be done in consequence of it, shall be the Contractor's responsibility and shall not constitute an Authority Change;

      - before or after the Services Availability Date the Contractor shall:

        - clean up, or otherwise deal with, such Contamination, and take steps reasonably necessary to prevent the recurrence of the same, all in accordance with Good Industry Practice, all relevant Necessary Consents and Legislation; and

        - other than where clause 18.2.5.4 (Site Matters) applies and subject to clause 18.2.7 hold the Authority harmless from, and indemnify the Authority in respect of, all Direct Losses incurred by the Authority resulting from such Contamination; and

      - the Authority shall, but only to the extent that the Contractor is able to demonstrate to the Authority that it does not have the right to take action against third parties in its own name to recover the losses suffered or incurred by the Contractor in cleaning up or otherwise dealing with such Contamination, at the Authority's option either:

        - take such action against third parties in its own name as the Contractor may (acting reasonably) direct; or

        - permit the Contractor to take such action in the name of the Authority at the Contractor's own expense in which case the provisions of clauses 60.5 (Conduct of Claims) and 60.6 (Costs of Claims) shall apply as if the Contractor were the Indemnifying Party and the Authority were the Indemnified Party, except that the Contractor shall not pay or settle such claims without the prior consent of the Authority,

subject to the Contractor indemnifying the Authority in respect of all costs properly and reasonably incurred by the Authority in respect of such action. Where the Authority takes action under clause 18.2.5.4.1 (Site Matters) or 18.2.5.4.2 (Site Matters) (or where it is otherwise obliged to take action against third parties in respect of such losses), the Authority shall be liable to the Contractor for all losses suffered or incurred by the Contractor as a result of its obligations under this clause 18.2.5 (Site Matters), provided that the Contractor's entitlement in respect of any matter to which this clause 18.2.5.4 (Site Matters) applies shall be limited to the amount recovered by or in the name of the Authority from the relevant third party in respect of the losses referred to in this clause 18.2.5.4 (Site Matters).

    - To the extent that any part(s) of the Site[s] suffer from or are affected by Contamination arising from a source off Site where such off Site source is land for which the Authority is responsible, the Authority shall be responsible for such Contamination and the provisions of clause 18.2.4 (Site Matters) shall apply.

    - The Contractor's responsibility and liability under clause 18.2.5 (Site Matters) shall be limited to the amount recovered by the Contractor from the third party responsible for the Contamination arising from the source off the Site subject to the Contractor having taken all reasonable steps (including as applicable the operation of clause 18.2.5.4) to recover the losses suffered or incurred.

  - Consents and Planning Approval

[Subject to clause 18.3A (Authority Necessary and Authority Planning Conditions Consents), and clause 18.3B (Judicial Review Proceedings)] the Contractor shall:

    - obtain and maintain all Necessary Consents which may be required for the performance of the Project;

    - be responsible for obtaining each Necessary Consent (which it is required to obtain pursuant to clause 18.3.1 (Consents and Planning Approval)) within the period of its validity in accordance with its terms;

    - supply free of charge to the Authority's Representative a copy of any application for a Necessary Consent (with a copy of all accompanying drawings and other documents) and a copy of any Necessary Consent obtained;

    - comply with the conditions attached to any Necessary Consents and procure that no such Necessary Consent is breached by it or any person under its control and use all reasonable endeavours to procure that no Necessary Consent is revoked and that all Necessary Consents continue in full force and effect for such time as is necessary for the Contractor to carry out the Works and/or the Services;

    - not (and shall use all reasonable endeavours to procure that any other person over whom it has control shall not) without the prior consent of the Authority under this Agreement (which consent shall not be unreasonably withheld or delayed) apply for or agree to any change, relaxation or waiver of any Necessary Consent (whether obtained before or after the date of this Agreement) or of any condition attached to it but, subject to the compliance by the Contractor with its obligations under this clause 18.3 (Consents and Planning Approval), references in this Agreement to Necessary Consents shall be construed as referring to the Necessary Consents as from time to time varied, relaxed or waived.

[18.3A	Authority Necessary Consents and Authority Planning Conditions

18.3A.1	The Authority shall obtain the Authority Necessary Consents, or shall procure that the Authority Necessary Consents are obtained, subject to the Contractor using all reasonable endeavours to assist the Authority to obtain or procure the obtaining of the Authority Necessary Consents.

18.3A.2	Where the Authority has obtained or procured the obtaining of an Authority Necessary Consent then such consent shall be treated as a Necessary Consent for the purposes of clauses 18.3.2, 18.3.4 and 18.3.5 (Consents and Planning Approval) unless such ongoing obligations and/or maintenance can only reasonably be carried out or procured by the Authority and the Contractor shall not be responsible for or in relation to any revocation or discontinuance of any Necessary Consent or Authority Necessary Consent to the extent caused by or attributable to any act or omission of the Authority or any Authority Related Party.

18.3A.3	[The Authority shall discharge or procure the discharge of the Authority Planning Conditions [subject to the Contractor using all reasonable endeavours to assist the Authority to discharge or procure the discharge of the Authority Planning Conditions].]

[18.3B	Judicial Review Proceedings

18.3B.1	Either Party shall notify the other forthwith upon becoming aware of any Judicial Review Proceedings.

18.3B.2	If in accordance with clause 18.3B.1 either Party serves a notice then:

18.3B.2.1	the Authority shall be entitled by notice in writing to the Contractor (the Suspension Notice) to require the Contractor to suspend the Works (or the relevant part thereof) and the Contractor will forthwith suspend the Works (or the relevant part thereof) upon receipt of the Suspension Notice at the Site which is the subject of any Judicial Review Proceedings and such suspension shall subsist subject to clause 18.3B.5.1 until such time as (i) such Judicial Review Proceedings are finally dismissed or withdrawn; or (ii) provided that there is no subsisting Judicial Review Proceedings Action the Authority informs the Contractor that the Works (or the relevant part thereof) should be resumed (whichever is the earlier); and/or

18.3B.2.2 	the Contractor must suspend the Works (or the relevant part thereof) at the Site which is the subject of any Judicial Review Proceedings Action and forthwith give notice of such suspension in writing to the Authority (the Contractor Suspension Notice) and such suspension shall subsist subject to clause 18.3B.5.2 until such time as (i) such Judicial Review Proceedings Action is finally disposed of thereby enabling the Works to resume; (ii) this Agreement is varied by means of a Authority Change in order to permit the Contractor lawfully to resume the Works (or the relevant part thereof) and/or perform its obligations under this Agreement; or (iii) the Parties otherwise agree in writing that the Works (or the relevant part thereof) should be resumed (whichever is the earlier).

18.3B.3	Save for where the Contractor or a Contractor Related Party (and for the purposes of this clause 18.3B.3 only "Contractor or a Contractor Related Party" shall exclude an employee or agent of the Contractor or of a Contractor Related Party acting in a personal capacity) has brought or caused to be brought on its behalf Judicial Review Proceedings, any suspension of the Works (or the relevant part thereof) pursuant to clause 18.3B.2.1 or 18.3B.2.2 shall be deemed to be a Compensation Event from the date of the Suspension Notice or Contractor Suspension Notice as appropriate and the provisions of clause 16 (Extension of Time) shall apply (and for the purposes of the provisions of clause 16.1 (Notice) the Contractor is deemed to have become aware that there will be or is likely to be a delay in the commencement or completion of the Works on the date of receipt of the Suspension Notice or the date of the Contractor Suspension Notice as appropriate).

18.3B.4	Where a Contractor Related Party (and for the purposes of this clause 18.3B.4 only "Contractor Related Party" shall exclude an employee or agent of the Contractor or any Contractor Related Party acting in a personal capacity) has brought or caused to be brought on the Contractor Related Party's behalf Judicial Review Proceedings any suspension of the Works (or the relevant part thereof) pursuant to clause 18.3B.2 or 18.3B.3 shall be deemed to be a Relief Event from the date of the Suspension Notice or Contractor Suspension Notice as appropriate and the provisions of clause 55 (Relief Events) shall apply but solely for the purpose of entitling the Contractor to apply for relief from any rights of the Authority to terminate this Agreement for Contractor Default pursuant to limbs (h), (i); and/or (j) of that definition.

18.3B.5	If by the date falling [twelve (12)] months after the date of the:

18.3B.5.1	Suspension Notice, the Works (or the relevant part thereof) are still suspended pursuant to clause 18.3B.2.1; or

18.3B.5.2	Contractor Suspension Notice, the Works (or the relevant part thereof) are still suspended pursuant to clause 18.3B.2.2,

then unless agreed otherwise in writing between the Parties, the Authority will issue an Authority Notice of Change to remove that Facility from the scope of the Project and the provisions of paragraphs 2 to 14 of Part 4 of Schedule 24 shall apply save that the Contractor shall not be entitled to serve a notice under paragraph 3.1 of Part 4 of Schedule 24 in respect of such Authority Change.]

  - No Warranty

Except as otherwise expressly provided in this Agreement the Contractor shall take the Site[s] in [its/their] state and condition in all respects as at the date of this Agreement and nothing in this Agreement or otherwise shall constitute or imply a warranty by or on the part of the Authority as to the fitness and suitability of the Site[s] or any part thereof for the Works or Services or for any other purpose.

  - Third Party Rights

The Contractor shall observe and comply with any third party rights (including public rights) which may exist from time to time in respect of land comprising and adjoining the Site[s], and the Contractor shall ensure that the Works and Services are carried out in such a way as not to interfere with access to and use and occupation of public or private roads or footpaths by any person who is entitled to any such access, use or occupation.

  - Fire Folder

The parties shall each act reasonably and in good faith to procure that an up-to-date fire folder is maintained for [the/each] Facility in accordance with government guidance referring to the Regulatory Reform (Fire Safety) Order 2005. In particular the Contractor shall:

    - design and install a fire alarm system emergency lighting [and a sprinkler system];

    - provide information relating to the operation of the fire alarm system and emergency lighting [and sprinkler system];

    - maintain maintenance/test records for the fire alarm systems and emergency lighting [and sprinkler system]; and

    - prepare risk assessments for emergency events including fires;

    - prepare and communicate the evacuation procedures including instruction to staff and visitors at the [Facility/Facilities] on the correct action when discovering a fire and on the correct action when the fire alarm is sounded;

    - prepare notices/signs reinforcing the evacuation procedures; and

    - take all reasonable steps to maintain discipline of the occupants of the [Facility/Facilities] to prevent fires and deliberate and/or accidental activation of the system.

  - [Defects and Asbestos]

    - Defects

The Contractor accepts, in relation to the Buildings other than the New Buildings, entire responsibility (including any financial and other consequences which result whether directly or indirectly) for:

      - any Defects identified in the Buildings Survey[s]; and

      - any Defects that would have been identified in any Buildings Survey[s] had [that/those] survey[s] been carried out with the level of skill and care reasonably to have been expected from competent professionals carrying out such survey or (unless access to carry out additional surveys has been denied by the Authority and then only to the extent that such access was denied) would have been identified had the Contractor carried out such additional surveys as it would have been reasonable to expect an experienced contractor to have carried out in the circumstances; and

      - any Defects caused by the Contractor,

provided that where the Contractor is, in the reasonable opinion of the Authority, diligently pursuing the party who is responsible for the Buildings Survey, then any delay to the Services Availability Date caused by a Defect shall be treated as a Relief Event, subject to and in accordance with clause 55 (Relief Events).

    - The Authority accepts, in relation to the Buildings other than the New Buildings, entire responsibility for Defects which have not been identified in the Buildings Survey[s] (other than those referred to in clause 18.7.1 (Defects) and the discovery of any such Defects shall:

      - prior to the Services Availability Date [for a Facility] constitute a Compensation Event subject to and in accordance with clause 16,

      - [in respect of Post Completion Works prior to the Post Completion Works Acceptance Date constitute a Compensation Event subject to and in accordance with clause 16 (Extensions of Time);] and

      - after the Services Availability Date [for a Facility] be deemed to be a Relief Event and no Performance Adjustment Points will accrue and no Performance Adjustments may be made in respect of the relevant Zone pursuant to Schedule 6 (Payment and Performance Monitoring System) for the period during which the Defect subsists and/or in respect of which remedial works are being carried out and any work or change to the Services or to the operation of the affected Facility as a result or which is required or instructed to be done in consequence of it, shall constitute an Authority Change.

    - The Contractor accepts, in relation to the New Buildings, entire responsibility (including any financial and other consequences which result whether directly or indirectly) for any Defects.

    - Asbestos Liability

Subject to clauses 18.7.5 (Asbestos Liability) and 18.7.6 (Asbestos Liability), the Contractor accepts, in relation to the Buildings other than the New Buildings, full responsibility (including any financial and other consequences which result whether directly or indirectly) for:

      - any Asbestos identified in the Asbestos Survey[s]; and

      - any Asbestos that ought reasonably to have been discovered or that could otherwise have been reasonably expected to have been identified or found in the Asbestos Survey[s] [given the scope of such Asbestos Survey[s]] or would have been identified, had that survey been carried out with the level of skill and care reasonably to have been expected from competent professionals carrying out such survey,

provided that where the Contractor is, in the reasonable opinion of the Authority, diligently pursuing the party who is responsible for the Asbestos Survey, then any delay to the Services Availability Date caused by such Asbestos shall be treated as a Relief Event, subject to and in accordance with clause 55 (Relief Event).

    - The Authority accepts, in relation to the Buildings other than the New Buildings, full responsibility for Asbestos which has not been identified in the Asbestos Survey[s] (other than any Asbestos referred to in clause 18.7.4 (Asbestos Liability)) and the discovery of any such Asbestos shall:

      - prior to the Services Availability Date [for a Facility] constitute a Compensation Event subject to and in accordance with clause 16 (Extensions of Time) in respect of the Works;

      - [prior to the Post Completion Works Acceptance Date for a Facility constitute a Compensation Event subject to and in accordance with clause 16 (Extensions of Time) in respect of such Post Completion Works; and]

      - after the Services Availability Date [for a Facility] be deemed to be a Relief Event and no Performance Adjustment Points will accrue and no Performance Adjustments may be made in respect of any Zone in which Works [and Post Completion Works] have been completed for the period during which such Asbestos is subsisting and/or in respect of which removal or remedial works are being carried out and any work or change to the Services or to the operation of the affected Facility as a result or which is required or instructed to be done in consequence of it, shall constitute an Authority Change.

    - Unless the exposure arises directly or indirectly as a result of any act or omission of the Contractor or any Contractor Related Party, the Authority accepts, in relation to the Buildings other than the New Buildings, full responsibility (including any financial and other consequences which result whether directly or indirectly) for death and personal injury in respect of exposure to Asbestos in such Buildings.

  - Fossils and Antiquities

    - As between the parties, all fossils, antiquities and other objects having artistic, historic or monetary value and human remains which may be found on or at the Site[s] are or shall become, upon discovery, the absolute property of the Authority.

    - Upon the discovery of such item during the course of the Works or Services, the Contractor shall:

      - immediately inform the Authority's Representative of such discovery;

      - take all steps not to disturb the object and, if necessary, cease any Works or Services insofar as the carrying out of such Works or Services would endanger the object or prevent or impede its excavation; and

      - take all necessary steps to preserve the object in the same position and condition in which it was found.

    - The Authority shall procure that the Authority's Representative promptly, and in any event within [five (5)] [ten (10)] Business Days, issues an instruction to the Contractor specifying what action the Authority's Representative requires to be taken in relation to such discovery provided that if no such instruction is forthcoming within such period the Contractor may continue to carry out the Works or Services.

    - The Contractor shall promptly and diligently comply with any instruction issued by the Authority's Representative referred to in clause 18.8.3 (Fossils and Antiquities) at its own cost (except and to the extent that such instruction constitutes an Authority Change pursuant to clause 18.8.6 (Fossils and Antiquities) in which case the provisions of the Change Protocol shall apply).

    - If directed by the Authority's Representative, the Contractor shall allow representatives of the Authority to enter the Site[s] for the purposes of removal or disposal of such discovery, provided that such entry shall be subject to the Authority complying with all relevant safety procedures, which shall include any relevant health and safety plans for the construction of the Facility from time to time and any reasonable directions with regard to site safety that may be issued by or on behalf of the Contractor's Representative from time to time.

    - If any instruction referred to in clause 18.8.3 (Fossils and Antiquities) includes a requirement for the Contractor to suspend the carrying out of the Works or Services and/or to carry out works (being any work of alteration, addition, demolition or extension or variation in [any/the] Facility) which are not works which would be strictly necessary for the purpose of compliance with Legislation or any Necessary Consents, such works or instruction to suspend shall be deemed to be an Authority Change and the provisions of the Change Protocol shall apply.

    - The Authority shall act promptly and diligently in dealing with its obligations in this clause 18.8 (Fossils and Antiquities) in relation to any find so as to mitigate any effect on the Contractor, the Works and/or the Services.

- Monitoring and Inspection

  - Right of Inspection

The Contractor shall procure that the Authority or any representative or adviser of the Authority shall have, at all reasonable times and upon giving reasonable notice, the right (but not so as to delay or impede the progress of the Works) to enter [any/the] Site[s] in order to inspect the state and progress of the Works (and to ascertain whether they are being properly executed), the operation and maintenance of the Project and to monitor compliance by the Contractor with its obligations under this Agreement.

  - Right to Open Up

    - Subject to clause 19.2.2 the Authority's Representative shall have the right at any time prior to:

      - the Services Availability Date for a Facility in respect of the Works; and

      - [the Post Completion Works Acceptance Date for a Facility in respect of the Post Completion Works],

to request the Contractor to open up and inspect any part or parts of such Works [or Post Completion Works] at that Facility where the Authority's Representative reasonably believes that such part or parts of the Works [or Post Completion Works] is or are defective and the Contractor shall comply with such request.

    - Prior to exercising his right pursuant to clause 19.2.1 (Right to Open Up) the Authority's Representative shall notify the Contractor of his intention to exercise such right, setting out detailed reasons.

    - If, following the exercise by the Authority's Representative of his right pursuant to clause 19.2.1 (Right to Open Up), the inspection shows that the relevant part or parts of the Works are not defective, the exercise of such rights shall, subject to (and in accordance with) the provisions of clause 16 (Extensions of Time), be treated as a Compensation Event.

    - If, following the exercise by the Authority's Representative of his right pursuant to clause 19.2.1 (Right to Open Up), the inspection shows that the relevant part or parts of the Works is or are defective, the Contractor shall rectify and make good such defect(s) and any consequence of such rectification and/or making good defect(s) shall be carried out by the Contractor at no cost to the Authority and the Contractor shall not be entitled to any extension of time in relation to such rectification and making good of the Works.

    - If, following the exercise by the Authority's Representative of his right pursuant to clause 19.2.1 (Right to Open Up), the Authority's Representative is of the opinion that the inspection shows that the relevant part or parts of the Works is or are defective and the Contractor does not agree with such opinion, the matter shall be determined in accordance with clause 64 (Dispute Resolution).

    - Without prejudice to the rights of the Authority's Representative pursuant to this clause 19.2 (Right to Open Up) the parties acknowledge that the exercise of such rights shall not in any way affect the obligations of the Contractor under this Agreement save as expressly set out in this clause 19 (Monitoring and Inspection).

  - Inspection of Facilities

The Authority or a representative or advisor of the Authority may at all reasonable times and on reasonable notice and subject to obtaining the consent of the relevant manufacturer or supplier (which the Contractor shall use all reasonable endeavours to obtain) enter upon any property used by the Contractor as training or workshop facilities and places where work is being prepared or materials are being obtained for the Project for the purposes of general inspection and of attending any test or investigation being carried out in respect of the Works.

  - Contractor's Reasonable Assistance

The Contractor shall procure that satisfactory facilities are made available to the Authority and any representative of the Authority and that reasonable assistance is given for the purposes of clauses 19.1 (Right of Inspection), 19.2 (Right to Open Up) and 19.3 (Inspection of Facilities), subject to the Contractor's and the Sub-Contractors' construction obligations not being adversely affected and to the Authority reimbursing the Contractor for any reasonable costs or expenses incurred as a result of the action taken by the Authority under clauses 19.1 (Right of Inspection), 19.2 (Right to Open Up) and 19.3 (Inspection of Facilities).

  - Health and Safety Requirements

The Authority and its representative shall at all times comply with all relevant health and safety procedures which shall include any relevant health and safety plans for the construction of the Facilities, the Building Contractor's Site Rules from time to time and any reasonable directions with regard to site safety that may be issued by or on behalf of the Building Contractor Site Manager from time to time when exercising its rights under this clause 19 (Monitoring and Inspection).

  - Supply of Information

The Contractor shall supply to the Authority and any representative or adviser of the Authority visiting [any of/the] Site[s] pursuant to clauses 19.1 (Right of Inspection), 19.2 (Right to Open Up) and 19.3 (Inspection of Facilities) such information in respect of the Works as may reasonably be required.

  - Site Meetings, Monitoring and Inspection

    - The Authority's Representative shall have such rights of access to the Site[s] in an Emergency as it (acting reasonably) considers suitable in the circumstances

    - Without prejudice to the generality of clause 19.7.1 (Site Meetings, Monitoring and Inspection) the Contractor shall procure that monthly progress meetings and site meetings are held and that the Authority's Representative shall have the right to attend such monthly progress meetings and site meetings and to attend as observer such other meetings as the Authority's Representative may reasonably request.

  - Increased Monitoring

If, following any viewing, visit or inspection made by the Authority, it is discovered that there are defects in the Works or that the Contractor has materially failed to comply with the Authority's Requirements or the Contractor's Proposals, the Authority may (without prejudice to any other right or remedy available to it) by notice to the Contractor increase the level of its monitoring of the Contractor until such time as the Contractor shall have demonstrated to the reasonable satisfaction of the Authority that it is capable of performing and will perform all its obligations under this Agreement.

  - Damage

Subject to clause 61.14 (Claims), if the Authority or an Authority Related Party causes material damage to the Site[s] in exercising any right under this clause 19 (Monitoring and Inspection), then such damage shall be deemed to be a Compensation Event.

- Notification of Services Availability [and/or Acceptance of Post Completion Works]

  - Inspection of [a/the] Facility

The Contractor shall give the Authority and the Independent Certifier not less than five (5) Business Days' notice of the date when it proposes to inspect [a/the] Facility with a view to achieving:

    - the issue of an Acceptance Certificate in respect of the [relevant] Facility; and/or

    - [the issue of the Post Completion Works Acceptance Certificate in respect of the [relevant] Facility;]

and on such dates the Independent Certifier shall inspect the Facility and representatives from the Authority and the Contractor shall be entitled to make a joint inspection with the Independent Certifier.

  - Dates on which Services Availability may occur

The Services Availability Date for [any/the] Facility shall be the date on which the Acceptance Certificate is issued in respect [of the relevant Facility/thereof] [provided that if the Acceptance Certificate is issued prior to the Planned Services Availability Date, the Services Availability Date [for that Facility] shall be the Planned Services Availability Date.]

  - Independent Certifier

    - The Independent Certifier's Deed of Appointment specifies the duties of the Independent Certifier owed to the Authority and the Contractor.

    - The Authority and the Contractor shall on or before the date of this Agreement [execute the Independent Certifier's Deed of Appointment which shall be forwarded to the Independent Certifier for execution of such deed within 15 Business Days of the date of this Agreement][procure that the Independent Certifier's Deed of Appointment is executed by the parties to it.]

    - The Authority and the Contractor shall each comply with their respective obligations under the Independent Certifier's Deed of Appointment and shall take all reasonable steps to procure that the Independent Certifier carries out the Independent Certifier services upon the terms of the Independent Certifier's Deed of Appointment.

    - The Authority and the Contractor agree to co-operate with each other generally in relation to all matters within the scope of or in connection with the Independent Certifier's Deed of Appointment. Instructions and representations issued or made by either of the Authority or the Contractor to the Independent Certifier shall be simultaneously copied by that party to the other and both parties shall be entitled to attend all inspections undertaken by or meetings involving the Independent Certifier.

  - Issue of Acceptance Certificate or notice of Non Completion

    - Within five (5) Business Days of any inspection referred to in clause 20.1 (Inspection of [a/the] Facility) [to determine whether Services Availability or completion of the Post Completion Works (as the case may be) has been achieved] the Independent Certifier shall either:

      - issue an Acceptance Certificate confirming that he is satisfied that the Services Availability Requirements have been met in respect of the [relevant] Facility; or

      - [issue a Post Completion Works Acceptance Certificate confirming that he is satisfied that the [relevant] Post Completion Works Acceptance Requirements have been met in respect of the [relevant] Facility; or]

      - issue a notice stating that the Acceptance Certificate [or the [relevant] Post Completion Works Acceptance Certificate (as the case may be)] has not been issued and specifying any outstanding matters that must be attended to before an Acceptance Certificate [or the Post Completion Works Acceptance Certificate (as the case may be)] can be issued in respect of the [relevant] Facility,

provided that if the Services Availability Requirements [or the Post Completion Works Acceptance Requirements] have been met, the Independent Certifier shall issue [an/the] Acceptance Certificate [or the relevant Post Completion Works Acceptance Certificate (as the case may be)] in respect of [a/the] Facility notwithstanding that there are Snagging Items in respect of the Facility.

    - The parties shall procure that where the Independent Certifier reasonably considers that the Services Availability Requirements [or the [relevant] Post Completion Works Acceptance Requirements (as the case may be)] have not been met it shall immediately following its inspection pursuant to clause 20.1 (Inspection of [a/the] Facility) issue to the Authority and the Contractor a notice (a Notice of Non Completion) detailing all outstanding matters which are required to be attended to before the [relevant] Facility can be considered to have met the Services Availability Requirements [or the [relevant] Post Completion Works can be considered to have met the [relevant] Post Completion Works Acceptance Requirements (as the case may be)]. Following receipt of a Notice of Non Completion the Contractor shall attend to such matters and shall give the Authority and the Independent Certifier further notice in accordance with clause 20.1 (Inspection of [a/the] Facility) (but dealing only with matters raised in the Notice of non-Completion and with a notice period of no less than twenty four (24) hours for the purposes of clause 20.1) (Inspection of [a/the] Facility) so that the procedures in clause 20.4.1 (Issue of Acceptance Certificate or Notice of Non-Completion) are repeated as often as necessary to ensure that all outstanding matters in relation to the [relevant] Facility are attended to and an Acceptance Certificate [or a Post Completion Works Acceptance Certificate (as the case may be)] can be issued in accordance with clause 20.4.1.1 or 20.4.1.2 (Issue of Acceptance Certificate or Notice of Non-Completion).

  - Effect of Issue of Acceptance Certificate [or Post Completion Works Acceptance Certificate]

The issue of an Acceptance Certificate [or Post Completion Works Acceptance Certificate] shall, in the absence of manifest error, bad faith or fraud, indicate for the purpose of ascertaining the Services Availability Date [or the Post Completion Works Acceptance Date (as applicable)] that the relevant Facility is in compliance with the Services Availability Requirements [(or that the relevant Post Completion Works are in accordance with the Post Completion Works Acceptance Requirements (as the case may be))] and, without prejudice to the right of either party to make a claim under the Independent Certifier's Deed of Appointment, shall in no way lessen or affect the other obligations of the Contractor under this Agreement in relation to that Facility or any other part of the Works or the Services or signify the Authority's approval of the means of delivery of the Services, and the Contractor shall pursuant to clause 20.6 (Snagging Items) following the date of issue of the Acceptance Certificate [or Post Completion Works Acceptance Certificate] carry out and complete such (if any) of the items on the Snagging List as have not been so completed on the date of issue of the Acceptance Certificate [or Post Completion Works Acceptance Certificate].

  - Snagging Items

In the event that [an/the] Acceptance Certificate [or Post Completion Works Acceptance Certificate] [for a Facility] is expressed to be subject to Snagging Items:

    - The Independent Certifier shall within five (5) Business Days of the issue of the [relevant] Acceptance Certificate [or Post Completion Works Acceptance Certificate] issue to the Contractor and the Authority a list of the relevant Snagging Items [for that Facility] (the Snagging List). Within five (5) Business Days of receipt from the Independent Certifier of the Snagging List the Contractor shall provide to the Authority and the Independent Certifier a reasonable programme for making good each Snagging Item set out in the Snagging List provided that such programme shall require that each Snagging Item shall be made good within twenty (20) Business Days of the date of the agreement or determination of that programme or within such time as is reasonably practicable. The parties shall seek to agree such programme and in default of agreement shall refer the matter for determination under the Dispute Resolution Procedure. The programme agreed or determined in accordance with this clause 20.6 (Snagging Items) shall be known as the Snagging Programme.

    - The Contractor shall procure that each Snagging Item is made good in accordance with the Snagging Programme to the satisfaction of the Independent Certifier. If any Snagging Item has not been rectified by the date set out in the Snagging Programme then the Authority shall be entitled to effect such repairs as may be necessary and recover the costs of doing so from the Contractor as a debt.

  - Site Clearance

Following issue of an Acceptance Certificate in respect of [a/the] Facility, the Contractor shall or shall procure that the Building Contractor shall [carry out the Post Completion Works at the Site [relating to such Facilities] so that such Post Completion Works are completed by the relevant Planned Post Completion Works Acceptance Date provided that in default the Authority shall be entitled to employ an alternative contractor to carry out such Post Completion Works and shall be entitled to be reimbursed by the Contractor for any costs properly and reasonably incurred in the carrying out of such Post Completion Works] / [clear from the [relevant] Site to the reasonable satisfaction of the Authority all temporary structures and equipment and in default the Authority shall be entitled to employ an alternative contractor to clear them and shall be entitled to be reimbursed by the Contractor for any costs reasonably incurred in clearing or procuring the clearing of them provided that the Authority shall not be entitled to exercise such right for a period of one (1) week following the date of the Acceptance Certificate [for that Facility].]

  - Defects liability

    - Any Contractor Defects which are apparent on [the/a] Services Availability Date [or Post Completion Works Acceptance Date] or which shall appear within the Contractor Defects Liability Period shall be specified by the Authority in a Schedule of Contractor Defects which shall be delivered to the Contractor as an instruction of the Authority to make good the Contractor Defects listed not later than ten (10) Business Days after the expiration of the Contractor Defects Liability Period, and within a reasonable time after the receipt of such Schedule, the Contractor Defects specified shall be made good by the Contractor at no cost to the Authority.

    - Notwithstanding clause 20.8.1 (Defects liability), the Authority may, not later than ten (10) Business Days after the expiration of the Contractor Defects Liability Period, whenever it considers it necessary so to do, issue instructions requiring any Contractor Defect which became apparent within ten (10) Business Days following the end of the Contractor Defects Liability Period to be made good and the Contractor shall within a reasonable time (and in any event within a period of ten (10) Business Days) after receipt of such instructions comply with the same at no cost to the Authority.

    - In cases of an Emergency the Authority's instructions under clauses 20.8.1 and 20.8.2 (Defects liability) may require any matter to be made good within such period of time specified in the instruction as the circumstances shall require, and the provisions of clauses 20.8.1 and 20.8.2 (Defects liability) shall be applied by reference to such reduced time period.

    - If the Contractor fails to comply with an instruction issued pursuant to clauses 20.8.1 and 20.8.2 (Defects liability) within ten (10) Business Days or such other period as may be agreed between the parties, of the relevant instruction, the Authority may itself carry out or employ and pay others to carry out the necessary making good, recovering from the Contractor as a debt the costs and losses incurred as a result of such Contractor Defect.

    - When all Contractor Defects which the Authority may have required to be made good under clauses 20.8.1 and 20.8.2 (Defects liability) have been made good, the Independent Certifier shall issue a certificate to that effect, which certificate shall not be unreasonably delayed or withheld, and completion of making good defects shall be deemed for all the purposes of this Agreement to have taken place on the day stated in such notice (the Certificate of Making Good Defects) provided that the Independent Certifier shall not be required to issue any Certificate of Making Good Defects any earlier than ten (10) Business Days after the expiry of the Contractor Defects Liability Period.

- Delay And Supervening Unavailability

  - [Without prejudice to the provisions of Part 7 (Termination) of  this Agreement, the Authority shall not be entitled to claim liquidated or general damages in respect of the Services Availability Date occurring after the corresponding Planned Services Availability Date [for that Facility] [or in respect of a Post Completion Works Acceptance Date occurring after its corresponding Planned Post Completion Works Acceptance Date].]

OR

21.1	[If [an/the] Acceptance Certificate shall not have been issued [in relation to a Facility] by the Planned Services Availability Date [for that Facility], the Authority shall be entitled to issue a notice or notices in writing to the Contractor notifying the Contractor of the delay and that liquidated damages may become payable. In the event of a revised Planned Services Availability Date [for the relevant Facility] being fixed after the issuing of such a notice, such fixing shall cancel the relevant earlier notice and the Authority shall issue such further notices in writing under this clause 21.1 (Delay and Supervening Unavailability) as may be necessary.

  - Provided a notice or notices has or have been issued under clause 21.1 (Delay and Supervening Unavailability) (and has or have not been cancelled), and subject to clause 21.3 (Delay and Supervening Unavailability), then from the [relevant] Planned Services Availability Date until (i) the Services Availability Date; or (ii) if earlier, the Termination Date; or (iii) the date on which the Services Availability Date would otherwise have occurred if a Compensation Event occurs following the Planned Services Availability Date and this delays the Services Availability Date (each a "LAD End Date"), the Contractor shall, upon the Authority's demand, pay or allow to the Authority by way of liquidated and ascertained damages, the LAD Amount in respect of each day or part of a day that elapses after the Planned Services Availability Date up to and including the LAD End Date. The Authority may (at any time after demanding the same) deduct liquidated damages arising under this clause 21.2 (Delay and Supervening Unavailability) from any sum due or to become due to the Contractor under this Agreement. Further or alternatively, the Authority may recover the same from the Contractor as a debt, and such debt shall be payable by the Contractor within five (5) Business Days of the Authority's demand

  - If a later Planned Services Availability Date is fixed pursuant to clause 21.1 (Delay and Supervening Unavailability) and, prior to such fixing, the Authority has recovered from the Contractor any LAD Amount based on a previously applicable Planned Services Availability Date which is earlier than that newly fixed, the Authority shall repay or credit to the Contractor following the Services Availability Date any LAD Amount recovered which was in excess of the Authority's entitlement.

  - The Authority and the Contractor agree and intend that the LAD Amounts which the Contractor may become liable to pay pursuant to this clause 21 (Delay and Supervening Unavailability) are not a penalty but a genuine pre-estimate of the loss which the Authority will suffer as a result of a delay in the achievement of the issue of an Acceptance Certificate after the relevant Planned Services Availability Date.

Part 4 – The Services

- Principal Obligations

  - Standard of Performance

Subject to clause 22.2 (Discrepancies):

    - the Contractor will at all times during the Services Period ensure that the Services [at each Facility] comply with and meet all the requirements of this Agreement, the Services Specification, the Service Delivery Proposals, Good Industry Practice, Guidance, Quest, [Sport England Guidance] and all applicable Authority's Policies and Legislation with effect from the [relevant] Services Availability Date [for that Facility];

    - the Contractor shall ensure, and shall procure that any Contractor Related Party shall ensure, that the Services are carried out in compliance with the Equality Requirements;

    - the Contractor will at all times during the Services Period ensure that the Services are performed by appropriately qualified and trained personnel; and

    - the Contractor shall ensure that new materials or recycled materials that are in accordance with British Standards and/or Good Industry Practice only will be used in carrying out the Services (unless the Authority agrees otherwise in writing or the contrary is set out in the Services Specification) and all goods used or included in the Services will be of satisfactory quality, and there will be used or included in the Services none of those products and materials listed in Part 1 of Schedule 9 (Prohibited Materials) nor any products or materials not in conformity with relevant British or European Union Standards or codes of practice which at the time of use are widely known to facilities management contractors or members of the relevant design profession within the European Union to be deleterious to health or safety or to the durability of buildings and/or other structures and/or finishes and/or plant and machinery in the particular circumstances in which they are used.

  - Discrepancies

In the event of a conflict or potential conflict between the standards listed in clause 22.1 (Standard of Performance), the Contractor shall notify the Authority in writing of the same and the Contractor shall submit proposals to the Authority for review through the Schedule 8 (Review Procedure) as to how it proposes to deal with such inconsistency or conflict and, after such review, the standards shall be amended accordingly and any amendment shall be made without adjustment to the Annual Payment. The Authority may not withhold its approval (or impose conditions in giving its approval) where the purpose of such withholding or such conditions is to deal with matters other than the correcting of any such inconsistency or conflict.

- Condition of the [Facility/Facilities]

  - Maintenance

The Contractor shall ensure on a continuing basis that at all times its maintenance and operating procedures set out in the Service Delivery Proposals are and remain sufficient to ensure that:

    - the [Facility /Facilities] (when constructed) meet the requirements of this Agreement and the Authority's Requirements;

    - the [Facility is/Facilities are] kept in good structural and decorative order (subject to fair wear and tear) in accordance with this Agreement, the Authority's Requirements and the Service Delivery Proposals;

    - it can maintain the design intention of the [Facility/Facilities] to achieve [its/their] full working life as set out in [paragraph 1.12] of the Technical Specification for the duration of the Contract Period;

    - the Contractor can deliver the Services in accordance with this Agreement and the Services Specification; and

    - the [Facility is/Facilities are] handed back to the Authority on the Expiry Date in a condition complying with the Handback Requirements.

  - Surveys

    - If the Authority reasonably believes that the Contractor is in breach of its obligations under clause 23.1 (Maintenance) then it may carry out or procure the carrying out of a survey of the [Facility/Facilities] to assess whether the [Facility has/Facilities have] been and [is/are] being maintained by the Contractor in accordance with its obligations under clause 23.1 (Maintenance). This right may not be exercised more than once every [two (2) years].

    - The Authority shall notify the Contractor in writing a minimum of ten (10) Business Days in advance of the date it wishes to carry out the survey. The Authority shall consider in good faith any reasonable request by the Contractor for the survey to be carried out on a different date if such request is made at least five (5) Business Days prior to the notified date and the Contractor (acting reasonably) is able to demonstrate that carrying out the survey on the notified date would materially prejudice the Contractor's ability to provide the Services.

    - When carrying out any survey, the Authority shall use reasonable endeavours to minimise any disruption caused to the provision of the Services by the Contractor. The cost of the survey, except where clause 23.2.4 (Surveys) applies, shall be borne by the Authority. The Contractor shall give the Authority (free of charge) any reasonable assistance required by the Authority from time to time during the carrying out of any survey.

    - If a survey shows that the Contractor has not complied or is not complying with its obligations under clause 23.1 (Maintenance), the Authority shall:

      - notify the Contractor of the standard that the condition of the [Facility/Facilities] should be in to comply with its obligations under clause 23.1 (Maintenance) and this Agreement generally;

      - specify a reasonable period within which the Contractor must carry out such rectification and/or maintenance work; and

      - if the survey shows a material non-compliance by the Contractor with its obligations under clause 23.1 (Maintenance), be entitled to be reimbursed by the Contractor for the cost of the survey and any administrative costs incurred by the Authority in relation to the survey [other than where the costs of the rectification and/or maintenance work are less than the costs of the survey in which case the cost of the survey shall be shared equally between the Authority and the Contractor].

    - The Contractor shall carry out such rectification and/or maintenance work within the period specified by the Authority and any costs it incurs in carrying out such rectification and/or maintenance work shall be at its own expense.

    - In the event of any failure by the Contractor to comply with clause 23.2.5 (Surveys) or if the Authority is or becomes aware of a breach by the Contractor of its obligations under clause 23.2.5 (Surveys) then the Authority shall be entitled to exercise its right of access and remedy such breach in accordance with Good Industry Practice and shall be entitled to recover any costs or expenses incurred in so doing from the Contractor as a debt.

  - Programmed Maintenance

The Contractor shall undertake Programmed Maintenance of the [Facility/Facilities] in accordance with a Schedule of Programmed Maintenance which has been approved or not commented on by the Authority under the Review Procedure.

  - Schedule of Programmed Maintenance

    - No later than two (2) months prior to the Planned Services Availability Date [for each Facility], the Contractor shall submit to the Authority's Representative in accordance with Schedule 8 (Review Procedure) a Schedule of Programmed Maintenance [for that Facility] for the period from the Planned Services Availability Date to the expiry of that Contract Year.

    - Not later than two (2) months prior to the commencement of each subsequent Contract Year the Contractor shall submit to the Authority's Representative in accordance with Schedule 8 (Review Procedure) a Schedule of Programmed Maintenance for that Contract Year.

    - Each Schedule of Programmed Maintenance shall contain the following information (the Programmed Maintenance Information):

      - details of the proposed start and end dates for each period of Programmed Maintenance, the works to be carried out and the proposed hours of work (including any proposed closures of the [Facility/Facilities] or any element therein);

      - details of any effect of the Programmed Maintenance on the delivery of any of the Services and

      - a Lifecycle Schedule.

    - Not later than twenty (20) Business Days prior to the commencement of any Contract Month, the Contractor may submit to the Authority's Representative in accordance with paragraph 3.1.7 of Schedule 8 (Review Procedure) a revision to the Schedule of Programmed Maintenance for the Contract Year in which the relevant Contract Month falls showing the effect of the proposed changes to the Programmed Maintenance Information. If the Authority's Representative does not raise comments on such proposed revision in accordance with Schedule 8 (Review Procedure), the Schedule of Programmed Maintenance as revised shall become the Schedule of Programmed Maintenance in respect of that Contract Year.

    - Where the Authority's Representative raises comments in respect of any Programmed Maintenance periods and/or hours of work shown in a Schedule of Programmed Maintenance in accordance with paragraph 3.1.7 of Schedule 8 (Review Procedure), he shall indicate whether, and if so when, the Programmed Maintenance can be re-scheduled and the Contractor shall amend the relevant Schedule of Programmed Maintenance accordingly.

    - The Contractor shall not carry out any Programmed Maintenance save in accordance with a Schedule of Programmed Maintenance to which no objection has been made under Schedule 8 (Review Procedure) or, where comment has been raised in respect of the Programmed Maintenance periods and/or time, the Schedule of Programme Maintenance has been amended pursuant to this clause 23 (Condition of the [Facility/Facilities]).

    - Notwithstanding that there has been no objection to a Schedule of Programmed Maintenance, the Authority's Representative may, at any time, require the Contractor to accelerate or defer any Programmed Maintenance by giving written notice to the Contractor, (unless otherwise agreed) not less than forty (40) Business Days prior to the scheduled date for carrying out such Programmed Maintenance (where applicable, as accelerated), which notice shall set out the time and/or periods at or during which the Authority requires the Programmed Maintenance to be performed. The Contractor shall, within ten (10) Business Days, notify the Authority of the amount of any additional reasonable costs which it will incur as a direct consequence of such acceleration or deferment (the Estimated Increased Maintenance Costs) and an estimate of any Revenue it will lose, calculated by reference to Schedule 23 (Loss of Revenue). The Authority shall, within a further period of ten (10) Business Days following receipt by the Authority of notification of the amount of the Estimated Increased Maintenance Costs [and estimated Loss of Revenue], at its option, either confirm or withdraw its request to accelerate or defer the Schedule of Programmed Maintenance. If the Authority does not respond within this ten (10) Business Day period, the request shall be deemed to have been confirmed. The Authority shall reimburse the Contractor:

      - the direct and reasonable costs actually incurred by the Contractor as a consequence of such acceleration or deferment up to, but not exceeding, the amount of the Estimated Increased Maintenance Costs; and

      - the Revenue actually lost by the Contractor as a consequence of such acceleration or deferment, calculated by reference to Schedule 23 (Loss of Revenue), up to but not exceeding the amount of estimated Loss of Revenue.

    - Where Programmed Maintenance scheduled to be carried out in accordance with the Schedule of Programmed Maintenance has been deferred by the Authority's Representative under this clause 23 (Condition of the [Facility/Facilities]), the Contractor shall not be treated as having failed to perform the Services on account of the condition of the [Facility/Facilities] or any part of [it/them] from the time the Programmed Maintenance was scheduled to have been completed until the time the deferred Programmed Maintenance was scheduled to have been completed, but not afterwards, provided always, to avoid doubt, that the Contractor shall not be relieved from the consequences of any failure to maintain the [Facility/Facilities] in respect of any period prior to the period for performing the particular work according to the Schedule of Programmed Maintenance.

    - [The Contractor shall deliver to the Authority's Representative not less than two (2) months prior to the first Planned Services Availability Date and two (2) months prior to the commencement of each subsequent Contract Year the latest version of the Five Year Maintenance Plan.]

  - Unprogrammed Maintenance Works

    - If during the Minimum Opening Hours, the need arises for Maintenance Works which are not scheduled to be carried out as part of Programmed Maintenance (Unprogrammed Maintenance Works), the Contractor may carry out such Unprogrammed Maintenance Works provided that the Contractor shall notify the Authority's Representative as soon as reasonably possible (and in any event, within two (2) Business Days of the occurrence) of the extent of the necessary Unprogrammed Maintenance Works and the reasons for them. The Contractor shall take all reasonable steps to minimise the duration of such Unprogrammed Maintenance Works.

    - For the avoidance of doubt, there shall be no restrictions on the performance of Unprogrammed Maintenance Works carried out outside of the Minimum Opening Hours.

    - Nothing in this clause 23.5 (Unprogrammed Maintenance Works) shall prevent the allocation of Performance Adjustment Points and/or Performance Adjustments in accordance with this Agreement.

  - Programmed Replacement

    - The Contractor shall or shall procure the replacement of Lifecycle Assets in accordance with the [Five Year Maintenance Plan and the] relevant Lifecycle Schedule.

    - No later than forty (40) Business Days before each occasion on which any part of the Facilities is due for replacement (as identified in the Lifecycle Schedule), where the Contractor does not believe it is necessary to undertake such replacement, the Contractor shall submit to the Authority (under the Review Procedure) a written statement detailing:

      - the replacement(s) which the Lifecycle Schedule records as being due; and

      - why the Contractor does not believe it is necessary to undertake such replacement having regard to the condition of the relevant part and the Contractor's obligations under this Agreement.

    - If the Authority approves in accordance with the Review Procedure (or it is determined in accordance with the Dispute Resolution Procedure) that the replacement should be deferred, the Contractor shall amend the Lifecycle Schedule to reflect such deferral.

    - Without prejudice to clause 23.6.3 (Programmed Replacement) the Contractor shall replace any items listed in the Lifecycle Schedule with parts of at least equivalent standard to those at the Services Availability Date for [such/the] Facility measured by reference to the standards set out in the Facilities Requirements and Technical Specification measured in each case against the current standards for the relevant part so that as a minimum any replacement part should have an equivalent or greater anticipated lifespan at the same quality as the original part provided that nothing in this clause 23.6.4 (Programmed Replacement) shall require the relevant elements of the [Facility/Facilities] to have a longer working life than required by [paragraph 1.12] of the Technical Specification.

    - In the event that the Contractor fails to either:

      - replace any part of [the/a] Facility by the date that it is due for replacement (as identified in the Lifecycle Schedule); and

      - comply with clause 23.6.4 (Programmed Replacement),

and such failure is not remedied within one (1) month of receipt of written notice of such failure from the Authority, the Authority may remedy such failure itself and recover the cost from the Contractor.

  - Lifecycle Records

The Contractor shall upon written request permit the Authority access to all the Contractor's records, receipts, invoices, reports, drawings, technical specifications and performance logs relating to any Lifecycle Asset, so as to enable the Authority to obtain an accurate assessment of the Programmed Maintenance undertaken. The Contractor shall provide all reasonable co-operation and assistance to the Authority to allow it access to such documents and information and shall in a bona fide manner respond promptly to all reasonable requests for further documents and information made by the Authority in respect of any Lifecycle Asset and the condition of the same, provided always that such access shall not in any way obstruct, hinder or prevent the Contractor in the provision of the Services. The Contractor shall maintain all documents and information relating to any Lifecycle Asset.

- Hazardous Substances

  - Storage

The Contractor shall ensure that any hazardous materials or equipment used or intended to be used in the carrying out of the Works or the provision of the Services are kept under control and in safe keeping in accordance with all relevant Legislation and Good Industry Practice, and shall ensure that all such materials are properly and clearly labelled on their containers, and shall promptly inform the Authority of all such materials being used or stored at the Site[s] and shall comply with any other reasonable requirement of the Authority in respect of such materials and equipment.

  - COSHH Register

The Contractor shall maintain a COSHH register in relation to [each/the] Facility and shall ensure that a copy of each register is held at the [relevant] Facility, at the Contractor's registered office and that a copy is given to the Authority. The Authority shall notify the Contractor of any items which it or any Authority Related Party is using or storing at [any of/the] Site[s] and which requires to be included in such register.

- Emergencies

  - Additional or Alternative Services

If an Emergency arises during the Services Period which cannot be dealt with by performance of the Services, the Authority may instruct the Contractor to use its best endeavours to procure that such additional or alternative services are undertaken by the Contractor as and when required by the Authority to ensure that the Emergency is dealt with and normal operation of the [relevant] Facility resumes as soon as is reasonably practicable provided that the Contractor shall not be obliged to provide any service which it is neither qualified nor competent to provide.

  - Costs

The properly incurred costs of the Contractor of any additional or alternative services provided to the Authority under clause 25.1 (Additional or Alternative Services) and/or any Loss of Revenue (if any) arising as a direct result of the Contractor providing any additional or alternative services shall be borne by the Authority (unless the Emergency was caused by the Contractor, in which case such costs and/or Loss of Revenue shall be borne by the Contractor). In respect of any such properly incurred costs and/or Loss of Revenue, these shall be paid against the Contractor's invoice in accordance with clauses 36 (Payment during the Works Period) and 37 (Payment during the Services Period). If such costs and/or Loss of Revenue are not agreed, the matter shall be referred to the Dispute Resolution Procedure.

- Performance Monitoring

  - Contractor Monitoring

The Contractor shall monitor its performance in the delivery of the Services in accordance with the provisions of Schedule 6 (Payment and Performance Monitoring System).

  - Authority Monitoring

The Authority may elect, at its own cost, to undertake its own performance monitoring at any stage during the Services Period for any purpose, including in order to ensure that the Services are being provided in accordance with this Agreement. The Contractor will use its reasonable endeavours to assist the Authority in such an exercise. The Authority shall be entitled to notify the Contractor of the outcome of the performance monitoring exercise, and the Contractor shall have due regard to the Authority's comments in relation to the future provision of the Services.

  - Without prejudice to the Authority's rights under clause 39.3 (Termination on Contractor Default) and to any other express rights under this Agreement, where the Contractor has been found to:

    - be fraudulent in the submission of monitoring reports or claims for payment under clause 37 (Payment during the Services Period); or

    - have submitted at least [two (2)] materially erroneous monitoring reports, within a [three (3)] month period,

the Authority may by notice to the Contractor increase the level of its monitoring of the Contractor, and/or (at the Authority's option), of the Contractor's monitoring of its own performance of its obligations under this Agreement in respect of the relevant Service or Services the subject of such fraudulent or erroneous reporting until such time as the Contractor shall have demonstrated to the reasonable satisfaction of the Authority that it will perform (and is capable of performing) its obligations under this Agreement.

  - For the purposes of clause 26.3 (Authority Monitoring), the Authority acknowledges that if the Contractor has otherwise failed to have demonstrated to the reasonable satisfaction of the Authority as required by clause 26.3 (Authority Monitoring) but:

    - if the Contractor has removed the person or persons responsible for the fraudulent reporting; or

    - (under clause 26.3.2) (Authority Monitoring), if in the following [three (3)] month period following the Authority notice (if it has not already been established) there have been no further [materially] erroneous reports of any kind,

this shall be regarded as sufficient demonstration that the Contractor will perform and is capable of performing its obligations.

  - If the Authority issues a notice under clause 26.3 (Authority Monitoring), the Contractor shall bear its own costs and indemnify and keep the Authority indemnified at all times from and against all reasonable costs and expenses incurred by or on behalf of the Authority in relation to such increased level of monitoring arising due to circumstances under clause 26.3.1 (Authority Monitoring).

- Benchmarking

The benchmarking exercises shall be carried out as required by and in accordance with Schedule 18 (Benchmarking).

- Use Of The [Facility/Facilities] [and Surplus Share]

  - Priority

The [Facility/Facilities] shall be made available for use in the provision of the Services during the Services Period as set out in the Services Specification.

  - Use of the [Facility/Facilities]

The Contractor may enter into arrangements for use of the [Facility/Facilities] provided that:

    - any such use is in accordance with Legislation;

    - the use cannot reasonably be expected to impair the provision of the Services or such use is not incompatible with the use of the [Facility/Facilities] as [a] community leisure [centre/centres];

    - the use is not one which the Authority (acting reasonably) has objected to;

    - the use does not involve sponsorship, advertisement or other direct involvement by any organisation, entity or person engaged, or with substantial interest in the production or sale of products containing or derived from tobacco or the manufacture or sale of arms and weapons; or

    - the use is not one which could be expected to involve undue violence (provided that the provision of organised sport shall not be considered undue violence) or otherwise be incompatible with the ethos of the Authority.

  - Third Party Use

Subject to the Authority's Pricing Requirements [and the Services Specification], the Contractor shall be entitled to charge for, and be paid by, each User, a fee determined by the Contractor for the use made of the [Facility/Facilities].

  - Elections

The Contractor will allow the Authority to use the [Facility/Facilities] for the purpose of Elections provided reasonable prior notice has been given to the Contractor and the Authority agrees to pay for the use of the relevant parts of the [Facility/Facilities] for such purposes, with terms to be agreed between the parties acting reasonably. In exercising its right to use the [Facility/Facilities] pursuant to this clause 28.4 (Elections) only the Authority shall be regarded as a User.

  - [Surplus Share]

[The Authority is entitled to share in the surpluses generated at the [Facility] [Facilities] in accordance with the sharing mechanism set out in Schedule 19 (Surplus Share).]

  - Handback Activities

The parties shall comply with the provisions set out in Schedule 30 (Handback).

- TUPE and Employees

  - Relevant Transfers

The Authority and the Contractor agree that the following events:

    - the Service Transfer Date; and

    - where the identity of a provider (including the Authority) of any service which constitutes or which will constitute one of the Services is changed whether in anticipation of changes pursuant to this Agreement or not,

shall constitute a Relevant Transfer and that the contracts of employment of any Relevant Employees shall have effect (subject to Regulation 4(7) of TUPE) thereafter as if originally made between those employees and the new provider except insofar as such contracts relate to those parts of an occupational pension scheme relating to old age, invalidity and survivors' benefits.

The Authority shall comply with its obligations under TUPE in respect of each Relevant Transfer pursuant to clause 29.1.1 (Relevant Transfers) and the Contractor shall comply and shall procure that each Sub-Contractor shall comply with its obligations under TUPE in respect of each Relevant Transfer pursuant to clause 29.1.1 (Relevant Transfers) and each of the Authority and the Contractor shall indemnify the other against any Direct Losses sustained as a result of any breach of this clause 29.1 (Relevant Transfers) by the party in default save that there shall be no obligation on the Authority to indemnify the Contractor for any breach by the Authority of its obligations under Regulation 13 of TUPE, or any award of compensation under Regulation 15 where such failure arises from the failure of the Contractor or any Sub-Contractor to comply with its or their duties under Regulation 13 of TUPE.

  - [Offer of Employment

    - If TUPE does not apply to any person who is an Authority Existing Employee, the Contractor shall offer to or shall procure the offer by the relevant Sub-Contractor to each and every such employee a new contract of employment commencing on the Service Transfer Date under which the terms and conditions including full continuity of employment shall not differ from those enjoyed immediately prior to the Service Transfer Date (except insofar as such terms and conditions relate to old age, invalidity and survivors' benefits under an occupational pension scheme) and the offer shall be in writing, shall be open to acceptance for a period of not less than ten (10) Business Days and shall be made:

      - if it is believed that TUPE will not apply to a person, not less than ten (10) Business Days before the Service Transfer Date; or

      - if it is believed that TUPE applies to a person but it is subsequently decided that TUPE does not so apply, as soon as is practicable and in any event no later than ten (10) Business Days after that decision is known to the Contractor.

    - Where any such offer as referred to in clause 29.2.1 (Offer of Employment) is accepted, the Authority shall indemnify and keep indemnified in full the Contractor on the same terms and conditions as those set out in clauses 29.6.1, 29.6.2 and 29.6.3 (Indemnities) of this Agreement as if there had been a Relevant Transfer in respect of each and every Authority Existing Employee who has accepted any such offer and the provisions of clauses 29.4.1 to 29.4.8 (Employment Costs) shall apply in the event of any resulting increase or decrease in the Remuneration Costs and Reorganisation Costs.

    - Where any such offer as referred to in clause 29.2.1 (Offer of Employment) is accepted, the Contractor shall act and shall procure that each relevant Sub-Contractor shall act in all respects as if TUPE had applied to each and every Authority Existing Employee who has accepted any such offer and shall comply with clause 30 (Pensions) of this Agreement in respect of each and every such employee who was immediately before the Service Transfer Date an Authority Existing Employee.

    - For the avoidance of doubt, where any such offer as referred to in clause 29.2.1 (Offer of Employment) is not accepted and TUPE does not apply, the Authority Existing Employee shall remain an employee of the Authority.]

  - Emoluments and Outgoings

    - The Authority shall be responsible for [or shall use reasonable endeavours to procure that any other employer of a Relevant Employee is responsible for] all remuneration, benefits, entitlements and outgoings in respect of the [Relevant Employees] [Transferring Employees], including without limitation all wages, holiday pay, bonuses, commissions, payments of PAYE, national insurance contributions, pension contributions, up to the Service Transfer Date.

    - The Contractor shall be responsible or shall procure that any relevant Sub-Contractor is responsible for all remuneration, benefits, entitlements and outgoings in respect of the Relevant Employees and any other person who is or will be employed or engaged by the Contractor or any Sub-Contractor in connection with the provision of any of the Services, including without limitation all wages, holiday pay, bonuses, commission, payment of PAYE, national insurance contributions, pension contributions, from and including the Service Transfer Date.

  - Employment Costs

    - The Authority has supplied to the Contractor the information, as at the date of this Agreement, which is contained in Schedule 11 Part 1 (the First Employee List) regarding the identity, number, age, sex, length of service, job title, grade and terms and conditions of employment of and other matters affecting each of those employees of the Authority and of any sub-contractor of the Authority who it is expected, if they remain in the employment of the Authority or of the sub-contractor of the Authority as the case may be until immediately before the Service Transfer Date, would be Relevant Employees but the Authority gives no warranty as to the accuracy or completeness of this information.

    - The Authority shall supply to the Contractor an update of the First Employee List at [three monthly] intervals from the date of this Agreement and an updated list ten (10) Business Days before the Service Transfer Date. The Authority shall also supply to the Contractor within five (5) Business Days after the Service Transfer Date information, which was correct as at the Service Transfer Date, in respect of the Relevant Employees on all the same matters as should be provided in the First Employee List. This list is the Final Employee List [and where there is more than one Service Transfer Date the Final Employee List means each list so prepared in respect of each Service and at each Service Transfer Date]. The Authority gives and shall give no warranty as to the accuracy or completeness of any information contained in [any update of the First Employee List or in] the Final Employee List.

    - Without Prejudice to clauses 29.4.1 (Employment Costs), 29.4.2 (Employment Costs) and 29.5 (Union Recognition), the Authority shall or shall procure if it has the contractual or legal powers to do so and shall otherwise use all reasonable endeavours to procure that every relevant sub-contractor of the Authority shall:

      - provide the Employee Liability Information to the Contractor at such time or times as required by TUPE; and

      - update the Employee Liability Information to take account of any changes as required by TUPE.

The Authority gives and shall give no warranty as to the accuracy or completeness of the Employee Liability Information supplied by the Authority or any of its relevant sub-contractors.

    - The Contractor has provided to the Authority, and the Authority has agreed, the details set out in Schedule 11 Part 3 (Proposed Workforce Information) which show, in respect of each of the Services, the following information:

      - the workforce which the Contractor proposes to establish to provide the Services (the Proposed Workforce) classified by reference to grade, job description, hours worked, shift patterns, pay scales, rates of pay, terms and conditions and pension arrangements;

      - the monthly costs of employing the Relevant Employees who are expected to be engaged in the provision of the Services. These costs (the Remuneration Costs) have been calculated on the basis of (amongst other things) the information contained in the First Employee List; and

      - the costs, including any lump sum payments, which have been agreed between the parties for the purposes of any reorganisation which may be required to establish the Proposed Workforce or a workforce which is as close as reasonably practicable to the Proposed Workforce [(including but not limited to costs associated with dismissal by reason of redundancy or capability and costs of recruitment)]. These costs (the Reorganisation Costs) have been calculated by the Contractor and the Sub-Contractors on the basis of (amongst other things) the information contained in the First Employee List.

    - If at any time (including, for the avoidance of doubt, after the submission of the Final Employee List) the Remuneration Costs and/or the Reorganisation Costs require to be adjusted on account of any differences between the information contained in the First Employee List and that contained in the Final Employee List, or on account of any inaccuracies in or omissions from the information contained in the First Employee List or the Final Employee List then (subject to clauses 29.4.6, 29.4.7 and 29.4.9 (Employment Costs)) there shall be a corresponding adjustment to the Annual Payment to compensate for any such difference.

    - If the circumstances described in clause 29.4.5 (Employment Costs) arise:

      - in circumstances where there are more Relevant Employees than shown on the Final Employee List then the parties shall discuss the implications for the provision of Services; and

      - the Contractor and the relevant Sub-Contractor shall take all reasonable steps to mitigate any additional costs and any adjustment to the Annual Payment shall be calculated as if they had done so.

    - In calculating any adjustment to be made to the Annual Payment pursuant to clause 29.4.5 (Employment Costs):

      - no account shall be taken of a decrease in the Remuneration Costs or Reorganisation Costs to the extent that it arises from a reduction in the number of Relevant Employees or their whole time equivalent such that there are, immediately after the Service Transfer Date, fewer suitably qualified persons available than are required in order to establish the Proposed Workforce and to the extent that the Contractor has employed replacement staff on equivalent remuneration and has used all reasonable endeavours to mitigate all expenses in recruiting and employing such replacement staff;

      - to avoid double counting, no account shall be taken of any change to the Remuneration Costs or the Reorganisation Costs to the extent that the Contractor has been or will be compensated as a result of any Indexation of the Annual Payment under this Agreement;

      - to avoid doubt any changes in costs which fall to be dealt with under clause 29.4.5 (Employment Costs) and which arise from a Change in Law shall be dealt with in accordance with the provisions of clause 29.4.5 (Employment Costs) and shall not be taken into account for the purposes of clause 56 (Change in Law);

      - no adjustments under clause 29.4.5 (Employment Costs) shall be made in respect of overpayments made by the Contractor or a Sub-Contractor to Relevant  Employees which arise from reliance on the Final Employee List to the extent that the Contractor or the Sub-Contractor is unable to correct overpayments in respect of continuing employment having taken reasonable steps to do so;

      - if there are underpayments by the Contractor or a Sub-Contractor to Relevant Employees, whether claimed or established as unlawful deductions from wages or as a breach of contract, which arise from reliance on the Final Employee List, there shall be an immediate increase to the [Initial Services payment or] Annual Payment [(as the case may be)] in respect of all such liabilities of the Contractor or the Sub-Contractor for all such underpayments which are retrospective (save that any such liabilities which relate to the period prior to the Service Transfer Date shall be dealt with in accordance with clauses 29.3.1 (Emoluments and Outgoings) and 29.6.1 to 29.6.3 (Indemnities)) and an appropriate increase in respect of such liabilities of the Contractor which represent ongoing costs;

      - in order to prevent duplication, no adjustment shall be made under this clause 29.4.7 (Employment Costs) if any indemnity given by the Authority under any other provision of this Agreement would apply; and

      - no adjustments under clause 29.4.5 (Employment Costs) shall be made to the extent that any payment is made to the Contractor or Sub-Contractor under Regulation 12 of TUPE.

    - Either party may propose an adjustment to the Annual Payment pursuant to clause 29.4.5 (Employment Costs) by giving not less than [ten (10)] Business Days' notice to the other. Each party will provide or procure the provision to the other, on an open book basis, access to any information or data which the other party reasonably requires for the purpose of calculating or confirming the calculation of any adjustment pursuant to clause 29.4.5 (Employment Costs).

    - In relation to all matters described in clauses 29.4.6 and 29.4.7 (Employment Costs) the Contractor and the Authority shall, and the Contractor shall procure that the relevant Sub-Contractor shall, co-operate with the other or others and take all reasonable steps to mitigate any costs and expenses and any adverse effect on industrial or employee relations.

    - The Authority shall and the Contractor shall and shall procure that each and every Sub-Contractor shall take all reasonable steps, including co-operation with reasonable requests for information, to ensure that each and every Relevant Transfer pursuant to this Agreement takes place smoothly with the least possible disruption to the services of the Authority including the Services and to the employees who transfer.

  - Union Recognition

    - The Authority shall and shall procure if it has the contractual or legal powers to do so and shall otherwise use all reasonable endeavours to procure that every relevant sub-contractor of the Authority shall supply to the Contractor no later than five (5) Business Days prior to the Service Transfer Date true copies of its union recognition agreement(s) and the Contractor shall and shall procure that each and every Sub-Contractor shall in accordance with TUPE recognise the trade unions representing Relevant Employees (as relevant to each Sub-Contractor) after the transfer to the same extent as they were recognised by the Authority or the Authority's relevant sub-contractor before the Service Transfer Date.

    - The Contractor shall procure that, on each occasion on which the identity of a Sub-Contractor changes pursuant to this Agreement, in the event that there is a Relevant Transfer, the new Sub-Contractor shall in accordance with TUPE recognise the trade unions representing the employees whose contracts of employment transfer to the new Sub-Contractor to the same extent as they were recognised before the change of identity of the Sub-Contractor in respect of the provision of the Services at the Authority's premises.

  - Indemnities

    - The Authority shall indemnify and keep indemnified in full the Contractor (for itself and for the benefit of each relevant Sub-Contractor) against all Direct Losses incurred by the Contractor or any relevant Sub-Contractor in connection with or as a result of:

      - a breach by the Authority of its obligations under clause 29.3.1 (Emoluments and Outgoings);

      - subject to clause 29.6.5 (Indemnities) any claim or demand by any Transferring Employee arising out of the employment of any Transferring Employee provided that this arises from any act, fault or omission of the Authority in relation to any Transferring Employee prior to the date of the Relevant Transfer (save where such act, fault or omission arises as a result of the Contractor's or any relevant Sub-Contractor's failure to comply with Regulation 13 of TUPE) and any such claim is not in connection with the Relevant Transfer.

    - Where any liability in relation to any Transferring Employee, in respect of his or her employment by the Authority or its termination which transfers in whole or part in accordance with TUPE and/or the Directive arises partly as a result of any act or omission occurring on or before the relevant Service Transfer Date and partly as a result of any act or omission occurring after the relevant Service Transfer Date, the Authority shall indemnify and keep indemnified in full the Contractor or the relevant Sub-Contractor against only such part of the Direct Losses sustained by the Contractor or any Sub-Contractor in consequence of the liability as is reasonably attributable to the act or omission occurring before the relevant Service Transfer Date.

    - The indemnities contained in clause 29.6.1 (Indemnities) shall apply as if references in those clauses to any Transferring Employee also included a reference to any Relevant Employee and references to any act, fault or omission of the Authority also included a reference to  the relevant Third Party Contractor employer of the Relevant Employee prior to the Service Transfer Date to the extent that the Authority recovers any sum in respect of the subject matter of those indemnities from such Third Party Contractor under any indemnity or other legal entitlement it has against such Third Party Contractor. The Authority will use all reasonable endeavours to recover any such sums under any such entitlement as is mentioned in this clause 29.6.3 (Indemnities).

    - The Contractor shall indemnify and keep indemnified in full the Authority, and at the Authority's request each and every service provider who shall provide any service equivalent to any of the Services after expiry or earlier termination of this Agreement (Future Contractor) against:

      - all Direct Losses incurred by the Authority or any Future Contractor in connection with or as a result of any claim or demand against the Authority or any Future Contractor by any person who is or has been employed or engaged by the Contractor or any Sub-Contractor in connection with the provision of any of the Services where such claim arises as a result of any act, fault or omission of the Contractor and/or any Sub-Contractor after the Service Transfer Date;

      - all Direct Losses incurred by the Authority or any Future Contractor in connection with or as a result of a breach by the Contractor of its obligations under clause 29.3.2 (Emoluments and Outgoings); and

      - all Direct Losses incurred by the Authority or any Future Contractor in connection with or as a result of any claim by any trade union or staff association or employee representative (whether or not recognised by the Contractor and/or the relevant Sub-Contractor in respect of all or any of the Relevant Employees) arising from or connected with any failure by the Contractor and/or any Sub-Contractor to comply with any legal obligation to such trade union, staff association or other employee representative whether under Regulations 13 or 14 of TUPE or any award of compensation under Regulation 15 of TUPE, under the Directive or otherwise and, whether any such claim arises or has its origin before or after the date of the Service Transfer  Date.

    - The Contractor shall indemnify and keep indemnified in full the Authority, against all Direct Losses incurred by the Authority in connection with or as a result of:

      - the change of identity of employer occurring by virtue of TUPE to the Contractor or the relevant Sub-Contractor being significant and detrimental to any of the Relevant Employees or to any person who would have been a Relevant Employee but for their objection or resignation (or decision to treat their employment as terminated under Regulation 4(9) of TUPE) on or before the Service Transfer Date as a result of the change in employer, and whether such claim arises before, on or after the Service Transfer Date;

      - any proposed or actual change by the Contractor or any Sub-Contractor to the Relevant Employees' working conditions, terms or conditions or any proposed measures of the Contractor or the relevant Sub-Contractor which are to any of the Relevant Employees' material detriment or to the material detriment of any person who would have been a Relevant Employee but for their objection or resignation (or decision to treat their employment as terminated under Regulation 4(9) of TUPE) on or before the Service Transfer Date as a result of any such proposed changes or measures, and whether such claim arises before, on or after the Service Transfer Date; and

      - any claim arising out of any misrepresentation or mis-statement whether negligent or otherwise made by the Contractor or Sub-Contractor to the Relevant Employees or their representatives whether before on or after the Service Transfer Date and whether liability for any such claim arises before on or after the Service Transfer Date.

    - For the avoidance of doubt, the indemnities in clauses 29.6.4 and 29.6.5 (Indemnities) shall not apply in respect of any sum for which the Authority is to indemnify the Contractor or a relevant Sub-Contractor pursuant to clause 29.6.1 (Indemnities) or as a result of any adjustment to the Annual Payment in accordance with clause 29.4.5 (Employment Costs) or to the extent that the claim arises from a wrongful act or omission of the Authority.

    - Clause 60.5 (Conduct of Claims) of this Agreement shall apply where any claim is made in respect of the indemnities given under this clause 29.6 (Indemnities).

  - Provision of Details and Indemnity

The Contractor shall immediately upon request by the Authority provide to the Authority details of any measures which the Contractor or any Sub-Contractor envisages it or they will take in relation to any employees who are or who will be the subject of a Relevant Transfer pursuant to clause 29.1.1 (Relevant Transfers), and if there are no measures, confirmation of that fact, and shall indemnify the Authority against all Direct Losses resulting from any failure by the Contractor to comply with this obligation.

  - Retendering

    - The Contractor shall (and shall procure that any Sub-Contractor shall) within the period of twelve (12) months immediately preceding the Expiry Date or following the service of a notice under clause 29.9 (Termination of Agreement) or as a consequence of the Authority notifying the Contractor of its intention to retender this Agreement:

      - on receiving a request from the Authority provide in respect of any person engaged or employed by the Contractor or any Sub-Contractor in the provision of the Services (the Assigned Employees) full and accurate details regarding the identity, number, age, sex, length of service, job title, grade and terms and conditions of employment of and other matters affecting each of those Assigned Employees who it is expected, if they remain in the employment of the Contractor or of any Sub-Contractor as the case may be until immediately before the Termination Date or Expiry Date (as appropriate), would be Returning Employees (the Retendering Information);

      - provide the Retendering Information promptly and at no cost to the Authority;

      - notify the Authority forthwith in writing of any material changes to the Retendering Information promptly as and when such changes arise;

      - be precluded from making any material increase or decrease in the numbers of Assigned Employees;

      - be precluded from making any increase in the remuneration or other change in the terms and conditions of the Assigned Employees other than in the ordinary course of business and with the Authority's prior written consent; and

      - be precluded from transferring any of the Assigned Employees to another part of its business or moving other employees from elsewhere in its or their business who have not previously been employed or engaged in providing the Services to provide the Services save with the Authority's prior written consent.

    - Without prejudice to clauses 29.8.1 and 29.8.3 (Retendering) the Contractor shall provide and shall procure that any Sub-Contractor shall provide the Employee Liability Information to the Authority at such time or times as are required by TUPE, and shall warrant at the time of providing such Employee Liability Information, that such information will be updated to take account of any changes to such information as is required by TUPE.

    - The Contractor shall and shall keep indemnified in full the Authority and at the Authority's request any Future Contractor against all Direct Losses arising from any claim by any party as a result of the Contractor or Sub-Contractor failing to provide or promptly to provide the Authority and/or any Future Contractor where requested by the Authority with any Retendering Information and/or Employee Liability Information or to provide full Retendering Information and/or Employee Liability Information or as a result of any material inaccuracy in or omission from the Retendering Information and/or Employee Liability Information [provided that this indemnity shall not apply in respect of the Retendering Information to the extent that such information was originally provided to the Contractor by the Authority and was materially inaccurate or incomplete when originally provided].

  - Termination of Agreement

    - On the expiry or earlier termination of this Agreement, the Authority and the Contractor agree that it is their intention that TUPE shall apply in respect of the provision thereafter of any service equivalent to a Service but the position shall be determined in accordance with Legislation at the Expiry Date or Termination Date as the case may be and this clause 29.9 (Termination of Agreement) is without prejudice to such determination.

    - For the purposes of this clause 29.9 (Termination of Agreement) Returning Employees shall mean those employees wholly or mainly engaged in the provision of the Services as the case may be as immediately before the Expiry Date or Termination Date whose employment transfers to the Authority or a Future Contractor pursuant to TUPE. Upon expiry or termination of this Agreement for whatever reason (such date being termed the Return Date), the provisions of this clause 29.9 (Termination of Agreement) will apply:

      - the Contractor shall or shall procure that all wages, salaries and other benefits of the Returning Employees and other employees or former employees of the Contractor or the Sub-Contractors (who had been engaged in the provision of the Services) and all PAYE tax deductions, pension contributions and national insurance contributions relating thereto in respect of the employment of the Returning Employees and such other employees or former employees of the Contractor or Sub-Contractors up to the Return Date are satisfied;

      - without prejudice to clause 29.9.2.1 (Termination of Agreement), the Contractor shall:

        - remain (and procure that Sub-Contractors shall remain) (as relevant) responsible for all the Contractor's or Sub-Contractor's employees (other than the Returning Employees) on or after the Expiry Date or Termination Date and shall indemnify the Authority and any Future Contractor against all Direct Losses incurred by the Authority or any Future Contractor resulting from any claim whatsoever whether arising before on or after the Return Date by or on behalf of any of the Contractor's or Sub-Contractor's employees who do not constitute the Returning Employees;

        - in respect of those employees who constitute Returning Employees the Contractor shall indemnify the Authority and any Future Contractor against all Direct Losses incurred by the Authority or any Future Contractor resulting from any claim whatsoever by or on behalf of any of the Returning Employees in respect of the period on or before the Return Date (whether any such claim, attributable to the period up to and on the Return Date, arises before, on or after the Return Date) including but not limited to any failure by the Contractor or any Sub-Contractor to comply with its or their obligations under Regulations 13 and 14 of TUPE and any award of compensation under Regulation 15 of TUPE and/or Article 6 of the Directive as if such Legislation applied, even if it does not in fact apply save to the extent that any such failure to comply arises as a result of an act or omission of the Authority or any Future Contractor.

    - The Authority shall be entitled to assign the benefit of this indemnity to any Future Contractor.

  - [Offer of Employment on Expiry or Termination

    - If TUPE does not apply on the expiry or earlier termination of this Agreement, the Authority shall ensure that each relevant Future Contractor (including where applicable the Authority) shall offer employment to the persons employed by the Contractor or a Sub-Contractor who are wholly or mainly engaged in the provision of the relevant Services immediately before the Return Date.

    - If an offer of employment is made in accordance with clause 29.10.1 (Offer of Employment on Expiry or Termination), the employment shall be on the same terms and conditions (except for entitlement to membership of an occupational pension scheme, which shall be dealt with in accordance with clause 30 (Pensions) as applied immediately before the expiry or earlier termination of this Agreement including full continuity of employment, except that the Authority or Future Contractor may at its absolute discretion not offer such terms and conditions if there has been any change to the terms and conditions of the persons concerned in breach of clause 29.8 (Retendering).

    - Where any such offer as referred to in clause 29.10.1 (Offer of Employment on Expiry or Termination) is accepted, the Contractor shall indemnify and keep indemnified in full the Authority and/or any Future Contractor on the same terms and conditions as those set out in clause 29.6 (Indemnities) of this Agreement as if there had been a Relevant Transfer in respect of each and every employee who has accepted any such offer and for the purposes of this clause 29 (TUPE and Employees) each and every such employee shall be treated as if they were a Returning Employee.

    - For the avoidance of doubt, where any such offer as referred to in clause 29.10.1 (Offer of Employment on Expiry or Termination) is not accepted and TUPE does not apply, the employee shall remain an employee of the Contractor or Sub-Contractor as appropriate.]

  - Redundancy on Expiry or Termination

    - If, on the expiry or earlier termination of this Agreement, all or any of the Services cease to be required by the Authority such that any person employed by the Contractor or Sub-Contractor who is wholly or mainly assigned to such Services is redundant, the Authority will bear Redundancy Costs associated with such person's redundancy subject to the Contractor or Sub-Contractor complying with the obligations described in clause 29.11.2 (Redundancy on Expiry or Termination).

    - The Contractor shall, and shall procure that any Sub-Contractor shall, use all reasonable endeavours to redeploy any person who is redundant in circumstances described in clause 29.11.1 (Redundancy on Expiry or Termination).

  - Sub-Contractors

In the event that the Contractor enters into any Sub-Contract in connection with this Agreement, it shall impose obligations on its Sub-Contractors in the same terms as those imposed on it pursuant to clauses 29 (TUPE and Employees), 30 (Pensions) and 31 (Employees - General) and shall procure that the Sub-Contractor complies with such terms. The Contractor shall indemnify and keep the Authority indemnified in full against all Direct Losses, incurred or by the Authority or any Future Contractor as a result of or in connection with any failure on the part of the Contractor to comply with this clause 29.12 (Sub-Contractors) and/or the Sub-Contractor's failure to comply with such terms.

- Pensions

  - Contractor to Become an Admission Body

Where the Contractor or a Sub-Contractor employs any Eligible Employees from a Relevant Transfer Date and wishes to offer those Eligible Employees membership of the LGPS, the Contractor shall procure that it and/or each relevant Sub-Contractor shall become an Admission Body. The Contractor shall before the Relevant Transfer Date execute and procure that each relevant Sub-Contractor executes a Contractor Admission Agreement which will have effect from and including the Relevant Transfer Date.

  - Contractor Admission Agreement

    - The Authority shall before the Relevant Transfer Date execute each of the Contractor Admission Agreements referred to in clause 30.1 (Contractor to Become an Admission Body) and will procure that the Administering Authority executes each such Contractor Admission Agreement before the Relevant Transfer Date.

### The Authority shall procure that when the Contractor or a Sub-Contractor enters into the Contractor Admission Agreement pursuant to clause 30.1 (Contractor to Become an Admission Body) the Contractor or Sub-Contractor shall be credited by the Administering Authority with a notional fund within the Fund at the Relevant Transfer Date (which for the avoidance of doubt shall not constitute an admission agreement fund for the purposes of Regulation 54 of the LGPS Regulations) (the Notional Fund). The amount of the Notional Fund shall be determined by an actuary appointed by the Administering Authority by reference to the aggregate of the benefits, whether immediate, prospective or contingent, payable under the LGPS immediately before the Relevant Transfer Date in relation to the Eligible Employees who are active members of the LGPS or join the LGPS on the Relevant Transfer Date and such Eligible Employees' spouses and dependants, by reference to the pensionable service in the LGPS up to the Relevant Transfer Date but making proper allowance for projected increases in the rate of pensionable salary of each such Eligible Employee to date of withdrawal, retirement or death and increases in pensions in payment using the demographic and actuarial assumptions which were adopted for the most recent funding valuation of the Fund.

    - Subject to clauses 30.2.5, 30.2.6.1 and 30.2.9 (Contractor Admission Agreement), if at any time during the term of this Agreement the Administering Authority, pursuant to the Contractor Admission Agreement or the LGPS Regulations, requires the Contractor or any Sub-Contractor to pay employer contributions or payments to the Fund in aggregate in excess of the Initial Contribution Rate, the excess of employer contributions above the Initial Contribution Rate (the Excess Amount) shall be paid by the Contractor or the Sub-Contractor, as the case may be, and the Contractor or any Sub-Contractor (as the case may be) shall be reimbursed in accordance with clause 30.2.9 (Contractor Admission Agreement).

    - Subject to clauses 30.2.5, 30.2.8 and 30.2.10 (Contractor Admission Agreement), if during the term of this Agreement, the Administering Authority, pursuant to the Contractor Admission Agreement or the LGPS Regulations, requires the Contractor or any Sub-Contractor to pay employer contributions or payments to the Fund in aggregate below the Initial Contribution Rate, the Contractor shall or shall procure that the Sub-Contractor shall reimburse the Authority an amount equal to A–B (the Shortfall Amount) in accordance with clause 30.2.10 where:

A =	the amount which would have been paid if contributions and payments had been paid equal to the Initial Contribution Rate; and

B =	the amount of contributions or payments actually paid by the Contractor or Sub-Contractor, as the case may be, to the Fund.

### Subject to clauses 30.2.5, 30.2.6.1 and 30.2.9 (Contractor Admission Agreement), where the Administering Authority obtains an actuarial valuation and a revised rates and adjustment certificate under the LGPS Regulations and/or the terms of the Contractor Admission Agreement when the Contractor Admission Agreement ceases to have effect and the Contractor or any Sub-Contractor is required to pay any revised contribution or payment to the Fund representing any exit payment under Regulation 64 of the LGPS Regulations (the Exit Contribution), such contribution or payment shall be paid by the Contractor or any Sub-Contractor (as the case may be) and the Contractor or any Sub-Contractor (as the case may be) shall be reimbursed in accordance with clause 30.2.9 (Contractor Admission Agreement).

### The Contractor shall and shall procure that any Sub-Contractors shall at all times be responsible for the following:

#### any employer contributions relating to the costs of early retirement benefits arising on redundancy or as a result of business efficiency under Regulation 30(7) of the LGPS Regulations or otherwise other than where the Authority has entered into a contractual commitment to make the individual Eligible Employee redundant before the Relevant Transfer Date or on termination or expiry of this Agreement;

#### any payment of Fund benefits on the grounds of ill health or infirmity of mind or body and any associated costs unless such grounds of ill health or infirmity of mind or body were diagnosed by a recognised medical practitioner and the results were notified to the Authority prior to the Relevant Transfer Date;

#### any employer contributions relating to the costs of flexible retirement where the actuarial reduction is waived in whole or in part or a cost neutral reduction is not applied with the consent of the Contractor or any relevant Sub-Contractor;

#### any employer contributions relating to the costs of enhanced benefits made at the discretion of the Contractor or any relevant Sub-Contractors including without limitation under Regulation 31 of the LGPS Regulations or otherwise;

#### any increase to the employer contribution rate resulting from the award of pay increases by the Contractor or relevant Sub-Contractors in respect of all or any of the Eligible Employees in excess of the pay increases assumed in the Fund's most recent actuarial valuation; and

#### to the extent not covered above, any other costs arising out of or in connection with the exercise of any discretion or the grant of any consent under the LGPS Regulations by the Contractor or any relevant Sub-Contractors where a member does not have an absolute entitlement to that benefit under the LGPS.

    - For the purposes of calculating the Exit Contribution or Excess Amount, any part of an Exit Contribution or Excess Amount, as the case may be, which is attributable to any matters for which the Contractor or Sub-Contractors are responsible for under clause 30.2.5 (Contractor Admission Agreement) shall be disregarded.

    - For the purpose of calculating the Shortfall Amount, any increase in the contributions or payments which are attributable to matters which are the Contractor's or relevant Sub-Contractor's responsibility for under clause 30.2.5 (Contractor Admission Agreement) shall be disregarded.

    - Where an Excess Amount or an Exit Contribution is paid by the Contractor or any Sub-Contractor, the Contractor shall, subject to clause 30.2.11 (Contractor Admission Agreement), forthwith as the liability to make the payment arises, invoice the Authority for payment of the Excess Amount or Exit Contribution and the Authority shall make payment to the Contractor or any Sub-Contractor of the required amount within [twenty (20)] Business Days of receipt of the invoice.

    - Where a Shortfall Amount is payable by the Contractor or any Sub-Contractor, the Contractor shall or shall procure that the Sub-Contractor, forthwith as the liability arises, notify the Authority of the Shortfall Amount, subject to clause 30.2.11 (Contractor Admission Agreement), and shall make payment to the Authority of the required amount within [twenty (20)] Business Days of the notification.

    - [If there is a dispute about the amount of payments due under clauses 30.2.2, 30.2.4, or 30.2.5 (Contractor Admission Agreement) the Contractor and/or the Sub-Contractor, as the case may be, and the Authority shall co-operate in good faith to reach agreement about the amounts due. If agreement cannot be reached about the amounts due then within 28 days of one party notifying the other that a dispute has arisen, the matter may be referred by either party to an independent actuary agreed by the parties or, failing such agreement within 14 days from the first nomination of an actuary by the Contractor and/or the Sub-Contractor, as the case may be, or the Authority to the other, the independent actuary shall be appointed by the President for the time being of the Institute and Faculty of Actuaries on the application of either the Contractor and/or the Sub-Contractor, as the case may be, or the Authority. The independent actuary so appointed shall act as expert and not as arbitrator, his decision shall be final and binding on the parties in the absence of manifest error and his costs shall be split equally.]

  - Indemnity for a Breach of the Contractor Admission Agreement

Without prejudice to the generality of this clause 30.3 (Indemnity for a Breach of the Contractor Admission Agreement), the Contractor hereby indemnifies the Authority and/or any Future Contractor and, in each case, their sub-contractors from and against all Direct Losses suffered or incurred by it or them which arise from any breach by the Contractor or any Sub-Contractor of the terms of the Contractor Admission Agreement to the extent that such liability arises before or as a result of the termination or expiry of this Agreement (howsoever caused).

  - Indemnity or Bond or Guarantee

Without prejudice to the generality of the requirements of this clause 30 (Pensions), the Contractor shall procure that it and each relevant Sub-Contractor shall as soon as reasonably practicable obtain any indemnity or bond required in accordance with the Contractor Admission Agreements. Where for any reason it is not desirable for the Contractor or Sub-Contractor to enter into an indemnity or bond, the Contractor shall procure that it and each relevant Sub-Contractor shall as soon as reasonably practicable secure a guarantee in a form acceptable to the Administering Authority in accordance with the Contractor Admission Agreement.

  - Right of Set-Off

The Authority shall have a right to set off against any payments due to the Contractor under this Agreement an amount equal to any overdue employer and employee contributions and other payments (and interest payable under the LGPS  Regulations) due from the Contractor or from any relevant Sub-Contractor (as applicable) under the Contractor Admission Agreement.

  - Contractor Ceases to be an Admission Body

If the Contractor or any Sub-Contractor employs any Eligible Employees from a Relevant Transfer Date and:

    - the Contractor or any relevant Sub-Contractor does not wish to offer those Eligible Employees membership of  the LGPS; or

    - the Authority, the Contractor or any relevant Sub-Contractor are of the opinion that it is not possible to operate the provisions of clauses 30.1 (Contractor to Become an Admission Body) to 30.5 (Right of Set Off) inclusive; or

    - if for any reason after the Relevant Transfer Date the Contractor or any relevant Sub-Contractor ceases to be an Admission Body other than on the date of termination or expiry of this Agreement or because it ceases to employ any Eligible Employees,

then the provisions of clauses 30.1 (Contractor to Become an Admission Body) to 30.5 (Right of Set Off) inclusive shall not apply (without prejudice to any rights of the Authority under those clauses) and the provisions of clause 30.7 (Contractor Scheme) shall apply.

  - Contractor Scheme

    - The Contractor shall or shall procure that any relevant Sub-Contractor shall not later than the Relevant Transfer Date or the Cessation Date (as the case may be) nominate to the Authority in writing the occupational pension scheme or schemes which it proposes shall be the 'Contractor Scheme' for the purposes of this clause 30.7 (Contractor Scheme). Such pension scheme or schemes must be:

      - established within three (3) months prior to the Relevant Transfer Date or Cessation Date (as the case may be) and maintained until any payment to be made under Schedule 22 (Bulk Transfer Terms) is made;

      - reasonably acceptable to the Authority (such acceptance not to be unreasonably withheld or delayed);

      - registered within the meaning of the Finance Act 2004; and

      - certified by [the Government Actuary's Department] [an actuary nominated by the Authority in accordance with relevant guidance produced by the Government Actuary's Department] as providing benefits which are broadly comparable to those provided by the LGPS;

    - The Contractor undertakes to the Authority (for the benefit of the Authority itself and for the Authority as agent and trustee for the benefit of the Eligible Employees) that it shall and shall procure that any relevant Sub-Contractor shall procure that:

      - the Eligible Employees shall by [three (3)] months before the Relevant Transfer Date or the Cessation Date (as the case may be) be offered membership of the Contractor Scheme with effect from and including the Relevant Transfer Date or Cessation Date (as the case may be);

      - the Contractor Scheme shall provide benefits in respect of the Eligible Employees' periods of service on and after the Relevant Transfer Date or Cessation Date (as the case may be) which [the Government Actuary's Department] [an actuary nominated by the Authority in accordance with relevant guidance produced by the Government Actuary's Department] shall certify to be broadly comparable to the benefits which the Eligible Employees would have been entitled to under the LGPS had they continued in membership of the LGPS;

      - on and from the Relevant Transfer Date or Cessation Date (as the case may be) until the earlier of:

        - [three (3)] months after the date on which the Eligible Employees are first able to join the Contractor Scheme; and

        - the date on which the Eligible Employee joins the Contractor Scheme,

the Contractor shall provide death benefits for and in respect of the Eligible Employees which are certified by [the Government Actuary's Department] [an actuary nominated by the Authority in accordance with relevant guidance produced by the Government Actuary's Department] as being broadly comparable to those that would otherwise have been provided in respect of those Eligible Employees by the LGPS;

      - if the Contractor Scheme is terminated, a replacement pension scheme shall be provided with immediate effect for those Eligible Employees who are still employed by the Contractor or relevant Sub-Contractor. The replacement scheme must comply with this clause 30.7 (Contractor Scheme) as if it were the Contractor Scheme; and

      - before the Relevant Transfer Date or Cessation Date (as the case may be) the trustees of the Contractor Scheme shall undertake by deed to the Authority and to the Administering Authority that they shall comply with the provisions of clauses 30.7.1.1 to 30.7.1.4 (Contractor Scheme), 30.8.1 30.8.2 and 30.8.4 (Undertaking from the Contractor) and Schedule 22 (Bulk Transfer Terms).

    - Schedule 22 (Bulk Transfer Terms) shall apply in relation to the terms for bulk transfers from the LGPS to the Contractor's Scheme following the Relevant Transfer Date and any subsequent bulk transfers on termination or expiry of this Agreement.

  - Undertaking from the Contractor

The Contractor undertakes to the Authority (for the benefit of the Authority itself and for the Authority as agent and trustee for the benefit of the Eligible Employees) that:

    - all information which the Authority or the Administering Authority or their respective professional advisers may reasonably request from the Contractor or any relevant Sub-Contractor for the administration of the LGPS or  concerning any other matters raised in clause 30.7 (Contractor Scheme), clause 30.8 (Undertaking from the Contractor) or Schedule 22 (Bulk Transfer Terms) shall be supplied to them as expeditiously as possible;

    - it shall not and shall procure that any relevant Sub-Contractor shall not, without the consent in writing of the Authority (which shall only be given subject to the payment by the Contractor or the relevant Sub-Contractor of such reasonable costs as the Authority or the Administering Authority may require) consent to instigate, encourage or assist any event which could impose on the Authority a cost in respect of any Eligible Employee greater than the cost which would have been payable in respect of that Eligible Employee had that consent, instigation, encouragement or assistance not been given;

    - until the Relevant Transfer Date, it shall not and shall procure that any relevant Sub-Contractor shall not issue any announcements (whether in writing or not) to the Eligible Employees concerning the matters stated in clauses 30.1 (Contractor to Become an Admission Body) to 30.6 (Contractor ceases to be an Admission Body) inclusive without the consent in writing of the Authority and the Administering Authority (not to be unreasonably withheld or delayed);

    - it shall not and shall procure that any relevant Sub-Contractor shall not take or omit to take any action which would materially affect the benefits under the LGPS or under the Contractor Scheme of any Eligible Employees who are or will be employed wholly or partially in connection with the Services without the prior written agreement of the Authority (not to be unreasonably withheld or delayed) provided that the Contractor and/or such Sub-Contractor will be so entitled without the requirement of consent to give effect to any pre-existing contractual obligations to any Eligible Employees; and

    - it shall and shall procure that any relevant Sub-Contractor shall offer any of its Eligible Employees who cease to be engaged in the provision of the Services and thereby cease to be eligible for membership of the LGPS membership of the Contractor Scheme immediately after ceasing to be so engaged.

  - Discretionary Benefits

    - Where the Contractor or a Sub-Contractor is an Admission Body, the Contractor shall and/or shall procure that any relevant Sub-Contractor shall award benefits (where permitted) to the Eligible Employees under the LGPS in circumstances where the Eligible Employees would have received such benefits had they still been employed by the Authority; and

    - Where the award of benefits in clause 30.9.1 is not permitted under the LGPS or the Contractor and/or a Sub-Contractor is not an Admission Body, the Contractor shall and/or shall procure that any Sub-Contractor shall award benefits to the Eligible Employees which are identical to the benefits the Eligible Employees would have received under the LGPS in circumstances where the Eligible Employees would have received such benefits had they still been employed by the Authority.

    - Under clause 30.9.1 and 30.9.2 (Discretionary Benefits), where such benefits are of a discretionary nature, they shall be awarded on the basis of the Authority's written policy in relation to such benefits at the time of the Relevant Transfer Date (which the Authority shall provide upon request). Where the payment of such benefits is not, for whatever reason, possible, the Contractor shall and/or shall procure that any relevant Sub-Contractor shall compensate the Eligible Employees in a manner which is broadly comparable or equivalent in cash terms.

  - Claims from Eligible Employees or Trade Unions

The Contractor hereby indemnifies the Authority and/or any Future Contractor and, in each case, their sub-contractors from and against all Direct Losses suffered or incurred by it or them which arise from claims by Eligible Employees of the Contractor and/or of any Sub-Contractor or by any trade unions, elected employee representatives or staff associations in respect of all or any such Eligible Employees which losses:

    - relate to pension rights in respect of periods of employment on and after the Relevant Transfer Date until the date of termination or expiry of this Agreement; or

    - arise out of the failure of the Contractor and/or any relevant Sub-Contractor to comply with the provisions of this clause 30 before the date of termination or expiry of this Agreement.

  - Contracts (Rights of Third Parties) Act 1999

The Authority and the Contractor or Sub-Contractor agree that clause 2 (Exclusion of Legislation) of this Agreement shall not apply to this clause 30 (Pensions).

  - Liability for Costs

The costs of the Authority necessarily and reasonably incurred in connection with the Contractor Admission Agreement and/or of obtaining the necessary certification of comparability in accordance with clause 30.7.1.4 (Contractor Scheme) shall be borne by the Contractor.

  - Transfer to another Employer

Save on expiry or termination of this Agreement, if the employment of any Eligible Employee transfers to another employer (by way of a transfer under TUPE) the Contractor shall and shall procure that any relevant Sub-Contractor shall:

    - consult with and inform those Eligible Employees of the pension provisions relating to that transfer; and

    - procure that the employer to which the Eligible Employees are transferred (the New Employer) complies with the provisions of this clause 30 (Pensions) provided that references to the Sub-Contractor will become references to the New Employer, references to Relevant Transfer Date will become references to the date of the transfer to the New Employer and references to Eligible Employees will become references to the Eligible Employees so transferred to the New Employer.

  - Pension Issues on Expiry or Termination

The Contractor shall (and shall procure that each relevant Sub-Contractor shall):

    - maintain such documents and information as will be reasonably required to manage the pension rights of and aspects of any onward transfer of any person engaged or employed by the Contractor or any Sub-Contractor in the provision of the Services on the expiry or termination of this Agreement (including without limitation identification of the Eligible Employees);

    - promptly provide to the Authority such documents and information mentioned in clause 30.14.1 (Pensions Issues on Expiry or Termination) which the Authority or the Administering Authority may reasonably request in advance of the expiry or termination of this Agreement; and

    - fully co-operate (and procure that the trustees of the Contractor Scheme shall fully co-operate) with the reasonable requests of the Authority or the Administering Authority relating to any administrative tasks necessary to deal with the pension rights of and aspects of any onward transfer of any person engaged or employed by the Contractor or any Sub-Contractor in the provision of the Services on the expiry or termination of this Agreement.

  - Compliance with Part 1 Pensions Act 2008

The Contractor shall and shall procure that any relevant Sub-Contractor shall comply with the requirements from time to time under Part 1 of the Pensions Act 2008 to make a minimum level of contributions to the National Employee Savings Trust or other qualifying scheme.

  - Compliance with section 257 and 258 Pensions Act 2004

The Contractor shall and shall procure that any relevant Sub-Contractor shall comply with sections 257 and 258 of the Pensions Act 2004 in relation to any Relevant Employee (excluding, for the avoidance of doubt any Eligible Employees) who is on or immediately prior to the Relevant Transfer Date:

    - a member of or is entitled to be a member of their employer's occupational pension scheme; or

    - would have become eligible to be a member of their employer's occupational pension scheme had he 	served out the usual waiting period.

- Employees – General

  - Disclosure and Barring

The Contractor shall procure that in respect of all potential staff or persons performing any of the Services [(other than Relevant Employees/Transferring Employees)] (each a Named Employee) before a Named Employee begins to attend the Site[s] to perform any of the Services and only to the extent required under the Home Office Guidance:

    - each Named Employee is questioned as to whether he or she has any Convictions or Asbos;

    - the results are obtained of a check of the most extensive available kind made with the Disclosure and Barring Service in respect of each Named Employee; and

    - a copy of the results of such checks as are referred to in clause 31.1.2 (Disclosure and Barring) are notified to the Authority.

  - The Contractor shall procure that only to the extent required by the Home Office Guidance in relation to the Services:

    - no person who appears on a Barred List following the results of a Disclosure and Barring Service check shall be employed or engaged in the performance of any [Works or] Services; and

    - it shall and shall procure that all sub-contractors shall comply with all reporting requirements to the Disclosure and Barring Service.

  - The Contractor shall procure that no person who discloses any Convictions or Asbos, or who is found to have any Convictions or Asbos following the results of a Disclosure and Barring Service check, is employed or engaged without the Authority's prior written consent (such consent not to be unreasonably withheld or delayed).

  - Insofar as permitted by Legislation, the Contractor shall procure that the Authority is kept advised at all times of any member of staff who, subsequent to his/her commencement of employment as a member of staff:

    - receives a Conviction or Asbo which becomes known to the Contractor or any sub-contractor or whose previous Convictions or Asbos become known to the Contractor or any sub-contractor;

    - in respect of whom information is referred to the Disclosure and Barring Service pursuant to the Disclosure and Barring Scheme; or

    - who is placed on a Barred List pursuant to the Disclosure and Barring Scheme.

  - In the event that any member of staff or any employee of any sub-contractor of any tier involved in the provision of the [Works or] Services is added to a Barred List, the Contractor shall procure that such member of staff or employee of a sub-contractor is immediately removed from the Site and shall cease to be engaged in the performance of [the Works or] the Services.

  - Save to the extent prescribed otherwise pursuant to the Disclosure and Barring Scheme, this clause 31 (Employees – General) shall not apply to those individuals who shall be required by the Contractor or any sub-contractor to attend on any of the Sites to provide emergency reactive services. In the case of such individuals, the Contractor shall or shall procure that any sub-contractor shall ensure that such individuals are accompanied at all times while on each Site by a member of the Contractor or any sub-contractor's staff who has been properly employed or engaged in accordance with clauses 31.1 to 31.3 (Employees – General).

  - Conduct of Staff

Whilst engaged at the Sites the Contractor shall and shall procure that any sub-contractor shall comply with the Authority's Policies relating to the conduct of staff and security arrangements. The Authority (acting reasonably) may:

    - instruct the Contractor that disciplinary action is taken against any employee of the Contractor or any sub-contractor involved in the provision of the Services (in accordance with the terms and conditions of employment of the employee concerned) where such employee misconducts himself or is incompetent or negligent in his duties (in which case the Authority shall co-operate with any disciplinary proceedings and shall be advised in writing of the outcome); or

    - where the Authority has reasonable grounds for considering that the presence or conduct of an employee at any location relevant to the performance of the Services is undesirable, require the exclusion of the relevant employee from the relevant location(s).

  - Admission to the Site[s]

    - Subject to the remainder of this clause 31.8 (Admission to the Site[s]), the Contractor shall at least twenty (20) Business Days before the date on which the Contractor first carries out any of the Works or provides any of the Services provide the Authority with a written list of the names and addresses of all employees or other persons who it expects may require admission to each Site in connection with the carrying out of the Works or provision of the Services, specifying the capacities in which those employees or other persons are concerned with the Works or Services and giving such other particulars as the Authority may require. The Contractor shall update this information as and when any such individuals are replaced or complemented by others, not less than twenty (20) Business Days before their inclusion. The decision of the Authority on whether any person is to be refused admission to a Site shall be final and conclusive and the Authority shall not be obliged to give reasons for its decision.

    - Where the Contractor is unable (acting reasonably) to comply with clause 31.8.1 (Admission to the Site[s]) by the time period specified in it then the Contractor shall comply with its obligations under that clause as soon as reasonably practicable and by no later than the end of the day on which the relevant individual first goes on Site. Until such time as the Contractor has complied with its obligations in respect of that individual, he or she shall at all times be accompanied on any Site by a member of the Contractor or sub-contractor's staff who has been properly notified to the Authority in accordance with clause 31.8.1.

    - This clause 31.8 shall not apply to those individuals who shall be required by the Contractor or any sub-contractor to attend on Site to provide emergency reactive services. In the case of such individuals, the Contractor shall or shall procure that any sub-contractor shall ensure that such individuals are accompanied at all times while on each Site by a member of the Contractor or sub-contractor's staff who has been properly notified to the Authority in accordance with the terms of this clause 31.8.1 (Admission to the Site[s]).

  - Refusal of Admission

The Authority reserves the right to refuse to admit to the Sites any person, employed or engaged by the Contractor or a sub-contractor, whose admission would, in the opinion of the Authority, present a risk to themselves or an Authority Related Party or property, and shall not be obliged to give any reasons for such refusal.

  - Decision to Refuse Admission

The decision of the Authority as to whether any person is to be refused admission to the Sites pursuant to clause 31.9 (Refusal of Admission) shall be final and conclusive. If the Authority declines to give reasons and/or where reasons are given but are found to be unreasonable for exercising its rights under clauses 31.8 (Admission to the Site[s]) and 31.9 (Refusal of Admission) and 31.11 (Removal from Site[s]), the Authority shall indemnify the Contractor and keep the Contractor indemnified (for itself and for the benefit of each relevant sub-contractor) against all Direct Losses provided that the Contractor or the relevant sub-contractor has used its reasonable endeavours to re-deploy that person elsewhere and/or to mitigate the claim.

  - Removal from Site[s]

The Contractor shall comply with and/or procure compliance with any notice issued by the Authority from time to time requiring the removal from any of the Sites of any person employed thereon who in the opinion of the Authority acting reasonably is not acceptable on the grounds of risk to themselves or an Authority Related Party or property and that such persons shall not be employed again upon the Project without the written consent of the Authority.

  - Relief from Performance Adjustment Points and Performance Adjustments

Where the Authority exercises its rights under this clause 31 (Employees – General) and it can be shown that:

    - the Contractor or any sub-contractor has acted in accordance with the relevant provisions of this clause 31; or

    - the Authority did not act reasonably in instructing the Contractor not to employ and/or in requesting any removal and/or in refusing admission,

then the Authority shall give the Contractor such relief from Performance Adjustment Points and Performance Adjustments for a reasonable period to allow the Contractor or any sub-contractor to make alternative arrangements to replace the person whose employment has been refused or whose removal has been requested. For the avoidance of doubt, any relief from Performance Adjustment Points and Performance Adjustments given under this clause 31.12 (Relief from Performance Adjustment Points and Performance Adjustments) shall only be in respect of those Services in which such person is or would have been engaged.

  - Resources and Training

The Contractor shall procure that:

    - there shall be at all times a sufficient number of staff (including all relevant grades of supervisory staff) engaged in the provision of the Services with the requisite level of skill and experience. This obligation shall include ensuring that there are sufficient staff to cover periods of holiday, sickness, other absences and anticipated and actual peaks in demand for each of the Services; and

    - all staff receive such training and supervision as is necessary to ensure the proper performance of the Services under this Agreement.

  - Personnel Policies and Procedures

The Contractor shall procure that there are set up and maintained by it and by all sub-contractors involved in the provision of the Services, personnel policies and procedures covering all relevant matters (including discipline, grievance, equal opportunities and health and safety). The Contractor shall procure that the terms and implementation of such policies and procedures comply with Legislation and Good Industry Practice and that they are published in written form and that copies of them (and any revisions and amendments to them) are forthwith issued to the Authority.

- Operating Manual

  - Maintenance of Manual

The Contractor shall throughout the Services Period maintain and update an operating and maintenance manual setting out the procedures for providing the Services (the Operating Manual).

  - Access to Manual

The Contractor shall at the request of the Authority provide the Authority with access to the Operating Manual in order to demonstrate that the Contractor has complied with its obligation to maintain and update the Operating Manual under clause 32.1 (Maintenance of Manual).

  - Copy on Termination

On termination of this Agreement (howsoever arising including expiry), the Contractor shall within ten (10) Business Days provide a copy of the Operating Manual to the Authority.

- Quality Assurance

  - The Contractor shall procure that all aspects of the Works and the Services are the subject of, and are conducted in accordance with the approved quality assurance systems as set out in clause 33.2 and 33.3 (Quality Assurance) below.

  - Not later than ten (10) Business Days following the Commencement Date, the Contractor shall submit to the Authority's Representative a proposed quality assurance system for the Works complying with ISO 9001 or, where it does not so comply, the system set out in the Construction Proposals.

  - The Contractor shall procure that the Building Contractor is, at all times during the Works Period, registered pursuant to BS 5750 or ISO 9001 (or such other quality standard as may replace or supersede the same or, in the absence of a replacement or a superseding quality standard or equivalent or such other quality assurance system acceptable to the Authority (acting reasonably)) in relation to the Works.

  - The Contractor shall appoint (or shall procure the appointment of) as soon as reasonably practicable following the date of this Agreement a quality manager, who may be directly involved in the day-to-day performance of the Works and Services, and who shall in respect of the Works:

    - ensure the effective operation of and implementation of the aforementioned quality assurance systems;

    - audit the aforementioned quality assurance systems at regular intervals and report the findings of such audit to the Contractor and the Authority;

    - review the aforementioned quality assurance systems at intervals agreed with the Authority to ensure their continued suitability and effectiveness; and

    - liaise with the Authority on all matters relating to quality assurance,

and in respect of the Services:

    - implement and monitor a quality assurance system; and

    - liaise with the Authority on all matters relating to quality assurance.

  - The Authority may carry out periodic audits of the aforementioned quality assurance systems and Quest at approximate intervals of three (3) months and may carry out other periodic monitoring, spot checks and auditing of the Contractor's quality systems. The Contractor shall procure that the Authority shall have a like right in respect of any relevant sub-contractors. The Contractor shall co-operate and shall procure that any relevant sub-contractor co-operates with the Authority including providing it with all information and documentation which it reasonably requires in connection with its right under this clause 33 (Quality Assurance).

- Co-operation For Investigation And Security

  - The Contractor shall co-operate with any investigation relating to a breach of security relating to the Project which is carried out by or on behalf of the Authority and:

    - shall use its reasonable endeavours to make its employees (and other Contractor Related Parties) identified by the Authority available to be interviewed by the Authority for the purposes of the investigation; and

    - shall, subject to any legal restriction on their disclosure, provide all copies of documents, records or other material of any kind which may reasonably be required by the Authority for the purposes of the investigation. The Authority shall have the right to retain copies of any such material for use in connection with the investigation.

  - The Authority shall, insofar as is practical, inform the Contractor of any specific or general security information which would reasonably be expected to affect the security of the Contractor or any Contractor Related Party or their property.

  - The Contractor shall comply with the Authority's reasonable reporting requirements relating to infectious and notifiable diseases to the extent made known to the Contractor.

- Service Delivery Proposals

  - For the avoidance of doubt, the Services Specification shall at all times have priority over the Service Delivery Proposals and the Contractor shall be obliged to comply with the Services Specification and provide the Services in accordance with the Services Specification.

  - Any changes to the Service Delivery Proposals may only be made in accordance with the Review Procedure.

Part 5 - Payment

- Payment during the Works Period

  - Contract Sum

The Authority shall pay the Contractor the Contract Sum for the carrying out of the Works. The Indicative Payment Schedule sets out the likely cost profile of the Works.

  - Applications for payment

Following the end of each calendar month ("Relevant Month") during which the Works are being carried out, the Contractor will provide the Authority within five (5) Business Days:

    - an application for payment showing the amount the Contractor considers to be due on the payment due date in accordance with clause 36.7 (Payment due date) together with the basis on which the sum is calculated, together with a summary of the total amount previously paid; and

    - a copy of the certificate of such completed works certified by the Independent Certifier.

  - Information

    - Each application shall specify the amount that the Contractor considers to be due on the payment due date referred to in clause 36.7 (Payment due date) together with the basis on which the sum is calculated up to and including the Relevant Month, and a summary of the total amount previously paid by reference to:

      - the Gross Valuation;

      - any Authority Change or any Qualifying Change in Law to which the Contractor is entitled under this Agreement;

      - any other payment to which the Contractor is entitled under this Agreement;

      - costs or losses which the Authority is liable to pay to the Contractor in respect of Compensation Events pursuant to clause 16 of this Agreement;

and in the case of clauses 36.3.1.2 to 36.3.1.4 (inclusive), the application will be made following the month in which such entitlement arose or such losses or costs were incurred.

    - The "Gross Valuation" shall reflect the value of the Works completed for the Relevant Month. For the purposes of this clause 36.3 (Information), the value of the Works completed shall be determined by reference to the [Contract Sum Analysis] as referred to in [the Building Contract][the Construction Proposals] together with any updated Indicative Payment Schedule produced in accordance with clause 36.9 (Adjustments to the Contract Sum and Indicative Payment Schedule).

    - Each application shall, to the extent relevant, be accompanied by:

      - a programme recording actual progress to the end of the Relevant Month;

      - full and detailed particulars of the amount claimed under any of clauses 36.3.1.2 to 36.3.1.4 (inclusive);

      - a valid VAT invoice.

  - Additional information

The Contractor will provide any additional information and explanation that the Authority may reasonably request.

  - Payment notice

    - Within 10 Business Days after receipt by the Authority of the Contractor's application for payment in accordance with clauses 36.2 (Applications for payment) and 36.4 (Information) the Authority or the Authority's Representative will give notice to the Contractor of the amount of the payment made or proposed to be made being the amount claimed by the Contractor which is not disputed by the Authority and shall pay that amount to the Contractor by the final date for payment referred to in clause 36.8 (Final date for payment) (the Notified Sum). Any failure to reach agreement shall be resolved in accordance with the Dispute Resolution Procedure. It is immaterial that the Notified Sum may be zero.

    - If the Authority does not give notice to the Contractor of the amount of the payment to be made or proposed to be made in accordance with clause 36.5.1 the payment to be made by the Authority to the Contractor shall, subject to any Pay Less Notice which may be issued in accordance with clause 36.6 (Pay less notice), be the amount as set out in the Contractor's application for payment in accordance with clause 36.2 (Applications for payment) and 36.4 (Information).

  - Pay Less Notice

At least 5 Business Days before the final date for payment the Authority may give notice to the Contractor that the Authority intends to pay less than the Notified Sum (a Pay Less Notice) or the amount as set out in the Contractor's application for payment in accordance with clause 36.22 (Applications for payment) and 36.4 (Information). It is immaterial that the amount then considered to be due may be zero.

Any Pay Less Notice shall set out:

    - the sum that the Authority considers to be due to the Contractor when the Pay Less Notice is served; and

    - the basis on which the sum is calculated.

  - Payment due date

The payment of the sums due to the Contractor in accordance with clause 36.5 (Payment notice) subject to any Pay Less Notice issued by the Authority in accordance with clause 36.6 (Pay less notice), will be due 10 Business Days after the receipt by the Authority of the Contractor's application for payment in accordance with clauses 36.22 (Applications for payment) and 36.4 (Information). In the case of any VAT payable to the Contractor, the VAT shall be due 14 days after receipt by the Authority of a valid VAT invoice.

  - Final date for payment

The final date for payment of any sums referred to in clauses 36.6 (Pay less notice) 36.7 (Payment due date), 36.10 (Final statement and Repayment) shall be 10 Business Days after the relevant payment due date referred to in clause 36.7 (Payment due date).

  - Adjustments to the Contract Sum and Indicative Payment Schedule

Whenever there is any adjustment to the amounts due to the Contractor (either upwards or downwards) in accordance with this Agreement, the Contract Sum will then be adjusted accordingly and the parties will endeavour to agree an appropriate adjustment to the Indicative Payment Schedule, failing which such adjustments will be determined in accordance with the Dispute Resolution Procedure.

  - Final statement and Repayment

    - Not later than 3 months after the issue of the Certificate of Making Good Defects in accordance with clause 20.8, the Contractor shall provide to the Authority completed template cost proformas setting out the actual costs incurred in relation to the Works together with a breakdown of:

      - all the payments made to the Contractor during the period of this Agreement; and

      - any further payments due to the Contractor in accordance with this Agreement, together with a full explanation of any additional payments due, over and above previously agreed payments in respect of the Works including the balance of the Contract Sum,

in each case so far as such payments relate to the carrying out and completion of the Works.

    - Clauses 36.5 (Payment notice) to 36.8 (Final Date for Payment) shall apply in respect of any sum which the Contractor claims is due pursuant to this clause 36.10.

  - VAT

All sums payable by or to the Authority or the Contractor are exclusive of VAT. In the case of any VAT payable, the VAT shall be due 14 days after receipt by the receiving party of a valid VAT invoice.

  - Interest on late payments

If the Authority is late in making any payment due to the Contractor in accordance with this Agreement (which for the avoidance of doubt shall not include any amounts withheld by the Authority in accordance with clause 36.6 (Pay less notice) unless it is subsequently determined that any such amount should not have been withheld), the Authority shall pay interest on the amount of the late payment at the Prescribed Rate from the final date for payment of that amount until the date on which the relevant payment is received by the Contractor.

  - Right to suspend performance for non-payment

In addition to the right to claim interest on late payments in accordance with clause 36.12 (Interest on late payments), the Contractor shall be entitled to exercise its statutory right to suspend the performance of any or all of its obligations under this Agreement in accordance with Section 112 of the HGCRA.

- Payment during the Services Period

  - Payment of the Monthly Payment

    - Following the [final] Services Availability Date the Authority shall pay the Contractor the Monthly Payment in respect of each Payment Period where the Annual Payment is a Deficit Annual Payment, and the Contractor shall pay the Authority the Monthly Payment in respect of each Payment Period where the Annual Payment is a Surplus Annual Payment, in each case calculated in accordance with Schedule 6 (Payment and Performance Monitoring System).

    - Where the Annual Payment is a Deficit Annual Payment, the Monthly Payment shall be reduced in each Payment Period by any Performance Adjustments applicable in accordance with Schedule 6 (Payment and Performance Monitoring System).

    - Where the Annual Payment is a Surplus Annual Payment, the Contractor shall separately pay to the Authority in respect of a Payment Period any Performance Adjustments applicable in accordance with Schedule 6 (Payment and Performance Monitoring System).

  - Report and Invoice

On the first Business Day of each Payment Period the Contractor shall submit to the Authority:

    - a report showing the Monthly Payment and any Performance Adjustments for the previous Contract Month and, individually, each item taken into account in calculating such Monthly Payment and Performance Adjustments pursuant to Schedule 6 (Payment and Performance Monitoring System); and

    - in respect of a Deficit Annual Payment, an invoice for the amount (if any) shown by the report as owing by the Authority to the Contractor, taking into account the Monthly Payment and any Performance Adjustments applied in accordance with clause 37.1.2, and for any VAT payable by the Authority in respect of that amount; or

    - in respect of a Surplus Annual Payment a statement showing the Monthly Payment payable by the Contractor to the Authority for the Authority to issue an invoice to the Contractor for such amount plus any VAT (if any) payable in respect of that amount. The Authority shall issue its invoice to the Contractor, taking account of the Contractor's statement (but not being bound by it),

(together the Application).

  - Final Payment Period

Where the Annual Payment is a Deficit Annual Payment:

    - during the final two Payment Periods, in addition to the amounts referred to in clause 37.2.2 (Report and Invoice) the Authority may withhold an amount equivalent to the average per Payment Period of the sum of the Performance Adjustments applicable to the previous six (6) Payment Periods until such time as the Contractor shall have provided a report to the Authority in respect of those Payment Periods containing the information set out in clause 37.2.1 (Report and Invoice); and

    - on receipt of the reports from the Contractor in respect of the final two Payment Periods the Authority may retain from the amounts withheld pursuant to clause 37.3.1 (Final Payment Period) a sum equivalent to the sum of the Performance Adjustments identified in the report or any other amount agreed by the parties or determined pursuant to clause 64 (Dispute Resolution) as owing to the Authority. The Authority shall pay the balance of any monies withheld to the Contractor or if it is agreed or determined the Contractor owes monies to the Authority in excess of those sums withheld, the Contractor shall pay such additional amounts to the Authority, in each case with interest on that amount at the Prescribed Rate calculated on a daily basis and compounded quarterly from the date on which the payment was withheld by the Authority pursuant to clause 37.3.1 (Final Payment Period) or from the date on which over payment was made (in the case of excessive claims by the Contractor) until all relevant monies have been paid in full and whether before or after judgement.

  - Payment

    - Subject to clause 37.5 (Disputed Amounts), the Authority shall pay the amount stated in any invoice submitted under clause 37.2.2 (Report and Invoice) and the Contractor shall pay the amounts stated in any invoices submitted by the Authority pursuant to clause 37.2.3 on the final Business Day of the Payment Period in question.

    - Where the Annual Payment is a Surplus Annual Payment, the amount of any Performance Adjustments calculated in accordance with Schedule 6 (Payment and Performance Monitoring System) shall be paid by the Contractor to the Authority at the same time as the Monthly Payment in respect of the relevant Payment Period is paid.

  - Disputed Amounts

    - If either party (Disputing Party) disputes the other Party's (Claiming Party) entitlement to any part of the amount claimed by the Contractor pursuant to clause 37.2 (Report and Invoice) in respect of any Payment Period the provisions of this clause 37.5 (Disputed Amounts) shall apply.

    - At least five (5) Business Days before the final date for payment due to the Claiming Party, the Disputing Party shall give notice to the Claiming Party of the following:

      - any amounts claimed by the Claiming Party that the Disputing Party objects to and is seeking to withhold; or

      - any amounts that the Disputing Party is owed by the Claiming Party (including any amounts previously overpaid to the Claiming Party) which the Disputing Party is seeking to withhold; or

      - any amount pursuant to clauses 37.2 and/or 37.3 that the Disputing Party is seeking to withhold.

Any notice shall set out the sum or sums proposed to be withheld, grounds for withholding payment and the amount attributable to each ground.

    - The Disputing Party shall notify the Claiming Party in writing within ten (10) Business Days of receipt by the Disputing Party of the relevant invoice and supporting report of that part of the amount (insofar as at the time of such notice the Disputing Party is reasonably able to quantify it) which the Disputing Party (acting in good faith) disputes (a Disputed Amount) and submit to the Claiming Party such supporting evidence as the Disputing Party may have.

    - The Authority may withhold payment of any Disputed Amount pending agreement or determination of the Contractor's entitlement in relation to the Disputed Amount but shall pay on the due date any undisputed amounts. The Contractor may, where there is a Surplus Annual Payment, withhold payment of any Disputed Amount pending agreement or determination of the Authority's entitlement in relation to the Disputed Amount but shall pay on the due date any undisputed amount.

  - Response to Disputing Party Notice

Within five (5) Business Days following receipt by the Claiming Party of any notice served by the Disputing Party pursuant to clause 37.5.2 (Disputed Amounts), the Claiming Party shall respond by notifying the Disputing Party as to whether or not it agrees with the statements made in that notice. If the Claiming Party indicates that it does agree, or if the Claiming Party fails to make such a response within that time limit, the Disputing Party shall be entitled:

    - to retain on a permanent basis any amounts withheld pursuant to clause 37.5.4 (Disputed Amounts); and

    - to reclaim from the Claiming Party the amount of any over-payment which may have been made to the Claiming Party together with interest on any such amount at the Prescribed Rate calculated on a daily basis and compounded quarterly from the date on which the over-payment was made until that amount has been paid in full and whether before or after judgment.

  - Dispute

If the Claiming Party responds (pursuant to clause 37.6 (Response to Disputing Party Notice)) that it does not agree with all or any of the statements made in any notice served by the Disputing Party pursuant to clause 37.5.2 (Disputed Amounts), the matter or matters in question shall be determined under the Dispute Resolution Procedure.

  - Determination of Dispute

If the determination of any dispute conducted pursuant to clause 37.7 (Dispute) shows that:

37.8.1	the Disputing Party has withheld any amount which the Claiming Party was entitled to be paid; or

37.8.2	the Claiming Party has claimed under clause 37.2 (Report and Invoice) any amount which it was not entitled to be paid,

the Disputing Party shall pay such amount to the Claiming Party or the Claiming Party shall repay such amount to the Disputing Party with interest in each case on that amount at the Prescribed Rate calculated on a daily basis and compounded quarterly from the date on which payment should have been made (in the case of failure to pay by the Disputing Party) or from the date on which over payment was made (in the case of excessive claims by the Claiming Party) until all relevant monies have been paid in full and whether before or after judgment.

  - Rights of Set Off

Each party shall be entitled to retain or set off any amount owed to it by the other party under this Agreement which has fallen due and payable against any amount due to the other party under this Agreement.

  - Set Off and Disputed Amounts

If the payment or deduction of any amount referred to in clause 37.9 (Rights of Set Off) is disputed then any undisputed element of that amount shall be paid and the disputed element shall be dealt with in accordance with the Dispute Resolution Procedure.

  - VAT on Payments

    - All amounts due under this Agreement are exclusive of VAT.

    - If any supply made or referred to in this Agreement is or becomes chargeable to VAT then the person receiving the supply (the Recipient) shall in addition pay the person making the supply (the Supplier) the amount of that VAT against receipt by the Recipient from the Supplier of a proper VAT invoice in respect of that supply.

    - Where under this Agreement any amount is calculated by reference to any sum which has or may be incurred by any person, the amount shall include any VAT in respect of that amount only to the extent that such VAT is not recoverable as input tax by that person (or a member of the same VAT group), whether by set off or repayment.

    - The Contractor shall provide the Authority with any information reasonably requested by the Authority in relation to the amount of VAT chargeable in accordance with this Agreement and payable by the Authority to the Contractor.

  - Indexation

The Annual Payment shall be adjusted in accordance with paragraph 3 of Schedule 6 (Payment and Performance Monitoring System).

  - [NNDR

The parties shall comply with the provisions of Schedule 27 (NNDR)].

- Continuous Improvement

  - Authority's Continuous Improvement Duty

    - The Contractor acknowledges that:

      - the Authority is subject to the Continuous Improvement Duty;

      - the provisions of this clause 38 (Continuous Improvement) are intended to assist the Authority in discharging its Continuous Improvement Duty in relation to the Services; and

      - the provisions of this clause 38.1.1 (Authority's Continuous Improvement Duty) shall apply in respect of the obligations of the Contractor and the Authority concerning the Continuous Improvement Duty and the 1999 Act generally.

    - The Contractor shall, throughout the Services Period, but only to the extent of its obligations in this Agreement, make arrangements to secure continuous improvement in the way in which the Services are provided, having regard to a combination of economy, efficiency and effectiveness.

    - The Contractor shall use reasonable endeavours to assist the Authority in demonstrating that the Authority is meeting its Continuous Improvement Duty in respect of this Agreement including:

      - complying with requests for information, data or other assistance made by the Authority in pursuance of its Continuous Improvement Duty in order to:

        - facilitate any inspection or audit undertaken by any Relevant Authority in connection with the Continuous Improvement Duty in respect of the Services, including any inspection undertaken with a view to verifying the Authority's compliance with its Continuous Improvement Duty;

        - assist the Authority in relation to any action taken by the Secretary of State;

        - enable the Authority to comply with any Government departmental direction; and

        - enable the Authority to report on its performance to Relevant Authorities.

      - complying with all requests by the Authority to procure the attendance of specific officers or employees of the Contractor or any Sub-Contractor (or to procure the attendance of any of its or their sub-contractors) at any meetings of the Authority at which the Services are to be discussed (but not, otherwise than in exceptional circumstances, more than [twice in any one year]); and

      - co-operating in audits and/or other inspections by Relevant Authorities.

  - Annual Service Report and Annual Service Plan

    - Without prejudice to any other provision in this Agreement the Contractor shall on the Annual Service Report Date at its own cost, provide to the Authority a written report (the Annual Service Report) in accordance with the requirements of the Services Specification.

    - The Contractor shall upon a written request from the Authority promptly provide such written evidence or other supporting information as the Authority may reasonably require to verify and audit the information and other material contained in the Annual Service Report.

    - If, in the Authority's reasonable opinion, the provision, performance or delivery of the Services (or any part) may be more effective, efficient and economic having regard to the Annual Service Report and the Continuous Improvement Duty, then the Authority may serve a written notice upon the Contractor (a Continuous Improvement Service Change Notice) stating the nature and timing of the changes to the provision, performance or delivery of the Services (or the relevant part) which the Authority desires.

    - The Contractor shall, within twenty (20) Business Days of the date of receipt of the Continuous Improvement Service Change Notice, provide the Authority at its own cost with a written statement (the Annual Service Plan) containing the Contractor's proposals to achieve the change to the Services (or the relevant part) in accordance with the Continuous Improvement Service Change Notice.

    - As soon as practicable after the Authority receives the Annual Service Plan, the parties shall discuss and agree the issues set out in the Annual Service Plan. In such discussions the Authority may modify the Continuous Improvement Service Change Notice, in which case the Contractor shall, as soon as practicable, and in any event not more than twenty (20) Business Days after the receipt of such modification, notify the Authority of any consequential changes to the Annual Service Plan.

    - If the parties cannot agree on the contents of the Annual Service Plan then the dispute will be determined in accordance with the Dispute Resolution Procedure.

    - As soon as practicable after the content of the Annual Service Plan has been agreed or otherwise determined in accordance with the Dispute Resolution Procedure the Authority shall:

      - confirm in writing the Annual Service Plan; or

      - withdraw the Continuous Improvement Service Change Notice.

    - If the Authority either withdraws the Continuous Improvement Service Change Notice or does not confirm the Annual Service Plan within twenty (20) Business Days of the Annual Service Plan having been agreed or determined under the Dispute Resolution Procedure then the Annual Service Plan and the Continuous Improvement Service Change Notice shall be deemed to have been withdrawn.

    - If the Authority confirms the Annual Service Plan then the Authority shall in accordance with the Change Protocol issue an Authority Notice of Change (which shall include all the information set out in the Continuous Improvement Service Change Notice).

    - The Contractor shall take all reasonable steps to mitigate any costs and maximise any savings arising as a consequence of a Continuous Improvement Service Change Notice and an Authority Notice of Change served under clause 38.2.9 (Annual Service Report and Annual Service Plan).

Part 6 - Termination

- Termination of this Agreement

  - Voluntary Termination by the Authority

    - The Authority may terminate this Agreement at any time on or before the Expiry Date by complying with its obligations under clause 39.1.2 (Voluntary Termination by the Authority).

    - If the Authority wishes to terminate this Agreement under this clause 39.1 (Voluntary Termination by the Authority), it must give a Termination Notice to the Contractor stating:

      - that the Authority is terminating this Agreement under this clause 39.1 (Voluntary Termination by the Authority);

      - that this Agreement will terminate on the date specified in the notice, which must be a minimum of twenty (20) Business Days after the date of receipt of the notice; and

      - whether the Authority has chosen to exercise its option under clause 39.1.3 (Voluntary Termination by the Authority).

    - On termination, the Authority shall have the option to require the Contractor to transfer its rights, title and interest in and to the Assets to the Authority or as directed by the Authority.

    - This Agreement will terminate on the date specified in the notice issued in accordance with clause 39.1.2 (Voluntary Termination by the Authority).

  - Termination on Authority Default

    - If an Authority Default has occurred and the Contractor wishes to terminate this Agreement, the Contractor must serve a termination notice (the Contractor Termination Notice) on the Authority within thirty (30) Business Days of becoming aware of the Authority Default.

    - The Contractor Termination Notice must specify the type of Authority Default which has occurred entitling the Contractor to terminate.

    - This Agreement will terminate on the day falling thirty (30) Business Days after the date the Authority receives the Contractor Termination Notice, unless the Authority rectifies the Authority Default within twenty (20) Business Days of receipt of the Contractor Termination Notice.

  - Termination on Contractor Default

    - Subject to clause 39.4 (Rectification), the Authority shall be entitled to terminate this Agreement by notice in writing to the Contractor if a Contractor Default has occurred.

    - On termination the Authority may require the Contractor to transfer all of its rights, title and interest in and to the Assets to the Authority or as directed by the Authority.

  - Rectification

    - If a Contractor Default has occurred and the Authority wishes to terminate this Agreement, it must serve a Termination Notice on the Contractor.

    - The Termination Notice must specify:

      - the type and nature of Contractor Default that has occurred, giving reasonable details; and

      - that in the case of any Contractor Default falling within limbs (a) (material breach), (g) (assignment, subcontracting and change of control) and (n) (insurance) of the definition of Contractor Default this Agreement will terminate on the day falling forty (40) Business Days after the date the Contractor receives the Termination Notice, unless:

        - in the case of a breach under limb (a) (material breach) of the definition of Contractor Default the Contractor puts forward an acceptable rectification programme within twenty (20) Business Days after the date the Contractor receives the Termination Notice (and implements such programme in accordance with its terms and rectifies the Contractor Default in accordance with the programme); or

        - in the case of any Contractor Default falling within limbs (a) (material breach), (g) (assignment, subcontracting and change of control) and (n) (insurance) of the definition of Contractor Default the Contractor rectifies the Contractor Default within forty (40) Business Days after the date the Contractor receives the Termination Notice; or

      - that in the case of any other Contractor Default (not being limbs (a) (material breach), (g) (assignment, subcontracting and change of control) or (n) (insurance)), this Agreement will terminate on the date falling forty (40) Business Days after the date the Contractor receives the Termination Notice.

    - If the Contractor either rectifies the Contractor Default within the time period specified in the Termination Notice, or implements the rectification programme, if applicable, in accordance with its terms, the Termination Notice will be deemed to be revoked and this Agreement will continue.

    - If either in the case of a Contractor Default within limb (a) (material breach) of the definition of that term where no acceptable rectification programme has been put forward pursuant to clause 39.4.2.2.1 or in the case of a Contractor Default falling within limbs (g) (assignment, subcontracting and change of control) or (n) (insurance) of the definition of Contractor Default, the Contractor fails to rectify the Contractor Default within the time period specified in the Termination Notice, the Authority may give notice stating that this Agreement will terminate on the date falling five (5) Business Days after the date of receipt of such notice.

    - If the Contractor fails to implement any rectification programme in accordance with its terms, this Agreement will terminate on the date falling thirty (30) Business Days after the date of notification by the Authority to the Contractor of such failure to implement the rectification programme in accordance with its terms.

- Termination for Persistent Breach by the Contractor

  - Warning Notice

If a particular breach, other than any breach for which Performance Adjustment Points and/or Performance Adjustments could have been applied, has continued for more than [fourteen (14)] days or occurred more than [three (3)] times in any [six (6)] month period then the Authority may serve a notice on the Contractor:

    - specifying that it is a formal warning notice;

    - giving reasonable details of the breach; and

    - stating that the breach is a breach which, if it recurs frequently or continues, may result in a termination of this Agreement.

  - Final Notice

If, following service of a warning notice the breach specified has continued beyond [thirty (30)] days or recurred in [three (3)] or more months within the [six (6)] month period after the date of service, then the Authority may serve another notice (a Final Warning Notice) on the Contractor:

    - specifying that it is a Final Warning Notice;

    - stating that the breach specified has been the subject of a warning notice served within the [six(6)] month period prior to the date of service of the Final Warning Notice; and

    - stating that if the breach continues for more than [fourteen (14)] days or recurs in [three (3)] or more months within the [six (6)] month period after the date of service of the Final Warning Notice, this Agreement may be terminated.

  - Currency of Warning Notices

A warning notice may not be served in respect of any incident of breach which has previously been counted in the award of a separate warning notice.

- Termination on Corrupt Gifts and Fraud

  - Corrupt Gifts and Fraud

The Contractor warrants that in entering into this Agreement it has not committed any Prohibited Act.

  - Termination for Corrupt Gifts and Fraud

    - If the Contractor or any Sub-Contractor (or anyone employed by or acting on behalf of any of them) or any of its or their agents or shareholders commits any Prohibited Act, then the Authority shall be entitled to act in accordance with the provisions of this clause 41.2 (Termination for Corrupt Gifts and Fraud).

    - Notwithstanding clauses 41.2.3 to 41.2.6 (Termination for Corrupt Gifts and Fraud), if a Prohibited Act is committed by the Contractor or by an employee not acting independently of the Contractor, then the Authority may terminate this Agreement by giving notice to the Contractor provided that, if the Prohibited Act is an offence under section 7(1) of the Bribery Act 2010, the Authority may not terminate this Agreement unless, acting reasonably, it considers termination of this Agreement to be in the best interests of the Project.

    - If the Prohibited Act is committed by an employee of the Contractor acting independently of the Contractor, then the Authority may give notice to the Contractor of termination and this Agreement will terminate, unless within [twenty (20)] Business Days of receipt of such notice the Contractor terminates the employee's employment and (if necessary) procures the performance of such part of the Works and/or Services by another person.

    - If the Prohibited Act is committed by a Sub-Contractor or by an employee of that Sub-Contractor not acting independently of that Sub-Contractor, then the Authority may give notice to the Contractor of termination and this Agreement will terminate, unless within [twenty (20)] Business Days of receipt of such notice the Contractor terminates the relevant Ancillary Document and procures the performance of such part of the Works and/or Services by another person provided that, if the Prohibited Act is an offence under section 7(1) of the Bribery Act 2010, the Authority may not terminate this Agreement unless, acting reasonably, it considers termination of this Agreement to be in the best interests of the Project.

    - If the Prohibited Act is committed by an employee of a Sub-Contractor acting independently of that Sub-Contractor, then the Authority may give notice to the Contractor of termination and this Agreement will terminate, unless within [twenty (20)] Business Days of receipt of such notice the Sub-Contractor terminates the employee's employment and (if necessary) procures the performance of such part of the Works and/or Services by another person.

    - If the Prohibited Act is committed by any other persons not specified in clauses 41.2.2 (Termination for Corrupt Gifts and Fraud) to 41.2.5 (Termination for Corrupt Gifts and Fraud), then the Authority may give notice to the Contractor of termination and this Agreement will terminate, unless within twenty (20) Business Days of receipt of such notice the Contractor procures the termination of such person's employment and of the appointment of their employer (where not employed by the Contractor or the Sub-Contractors) and (if necessary) procures the performance of such part of the Works and/or Services by another person provided that, if the Prohibited Act is an offence under section 7(1) of the Bribery Act 2010, the Authority may not terminate this Agreement unless, acting reasonably, it considers termination of this Agreement to be in the best interests of the Project.

    - Any notice of termination under this clause 41.2 (Termination for Corrupt Gifts and Fraud) shall specify:

      - the nature of the Prohibited Act;

      - the identity of the party whom the Authority believes has committed the Prohibited Act; and

      - the date on which this Agreement will terminate, in accordance with the applicable provision of this clause 41.2 (Termination for Corrupt Gifts and Fraud).

    - In this clause 41 (Termination on Corrupts Gifts and Fraud), the expression "not acting independently of" (when used in relation to the Contractor or a Sub-Contractor) means and shall be construed as acting with the authority of or knowledge of any one or more of the directors of the Contractor or the Sub-Contractor (as the case may be).

    - The Contractor undertakes to the Authority that it will throughout the duration of this Agreement use all reasonable endeavours to have in place adequate procedures (as referred to in section 7(2) of the Bribery Act 2010) designed to prevent persons associated with the Contractor from bribing any person with the intention of obtaining or retaining business for the Contractor or with the intention of obtaining or retaining an advantage in the conduct of business for the Contractor.

- Termination On Force Majeure

  - Obligations

No party shall be entitled to bring a claim for a breach of obligations under this Agreement by the other party or incur any liability to the other party for any losses or damages incurred by that other party to the extent that a Force Majeure Event occurs and the Affected Party is prevented from carrying out obligations by that Force Majeure Event. For the avoidance of doubt, the Authority shall not be entitled to terminate this Agreement for a Contractor Default if such Contractor Default arises from a Force Majeure Event (but without prejudice to clauses 42.4 (Unable to Agree), 42.5 (Consequences of Termination) or 42.6 (Notice to Continue)).

  - Notification for Force Majeure

On the occurrence of a Force Majeure Event, the Affected Party shall notify the other party as soon as practicable. The notification shall include details of the Force Majeure Event, including evidence of its effect on the obligations of the Affected Party and any action proposed to mitigate its effect.

  - Consultation

As soon as practicable following such notification, the parties shall consult with each other in good faith and use all reasonable endeavours to agree appropriate terms to mitigate the effects of the Force Majeure Event and facilitate the continued performance of this Agreement.

  - Unable to Agree

If no such terms are agreed on or before the date falling eighty (80) Business Days after the date of the commencement of the Force Majeure Event and such Force Majeure Event is continuing or its consequence remains such that the Affected Party is unable to comply with its obligations under this Agreement for a period of more than one hundred and twenty (120) Business Days, then, subject to clause 42.5 (Consequences of Termination), either party may terminate this Agreement by giving twenty (20) Business Days' written notice to the other party.

  - Consequences of Termination

If this Agreement is terminated under clause 42.4 (Unable to Agree) or clause 42.6 (Notice to Continue):

    - compensation shall be payable by the Authority in accordance with clause 49 (Compensation on Termination for Force Majeure); and

    - the Authority may require the Contractor to transfer all of its title, interest and rights in and to any Assets to the Authority or as directed by the Authority.

  - Notice to Continue

If the Contractor gives notice to the Authority under clause 42.4 (Unable to Agree) that it wishes to terminate this Agreement, then the Authority has the option either to accept such notice or to respond in writing on or before the date falling ten (10) Business Days after the date of its receipt stating that it requires this Agreement to continue. If the Authority gives the Contractor such notice (the Continuation Notice), then:

    - the Authority shall (where the Annual Payment is a Deficit Annual Payment) pay to the Contractor the Annual Payment and any Loss of Revenue (to the extent that such Loss of Revenue arises as a direct result of the Force Majeure Event) or, where the Annual Payment is a Surplus Annual Payment, the Contractor shall pay the Authority the Annual Payment less any Loss of Revenue arising as a direct result of the Force Majeure Event from the day after the date on which this Agreement would have terminated under clause 42.4 (Unable to Agree) as if the Services were being fully provided; and

    - this Agreement will not terminate until expiry of written notice (of at least twenty (20) Business Days) from the Authority to the Contractor that it wishes this Agreement to terminate.

  - Mitigation

The parties shall at all times following the occurrence of a Force Majeure Event use all reasonable endeavours to prevent and mitigate the effects of any delay and the Contractor shall at all times during which a Force Majeure Event is subsisting take all steps in accordance with Good Industry Practice to overcome or minimise the consequences of the Force Majeure Event.

  - Cessation of Force Majeure Event

The Affected Party shall notify the other party as soon as practicable after the Force Majeure Event ceases or no longer causes the Affected Party to be unable to comply with its obligations under this Agreement. Following such notification this Agreement shall continue to be performed on the terms existing immediately prior to the occurrence of the Force Majeure Event.

- Consequences of Termination

  - Compensation Provisions

If this Agreement is terminated pursuant to:

    - Clause 39.1 (Voluntary Termination by the Authority), the provisions of clause 46 (Compensation on Termination for Authority Default/Voluntary Termination) shall apply;

    - Clause 39.2 (Termination on Authority Default), the provisions of clause 46 (Compensation on Termination for Authority Default/Voluntary Termination) shall apply;

    - Clause 39.3 (Termination on Contractor Default), the provisions of clause 47 (Compensation on Termination for Contractor Default and Corrupt Gifts and Fraud) shall apply; or

    - Clause 41 (Termination on Corrupt Gifts and Fraud), the provisions of clause 47 (Compensation on Termination for Contractor Default and Corrupt Gifts and Fraud) shall apply;

    - Clause 42 (Termination on Force Majeure), the provisions of clause 49 (Compensation on Termination for Force Majeure) shall apply;

    - Clause 63 (Risks that become Uninsurable), the provisions of clause 49 (Compensation on Termination for Force Majeure) shall apply.

  - Termination of Agreement

Notwithstanding any other provisions of this Agreement, this Agreement shall only terminate in accordance with the express provisions of this Agreement.

  - Continuing Obligations

Save as otherwise expressly provided in this Agreement or as already taken into account in the calculation of any Termination Sum or other payment of compensation on termination pursuant to this Agreement, and notwithstanding the provisions of clause 52.2 (Exclusivity of Remedy) and 82 (Sole Remedy):

    - termination of this Agreement shall be without prejudice to any accrued rights or obligations under this Agreement as at the date of termination; and

    - termination of this Agreement shall not affect the continuing rights and obligations of the Contractor and the Authority under [clause 8 (Nature of Land Interests), clause 29 (TUPE and Employees), clause 30 (Pensions), 36 (Payment during the Works Period) to the extent any sums remain due, clause 37 (Payment during the Services Period) clause 45 (Transition to Another Contractor), Part 7 (Compensation on Termination), clause 59 (Freedom of Information and Confidentiality), clause 60 (Indemnities, Guarantees and Contractual Claims) in respect of any claim arising prior to the Termination Date, clause 62 (Reinstatement and Change of Requirement after Insured Event), clause 63 (Risks that Become Uninsurable), clause 64 (Dispute Resolution), clause 66 (Intellectual Property), clause 73 (Notices), clause 78 (Contractor's Records), clause 80 (Interest on Late Payment), clause 81 (Governing Law and Jurisdiction), clause 82 (Sole Remedy), clause 83 (No Double Recovery) and clause 86 (Capacity)] or under any other provision of this Agreement which is expressed to survive termination or which is required to give effect to such termination or the consequences of such termination.

- Surveys on Expiry and Retention Fund

  - Final Survey

    - No later than the date [eighteen (18)] months prior to the Expiry Date, the Authority shall be entitled to carry out or procure the carrying out of a final survey of the Site[s] to assess whether [it has/they have] been and [is/are] being maintained by the Contractor in accordance with its obligations under clause 23.1 (Maintenance).

    - The Authority shall notify the Contractor in writing a minimum of five (5) Business Days in advance of the date it wishes to carry out or procure the carrying out of the final survey. The Authority shall consider in good faith any reasonable request by the Contractor for the final survey to be carried out on a different date if such request is made at least two (2) Business Days prior to the notified date and the Contractor (acting reasonably) is able to demonstrate that carrying out the final survey on the notified date would materially prejudice the Contractor's ability to provide the Services.

  - Minimisation of Disruption

When carrying out the final survey, the Authority shall use reasonable endeavours to minimise any disruption caused to the provision of the Services by the Contractor. The Contractor shall afford the Authority or any person carrying out the survey (free of charge) any reasonable assistance required by the Authority during the carrying out of the final survey. The cost of the final survey shall be borne by the Authority.

  - Results of Survey

If the final survey shows that the Contractor has not complied with or is not complying with its obligations under clause 23.1 (Maintenance) the Authority shall:

    - notify the Contractor of the rectification and/or maintenance work which is required to bring the condition of the [Facility/Facilities] to the standard it would have been in if the Contractor had complied or was complying with its obligations under clause 23.1 (Maintenance) (the Required Standard);

    - specify a reasonable period within which the Contractor must carry out such rectification and/or maintenance work; and

    - if the survey shows a material non-compliance by the Contractor with its obligations under clause 23.1 (Maintenance), recover the cost of the survey from the Contractor by means of a withdrawal from the Retention Fund Account or deduction from the next payment of the Monthly Payment.

  - Maintenance Work

The Contractor shall carry out such rectification and/or maintenance work notified pursuant to clause 44.3.1 (the Outstanding Work) in order to reach the Required Standard within the period specified and any costs it incurs in carrying out the Outstanding Work shall be at its own expense.

  - Retention Fund

If the Contractor has been notified under clause 44.3.1 (Results of Survey) that rectification and/or maintenance work is required, [twelve (12)] months prior to the Expiry Date (to the extent the Outstanding Works have not been carried out by the Contractor in the interim):

    - where the Annual Payment is a Deficit Annual Payment, the Authority shall deduct the costs of that work as quantified by the survey referred to in clause 44.1 (Final Survey) from the next following instalment (or, if the amount of such instalment is insufficient, the next instalments as necessary) of Monthly Payment; or

    - where the Annual Payment is a Surplus Annual Payment, the Contractor shall pay the costs of that work as quantified by the survey referred to in clause 44.1 (Final Survey),

and in either case, the relevant party shall pay such amount into an interest bearing escrow account (the Retention Fund Account) (subject to clause 44.6 (Costs)).

  - Costs

If and to the extent that the Contractor carries out the Outstanding Work, to the extent that then or subsequently there are funds standing to the credit of the Retention Fund Account, the Contractor shall be reimbursed its costs of so doing by withdrawing amounts from the Retention Fund Account. If the aggregate of the amounts from time to time paid into the Retention Fund Account are insufficient to cover the Contractor's costs the Contractor shall bear the balance of such costs itself.

  - Failure to Carry Out Work

If and to the extent that the Contractor fails to carry out the Outstanding Work within the period specified in clause 44.3.2 (Results of Survey), the Authority shall be entitled to carry out itself, or procure, such rectification and/or maintenance work at the Contractor's expense and shall make withdrawals from the Retention Fund Account or, where there are insufficient funds in the Retention Fund Account, shall be entitled to recover such amounts from the Contractor as a debt payable on demand.

  - Balance of Fund

If:

    - all the rectification and/or maintenance work identified by the Authority or the person the Authority procures to carry out the final survey has been carried out to the Required Standard;

    - all such rectification and/or maintenance work has been paid for by the Contractor; and

    - no termination notice given in accordance with this Agreement is outstanding,

then the Authority shall pay any credit balance on the Retention Fund Account to the Contractor as soon as practicable.

- Transition To Another Contractor

  - Duty to Co-operate

During the final [six (6)] months of the Contract Period (where this expires by effluxion of time) or during the period of any Termination Notice of this Agreement, and in either case for a reasonable period thereafter, the Contractor shall co-operate fully with the transfer of responsibility for the Works and/or Services (or any of the Works and/or Services) to the Authority or any New Contractor of such works and/or services the same or similar to the Works and/or Services, and for the purposes of this clause 45 (Transition To Another Contractor) the meaning of the term 'co-operate' shall include:

    - liaising with the Authority and/or any New Contractor, and providing reasonable assistance and advice concerning the Works and/or Services and their transfer to the Authority or to such New Contractor;

    - allowing any New Contractor access (at reasonable times and on reasonable notice) to the [Facility/Facilities] but not so as to interfere with or impede the provision of the Works and/or Services;

    - (without prejudice to the obligations of the Contractor pursuant to clause 32 (Operating Manual)) providing to the Authority and/or to any New Contractor all and any information concerning the [Facility/Facilities] and the Works and/or Services which is reasonably required for the efficient transfer of responsibility for their performance but, to avoid doubt, information which is commercially sensitive to the Contractor [and/or Building Contractor and/or FM Contractor and/or Leisure Operator] shall not be provided (and for the purpose of this clause 45.1.3 (Duty to Co-operate), commercially sensitive shall mean Contractor IPR and information which would if disclosed to a competitor of the Contractor [and/or Building Contractor and/or FM Contractor and/or Leisure Operator] give that competitor a competitive advantage over the Contractor [and/or Building Contractor and/or FM Contractor and/or Leisure Operator] and thereby prejudice the business of the Contractor [and/or Building Contractor and/or FM Contractor and/or Leisure Operator] but shall, to avoid doubt, not include any information referred to in clause 29 (TUPE and Employees)); and

    - transferring its rights, title and interest in and to the Assets to the New Contractor with effect on and from the Termination Date or Expiry Date (as applicable).

  - Transfer of Responsibility

The Contractor shall use all reasonable endeavours to facilitate the smooth transfer of responsibility for the Works and/or Services to a New Contractor or to the Authority, as the case may be, and the Contractor shall take no action at any time during the Contract Period or thereafter which is calculated or intended, directly or indirectly, to prejudice or frustrate or make more difficult such transfer.

Part 7 - Compensation on Termination

- Compensation on Termination for Authority Default/Voluntary Termination

  - On termination of this Agreement pursuant to clauses 39.1 (Voluntary Termination by the Authority) or 39.2 (Termination on Authority Default), the Authority shall pay the Contractor in accordance with clauses 52 (Miscellaneous Compensation Provisions) and 53 (Method of Payment) an amount equal to the aggregate of (without double counting):

    - such amounts properly due to the Contractor and invoiced or applied for in accordance with clauses 36 (Payment during the Works Period) and 37 (Payment During the Services Period) in respect of the period prior to such termination but which have not been previously paid;

    - the Value of the Completed Works;

    - where a Deficit Annual Payment applies such amount that can be reasonably and properly attributed to Services carried out following the most recent invoice issued pursuant to clause 37 (Payment During the Services Period) and/or such other amounts properly due to the Contractor in accordance with this Agreement which, in each case remains due at the Termination Date, including any sum set off by the Contractor pursuant to clause 37.9;

    - any Sub-Contractor Breakage Costs;

    - the Profit Payment;

    - [any Capital Costs,] and

    - [any Forward Funded Amount];

LESS to the extent it is a positive amount, the aggregate of (without double counting):

    - where a Surplus Annual Payment applies such amounts properly due to the Authority in accordance with clause 37 (Payment During the Services Period) in respect of the period up to the Termination Date but which have not been previously paid

    - amounts which the Authority is entitled to set off pursuant to clause 37.9 (Rights of set off); and

    - DISU/BI Proceeds, to the extent that they compensate the Contractor in respect of any of the items listed at clauses 46.1.1 to 46.1.6.

- Compensation on Termination for Contractor Default and Corrupt Gifts and Fraud

  - On termination of this Agreement in accordance with clauses 39.3 (Termination on Contractor Default) or 41 (Termination on Corrupt Gifts and Fraud), the Contractor shall be liable to and shall pay the Authority:

    - the reasonable costs incurred by the Authority in the rectification of any part of any Facility which is necessary due to any failure of the Contractor to comply with its obligations under this Agreement;

    - where the Authority carries out a Retendering Process, the Retendering Costs;

    - where the Authority carries out a Retendering Process, an amount equal to the aggregate of the Retendered Annual Payment less the Current Annual Payment where it is a positive number;

    - an amount equal to the Retendered Works Remuneration Amount less the Contract Sum where it is a positive number;

    - all other Direct Losses which the Authority suffers or incurs arising out of any breach of this Agreement or as a result of the termination of this Agreement including (without limitation) any liability to any third party,

LESS, without double counting and subject to the Authority's right of set off under clause 37.9 (Rights of Set Off):

    - such amounts properly due to the Contractor and invoiced or applied for in accordance with clauses 36 (Payment during the Works Period) and 37 (Payment during the Services Period) in respect of the period prior to such termination but which have not been previously paid;

    - the Value of Completed Works;

    - where a Deficit Annual Payment applies, such amount that can be reasonably and properly attributed to Services carried out following the most recent invoice issued pursuant to clause 37 (Payment during the Services Period) and/or such other amounts properly due to the Contractor in accordance with this Agreement which, in each case, remains due at the Termination Date including any sum set off by the Contractor pursuant to clause 37.9;

    - [any Capital Costs,] and

    - [any Forward Funded Amount].

- Not used

- Compensation on Termination for Force Majeure

  - On termination of this Agreement under clause 42 (Termination on Force Majeure), the Authority shall pay to the Contractor in accordance with clauses 52 (Miscellaneous Compensation Provisions) and 53 (Method of Payment) an amount equal to the aggregate of (without double counting):

    - such amounts properly due to the Contractor and invoiced or applied for in accordance with clauses 36 (Payment during the Works Period) and 37 (Payment During the Services Period) in respect of the period prior to such termination but which have not been previously paid;

    - the Value of the Completed Works;

    - where a Deficit Annual Payment applies such amount that can be reasonably and properly attributed to Services carried out following the most recent invoice issued pursuant to clause 37 (Payment During the Services Period) and/or such other amounts properly due to the Contractor in accordance with this Agreement which, in each case remains due at the Termination Date including any sum set off by the Contractor pursuant to clause 37.9;

    - any Sub-Contractor Breakage Costs;

    - [any Capital Costs,] and

    - [any Forward Funded Amount],

LESS to the extent it is a positive amount, the aggregate of (without double counting):

    - where a Surplus Annual Payment applies such amounts properly due to the Authority in accordance with clause 37 (Payment During the Services Period) in respect of the period up to the Termination Date but which have not been previously paid

    - amounts which the Authority is entitled to set off pursuant to clause 37.9 (Rights of set off); and

    - DISU/BI Proceeds, to the extent that they compensate the Contractor in respect of any of the items listed at clauses 49.1.1 to 49.1.6.

- Assets

  - [Subject to clause 50.2] where this Agreement expires due to effluxion of time or terminates earlier, the Authority shall have the option to require the Contractor to transfer to the Authority its rights, title and interest in and to the Assets or as directed by the Authority at nil cost to the Authority.

  - [Where the Authority exercises its right under clause 50.1 and the Assets which are to be transferred include [                ], then to the extent that such [                ] is not already owned by the Authority or has not already been paid for through the Annual Payment or via another payment pursuant to this Agreement, the Authority shall pay to the Contractor the lesser of market value and written down value for such [        ].]

  - Transfer of Assets that are subject to an agreement of hire or hire purchase

    - If this Agreement is terminated prior to the Expiry Date or expires due to the effluxion of time at the Expiry Date, the Authority is entitled to instruct the Contractor to assign or novate any agreement of hire or hire purchase which relates to Assets to the Authority (or as the Authority directs) and the Contractor shall forthwith deliver up to the Authority such Assets.

    - If the Authority elects to exercise its rights to transfer the benefits of any agreement of hire or hire purchase where termination has occurred as a result of Contractor Default, the Authority reserves its right to take action against the Contractor should the Authority be obliged to take on a hire/hire purchase agreement on terms that are unreasonably restrictive or expensive compared to normal market rates for agreements of that nature in order to maintain the Services.

- Retendering Process

If the Authority elects to retender the Works and/or Services following termination under clauses 39.3 (Termination on Contractor Default) or 41 (Termination on Corrupt Gifts and Fraud), then the following provisions shall apply (the Retendering Process):

  - The objective of the retendering process shall be to retender the Works and/or Services and enter into a Retendered Contract with a replacement contractor.

  - The Authority shall (subject to any legal requirements preventing it from doing so) use its reasonable endeavours to complete the Retendering Process as soon as practicable.

  - The Authority shall notify the Contractor of the Qualification Criteria and the other requirements and terms of the Retendering Process, including the timing of the Retendering Process, and shall act reasonably in setting such requirements and terms.

  - The Contractor authorises the release of any information by the Authority under the Retendering Process which would otherwise be prevented under clause 59 (Freedom of Information and Confidentiality) that is reasonably required as part of the Retendering Process provided that the Authority shall not release information which is commercially sensitive as described or referred to in clause 45.1.3.

  - The Authority shall require bidders to bid on the basis that they will receive the benefit of any outstanding claims under any material damage insurance policies and amounts (if any) standing to the credit of the Joint Insurance Account under clause 62.2 (Reinstatement and Change of Requirements after Insured Event) on the date that the Retendered Contract is entered into.

  - As soon as practicable after tenders have been received, the Authority shall (acting reasonably) determine which (if any) of the tenderers it wishes to enter into a Retendered Contract with.

  - The replacement contractor shall be required to set out in its tender submission the proposed costs (including overhead and profit) for the Works (the Retendered Works Remuneration Amount) (if any) and as applicable the proposed annual payment amount (the Retendered Annual Payment).

  - The tenderers will be required to tender on the basis that the successful tenderer shall take the benefit of all existing bookings and any membership fees relating to each Facility.

- Miscellaneous Compensation Provisions

  - Gross Up of Termination Payments

If any amount of compensation payable by the Authority or the Contractor (whether payable as a lump sum or in instalments) under clauses 46 (Compensation on Termination for Authority Default/Voluntary Termination), 47 (Compensation on Termination for Contractor Default and Corrupt Gifts and Fraud) or 49 (Compensation on Termination for Force Majeure) is subject to Tax payable to a Relevant Authority in the United Kingdom, then the Authority shall pay to the Contractor or the Contractor shall pay to the Authority (as appropriate) such additional amount as will put the receiving party in the same after Tax position as it would have been in had the payment not been subject to Tax taking account of any relief, allowances deduction, setting off or credit in respect of Tax (whether available by choice or not) which may be available to the Contractor or the Authority to reduce the Tax to which the payment is subject.

  - Exclusivity of Remedy

Any and all sums irrevocably paid by the Authority to the Contractor or the Contractor to the Authority under this Part 7 shall be in full and final settlement of each party's rights and claims against the other for breaches and/or termination of this Agreement or any Project Document whether under contract, tort, restitution or otherwise, but without prejudice to:

    - any antecedent liability of the Contractor to the Authority which the Authority has been unable to set off pursuant to this Agreement;

    - any antecedent liability of either party to the other that arose prior to the Termination Date (but not from the termination itself) to the extent such liability has not already been taken into account in determining or agreeing the Termination Sum; and

    - any liabilities arising in respect of any breach by either party of their obligations under clause 43.3 (Continuing Obligations) which arises or continues after the Termination Date to the extent not taken into account in the calculation of any Termination Sum or other payment of compensation on termination pursuant to this Agreement.

- Method of Payment

  - Termination Sum

    - All amounts payable by a party to the other party pursuant to clauses 46 (Compensation on termination for Authority Default/Voluntary Termination) to 49 (Compensation on Termination for Force Majeure) of this Agreement shall [(save where the Authority elects to pay in instalments pursuant to clause 53.2)] be paid within forty (40) Business Days of receipt of an invoice demanding payment of the relevant amount. In the event of failure to make payment in accordance with this clause interest shall accrue on any unpaid element of the Termination Sum at the Prescribed Rate from the Termination Date until the date payment is made and any unpaid amount of the Termination Sum and accrued interest thereon shall be recoverable as a debt from the party that is liable to make payment.

    - For the avoidance of doubt, if the calculation of any Termination Sum produces a negative figure, then such sum shall not be paid by the party described as paying such sum pursuant to clauses 46 to 49, but shall instead be paid by the party described as receiving such sum pursuant to clauses 46 to 49 to the other party.

  - [Instalments

Where the Termination Sum is [£                      ] or more, the Authority may elect to pay it:

    - in pro-rated instalments for a period of [two (2)] years from the Termination Date, on the dates (the Instalment Dates) that the Monthly Payment would have been paid had the Termination Date not occurred; or

    - as the parties may otherwise agree.]

  - [Interest

Where the Authority elects to pay the Termination Sum in instalments pursuant to clause 53.2 (Instalments) above, from the Termination Date until the date of payment, interest shall accrue on any unpaid element of the Termination Sum at the Prescribed Rate and shall be payable on the next occurring Instalment Date.]

  - [Payment of outstanding element

If the Authority has elected to pay in accordance with clause 53.2 (Instalments) it may (on twenty (20) Business Days' prior written notice to the Contractor) elect to pay any outstanding element of the Termination Sum in full on any Instalment Date.]

  - [Authority Default in payment

If the Authority:

    - fails to make a payment to the Contractor in accordance with clauses 53.1 (Termination Sum) and/or 53.2 (Instalments) and/or 53.3 (Interest); or

    - breaches clause 67.1 (Restrictions on Transfer of this Agreement by the Authority),

the Contractor may issue a notice to the Authority declaring any unpaid and outstanding element of the Termination Sum together with any interest accrued pursuant to clause 53.3 (Interest) to be immediately due and payable.]

Part 8 - General

- Liaison

The parties shall give effect to the procedure set out in Schedule 10 (Liaison Procedure).

- Relief Events

  - Occurrence

If and to the extent that a Relief Event:

    - is the direct cause of either a failure by the Contractor

      - to commence the Works on or before the Start on Site Date; and/or

      - to achieve Services Availability on or before the [relevant] Planned Services Availability Date or (following the [relevant] Planned Services Availability Date but before the Longstop Date) is the direct cause of a delay in achievement of Services Availability; and/or

      - [to achieve completion of the Post Completion Works on or before the [relevant] Planned Post Completion Works Acceptance Date or (following the [relevant] Planned Post Completion Works Acceptance Date but before the Post Completion Works Longstop Date) is the direct cause of a delay in completion of the relevant Post Completion Works; or]

    - adversely affects the ability of the Contractor to perform any of its obligations under this Agreement,

then the Contractor shall be entitled to apply for relief from any rights of the Authority arising under clause 39.3 (Termination on Contractor Default) and its obligations under this Agreement.

  - Relief

To obtain relief, the Contractor must:

    - as soon as practicable, and in any event within twenty (20) Business Days after it becomes aware that the Relief Event has caused or is likely to cause delay and/or adversely affect the ability of the Contractor to perform its other obligations give to the Authority a notice of its claim for relief from its obligations under this Agreement, including full details of the nature of the Relief Event, the date of occurrence and its likely duration;

    - within five (5) Business Days of receipt by the Authority of the notice referred to in clause 55.2.1 (Relief), give full details of the relief claimed; and

    - demonstrate to the reasonable satisfaction of the Authority that:

      - the Contractor and its Sub-Contractors could not have avoided such occurrence or consequences by steps which they might reasonably be expected to have taken, without incurring material expenditure;

      - the Relief Event directly caused:

        - the delay in the commencement of the Works on or before the Start on Site Date; and/or

        - the delay in the achievement of Services Availability on or before the [relevant] Planned Services Availability Date or (following the [relevant] Planned Services Availability Date but before the Longstop Date) any delay in the achievement of Services Availability; and/or

        - [any delay in the completion of the Post Completion Works on or before the relevant Planned Post Completion Works Acceptance Date or (following the relevant Planned Post Completion Works Acceptance Date but before the Post Completion Works Longstop Date) any delay in completing the relevant Post Completion Works; and/or]

        - the need for relief from obligations;

      - the time lost and/or relief from the obligations under this Agreement claimed could not reasonably be expected to be mitigated or recovered by the Contractor acting in accordance with Good Industry Practice, without incurring material expenditure; and

      - the Contractor is using reasonable endeavours to perform its obligations under this Agreement.

  - Consequences

In the event that the Contractor has complied with its obligations under clause 55.2 (Relief), then:

    - the Start on Site Date; and/or

    - the [relevant] Planned Services Availability Date and/or following the [relevant] Planned Services Availability Date, the Longstop Date; and/or

    - [the [relevant] Planned Post Completion Works Acceptance Date and/or following the [relevant] Planned Post Completion Works Acceptance Date, the Post Completion Works Longstop Date];

shall be postponed by such time as shall be reasonable for such a Relief Event, taking into account the likely effect of delay; and/or

    - the Authority shall not be entitled to exercise its right to terminate this Agreement under clause 39.3 (Termination on Contractor Default) and, [subject to clause 55.4 (Performance Adjustment Points  and Performance Adjustments),] shall give such other relief as has been requested by the Contractor.

  - Performance Adjustment Points and Performance Adjustments

Nothing in clause 55.3 (Consequences) shall, where the Annual Payment is a Deficit Annual Payment, affect any entitlement to apply Performance Adjustment Points and/or Performance Adjustments under clause 37 (Payment during the Services Period) and Schedule 6 (Payment and Performance Monitoring System) during the period in which the Relief Event is subsisting provided that any such Performance Adjustment Points and Performance Adjustments shall be disregarded for the purposes of the Authority's right to terminate this Agreement for a Contractor Default.

  - Information

In the event that information required by clause 55.2 (Relief) is provided after the dates referred to in that clause, then the Contractor shall not be entitled to any relief during the period for which the information is delayed.

  - Notice

The Contractor shall notify the Authority if at any time it receives or becomes aware of any further information relating to the Relief Event, giving details of that information to the extent that such information is new or renders information previously submitted materially inaccurate or misleading.

  - Disputes

If the parties cannot agree the extent of the relief required, or the Authority disagrees that a Relief Event has occurred or that the Contractor is entitled to any extension to the Start on Site Date and/or [the/any] Planned Services Availability Date and/or (following [the/any] Planned Services Availability Date) to the Longstop Date [and/or any Planned Post Completion Works Acceptance Date and/or (following [the/any] Planned Post Completion Works Acceptance Date) to the Post Completion Works Longstop Date] and/or relief from other obligations under this Agreement, the parties shall resolve the matter in accordance with the Dispute Resolution Procedure.

- Change in Law

  - Occurrence

The Contractor shall take all steps necessary to ensure that the Works and the Services are performed in accordance with the terms of this Agreement following any Change in Law.

  - Qualifying Change in Law

If a Qualifying Change in Law occurs or is shortly to occur, then either party may write to the other to express an opinion on its likely effects, giving details of its opinion of:

    - any necessary change to the Works or the Services;

    - whether any changes are required to the terms of this Agreement to deal with the Qualifying Change in Law;

    - whether relief from compliance with obligations is required, including the obligation of the Contractor to commence the Works by the Start on Site Date, to achieve Services Availability by the Planned Services Availability Date in relation to [the/a] Facility [, to complete the Post Completion Works before the [relevant] Planned Post Completion Works Acceptance Date] and/or meet the Authority's Requirements and/or the Contractor's Proposals during the implementation of any relevant Qualifying Change in Law;

    - any Change in Revenue that will result from the relevant Qualifying Change in Law;

    - any estimated Change in Costs that directly result from the Qualifying Change in Law; and

    - any Capital Expenditure that is required or no longer required as a result of a Qualifying Change in Law taking effect after the final Services Availability Date,

in each case giving in full detail the procedure for implementing the change in the Works or in the Services. Responsibility for the costs of implementation (and any resulting variation to the Annual Payment) shall be dealt with in accordance with clauses 56.3 (Parties to Discuss) to 56.6 (Adjustment to Annual Payment).

  - Parties to Discuss

As soon as practicable after receipt of any notice from either party under clause 56.2 (Qualifying Change in Law), the parties shall discuss and agree the issues referred to in clause 56.2 (Qualifying Change in Law) and any ways in which the Contractor can mitigate the effect of the Qualifying Change in Law, including:

    - providing evidence that the Contractor has used reasonable endeavours (including (where practicable) the use of competitive quotes) to oblige its sub-contractors to minimise any increase in costs or decrease in Revenue and maximise any reduction in costs or increase in Revenue;

    - demonstrating how any Capital Expenditure to be incurred or avoided is being measured in a cost effective manner, including showing that when such expenditure is incurred or would have been incurred, foreseeable Changes in Law at that time have been taken into account by the Contractor;

    - giving evidence as to how the Qualifying Change in Law has affected prices charged by any similar businesses to the Project, including similar businesses in which the shareholders or their Affiliates carry on business; and

    - demonstrating that any expenditure that has been avoided, which was anticipated to be incurred to replace or maintain assets that have been affected by the Qualifying Change in Law concerned, has been taken into account in the amount which in its opinion has resulted or is required under clauses 56.2.5 (Qualifying Change in Law) and/or 56.2.6 (Qualifying Change in Law);

  - Change Agreed

If the parties agree or it is determined under the Dispute Resolution Procedure that the Contractor is required to incur additional Capital Expenditure due to a Qualifying Change in Law, then the Contractor shall use its reasonable endeavours to obtain funding for such Capital Expenditure on terms reasonably satisfactory to it.

  - Financing

If the Contractor has used reasonable endeavours to obtain funding for the Capital Expenditure referred to in clause 56.4 (Change Agreed), but has been unable to do so within forty (40) Business Days of the date that agreement or determination pursuant to clause 56.4 (Change Agreed) occurred, then the Authority shall pay to the Contractor an amount equal to that Capital Expenditure [on or before the date falling twenty (20) Business Days after the Capital Expenditure has been incurred] [in instalments to be paid on the value of works carried out on a monthly basis].

  - Adjustment to Annual Payment

Any compensation payable under this clause 56 (Changes in Law) by means of an adjustment to or reduction in the Annual Payment shall be determined and made in accordance with clause 69 (Financial Adjustments).

  - Payment of Irrecoverable VAT

The Authority shall pay to the Contractor from time to time as the same is incurred by the Contractor sums equal to any Irrecoverable VAT but only to the extent that it arises as a result of a Change in Law. Any such payment shall be made within twenty (20) Business Days of the delivery by the Contractor to the Authority of written details of the amount involved accompanied by details as to the grounds for and computation of the amount claimed. For the purposes of this clause 56.7, Irrecoverable VAT means input VAT incurred by the Contractor on any supply which is made to it which is used or to be used exclusively in performing the Works or the Services or any of the obligations or provisions under this Agreement (together with input VAT incurred as part of its overhead in relation to such activities) to the extent that the Contractor is not entitled to repayment or credit from HM Revenue & Customs in respect of such input VAT.

- Authority and Contractor Changes

The provisions of Schedule 24 (Change Protocol) shall have effect in respect of Changes except as otherwise expressly provided in this Agreement.

- Authority Step-In

  - Right to Step-In

If the Authority reasonably believes that it needs to take action in connection with the Services:

    - because a serious risk exists to the health or safety of persons or property or to the environment;

    - to discharge a statutory duty; and/or

    - because an Emergency has arisen,

then the Authority shall be entitled to take action in accordance with clauses 58.2 (Notice to the Contractor) to 58.5 (Step-In on Contractor Breach).

  - Notice to the Contractor

If clause 58.1 (Right to Step-In) applies and the Authority wishes to take action, the Authority shall notify the Contractor in writing of the following:

    - the action it wishes to take;

    - the reason for such action;

    - the date it wishes to commence such action;

    - the time period which it believes will be necessary for such action; and

    - to the extent practicable, the effect on the Contractor and its obligation to carry out the Works and/or provide the Services during the period such action is being taken.

  - Action by Authority

    - Following service of such notice, the Authority shall take such action as notified under clause 58.2 (Notice to the Contractor) and any consequential additional action as it reasonably believes is necessary (together, the Required Action) and the Contractor shall give all reasonable assistance to the Authority while it is taking the Required Action. The Authority shall provide the Contractor with notice of completion of the Required Action and shall use reasonable endeavours to provide such advance notice as is reasonably practicable of its anticipated completion.

    - Where the Required Action has been taken otherwise than as a result of a breach by the Contractor, the Authority shall undertake the Required Action in accordance with Good Industry Practice and shall indemnify the Contractor against all Direct Losses where it fails to do so.

  - Step-In without Contractor Breach

If the Contractor is not in breach of its obligations under this Agreement, then for so long as and to the extent that the Required Action is taken, and this prevents the Contractor from carrying out the Works and/or providing any part of the Services:

    - the Contractor shall be relieved from its obligations to carry out the Works and/or provide such part of the Services; and

    - in respect of the period in which the Authority is taking the Required Action and provided that the Contractor provides the Authority with reasonable assistance (such assistance to be at the expense of the Authority to the extent that incremental costs are incurred) the Annual Payment, where it is a Deficit Annual Payment due from the Authority to the Contractor, shall equal the amount the Contractor would receive if it were satisfying all its obligations and providing the Services affected by the Required Action in full together with any Loss of Revenue (but only to the extent that such Loss of Revenue arises as a direct result of the Authority taking the Required Action) over that period; or

    - where the Annual Payment is a Surplus Annual Payment due from the Contractor to the Authority it shall be suspended and the Authority shall account to the Contractor for all revenue received by the Authority in respect of the Services affected by the Required Action in full, together with any Loss of Revenue (but only to the extent that such Loss of Revenue arises as a direct result of the Authority taking the Required Action) over that period less such amount of the Surplus Annual Payment that would have been payable over that period had the Required Action not been taken subject to the Contractor being in a no worse position in respect of the amount of revenue and Loss of Revenue received or paid.

  - Step-In on Contractor Breach

If the Required Action is taken as a result of a breach of the obligations of the Contractor under this Agreement, then for so long as and to the extent that the Required Action is taken, and this prevents the Contractor from carrying out any part of the Works and/or providing any part of the Services:

    - the Contractor shall be relieved of its obligations to carry out such part of the Works and/or provide such part of the Services; and

    - in respect of the period in which the Authority is taking the Required Action, the Annual Payment, where it is a Deficit Annual Payment due from the Authority to the Contractor shall equal the amount the Contractor would receive if it were satisfying all its obligations and carrying out the Works and/or providing the Services affected by the Required Action in full over that period, less an amount equal to all the Authority's costs of operation in taking the Required Action having deducted any revenue received by the Authority and which is due to the Contractor; or

    - where the Annual Payment is a Surplus Annual Payment due from the Contractor to the Authority it shall be suspended and the Authority shall account to the Contractor for all revenue received by the Authority in respect of the Services affected by the Required Action in full over that period, less:

      - an amount equal to all the Authority's costs of operation in taking the Required Action; and

      - the Surplus Annual Payment adjusted pro rata for that period.

- Freedom of Information and Confidentiality

  - Duty of Confidentiality

    - The parties agree that the terms of this Agreement and each Project Document shall, subject to clause 59.1.2 (Duty of Confidentiality), not be treated as Confidential Information and may be disclosed without restriction.

    - Clause 59.1.1 (Duty of Confidentiality) shall not apply to terms of this Agreement or a Project Document designated as Commercially Sensitive Information and listed in Part 1 of Schedule 21 (Commercially Sensitive Contractual Provisions) to this Agreement, which shall, subject to clause 59.2 (Permitted Disclosure), be kept confidential for the relevant periods specified in that Part.

    - The parties shall keep confidential all Confidential Information received by one party from the other party relating to this Agreement and the Project Documents or the Project and shall use all reasonable endeavours to prevent their employees and agents from making any disclosure to any person of any Confidential Information.

  - Permitted Disclosure

Clauses 59.1.2 and 59.1.3 (Duty of Confidentiality) shall not apply to:

    - any disclosure of information that is reasonably required by any person engaged in the performance of their obligations under this Agreement for the performance of those obligations;

    - any matter which a party can demonstrate is already or becomes generally available and in the public domain otherwise than as a result of a breach of this clause 59 (Freedom of Information and Confidentiality);

    - any disclosure to enable a determination to be made under the Dispute Resolution Procedure or in connection with a dispute between the Contractor or any of its sub-contractors;

    - any disclosure which is required pursuant to any statutory, legal (including any order of a court of competent jurisdiction) or Parliamentary obligation placed upon the party making the disclosure or the rules of any stock exchange or governmental or regulatory authority having the force of law or if not having the force of law, compliance with which is in accordance with the general practice of persons subject to the stock exchange or governmental or regulatory authority concerned;

    - any disclosure of information which is already lawfully in the possession of the receiving party, prior to its disclosure by the disclosing party;

    - any provision of information to the parties' own professional advisers or insurance advisers or funders (or to their funder's professional advisers or insurance advisers) [or to the Leisure Operator or the FM Contractor for the purposes of performance under [its/their respective] Sub-Contracts] or, where it is proposed that a person should or may provide funds (whether directly or indirectly and whether by loan, equity participation or otherwise) to the Contractor [and/or Holdco] to enable it to carry out its obligations under this Agreement, or may wish to acquire shares in the Contractor [and/or Holdco] in accordance with the provisions of this Agreement to that person or their respective professional advisers but only to the extent reasonably necessary to enable a decision to be taken on the proposal;

    - any disclosure by the Authority of information relating to the design, construction, operation and maintenance of the Project and such other information as may be reasonably required for the purpose of conducting a due diligence exercise to any proposed new contractor, its advisers and lenders should the Authority decide to re-tender this Agreement;

    - any registration or recording of the Necessary Consents and property registration required;

    - any disclosure of information by the Authority to any other department, office or agency of the Government or their respective advisors or to any person engaged in providing services to the Authority for any purpose related to or ancillary to the Agreement; and

    - any disclosure for the purpose of:

      - the examination and certification of the Authority's or the Contractor's accounts; or

      - any examination pursuant to the 1999 Act of the economy, efficiency and effectiveness with which the Authority has used its resources; or

      - complying with a proper request from either party's insurance advisers or insurers on placing or renewing any insurance policies; or

      - (without prejudice to the generality of clause 59.2.4) compliance with the FOIA and/or the Environmental Information Regulations,

provided that, for the avoidance of doubt, neither clauses 59.2.10.4 (Permitted Disclosure) or 59.2.4 (Permitted Disclosure) shall permit disclosure of Confidential Information otherwise prohibited by clause 59.1.3 (Duty of Confidentiality) where that information is exempt from disclosure under section 41 of the FOIA.

  - Obligations Preserved

Where disclosure is permitted under clause 59.2 (other than clauses 59.2.2, 59.2.4, 59.2.5, 59.2.8 and 59.2.10 (Permitted Disclosure)) the party providing the information shall procure that the recipient of the information shall be subject to the same obligation of confidentiality as that contained in this Agreement.

  - Audit

For the purposes of:

    - the examination and certification of the Authority's accounts;

    - the Local Government Finance Act 1982 (and any other Legislation relating to the inspection, examination and auditing of the Authority's accounts); and

    - an examination pursuant to the 1999 Act of the economy, efficiency and effectiveness with which the Authority has performed its functions,

the District Auditor and the Audit Commission may examine such documents as he or it may reasonably require which are owned, held or otherwise within the control of the Contractor and any sub-contractor and may require the Contractor and any sub-contractor to produce such oral or written explanations as he or it considers necessary.

  - Exploitation of Information

The Contractor shall not make use of this Agreement or any information issued or provided by or on behalf of the Authority in connection with this Agreement otherwise than for the purposes of this Agreement, except with the written consent of the Authority.

  - Information about Users and Authority Related Parties

Where the Contractor, in carrying out its obligations under this Agreement, is provided with information relating to Users and Authority Related Parties, the Contractor shall not disclose or make use of any such information otherwise than for the purpose for which it was provided, unless the Contractor has sought the prior written consent of that User or Authority Related Party and has obtained the prior written consent of the Authority.

  - Expiry

On or before the Expiry Date or the Termination Date, the Contractor shall ensure that all documents or computer records in its possession, custody or control, which contain information relating to any User or Authority Related Party including any documents in the possession, custody or control of a sub-contractor, are delivered up to the Authority.

  - Disclosure by Audit Commission

The parties acknowledge that the Audit Commission has the right to publish details of this Agreement (including Commercially Sensitive Information) in its relevant reports to Parliament.

  - The provisions of this clause 59 are without prejudice to the application of the Official Secrets Acts 1911 to 1989.

  - Freedom of Information

    - The Contractor acknowledges that the Authority is subject to the requirements of the FOIA and the Environmental Information Regulations and shall facilitate the Authority's compliance with its Information disclosure requirements pursuant to the same in the manner provided for in clauses 59.10.2 to 59.10.8 (Freedom of Information) (inclusive).

    - Where the Authority receives a Request for Information in relation to Information that the Contractor is holding on its behalf the Authority shall transfer to the Contractor such Request for Information that it receives as soon as practicable and in any event within five (5) Business Days of receiving a Request for Information and the Contractor shall:

      - provide the Authority with a copy of all such Information in the form that the Authority requires as soon as practicable and in any event within ten (10) Business Days (or such other period as the Authority acting reasonably may specify) of the Authority's request; and

      - provide all necessary assistance as reasonably requested by the Authority in connection with any such Information, to enable the Authority to respond to a Request for Information within the time for compliance set out in section 10 of the FOIA or Regulation 5 of the Environmental Regulations.

    - Following notification under clause 59.10.2 (Freedom of Information) and up until such time as the Contractor has provided the Authority with all the Information specified in clause 59.10.2.1 (Freedom of Information), the Contractor may make representations to the Authority  as to whether or not or on what basis Information requested should be disclosed, and whether further Information should reasonably be provided in order to identify and locate the Information requested, provided always that the Authority shall be responsible for determining at its absolute discretion:

      - whether the Information is exempt from disclosure under the FOIA and the Environmental Information Regulations; and

      - whether the Information is to be disclosed in response to a Request for Information,

and in no event shall the Contractor respond directly, or allow its sub-contractors to respond directly, to a Request for Information unless expressly authorised to do so by the Authority.

    - The Contractor shall ensure that all Information held on behalf of the Authority is retained for disclosure for at least six (6) years (from the date it is acquired) and shall permit the Authority to inspect such Information as requested from time to time.

    - The Contractor shall transfer to the Authority any Request for Information received by the Contractor as soon as practicable and in any event within two (2) Business Days of receiving it.

    - The Contractor acknowledges that any lists provided by him listing or outlining Confidential Information, are of indicative value only and that the Authority may nevertheless be obliged to disclose Confidential Information in accordance with the requirements of the FOIA and the Environmental Information Regulations.

    - In the event of a request from the Authority pursuant to clause 59.10.2 (Freedom of Information), the Contractor shall as soon as practicable, and in any event within [five (5)] Business Days of receipt of such request, inform the Authority of the Contractor's estimated costs of complying with the request to the extent these would be recoverable if incurred by the Authority under section 12(1) of the FOIA and the Fees Regulations. Where such costs (either on their own or in conjunction with the Authority's own such costs in respect of such Request for Information) will exceed the appropriate limit referred to in Section 12(1) of the FOIA and as set out in the Fees Regulations the Authority shall inform the Contractor in writing whether or not it still requires the Contractor to comply with the request and where it does require the Contractor to comply with the request the ten (10) Business Days' period for compliance shall  be extended by such number of additional days for compliance as the Authority is entitled to under Section 10 of the FOIA. In such case, the Authority shall notify the Contractor of such additional days as soon as practicable after becoming aware of them and shall reimburse the Contractor for such costs as the Contractor incurs in complying with the request to the extent the Authority is itself entitled to reimbursement of such costs in accordance with its own FOIA policy from time to time.

    - The Contractor acknowledges that (notwithstanding the provisions of this clause 59) the Authority may, acting in accordance with the Department of Constitutional Affairs' Code of Practice on the Discharge of Functions of Public Authorities under Part I of the Freedom of Information Act 2000 (the FOIA Code), be obliged under the FOIA, or the Environmental Information Regulations to disclose Information concerning the Contractor or the Project:

      - in certain circumstances without consulting with the Contractor; or

      - following consultation with the Contractor and having taken their views into account,

provided always that where clause 59.10.8.1 (Freedom of Information) applies, the Authority shall, in accordance with the recommendations of the FOIA Code, draw this to the attention of the Contractor prior to any disclosure.

- Indemnities, Guarantees and Contractual Claims

  - Contractor's Indemnity

    - The Contractor shall, subject to clause 60.2 (Contractor not Responsible), be responsible for, and shall release and indemnify the Authority on demand from and against all liability for Direct Losses arising from:

      - death or personal injury;

      - loss of or damage to property (including property belonging to the Authority or for which it is responsible) but excluding the land, buildings, plant, equipment and other assets which are the responsibility of the Contractor to provide under this Agreement and which form part of the [Facility/Facilities]; and

      - third party actions, claims and/or demands other than those which are the subject of the indemnity in clause 60.1.2,

which may arise out of, or in consequence of, the design, construction, operation or maintenance of the Site[s] and/or [Facility/Facilities] or the performance or non-performance by the Contractor of its obligations under this Agreement or the presence on the Authority's property of the Contractor or a Contractor Related Party or the presence on the land or buildings forming part of a Facility of any User.

    - The Contractor shall, subject to clause 60.2 (Contractor not Responsible), be responsible for, and shall release and indemnify the Authority or any Authority Related Party, on demand from and against all liability for Direct Losses and Indirect Losses arising from third party actions, claims or demands (as described in clause 60.1.1.3) brought against the Authority or any Authority Related Party for breach of statutory duty which may arise out of, or in consequence of a breach by the Contractor of its obligations under this Agreement to the extent that there are no other remedies available to the Authority under this Agreement.

  - Contractor not Responsible

The Contractor shall not be responsible or be obliged to indemnify the Authority for:

    - any matter referred to in clause 60.1 (Contractor's Indemnity) which arises as a direct result of the Contractor acting on a written notice issued by the Authority (and for the purposes of this clause 60.2.1, clause 1.6 (Responsibility for Related Parties) shall not apply);

    - any injury, loss, damage, cost and expense caused by the negligence or wilful misconduct of the Authority or any Authority Related Party (other than to the extent such negligence or wilful misconduct would not have occurred but for a breach by the Contractor of its obligations under this Agreement) or by the breach of the Authority of its obligations under this Agreement; or

    - in respect of any claim made pursuant to clause 60.1.2 to the extent that, when taken together with any other claims made under that clause over the [five(5)] previous years, the amount of the Contractor's Uninsured Losses exceeds [amount in words (£amount in figures) (Indexed).

  - Limitation of Indemnity

An indemnity by either party under any provision of this Agreement shall be without limitation to any indemnity by that party under any other provision of this Agreement.

  - Notification of Claims

Where either party (the Indemnified Party) wishes to make a claim under this Agreement against the other (the Indemnifying Party) in relation to a claim made against it by a third party (a Third Party Claim), the Indemnified Party shall give notice of the relevant claim as soon as reasonably practicable setting out full particulars of the claim.

  - Conduct of Claims

Subject to the rights of the insurers under the Required Insurances, the Indemnifying Party may at its own expense and with the assistance and co-operation of the Indemnified Party have conduct of the Third Party Claim including its settlement and the Indemnified Party shall not, unless the Indemnifying Party has failed to resolve the Third Party Claim within a reasonable period, take any action to settle or prosecute the Third Party Claim.

  - Costs of Claims

The Indemnifying Party shall, if it wishes to have conduct of any Third Party Claim, give reasonable security to the Indemnified Party for any cost or liability arising out of the conduct of the Third Party Claim by the Indemnifying Party.

  - Mitigation

The Indemnified Party shall at all times take all reasonable steps to minimise and mitigate any loss for which the Indemnified Party is entitled to bring a claim against the Indemnifying Party pursuant to this Agreement.

  - Sub-Contractor Losses

Where:

    - a Sub-Contractor is entitled to claim any compensation and/or relief from the Contractor under the Sub-Contracts; and

    - the Contractor subsequently makes a claim against the Authority under this Agreement in relation to such compensation and/or relief,

the Authority waives any right to defend the Contractor's claim on the ground that the Contractor is only required to pay compensation or grant relief to the Sub-Contractor under the Sub-Contracts to the extent that the same is recoverable from the Authority.

- Insurance

  - Requirement to Maintain

The Contractor shall, [in relation to a Facility,] for the period [from the Commencement Date/Start on Site Date] up to the Services Availability Date [at that Facility], take out and maintain or procure the maintenance of the insurances described in Part 1 of Schedule 14 (Insurances) and any other insurances as may be required by law. These insurances must be effective in each case not later than the date on which the relevant risk commences.

  - The Contractor shall [in relation to each Facility] during the Services Period take out and maintain or procure the maintenance of the insurances described in Part 2 of Schedule 14 (Insurances) and any other insurances as may be required by law.

  - Obligation on Parties

Neither party to this Agreement shall take any action or fail to take any reasonable action, or (insofar as it is reasonably within its power) permit anything to occur in relation to it, which would entitle any insurer to refuse to pay any claim under any insurance policy in which that party is an insured, a co-insured or an additional insured person.

  - Nature of the Insurances

With the exception of any insurances required by law, the insurances referred to in clauses 61.1 and 61.2 (Requirement to Maintain) shall:

    - name the Contractor as co-insured with any other party maintaining the insurance as required by Part 1 and Part 2 of Schedule 14 (Insurances);

    - provide for non-vitiation protection in respect of any claim made by the Authority as co-insured in accordance with Endorsement 2 in Part 3 of Schedule 14 (Insurances);

    - contain a clause waiving the insurers' subrogation rights against the Authority, its employees and agents in accordance with Endorsement 2 in Part 3 of Schedule 14 (Insurances);

    - provide for [twenty (20)] Business Days' prior written notice of their cancellation, non-renewal or amendment to be given to the Authority in accordance with Endorsement 1 in Part 3 of Schedule 14 (Insurances); and

    - in respect of the Physical Damage Policies provide for payment of any proceeds received by the Contractor  to be applied in accordance with clause 62 (Reinstatement and Change of Requirement after Insured Event).

  - The Contractor shall ensure that the insurances referred to in clauses 61.1 and 61.2 (Requirement to Maintain) shall name the Authority as a co-insured for its separate interest as required by Part 1 and Part 2 of Schedule 14 (Insurances).

  - Evidence of Policies

The Contractor shall provide to the Authority:

    - copies on request of all insurance policies referred to in clauses 61.1 and 61.2 (Requirement to Maintain) (together with any other information reasonably requested by the Authority relating to such insurance policies) and the Authority shall be entitled to inspect them during ordinary business hours; and

    - evidence that the premiums payable under all insurance policies have been paid and that the insurances are in full force and effect in accordance with the requirements of this clause 61 (Insurance) and Schedule 14 (Insurance).

  - Renewal Certificates

Renewal certificates in relation to any of the insurances required by clauses 61.1 and 61.2 (Requirement to Maintain) shall be obtained by the Contractor as and when necessary and copies (certified in a manner acceptable to the Authority) shall be forwarded by the Contractor to the Authority as soon as possible but in any event on or before the renewal date.

  - Breach

If the Contractor is in breach of clauses 61.1 and 61.2 (Requirement to Maintain), the Authority may pay any premiums required to keep such insurance in force or itself procure such insurance and may, in either case, recover such amounts from the Contractor on written demand.

  - Notification of Claims

The Contractor shall give the Authority notification within ten (10) Business Days after any claim in excess of [twenty thousand pounds (£20,000)] (Indexed) on any of the Required Insurances or which, but for the application of the applicable insurance policy excess, would be made on any of the Required Insurances and (if required by the Authority) give full details of the incident giving rise to the claim.

  - Limit of Liability

Neither failure to comply nor full compliance with the insurance provisions of this Agreement shall limit or relieve the Contractor of its other liabilities and obligations under this Agreement.

  - Premia

Save where expressly set out in this Agreement, the insurance premia for the Required Insurances and the amount of any loss that would otherwise be recoverable under any of the Required Insurances but for the applicable uninsured deductible and limit of indemnity in respect of such insurance shall at all times be the responsibility of the Contractor.

  - Authority Approval

The Required Insurances shall be effected with insurers approved by the Authority, such approval not to be unreasonably withheld or delayed.

  - Professional Indemnity Insurance

In addition to the Required Insurances, the Contractor undertakes to procure that the Building Contractor, its Principal Building Sub-Contractor(s) and members of the Professional Team take out and maintain in force professional indemnity insurance (PI Insurance), provided that such insurance is generally available in the market to members of the relevant party's profession at commercially reasonable rates and provided further that payment of any increased or additional premiums required by insurers by reason of the relevant party's  own claims record or other acts, omissions, matters or things peculiar to the relevant party will be deemed to be within the reasonable rates and, where such insurance is effected, and to:

    - provide evidence satisfactory to the Authority (as and when reasonably required by the Authority) of the PI Insurance being in full force and effect from the date of this Agreement until the date twelve (12) years from and including the completion of all the Works (such evidence to include details of the cover) including confirmation of territorial limits, levels of excess, insurers, policy number and indemnity limit equivalent to the amount and on the basis set out as being required in the applicable Collateral Warranty;

    - provide the Authority with copies of all notices under the PI Insurance relative to the Project;

    - provide the Authority with notice of:

      - any cancellation of the PI Insurance not less than twenty (20) Business Days prior to the relevant cancellation date unless such shorter period applies under the relevant policy;

      - any adverse material changes to or suspension of cover relevant to the Project not less than twenty (20) Business Days prior to the relevant change or suspension unless such shorter period applies under the relevant policy;

      - any event of which it becomes aware which may vitiate the PI Insurance;

      - any act, omission or event which may adversely affect the terms and scope of the PI Insurance relevant to the Project or invalidate or render it unenforceable;

    - inform the Authority as soon as reasonably practicable of any claim under the PI Insurance in respect of the Project of in excess of [one million pounds (£1,000,000)], provide such information to the Authority as the Authority may reasonably require in relation to such claim and provide notice of any potential breach of the aggregate limit;

    - disclose to the relevant insurers:

      - any matters which could reasonably be expected to be material in the context of the Project; and

      - any of the other insurances required to be maintained under this clause 61 (Insurance);

    - include the interests (if any) of the Authority in any claim or circumstances notified under the PI Insurance relevant to the Project and provide a copy of such notification to the Authority.

  - Claims

The Contractor shall where it is obliged to effect insurance under this clause 61 not bring any claim or action against the Authority (or any Authority Related Party) in respect of any loss or damage in circumstances where the Contractor is able to recover such loss or damage under such insurance (or where it would have been able to recover such loss had it been complying with its obligations under this Agreement) provided that, to avoid doubt, this clause 61.14 shall not by itself prevent the Contractor from claiming against the Authority (or any Authority Related Party) for any loss or damage not covered because of the level of deductibles under such insurance permitted by this Agreement or to the extent such loss or damage exceeds the maximum level of such insurance required by this Agreement.

  - Insurance Review Procedure

    - This procedure shall be used to determine whether the Authority shall bear any increase or benefit from any decrease in Relevant Insurance costs.

    - The Contractor's insurance broker shall prepare a report on behalf of both the Contractor and the Authority (the Joint Insurance Cost Report). The Joint Insurance Cost Report is to be prepared at the Contractor's expense and should, as a minimum, contain the following information for the relevant Insurance Review Period:

      - a full breakdown of the Actual Relevant Insurance Cost;

      - a full breakdown of the Base Relevant Insurance Cost;

      - a spreadsheet (the Insurance Summary Sheet) detailing separately:

        - the sum(s) insured/limit of indemnity (i.e. rateable factor) for each of the Relevant Insurances;

        - the premium rate for each of the Relevant Insurances;

        - the net premium paid (or to be paid) for each of the Relevant Insurances (i.e. excluding both insurance premium tax and brokers fees and commissions);

        - the deductible(s) for each Relevant Insurance;

        - details of any claims (paid or reserved) (including incident date, type and quantum) in excess of [ (£[  ])];

      - an assessment and quantification of each Project Insurance Change together with reasons thereof;

      - full details of any Portfolio Cost Savings;

      - any other reasons that the Contractor believes may have caused a change (by way of increase or decrease relative to the Base Relevant Insurance Cost) in the Actual Relevant Insurance Cost;

      - the opinion of the Contractor's insurance broker as to the reasons why the Actual Relevant Insurance Cost has varied from the Base Relevant Insurance Cost, specifying the impact of each of the factors and quantifying the amount attributable to each factor specified above;

      - the calculation of the Insurance Cost Differential and any Exceptional Cost or Exceptional Saving arising from this calculation;

      - evidence satisfactory to the Authority (acting reasonably) of any changes to circumstances generally prevailing in the Relevant Insurance Market that are claimed to account for the Insurance Cost Differential; and

      - details of movements from a recognised index, plus, if available from other appropriate sources, details of changes in insurance cost across the PFI/PF2 market as a whole and/or the PPP market as a whole.

    - The Contractor shall procure that its insurance broker no later than the date which is ten (10) Business Days after the Insurance Review Date, delivers to the Authority at the same time as it delivers to the Contractor at least two copies of the Joint Insurance Cost Report. Following receipt of the Joint Insurance Cost Report the Authority shall notify the Contractor in writing within fifteen (15) Business Days whether or not it accepts the Joint Insurance Cost Report including full details of any disagreement. If the Authority does not provide such notification and/or details of any disagreement to the Contractor within fifteen (15) Business Days, the Authority shall be deemed to have accepted the Joint Insurance Cost Report. If the Authority disagrees with any item in the Joint Insurance Cost Report, the parties shall use their respective reasonable endeavours acting in good faith to agree the contents of the Joint Insurance Cost Report. If the parties fail to agree the contents of the Joint Insurance Cost Report within thirty five (35) Business Days from the date it was delivered to the Authority, the matter shall be resolved pursuant to clause 64 (Dispute Resolution) provided always that references in clause 64.4 (Identity of Adjudicator) to an expert shall be construed as references to an independent insurance expert agreed by the parties or, in the absence of agreement, appointed by the President for the time being of the Chartered Institute of Arbitrators.

    - The Authority may make the Joint Insurance Cost Report available to any of its or HM Treasury's agents or any other Relevant Authority's agents or advisors or other body or bodies nominated by HM Treasury for insurance cost verification, benchmarking or similar purpose.

  - Exceptional Cost and Exceptional Saving

    - If, following the completion of the Insurance Review Procedure, it is agreed or determined that there is an Exceptional Cost, the Authority shall within thirty (30) days of completion of the Insurance Review Procedure make a one-off lump-sum payment to the Contractor equal to eighty five percent (85%) of the Exceptional Cost.

    - If, following the completion of the Insurance Review Procedure, it is agreed or determined that there is an Exceptional Saving, the Contractor shall, where the Annual Payment is a Deficit Annual Payment, within thirty (30) days of completion of the Insurance Review Procedure make a one-off lump-sum payment to the Authority equal to eighty five percent (85%) of the Exceptional Saving provided that to the extent such amount is greater than the Deficit Annual Payment ("Insurance Cost Saving Excess") the amount of any Insurance Cost Saving Excess shall not be payable and shall be retained by the Contractor.

    - Following the completion of the Insurance Review Procedure, if it is agreed or determined that there is neither an Exceptional Cost nor an Exceptional Saving, any Insurance Cost Differential shall be borne by or benefit the Contractor.

  - Insurance Cost Index

If at any time an Insurance Cost Index is published and intended for use in PFI/PF2 or contracts of a similar nature to this Agreement, the parties shall meet with a view to agreeing (a) its application to the Project, taking into account any relevant guidance issued by HM Treasury and (b) how a Portfolio Cost Saving may be accounted for when the index is in use.

  - Broker's Letter of Undertaking

    - On the date of this Agreement and within thirty (30) days following each renewal of Required Insurances, the Contractor shall deliver to the Authority a broker's letter of undertaking signed by the insurance broker to the Contractor in the Agreed Form as set out in Part 4 of Schedule 14 (Broker's Letter of Undertaking).

    - The Contractor shall procure that any broker(s) appointed during the currency of this Agreement shall:

      - owe the Authority such obligations and give to the Authority such warranties as are substantially the same as those set out in Part 4 of Schedule 14 (Broker's Letter of Undertaking) and in this clause 61; and

      - enter into an agreement in substantially the same form as that set out in Part 4 of Schedule 14 (Broker's Letter of Undertaking).

- Reinstatement and Change of Requirement after Insured Event

  - All insurance proceeds received under any policy referred to in paragraph 1 of Part 1 and paragraph 1 of Part 2 of Schedule 14 (Insurances) (the Physical Damage Policies) shall be applied to repair, reinstate and/or replace each part or parts of the assets in respect of which such proceeds were received.

  - Joint Account

The Contractor shall set up and at all times maintain an account in the joint names of the Authority and the Contractor (the Joint Insurance Account). All insurance proceeds paid under any Physical Damage Policy in respect of a single event (or a series of related events) in an amount in excess of £[minimum level] (Indexed) shall be paid into the Joint Insurance Account.

  - Obligations

Where a claim is made or proceeds of insurance are received or are receivable under any Physical Damage Policy in respect of a single event (or a series of related events) [in respect of that Facility] (the Relevant Incident) in an amount in excess of £[     ] (Indexed):

    - the Contractor shall deliver to the Authority as soon as practicable and in any event within twenty (20) Business Days after the making of the claim a plan prepared by the Contractor for the carrying out of the works necessary (the Reinstatement Works) to repair, reinstate or replace (the Reinstatement Outline) the Facility/Facilities which is or are the subject of the relevant claim or claims in accordance with this clause 62.3. The Reinstatement Outline shall set out:

      - if not the Building Contractor, the identity of the person proposed to effect the Reinstatement Works, which shall be subject to the prior written approval of the Authority; and

      - the proposed terms and timetable upon which the Reinstatement Works are to be effected (including the date that the Project will become fully operational), the final terms of which shall be subject to the prior written approval of the Authority (such approval not to be unreasonably withheld or delayed).

    - the Authority shall within ten (10) Business Days of receipt of the Reinstatement Outline notify the Contractor in writing that:

      - it is satisfied that the Reinstatement Outline will enable the Contractor to comply with its obligations to carry out the Reinstatement Works within a reasonable timetable, and that the identity of any person (set out in the Reinstatement Outline) that may be appointed to effect the Reinstatement Works is approved;

      - the identity of any person (set out in the Reinstatement Outline) that may be appointed to effect the Reinstatement Works is not approved together with its reasons for such non-approval in sufficient detail so as to enable the Contractor to understand the nature and extent of such non-approval and to assess whether the Authority's approval under clause 62.3.1.1 (Obligations) has been unreasonably withheld;

      - the Authority does not approve the Reinstatement Outline together with its reasons for such non-approval, in sufficient details so as to enable the Contractor to understand the nature and extent of such non-approval and to assess whether the Authority's approval under clause 62.3.1.2 (Obligations) has been unreasonably withheld; or

      - if the Authority does not make one (1) of the said responses within the period specified in clause 62.3.2 (Obligations) it shall be deemed to have approved the Reinstatement Outline, save where the Authority has reasonably requested any further information from the Contractor, in which case the time limit outlined in clause 62.3.2 (Obligations) will be deemed to commence upon receipt of such information by the Authority.

    - If the Authority gives notice of non-approval in accordance with clauses 62.3.2.2 or 62.3.2.3 the Contractor may amend and re-submit the Reinstatement Outline (the Amended Reinstatement Outline) to the Authority for its reconsideration and the Authority shall give its approval or non-approval within five (5) Business Days of the submission of the Amended Reinstatement Outline to the Authority. If the Authority does not approve the Amended Reinstatement Outline, it shall provide reasons for such non-approval in sufficient detail so as to enable the Contractor to understand the nature and extent of such non-approval and to assess whether the Authority's approval has been unreasonably withheld.

    - In the event that the Amended Reinstatement Outline or a person proposed to carry out the Reinstatement Works pursuant to the Amended Reinstatement Outline is not approved by the Authority in accordance with clause 62.3.3 the Contractor may submit the Amended Reinstatement Outline to the Dispute Resolution Procedure in order for it to be determined whether the Authority's approval under clause 62.3.3 (Obligations) was unreasonably withheld.

    - The Reinstatement Outline or the Amended Reinstatement Outline (as the case may be) as approved by the Authority pursuant to this clause 62 (Reinstatement and Change of Requirement after Insured Event) or as determined pursuant to the Dispute Resolution Procedure shall become the reinstatement plan (the Reinstatement Plan).

    - The Contractor shall effect the Reinstatement Works in accordance with the Reinstatement Plan, and:

      - shall enter into contractual arrangements to effect the Reinstatement Works with the person(s) identified in the Reinstatement Plan;

      - prior to the earlier to occur of the Termination Date or the Expiry Date, any amounts standing to the credit of the Joint Insurance Account (the Relevant Proceeds) (together with any interest accrued) may be withdrawn by the Contractor from the Joint Insurance Account as required to enable it to make payments in accordance with the terms of the contractual arrangements entered into to effect the Reinstatement Works and to meet any other reasonable costs and expenses of the Contractor for the sole purposes of funding the Reinstatement Works and the parties shall operate the signatory requirements of the Joint Insurance Account to give effect to such payments. Following the earlier to occur of the Termination Date and the Expiry Date, the Authority may withdraw amounts standing to the credit of the Joint Insurance Account for the purposes of funding any Reinstatement Works;

      - the Authority agrees and undertakes that, subject to compliance by the Contractor with its obligations under this clause 62 (Reinstatement and Change of Requirement after Insured Event), and provided that the Contractor procures that the Reinstatement Works are carried out and completed in accordance with this clause 62.3 it shall not exercise any right which it might otherwise have to terminate this Agreement by virtue of the event which gave rise to the claim for the Relevant Proceeds;

      - the Authority undertakes to use reasonable endeavours to assist the Contractor in the carrying out of the Reinstatement Plan;

      - after the Reinstatement Plan has been implemented to the reasonable satisfaction of the Authority and in accordance with this clause 62.3 the Authority shall permit withdrawal by the Contractor of any Relevant Proceeds then held in the Joint Insurance Account that have not been paid under this clause 62.3 in respect of the Relevant Incident, together with any interest accrued; and

      - subject to clause 60 (Indemnities, Guarantees and Contractual Claims), the Contractor shall be solely responsible for the payment of any deficiency.

  - Works Carried Out

Where insurance proceeds are to be used in accordance with this Agreement to repair, reinstate or replace any part of the [Facility/Facilities], the Contractor shall carry out the work in accordance with the Authority's Requirements and the Contractor's Proposals so that on completion of the work the provisions of this Agreement are complied with.

- Risks that Become Uninsurable

  - Uninsurable Risks

Nothing in clause 61 (Insurance) or this clause 63 (Risks that Become Uninsurable) shall oblige the Contractor to take out insurance in respect of a risk which is Uninsurable save where the predominant cause of the risk being Uninsurable is an act or omission of the Contractor or a Contractor Related Party.

  - Risks Become Uninsurable

If a risk usually covered by contractor's "all risks", property damage, third party liability, business interruption (but excluding loss of profits) or delay in start up (but excluding loss of profits) or statutory insurances, in each case required under this Agreement, becomes Uninsurable then:

    - the Contractor shall notify the Authority within five (5) Business Days of the risk becoming Uninsurable; and

    - if both parties agree, or it is determined in accordance with the Dispute Resolution Procedure, that the risk is Uninsurable and that:

      - the risk being Uninsurable is not caused by the actions, breaches, omissions or defaults of the Contractor or a sub-contractor; and

      - the Contractor has demonstrated to the Authority that the Contractor and a prudent board of directors of a company operating the same or substantially similar businesses in the United Kingdom to that operated by the Contractor would in similar circumstances (in the absence of the type of relief envisaged by this clause 63) be acting reasonably and in the best interests of the company if they resolved to cease to operate such businesses as a result of that risk becoming Uninsurable, taking into account inter alia (and without limitation) the likelihood of the Uninsurable risk occurring (if it has not already occurred), the financial consequences for such company if such Uninsurable risk did occur (or has occurred) and other mitigants against such consequences which may be available to such company,

then the parties shall meet to discuss the means by which the risk should be managed or shared (including considering the issue of self-insurance by either party).

  - Consequences

    - If the requirements of clause 63.2 (Risks that Become Uninsurable) are satisfied, but the parties cannot agree as to how to manage or share the risk, then:

      - in respect of such third party liability insurance only, the Authority shall (at the Authority's option) either pay to the Contractor an amount equal to the amount set out in clause 49 (Compensation on Termination for Force Majeure) and this Agreement will terminate or elect to allow this Agreement to continue and clause 63.3.1.2 (Consequences) shall thereafter apply in respect of such risk;

      - in respect of such contractor's "all risks" insurance, property damage insurance, third party liability insurance (if the Authority elects to allow the Agreement to continue in accordance with clause 63.3.1.1) business interruption (but not loss of profits), delay in start up (but not loss of profits) or statutory insurances this Agreement shall continue and on the occurrence of the risk (but only for as long as such risk remains Uninsurable) the Authority shall (at the Authority's option) either pay to the Contractor an amount equal to insurance proceeds that would have been payable had the relevant insurance continued to be available and this Agreement will continue, or an amount equal to the amount calculated in accordance with clause 49 (Compensation on Termination for Force Majeure) plus (in relation to third party liability insurance only) the amount of insurance proceeds that would have been payable whereupon this Agreement will terminate;

      - where pursuant to clauses 63.3.1.1 and/or 63.3.1.2 (Consequences) this Agreement continues then the Annual Payment, where it is a Deficit Annual Payment, shall be reduced in each Contract Year for which the relevant insurance is not maintained by an amount equal to the premium paid (or which would have been paid) by the Contractor in respect of the relevant risk in the Contract Year prior to it becoming Uninsurable (Indexed) from the date that the risk became Uninsurable provided that where in applying such amount the Deficit Annual Payment is reduced to zero or would after such payment result in a Surplus Annual Payment any such excess amount shall be for the account of the Contractor.

      - where the risk is Uninsurable for part of a Contract Year only the reduction in the Annual Payment (where it is a Deficit Annual Payment) shall be pro rated to the number of months for which the risk was Uninsurable; and

      - where pursuant to clauses 63.3.1.1 and/or 63.3.1.2 (Consequences) this Agreement continues the Contractor shall approach the insurance market at least every four months to establish whether the risk remains Uninsurable. As soon as the Contractor is aware that the risk is no longer Uninsurable, the Contractor shall take out and  maintain and procure the taking out and maintenance of insurance (to be incepted as soon as reasonably practicable) for such risk in accordance with this Agreement.

    - If, pursuant to clause 63.3.1.2 (Consequences), the Authority elects to make payment to the Contractor (such that the Agreement will terminate) (the Relevant Payment) the Contractor shall have the option (exercisable within twenty (20) Business Days of the date of such election by the Authority (the Option Period)) to pay to the Authority on or before the end of the Option Period, an amount equal to the insurance proceeds that would have been payable had the risk not become Uninsurable, in which case this Agreement will continue (and the Relevant Payment will not be made by the Authority), and the Contractor's payment shall be applied for the same purpose and in the same manner as insurance proceeds would have been applied had the relevant risk not become Uninsurable.

  - Increase in Insured Amounts

The limit of indemnity and the maximum deductibles for each of the Required Insurances shall be Indexed, provided such limits of indemnity and maximum deductibles shall only be increased on each renewal date such that the limit that is Indexed becomes equal to or exceeds the next whole insurable amount or deductible (as the case may be) available in the insurance market.

  - Unavailability of Terms or Conditions

    - If, upon the renewal of any insurance which the Contractor is required to maintain or to procure the maintenance of pursuant to this Agreement:

      - any Insurance Term is not available to the Contractor in the worldwide insurance market with reputable insurers of good standing; and/or

      - the insurance premium payable for insurance incorporating such Insurance Term is such that the Insurance Term is not generally being incorporated in insurance procured in the worldwide insurance market with reputable insurers of good standing by contractors in the United Kingdom,

(other than, in each case, by reason of one or more actions or omissions of the Contractor and/or any sub-contractors) then clause 63.5.2 (Unavailability of Terms or Conditions) shall apply.

    - If it is agreed or determined that clause 63.5.1 (Unavailability of Terms or Conditions) applies then the Authority shall waive the Contractor's obligations in clause 61 (Insurances) and/or Schedule 14 (Insurances) in respect of that particular Insurance Term and the Contractor shall not be considered in breach of its obligations regarding the maintenance of insurance pursuant to this Agreement as a result of the failure to maintain insurance incorporating such Insurance Term for so long as the relevant circumstances described in clause 63.5.1 (Unavailability of Terms or Conditions) continue to apply to such Insurance Term.

    - To the extent that the parties agree (acting reasonably), or it is determined pursuant to the Dispute Resolution Procedure, that an alternative or replacement term and/or condition of insurance is available to the Contractor in the worldwide insurance market with reputable insurers of good standing which if included in the relevant insurance policy would fully or partially address the Contractor's inability to maintain or procure the maintenance of insurance with the relevant Insurance Term, at a cost which contractors in the UK are (at such time) generally prepared to pay, the Contractor shall maintain or procure the maintenance of insurance including such alternative or replacement term and/or condition. Notwithstanding any other provision of this Agreement whatsoever, the costs of such insurance shall be subject to the premium costs sharing mechanism set out at clause 61.15 (Insurance Review Procedure).

    - [Where the Authority has exercised the waiver pursuant to clause 63.5.2 (Unavailability of Terms or Conditions), it shall, where a Deficit Annual Payment applies, be entitled to deduct from the Monthly Payment the Adjusted Amount, such amount being an amount equal to one twelfth the amount paid for the particular Insurance Term in the preceding Contract Year (using a reasonable estimate of such amount where a precise figure is not available) less any annual amount paid or payable by the Contractor to maintain and/or procure the maintenance of any (whether full or partial) alternative or replacement insurance in respect of such term or condition pursuant to clause 63.5.3 (Unavailability of Terms or Conditions).

    - While clause 63.5.1 (Unavailability of Terms or Conditions) applies, the Annual Payment where a Deficit Annual Payment applies shall be reduced each Contract Year by the Adjusted Amount, Indexed from the date that the particular Insurance Term is no longer available.]

    - The Contractor shall notify the Authority as soon as reasonably practicable and in any event within five days of becoming aware that clause 63.5.1.1 and/or 63.5.1.2 (Unavailability of Terms or Conditions) are likely to apply or (on expiry of the relevant insurance then in place) do apply in respect of an Insurance Term (irrespective of the reason for the same). The Contractor shall provide the Authority with such information as the Authority reasonably requests regarding the unavailability of the Insurance Term and the parties shall meet to discuss the means by which such unavailability should be managed as soon as is reasonably practicable.

    - In the event that clause 63.5.1.1 and/or 63.5.1.2 (Unavailability of Terms or Conditions) apply in respect of an Insurance Term (irrespective of the reasons for the same) the Contractor shall approach the insurance market at least every four months to establish whether clause 63.5.1.1 and/or 63.5.1.2 (Unavailability of Terms or Conditions) remain applicable to the Insurance Term. As soon as the Contractor is aware that clause 63.5.1.1 and/or 63.5.1.2 (Unavailability of Terms or Conditions) has ceased to apply to the Insurance Term, the Contractor shall take out and maintain or procure the taking out and maintenance of the  insurance (to be incepted as soon as is reasonably practicable) incorporating such Insurance Term in accordance with this Agreement and any amount of the Annual Payment adjusted pursuant to clause 63.5.4 or 63.5.5 (Unavailability of Terms and Conditions) shall cease to apply.

- Dispute Resolution

  - Disputes

Any dispute arising in relation to any aspect of this Agreement shall be resolved in accordance with this clause 64.

  - Consultation

If a dispute arises in relation to any aspect of this Agreement, the Contractor and the Authority shall consult in good faith in an attempt to come to an agreement in relation to the disputed matter and, if necessary, shall escalate the dispute for discussion between senior colleagues at the Authority and Contractor.

  - Adjudication

Without prejudice to clause 64.2 (Consultation), either party may give the other notice of its intention to refer the dispute to adjudication (the Notice of Adjudication). The Notice of Adjudication shall include a brief statement of the issue to be referred and the redress sought. The party giving the Notice of Adjudication (the Referring Party) shall on the same day and by the same means of communication send a copy of the Notice of Adjudication to an adjudicator selected in accordance with clause 64.4 (Identity of Adjudicator).

  - Identity of Adjudicator

The Adjudicator nominated to consider a dispute referred to him shall be selected on a strictly rotational basis from the relevant panel of experts selected in accordance with the following:

    - there shall be two (2) panels of experts, one (1) in respect of construction matters (the Construction Panel) and one (1) in respect of operational and maintenance matters (the Operational Panel). All the experts on each panel shall be wholly independent of the Contractor, the Authority, the relevant Sub-Contractor and any of the major competitors of the Contractor or relevant Sub-Contractor;

    - the Construction Panel shall be comprised of three (3) experts who shall be selected jointly by the Contractor and the Authority. Such selection shall take place within twenty (20) Business Days of the Commencement Date or otherwise as agreed between the parties;

    - the Operational Panel shall be comprised of three (3) experts who shall be selected jointly by the Contractor and the Authority. Such selection shall take place within twenty (20) Business Days of the Commencement Date or otherwise as agreed between the parties;

    - if any member of a panel resigns during the Contract Period, a replacement expert shall be selected by the Contractor and the Authority as soon as practicable;

    - in the event that the nominated Adjudicator is unable or unwilling to confirm acceptance of his appointment as Adjudicator within two (2) Business Days of receipt of the Notice of Adjudication, then the Referring Party shall invite the person next in line to act as the Adjudicator. In the event that the second panel member is unwilling or unable to confirm acceptance of his appointment as Adjudicator within two (2) days or if the parties disagree as to the relevant panel of experts to be used then the Referring Party may apply to the President for the time being of the Chartered Institute of Arbitrators who shall within three (3) Business Days of any such application nominate an Adjudicator to determine the issue set out in the Notice of Adjudication; and

    - if the Authority and the Contractor are unable to agree on the identity of the experts to be selected to the panels, the President for the time being of the Chartered Institute of Arbitrators shall appoint such expert(s) within thirty (30) days of any application for such appointment by either party.

  - Referral of the Dispute

Within seven (7) days of the service of the Notice of Adjudication, or as soon thereafter as the Adjudicator is appointed, the Referring Party shall serve its statement of case (the Referral Notice) on the Adjudicator and the other party (the Responding Party). The Referral Notice shall include a copy of this Agreement, details of the circumstances giving rise to the dispute as set out in the Notice of Adjudication, the reasons why the Referring Party is entitled to the redress sought, and the evidence upon which it relies.

  - Response to the Referral

The Responding Party shall serve its statement of case (the Response) on the Adjudicator and the Referring Party within a period of time to be directed by the Adjudicator. The Response shall include any arguments in response to the Referral Notice of the dispute set out in the Notice of Adjudication and any additional evidence on which the Responding Party relies.

  - Procedure

Subject to clause 64.18 (Sub-Contractors' Submissions), the Adjudicator shall have absolute discretion as to how to conduct the adjudication, including whether a meeting is necessary. He shall establish the procedure and timetable subject to any limitation within this Agreement. The parties shall comply with any request or direction of the Adjudicator in relation to the adjudication.

  - Adjudicator's Decision

In any event, the Adjudicator shall provide to both parties his written decision on the dispute, within twenty eight (28) days after the date of receipt of the Referral Notice (or such other period as the parties may agree). The Adjudicator shall be entitled to extend the said period of twenty eight (28) days by up to fourteen (14) days with the consent of the Referring Party. The Adjudicator shall state any reasons for his decision. Unless and until revised, cancelled or varied by the English courts, the Adjudicator's decision shall be binding on both parties who shall forthwith give effect to the decision.

  - Adjudicator's Costs

The Adjudicator's costs of any referral shall be borne as the Adjudicator shall specify or, in default, equally by the parties. Each party shall bear its own costs arising out of the referral, including legal costs and the costs and expenses of any witnesses.

  - Adjudicator as Expert

The Adjudicator shall be deemed not to be an arbitrator but shall render his decision as an expert, and the provisions of the Arbitration Act 1996 and the law relating to arbitration shall not apply to the Adjudicator or his determination or the procedure by which he reached his determination.

  - Adjudicator's Powers

The Adjudicator shall act fairly and impartially and may take the initiative in ascertaining the facts and the law. The Adjudicator shall have the power to open up, review and revise any opinion, certificate, instruction, determination or decision of whatever nature given or made under this Agreement.

  - Confidentiality

All information, data or documentation disclosed or delivered by a party to the Adjudicator in consequence of or in connection with his appointment as Adjudicator shall be treated as confidential. The Adjudicator shall not, save as permitted by clause 59 (Freedom of Information and Confidentiality), disclose to any person or company any such information, data or documentation and all such information, data or documentation shall remain the property of the party disclosing or delivering the same and all copies shall be returned to such party on completion of the Adjudicator's work.

  - Liability of Adjudicator

The Adjudicator is not liable for anything done or omitted in the discharge or purported discharge of his functions as Adjudicator unless the act or omission is in bad faith. Any employee or agent of the Adjudicator is similarly protected from liability.

  - Reference to the Courts

Either party may (within ninety (90) calendar days of receipt of the Adjudicator's decision or where the Adjudicator fails to give a decision pursuant to clause 64.8 (Adjudicator's Decision)) give notice to the other party of its intention to refer the dispute to the courts of England and Wales for final determination.

  - Parties' Obligations

The parties shall continue to comply with, observe and perform all their obligations hereunder regardless of the nature of the dispute and notwithstanding the referral of the dispute for resolution under this clause 64 and shall give effect forthwith to every decision of the Adjudicator and the courts delivered under this clause 64.

  - Similar Disputes

If any dispute arising under this Agreement raises issues which relate to:

    - any dispute between the Contractor and the Building Contractor arising under the Building Contract or otherwise affects the relationship or rights of the Contractor and/or the Building Contractor under the Building Contract (the Building Contract Dispute); or

    - any dispute between the Contractor and the FM Contractor arising under the FM Agreement or otherwise affects the relationship or rights of the Contractor and/or the FM Contractor under the FM Agreement (the FM Agreement Dispute); or

    - any dispute between the Contractor and the Leisure Operator arising under the Leisure Contract or otherwise affects the relationship or rights of the Contractor and/or the Leisure Operator under the Leisure Contract (the Leisure Contract Dispute),

then the Contractor may include as part of its submissions made to the Adjudicator or to the courts submissions made by the Building Contractor or by the FM Contractor or by the Leisure Operator as appropriate.

  - Jurisdiction over Sub-Contractors

The Adjudicator shall not have jurisdiction to determine the Building Contract Dispute, the Leisure Contract Dispute or the FM Agreement Dispute but the decision of the Adjudicator and/or the courts shall, subject to clause 64.14 (Reference to the Courts), be binding on the Contractor and the Building Contractor insofar as it determines the issues relating to the Building Contract Dispute, on the Contractor and the Leisure Operator insofar as it determines the issues relating to the Leisure Contract Dispute and on the Contractor and the FM Contractor insofar as it determines the issues relating to the FM Agreement Dispute.

  - Sub-Contractors' Submissions

Any submissions made by the Building Contractor, the Leisure Operator or the FM Contractor shall:

    - be made within the time limits applicable to the delivery of submissions by the Contractor; and

    - concern only those matters which relate to the dispute between the Authority and the Contractor under this Agreement.

  - Costs

Where the Building Contractor, the Leisure Operator or the FM Contractor makes submissions in any reference before:

    - the Adjudicator, the Adjudicator's costs of such reference shall be borne as the Adjudicator shall specify, or in default, one-third by the Authority and two-thirds (2/3) by the Contractor; and

    - the courts, the costs of the litigation shall be in the discretion of the court.

  - Authority's Liability

The Authority shall have no liability to the Building Contractor, the Leisure Operator or the FM Contractor arising out of or in connection with any decision of the Adjudicator or courts or in respect of the costs of the Building Contractor, the Leisure Operator or the FM Contractor in participating in the resolution of any dispute under this Agreement.

  - Access to Documents

The Contractor shall not allow the Building Contractor, the Leisure Operator or the FM Contractor access to any document relevant to issues in dispute between the Authority and the Contractor save where:

    - the document is relevant also to the issues relating to the Building Contract Dispute, the Leisure Contract Dispute or the FM Agreement Dispute as the case may be; and

    - the Contractor has first delivered to the Authority a written undertaking from the Building Contractor and/or the Leisure Operator and/or the FM Contractor (as appropriate) addressed to the Authority that they shall not use any such document otherwise than for the purpose of the dispute resolution proceedings under this Agreement and that they shall not disclose such documents or any information contained therein to any third party other than the Adjudicator or the courts or any professional adviser engaged by the Building Contractor, the Leisure Operator or the FM Contractor (as appropriate) to advise in connection with the dispute.

- Ordering of Goods and Services

Neither party shall place or cause to be placed any orders with suppliers or otherwise incur liabilities in the name of the other party or any representative of the other party.

- Intellectual Property

  - Project Data

The Contractor shall make available to the Authority free of charge (and hereby irrevocably licences the Authority to use) all Project Data that might reasonably be required by the Authority and the Contractor shall ensure that it obtains all necessary licences, permissions and consents to ensure that it can make the Project Data available to the Authority on these terms, for the purposes of:

    - the Authority providing the [Facility/Facilities] for leisure and ancillary purposes, its duties under this Agreement and/or any statutory duties which the Authority may have; and

    - following termination of this Agreement, the design or construction of the [Facility/Facilities], the operation, maintenance or improvement of the [Facility/Facilities] and/or the provision of works and/or services the same as or similar to the Works and/or Services,

(together, the Approved Purposes), and in this clause use shall include the acts of copying, modifying, adapting and translating the material in question and/or incorporating them with other materials and the term "the right to use" shall be construed accordingly.

  - Licence in respect of Intellectual Property Rights

The Contractor:

    - hereby grants to the Authority, free of charge, an irrevocable, non-exclusive and transferable (but only to any assignee or transferee of any rights or benefits under this Agreement or upon or at any time following termination of this Agreement) licence (carrying the right to grant sub-licences) to use the Intellectual Property Rights which are or become vested in the Contractor; and

    - shall, where any Intellectual Property Rights are or become vested in a third party, use all reasonable endeavours to procure the grant of a like licence to that referred to in clause 66.2.1 to the Authority,

in both cases, solely for the Approved Purposes.

  - Vesting of Intellectual Property Rights

The Contractor shall use all reasonable endeavours to ensure that any Intellectual Property Rights created, brought into existence or acquired during the term of this Agreement vest, and remain vested throughout the term of this Agreement, in the Contractor and the Contractor shall enter into appropriate agreements with any Contractor Related Party (or other third parties) that may create or bring into existence, or from which it may acquire, any Intellectual Property Rights.

  - Maintenance of data

To the extent that any of the data, materials and documents referred to in this clause are generated by or maintained on a computer or similar system, the Contractor shall:

    - use all reasonable endeavours to procure for the benefit of the Authority, at no charge or at the lowest reasonable fee, the grant of a licence or sub-licence for any relevant software to enable the Authority or its nominee to access and otherwise use (subject to the payment by the Authority of the relevant fee, if any) such data for the Approved Purposes. As an alternative, the Contractor may provide such data, materials or documents in a format which may be read by software generally available in the market at the relevant time or in hard copy format; and

    - enter into the National Computing Centre's then current multi-licence escrow deposit agreement or standard single licence escrow deposit agreement as appropriate in each case.

  - The Contractor shall ensure the back up and storage in safe custody of the data, materials and documents referred to in clause 66.4 in accordance with Good Industry Practice. Without prejudice to this obligation, the Contractor shall submit to the Authority's Representative for approval its proposals for the back up and storage in safe custody of such data, materials and documents and the Authority shall be entitled to object if the same is not in accordance with Good Industry Practice. The Contractor shall comply, and shall cause all Contractor Related Parties to comply, with all procedures to which the Authority's Representative has given its approval. The Contractor may vary its procedures for such back-up and storage subject to submitting its proposals for change to the Authority's Representative, who shall be entitled to object on the basis set out above.

  - Indemnity

    - Where a claim or proceeding is made or brought against the Authority which arises out of the infringement of any Intellectual Property Rights or because the use of any materials, plant, machinery or equipment in connection with the Works or the Project infringes any Intellectual Property Rights of a third party then, unless such infringement has arisen out of the use of any Intellectual Property by or on behalf of the Authority otherwise than in accordance with the terms of this Agreement, the Contractor shall indemnify the Authority at all times from and against all Direct Losses and Indirect Losses arising as a result of such claims and proceedings and the provisions of clause 60 (Indemnities, Guarantees and Contractual Claims) shall apply.

    - Where a claim or proceeding is made or brought against the Contractor which arises out of the infringement of any Intellectual Property Rights or because the use of any materials, plant, machinery or equipment in connection with the Works or the Project infringes any rights in or to any Intellectual Property Rights of a third party then, if such infringement has arisen out of the use of any Intellectual Property Rights by or on behalf of the Authority otherwise than in accordance with the terms of this Agreement and otherwise than as a result of a breach of this clause 66 by the Contractor then the Authority shall indemnify the Contractor at all times from and against all Direct Losses and Indirect Losses arising as a result of such claims and proceedings.

  - Licence to Contractor

The Authority hereby grants to the Contractor a non-transferable, non-exclusive, royalty free licence (carrying the right to grant sub-licences) to use for the duration of this Agreement only and only for purposes directly relating to the Project any Intellectual Property Rights relating to the Project which are or become vested in the Authority.

  - Intellectual Property Rights on expiry or termination of this Agreement

The rights referred to in clause 66.1 (Project Data) and clause 66.2 (Licence in respect of Intellectual Property Rights) shall not apply to the Contractor IPR upon or following termination or expiry of this Agreement provided that where a replacement item (for any item (or any Intellectual Property Rights in any item comprised in Contractor IPR)) is necessary for the operation and/or maintenance of the [Facility/Facilities] by the Authority and/or any New Contractor and is not available to the Authority and/or any New Contractor on reasonable commercial terms following such expiry or termination from any third party, then the Contractor may grant to the Authority, an irrevocable, non-exclusive and transferable licence (carrying the right to grant sub-licences) to use the relevant elements of such Contractor IPR for the Approved Purposes on reasonable commercial terms and rates.

- Assignment and Sub-Contracting

  - Restrictions on Transfer of this Agreement by the Authority

The rights and obligations of the Authority under this Agreement shall not be assigned, novated or otherwise transferred (whether by virtue of any Legislation or any scheme pursuant to any Legislation or otherwise) to any person other than to any public body (being a single entity) acquiring the whole of the Agreement and having the legal capacity, power and authority to become a party to and to perform the obligations of the Authority under this Agreement being:

    - a Minister of the Crown pursuant to an Order under the Ministers of the Crown Act 1975;

    - any Local Authority which has sufficient financial standing or financial resources to perform the obligations of the Authority under this Agreement; or

    - any other public body whose obligations under this Agreement are unconditionally and irrevocably guaranteed (in a form reasonably acceptable to the Contractor) by the Authority or a Minister of the Crown having the legal capacity, power and authority to perform the obligations under the guarantee and the obligations of the Authority under this Agreement.

  - Restriction on the Contractor

Subject to clause 67.3 (Exception), the Contractor shall not sub-contract, assign, underlet, charge, sell, bargain or otherwise deal in any way with the benefit of this Agreement in whole or in part except with the prior written consent of the Authority.

  - Exception

    - Nothing in this Agreement shall prohibit the Contractor from providing or procuring the provision of the Works or the Services from a Sub-Contractor having the legal capacity, power and authority to become a party to and perform the obligations of the relevant Sub-Contract and employing persons having the appropriate qualifications, experience and technical competence and having the resources available to it which are sufficient to enable it to perform the obligations of the Sub-Contractor under the relevant Sub-Contract provided that:

      - such Sub-Contractor's identity has been notified to the Authority and the Authority has approved it in writing;

      - the Contractor has complied with its obligations under clause 4.1 (Collateral Warranties [and Surveys][and Guarantees]);

      - if required by the Authority, such Sub-Contractor's terms of Sub-Contract have been notified to the Authority by the Contractor and the Authority has approved them in writing;

      - if required by the Authority, the Contractor provides the Authority with a certified copy of the Sub-Contract within ten (10) Business Days of the Sub-Contract being completed;

      - if required by the Authority, the Contractor procures a parent company guarantee or bond from the Sub-Contractor; and

      - the Contractor shall remain primarily and directly liable for the Contractor's obligations under this Agreement.

    - By entering into this Agreement, the Authority approves the appointment of the [Building Contractor, Leisure Operator and FM Contractor] under the [Building Contract, Leisure Contract and FM Agreement] in the Agreed Form, provided that the Contractor complies with its obligations under clause 4.1 (Collateral Warranties [and Surveys][and Guarantees]) and the Contractor shall remain primarily and directly liable for the Contractor's obligations under this Agreement.

  - Contractor's Obligations

The Contractor shall perform its obligations under and observe all the terms of any Sub-Contract with a Sub-Contractor.

  - Sub-Contractors

Nothing in this Agreement shall prohibit or prevent any Sub-Contractor employed by the Contractor from being employed by the Authority at any establishments of the Authority.

  - Replacement of Sub-Contractors

The rights set out in clause 67.6.1 (Replacement of Sub-Contractors) may be exercised on no more than two (2) occasions during the Contract Period and during the same period the rights set out in clause 67.6.3 (Replacement of Sub-Contractors) may be exercised no more than once.

    - On the substitution or replacement of the defaulting Leisure Operator or FM Contractor or a defaulting sub-contractor to the Leisure Operator or the FM Contractor (in all cases provided that the Contractor is acting in compliance with clause 7.1 (Ancillary Documents), the Contractor may elect that, for the purposes of clause 39.3 (Termination on Contractor Default) only:

      - any accrued Performance Adjustment Points and/or Performance Adjustments; and/or

      - any warning notices or Final Warning Notices in respect of clause 40 (Termination for Persistent Breach by the Contractor),

in each case relating to the relevant Services in respect of which the Leisure Operator or the FM Contractor (as the case may be) or any sub-contractor to the Leisure Operator or the FM Contractor (as the case may be) is being replaced, shall be cancelled. The Contractor shall notify the Authority on or before the appointment of any such substitute or replacement Leisure Operator or FM Contractor or sub-contractor (as the case may be) whether it elects for this clause 67.6 (Replacement of Sub-Contractors) to apply on that occasion.

    - Where an election is made pursuant to clause 67.6.1 (Replacement of Sub-Contractors) above on the substitution or replacement of the defaulting Leisure Operator or FM Contractor (as the case may be) or a defaulting sub-contractor (as the case may be) to the Leisure Operator or the FM Contactor then, for the purposes of clause 39.3 (Termination on Contractor Default) only:

      - no Performance Adjustment Points shall accrue for the purposes of sub-paragraph (k) of the definition of Contractor Default;

      - no Performance Adjustment Points shall accrue for the purposes of sub-paragraph (l) of the definition of Contractor Default; and

      - no warning notices or Final Warning Notices in respect of clause 40 (Termination for Persistent Breach by the Contractor) shall accrue for the purposes of sub-paragraph (b) of the definition of Contractor Default,

in respect of a Service during a period of two (2) months from the date on which that Service is first provided by the replacement or substitute Leisure Operator or FM Contractor or sub-contractor as appropriate. For the avoidance of doubt, Performance Adjustment Points and/or Performance Adjustments shall still be applied during that period but where as at the date of replacement pursuant to clause 67.6.1 (Replacement of Sub-Contractors) a ratchet is being applied pursuant to paragraphs [6.14 to 6.16] of the Payment and Performance Monitoring System the ratchet shall be reset with effect from the date of such replacement.

    - On the substitution or replacement of the defaulting Building Contractor or a defaulting sub-contractor to the Building Contractor (in both cases provided that the Contractor is acting in compliance with clause 7.1 (Ancillary Documents), the Contractor may elect that, for the purposes of clause 39.3 (Termination on Contractor Default) only any warning notices or Final Warning Notices in respect of clause 40 (Termination for Persistent Breach by the Contractor) in each case relating to the relevant Works in respect of which the Building Contractor or any sub-contractor to the Building Contractor is being replaced, shall be cancelled. The Contractor shall notify the Authority on or before the appointment of any such substitute or replacement Building Contractor or sub contractor whether it elects for this clause 67.6 to apply on that occasion.

    - Where an election is made pursuant to clause 67.6.3 (Replacement of Sub-Contractors) above on the substitution or replacement of the defaulting Building Contractor or a defaulting sub-contractor to the Building Contractor then, for the purposes of clause 39.3 (Termination on Contractor Default) only no warning notices or Final Warning Notices in respect of clause 40 (Termination for Persistent Breach by the Contractor) shall accrue for the purposes of sub-paragraph (b) of the definition of Contractor Default in respect of the Works during a period of two (2) months from the date on which such Works are first provided by the replacement or substitute Building Contractor or sub-contractor as appropriate.

- Change In Ownership

  - Restricted Share Transfer

    - No Change in Ownership may occur during the Lock-in Period.

    - Subject to clause 68.1.1, a Change in Ownership may only occur to a Suitable Third Party.

  - Notification

    - The Contractor shall provide the Authority with at least ten (10) Business Days' prior written notice of any Change in Ownership contemplated by clause 68.1 (Restricted Share Transfer).

    - The Authority may, not more than twice in any Contract Year, or at any time when a Contractor Default is outstanding, request that the Contractor inform it as soon as reasonably practicable and in any event within twenty (20) Business Days of receipt of the Authority's request for details of any Change in Ownership.

    - The Contractor's obligation under clause 68.2.1 shall, except where a legal transfer of shares is proposed, be limited to the extent of the Contractor's awareness.

    - The Contractor's obligation under clause 68.2.2 shall, except where a legal transfer of shares has occurred, be limited to the extent of the Contractor's awareness having made all reasonable enquiry.

    - For the purposes of this clause 68.2 (Notification) any change in legal or beneficial ownership of any shares that are listed on a recognised investment exchange (as defined in Section 285 of the Financial Services and Markets Act 2000) shall be disregarded.

- Financial Adjustments

  - Updating the Base Case

Whenever a Relevant Event or Loss of Revenue Event occurs, the financial consequence shall (save where otherwise provided in this Agreement or where the parties mutually agree otherwise) be determined in accordance with this clause 69 (Financial Adjustments). Where for the purposes of this clause 69 (Financial Adjustments) the Base Case is to be adjusted by reference to a Relevant Event or Loss of Revenue Event, this shall be carried out by the Contractor, in consultation with the Authority, to reflect the cumulative impact of any prior Relevant Event or Loss of Revenue Event on the version of the Base Case applicable immediately prior to the relevant adjustment and to reflect the impact of the Relevant Event or Loss of Revenue Event in respect of which such adjustment is being undertaken. In calculating the Change in Costs and Change in Revenue (in respect of Relevant Events) and in calculating the Loss of Revenue (in respect of Loss of Revenue Events) and in assessing other adjustments to be made to the Base Case arising from a Relevant Event or Loss of Revenue Event, the Contractor shall be entitled to take into account, inter alia:

    - any Change in Costs and Change in Revenue in respect of a Relevant Event and any Loss of Revenue (only) in respect of a Loss of Revenue Event;

    - reasonable economic assumptions prevailing at the time; and

    - changes in the prospective technical performance of the Project arising as a result of the Relevant Event or Loss of Revenue Event,

provided that the Authority shall not be required (and the Contractor shall not be entitled) to take into account the financial impact up to the date of the Relevant Event or Loss of Revenue Event of those risks which the Contractor bears under the terms of this Agreement, including (to the extent so borne by the Contractor under this Agreement) changes in VAT rates, taxation rates, CPI and the impact of Performance Adjustments.

  - Financial adjustment with respect to Changes in Costs during the Works Period

    - Whenever a Relevant Event occurs during the Works Period and gives rise to additional capital expenditure, the financial consequence with respect to Change in Costs shall (save where otherwise provided in this Agreement or where the parties mutually agree otherwise) be determined in accordance with this clause 69.2 (Financial adjustment during the Works Period). The Authority shall pay to the Contractor, by way of lump sum payment in accordance with clause 69.2.3 (Financial adjustment during the Works Period), the actual Change in Costs incurred by the Contractor arising from the Relevant Event, taking into account:

      - any Change in Costs;

      - reasonable economic assumptions prevailing at the time; and

      - changes in the prospective technical performance of the Project arising as a result of the Relevant Event.

    - If the parties are unable to agree the Change in Costs under clause 69.2.1 (Financial adjustment during the Works Period) within ten (10) Business Days of the Relevant Event occurring, then either party may refer the matter to the Dispute Resolution Procedure.

    - Any payment made by the Authority to the Contractor under this clause 69.2 (Financial adjustment during the Works Period) shall be made within twenty (20) Business Days of the later of the parties agreeing the Change in Costs or such amount being determined under the Dispute Resolution Procedure and that part of the Works to which such Change in Costs relates have been carried out and completed in accordance with this Agreement and certified as such by the Independent Certifier.

  - Application to the Base Case

Where, pursuant to this Agreement, either party is entitled to payment of any sum the assessment of which properly requires reference to the Base Case, the adjustment to the Annual Payment due shall be that required to ensure that, by reference to the Base Case adjusted under this clause 69 (Financial Adjustments), the Contractor is left in a no better and no worse position than under the version of the Base Case applicable immediately prior to the relevant adjustment, and shall be ascertained by determining the adjustment to the Annual Payment required to maintain the financial position of the Contractor with that in which it would have been under the version of the Base Case applicable immediately prior to the relevant adjustment.

  - No Better and no Worse

    - Subject to clause 69.4.2, any reference in this Agreement to no better and no worse or to leaving the Contractor in a no better and no worse position shall be construed by reference to the Contractor's:

      - rights, duties and liabilities under or arising pursuant to performance of this Agreement, the Building Contract, the Leisure Contract and the FM Agreement; and

      - ability to perform its obligations and exercise its rights under this Agreement, the Building Contract, the Leisure Contract and the FM Agreement,

so as to ensure that:

      - the Contractor is left in a position which is no better and no worse in relation to the [Base Profit, Base Head Office Costs and Base Modelled Costs (as defined in Schedule 18 (Benchmarking)] by reference to the version of the Base Case applicable immediately prior to the Relevant Event than had the Relevant Event not occurred; and

      - the ability of the Contractor to comply with this Agreement is not adversely affected or improved as a consequence of the Relevant Event.

    - In respect of any Loss of Revenue, the sum calculated pursuant to Schedule 23 (Loss of Revenue) and compensated by way of a lump sum payment, in instalments or by way of an adjustment to the Annual Payment shall be deemed to leave the Contractor in a 'no better and no worse position'.

    - Where in accordance with this Agreement any adjustment is to be made to the Annual Payment (where it is a Surplus Annual Payment) or where such adjustment would, when applied to the Annual Payment give rise to a Surplus Annual Payment the amount of the adjustment shall in all respects be limited so that in no circumstances will the Annual Payment, where it is a Surplus Annual Payment following an adjustment to be applied to it, exceed the Base Surplus Amount.

  - Replacement of Base Case and Loss of Revenue Schedule

    - Any Base Case produced following adjustments in accordance with this clause 69 (Financial Adjustments) shall, when it is approved by the Authority (such approval not to be unreasonably withheld), become the Base Case for the purposes of this Agreement until its further amendment in accordance with this Agreement.

    - When a Base Case is updated for the purposes of this clause 69 (Financial Adjustments), an updated Schedule 23 (Loss of Revenue) shall also be prepared. When the updated Schedule 23 (Loss of Revenue) is approved by the Authority (such approval not to be unreasonably withheld), it shall become Schedule 23 (Loss of Revenue) for the purposes of this Agreement until its further amendment in accordance with this Agreement.

  - Amendments to Logic and/or Formulae

    - Where it is necessary to amend the logic or formulae incorporated in the Base Case to permit adjustments to be made, this shall be done to the extent necessary and in accordance with generally accepted accounting principles.

    - Where any amendment is made to the logic or formulae incorporated in the Base Case, the Base Case, shall first be run as at the date immediately prior to amendment to ensure that the key ratios from the Base Case are maintained at no lower or no higher levels than the key ratios immediately post the amendment.

  - Copies of the Revised Base Case and Loss of Revenue Schedule

Following any change to the Base Case and/or Schedule 23 (Loss of Revenue) under the provisions of this clause 69 (Financial Adjustments), the Contractor shall promptly deliver a copy of the revised Base Case and/or Schedule 23 (Loss of Revenue) to the Authority in the same form as is established at the date of this Agreement or in such other form as may be agreed between the parties.

- Audit Access

The Contractor shall provide to the Authority's Representative all information, documents, records and the like in the possession of, or available to, the Contractor (and to this end the Contractor shall use all reasonable endeavours to procure that all such items in the possession of the Contractor or any sub-contractor shall be available to it and the Contractor has included or shall include, relevant terms in all contracts with sub-contractors to this effect) as may be reasonably requested by the Authority's Representative for any purpose in connection with this Agreement.

- No Agency

  - No Partnership or Employment

Nothing in this Agreement shall be construed as creating a partnership or as a contract of employment between the Authority and the Contractor.

  - Power to Bind

Save as expressly provided otherwise in this Agreement, the Contractor shall not be, or be deemed to be, an agent of the Authority and the Contractor shall not hold itself out as having authority or power to bind the Authority in any way.

  - Deemed Knowledge

Without limitation to its actual knowledge, the Contractor shall for all purposes of this Agreement, be deemed to have such knowledge in respect of the Project as is held (or ought reasonably to be held) by any Contractor Related Party.

- Entire Agreement

  - Prior Representations etc. Superseded

Except where expressly provided in this Agreement, this Agreement constitutes the entire agreement between the parties in connection with its subject matter and supersedes all prior representations, communications, negotiations and understandings concerning the subject matter of this Agreement.

  - Acknowledgements

Each of the parties acknowledges that:

    - subject to clauses 5.1 (Contractor Warranties), 6.4 (Authority Title Warranty) and [6.8 (Authority Warranted Data)] it does not enter into this Agreement on the basis of and does not rely, and has not relied, upon any statement or representation (whether negligent or innocent) or warranty or other provision (in any case whether oral, written, express or implied) made or agreed to by any person (whether a party to this Agreement or not) except those expressly repeated or referred to in this Agreement and the only remedy or remedies available in respect of any misrepresentation or untrue statement made to it shall be any remedy available under this Agreement; and

    - this clause shall not apply to any statement, representation or warranty made fraudulently, or to any provision of this Agreement which was induced by fraud, for which the remedies available shall be all those available under the law governing this Agreement.

- Notices

  - Form and Service of Notices

All notices under this Agreement shall be in writing and all certificates, notices or written instructions to be given under the terms of this Agreement shall be served by sending the same by first class post, [facsimile] or by hand, or leaving the same at:

| Contractor | Authority |
| --- | --- |
| [INSERT NAME] | [INSERT NAME] |
| [INSERT ADDRESS] | [INSERT ADDRESS] |
| [INSERT FAX NUMBER] | [INSERT FAX NUMBER] |

  - Provision of Information to Representatives

Where any information or documentation is to be provided or submitted to the Authority's Representative or the Contractor's Representative it shall be provided or submitted by sending the same by first class post, [facsimile] or by hand, or leaving the same at:

| Contractor's Representative | Authority's Representative |
| --- | --- |
| [INSERT NAME] | [INSERT NAME] |
| [INSERT ADDRESS] | [INSERT ADDRESS] |
| [INSERT FAX NUMBER] | [INSERT FAX NUMBER] |

  - Change of Details

Either party to this Agreement (and either Representative) may change its nominated address or facsimile number by prior notice to the other party.

  - Effectiveness of Notices

Notices given by post shall be effective upon the earlier of actual receipt and five (5) Business Days after mailing. Notices delivered by hand shall be effective upon delivery. [Notices given by facsimile shall be deemed to have been received where there is confirmation of uninterrupted transmission by a transmission report and where there has been no telephonic communication by the recipient to the senders (to be confirmed in writing) that the facsimile has not been received in legible form:

    - within two (2) hours after sending, if sent on a Business Day between the hours of 9am and 4pm; or

    - by 11am on the next following Business Day, if sent after 4pm on a Business Day but before 9am on that next following Business Day.]

- Severability

If any term, condition or provision of this Agreement shall be held to be invalid, unlawful or unenforceable to any extent, such term, condition or provision shall not affect the validity, legality and enforceability of the other provisions of or any other documents referred to in this Agreement.

- Waiver

  - Waiver to be Written

No term or provision of this Agreement shall be considered as waived by any party unless a waiver is given in writing by that party.

  - Extent of Waiver

No waiver under clause 75.1 (Waiver to be Written) shall be a waiver of a past or future default or breach, nor shall it amend, delete or add to the terms, conditions or provisions of this Agreement unless (and then only to the extent) expressly stated in that waiver.

- Public Relations and Publicity

  - Restriction

The Contractor shall not by itself, its employees or agents, and shall procure that its sub-contractors shall not communicate with representatives of the press, television, radio or other communications media on any matter concerning this Agreement or the Project without the prior written approval of the Authority.

  - Photographs

No permission to photograph or film in or upon any property used in relation to the Project shall be given unless the Authority has given its prior written approval (such approval not to be unreasonably withheld or delayed).

- Advertisements

The Contractor shall not exhibit or attach to any part of the Site[s] any notice or advertisement without the prior written permission of the Authority's Representative, save where otherwise required to comply with Legislation.

- Contractor's Records

  - Records and Open Book Accounting

The Contractor shall (and shall procure that each sub-contractor shall):

    - at all times maintain a full record of particulars of the costs of performing the Works and the Services;

    - upon request by the Authority, provide a written summary of any of the costs referred to in clause 78.1.1 (Records and Open Book Accounting), including details of any funds held by the Contractor specifically to cover such costs, in such form and detail as the Authority may reasonably require to enable the Authority to monitor the performance by the Contractor of its obligations under this Agreement;

    - provide such facilities as the Authority may reasonably require for its representatives to visit any place where the records are held and examine the records maintained under this clause 78.1 (Records and Open Book Accounting); and

    - provide to the Authority copies of its annual report and accounts within twenty (20) Business Days of publication.

  - Books of Account

Compliance with clause 78.1 (Records and Open Book Accounting) shall require the Contractor to keep (and where appropriate to procure that each sub-contractor shall keep) books of account in accordance with best accountancy practices with respect to this Agreement, showing in detail:

    - administrative overheads;

    - payments made to the Sub-Contractors and from the Sub-Contractors to their sub-contractors;

    - capital and revenue expenditure; and

    - such other items as the Authority may reasonably require from time to time to conduct costs audits for verification of cost expenditure or estimated expenditure, for the purpose of this Agreement,

and the Contractor shall have (and procure that its sub-contractors shall have) the books of account evidencing the items listed in sub-clauses 78.2.1 to 78.2.4 (Books of Account) inclusive, available for inspection by the Authority (and its advisers) upon reasonable notice, and shall provide a copy of these to the Authority as and when requested from time to time.

  - Maintenance of Records

    - The Contractor shall maintain or procure that detailed records relating to the performance of the Works and the delivery of the Services, in each case in accordance with Good Industry Practice, the requirements of clause 33 (Quality Assurance) and any applicable Legislation.

    - Without prejudice to clause 78.3.1 (Maintenance of Records), the Contractor shall maintain or shall procure that the following are maintained:

      - a full record of all incidents relating to health, safety and security which occur during the term of this Agreement;

      - full records of all maintenance procedures carried out during the term of this Agreement; and

      - full records of all staff matters including turnover, pay and disciplinary matters,

and the Contractor shall have the items referred to in clauses 78.3.2.1 (Maintenance of Records) to 78.3.2.3 (Maintenance of Records) available for inspection by the Authority (and its advisers) upon reasonable notice, and shall provide copies of these to the Authority as and when requested from time to time.

  - Auditor

The Contractor shall permit all records referred to in this clause 78 (Contractor's Records) to be examined and copied from time to time by the Authority's auditor (whether internal or external) and their representatives and other representatives of the Authority who reasonably require access to the same.

  - Retention

The records referred to in this clause 78 (Contractor's Records) shall be retained for a period of at least [five (5)] years after the Contractor's obligations under this Agreement have come to an end.

  - Termination or Expiry

Upon termination or expiry of this Agreement, and in the event that the Authority wishes to enter into another agreement for the operation and management of a project the same as or similar to the Project, the Contractor shall (and shall ensure that the sub-contractors will) comply with all reasonable requests of the Authority to provide information relating to the Contractor's costs of operating and maintaining the Project.

  - Provision of Information

The Contractor shall use all reasonable endeavours to assist the Authority in its preparation of any report required by the Department of Culture, Media and Sports or HM Treasury, from time to time.

  - Confidentiality

All information referred to in this clause 78 (Contractor's Records) is subject to the obligations set out in clause 59 (Freedom of Information and Confidentiality).

- Data Protection

  - General

    - In relation to all Personal Data, the Contractor shall at all times comply with the DPA as a data controller if necessary, including maintaining a valid and up to date registration or notification under the DPA covering the data processing to be performed in connection with the Project.

    - The Contractor and any sub-contractor shall only undertake processing of Personal Data reasonably required in connection with the Project and shall not transfer any Personal Data to any country or territory outside the European Economic Area.

  - No Disclosure

    - The Contractor shall not disclose Personal Data to any third parties other than:

      - to employees and sub-contractors to whom such disclosure is reasonably necessary in order for the Contractor to carry out the Works and/or the Services; or

      - to the extent required under a court order,

provided that disclosure under clause 79.2.1.1 (No Disclosure) is made subject to written terms substantially the same as, and no less stringent than, the terms contained in this clause 79.2.1 (No Disclosure) and that the Contractor shall give notice in writing to the Authority of any disclosure of Personal Data which either the Contractor or a sub-contractor is required to make under clause 79.2.1.2 (No Disclosure) immediately upon becoming aware of such a requirement.

    - The Contractor shall bring into effect and maintain all technical and organisational measures to prevent unauthorised or unlawful processing of Personal Data and accidental loss or destruction of, or damage to, Personal Data including to take reasonable steps to ensure the reliability of staff having access to the Personal Data.

    - The Authority may, at reasonable intervals, request a written description of the technical and organisational methods employed by the Contractor or the sub-contractors referred to in clause 79.2.2 (No Disclosure). Within twenty (20) Business Days of such a request, the Contractor shall supply written particulars of all such measures detailed to a reasonable level such that the Authority can determine whether or not, in connection with the Personal Data, it is compliant with the DPA.

  - The Contractor shall indemnify and keep indemnified the Authority against all Direct Losses incurred by it in respect of any breach of this clause 79 (Data Protection) by the Contractor and/or any act or omission of any sub-contractor which causes the Contractor to be in breach of this clause 79 (Data Protection).

- Interest on Late Payment

Save where otherwise specifically provided, where any payment or sum of money due from the Contractor to the Authority or from the Authority to the Contractor under any provision of this Agreement is not paid on the due date, it shall bear interest thereon at the Prescribed Rate from the due date (whether before or after any judgement) until actual payment and it is agreed between the parties that the Prescribed Rate and the provisions of this Agreement relating to the payment of compensation on termination of this Agreement following the occurrence of an Authority Default provide the Contractor with a substantial remedy pursuant to Sections 8 and 9 of the Late Payment of Commercial Debts (Interest) Act 1998.

- Governing Law and Jurisdiction

The Agreement shall be governed by and construed in all respects in accordance with the laws of England and Wales. Subject to clause 64 (Dispute Resolution), the English Courts shall have exclusive jurisdiction to settle any disputes which may arise out of or in connection with this Agreement.

- Sole Remedy

  - Common Law Rights for the Contractor

    - Without prejudice to any entitlement of the Contractor:

      - to specific performance of any obligation under this Agreement; or

      - to injunctive relief;

the Contractor's sole remedy in relation to matters for which an express right or remedy is stated in this Agreement shall be that right or remedy and the Contractor shall have no additional right or remedy arising by common law, in equity, by statute or otherwise.

    - The Contractor's sole remedy in relation to any Compensation Event shall be the operation of clause 16.5 (Effect of a Compensation Event).

  - Common Law Rights of the Authority

Subject to:

    - any other express right of the Authority pursuant to this Agreement; and

    - the Authority's right to claim, on or after termination of this Agreement, the amount of its reasonable costs, losses, damages and expenses suffered or incurred by it as a result of rectifying or mitigating the effects of any breach of this Agreement by the Contractor, save to the extent that the same has already been recovered by the Authority pursuant to this Agreement or has been taken into account to calculate any compensation payable pursuant to Part 7 (Compensation on Termination),

the sole remedy of the Authority in respect of a failure to provide the Services in accordance with this Agreement shall be the operation of Schedule 6 (Payment and Performance Monitoring System).

  - Nothing in clause 82.2 (Common Law Rights of the Authority) shall prevent or restrict the right of the Authority to seek injunctive relief or a decree of specific performance or other discretionary remedies of the court.

  - No Breach

The Contractor shall not be held to be failing to comply with its obligations under this Agreement to the extent that such failure to comply is a result of the Authority's breach of its obligations hereunder.

  - Indirect Losses

Save where stated to the contrary, the indemnities under this Agreement shall not apply and (without prejudice to the Authority's rights under the Payment and Performance Monitoring System) there shall be no right to claim damages for breach of this Agreement, in tort or on any other basis whatsoever, to the extent that any loss claimed by either party is for Indirect Losses. The Authority agrees that, notwithstanding the foregoing, any Losses of the Contractor arising under the Sub-Contracts as originally executed (or as amended in accordance with the terms of this Agreement) which are not of themselves Indirect Losses, shall not be excluded from such a claim solely by reason of this clause 82.

- No Double Recovery

Notwithstanding any other provisions of this Agreement, neither party shall be entitled to recover compensation or make a claim under this Agreement in respect of any loss that it has incurred to the extent that it has already been compensated in respect of that loss pursuant to this Agreement or otherwise.

- Counterparts

This Agreement may be executed in any number of counterparts, all of which when taken together shall constitute one and the same instrument.

- Construction Industry Scheme

  - This clause 85 relates to the Construction Industry Scheme (the Scheme) the framework of which is contained in the Finance Act 2004 with the operational details contained in the Income Tax (Construction Industry Scheme) Regulations 2005 SI 2005/2045 (the 2005 Regulations) and which commenced on 6 April 2007.

  - All payments made under this Agreement will be paid in accordance with this clause.

  - The parties believe that all payments made under this Agreement will be exempt from the Scheme under Regulation 23 SI 2005/2045 (Arrangements involving public bodies).

  - If and to the extent that payments are not exempt from the Scheme by virtue of Regulation 23, the parties agree to operate the Scheme in accordance with the 2005 Regulations, the Finance Act 2004 or any other statute or subordinate legislation (the Relevant Legislation) relating to the Scheme as from time to time modified or replaced whether before or after the date of this Agreement and in particular the Authority shall be entitled to make the statutory deduction from any payment due to the Contractor in accordance with the 2005 Regulations and/or the Relevant Legislation.

  - If compliance with this clause involves the Authority or the Contractor in not complying with any other of the terms of this Agreement (save for the parties' obligations to comply with all laws), then the provisions of this clause shall prevail.

- Capacity

Save as otherwise expressly provided, the obligations of the Authority under this Agreement are obligations of the Authority in its capacity as a contracting counterparty and nothing in this Agreement shall operate as an obligation upon, or in any other way fetter or constrain the Authority in any other statutory capacity as a Relevant Authority, nor shall the exercise by the Authority of its duties and powers in any other statutory capacity as a Relevant Authority lead to any liability under this Agreement (howsoever arising) on the part of the Authority to the Contractor.

SCHEDULE 1

AUTHORITY'S REQUIREMENTS

Part 1A – Facilities Requirements

Part 1B – Technical Specification

Part 2 – [Initial Services Specification]

Part 3 – Services Specification

SCHEDULE 2

CONTRACTOR'S PROPOSALS

Part 1 – Construction Proposals

Part 2 – Service Delivery Proposals

Part 3 – Construction Programme

SCHEDULE 3

NOT USED

SCHEDULE 4

[FACILITY/FACILITIES]

| Facility (including address) | Services Start Date | Planned Services Availability Date | [Planned Post Completion Works Acceptance Date] | Initial Amount (Daily Rate) |
| --- | --- | --- | --- | --- |

SCHEDULE 5

COMPLETION REQUIREMENTS

Part 1 – Services Availability Requirements

Services Availability Requirements shall mean that:

the Works [(excluding the Post Completion Works)] have been provided in accordance with the Facilities Requirements, [the Technical Specification] and the Construction Proposals, Good Industry Practice, all Necessary Consents, all applicable Authority's Policies and Legislation;

the Works [(excluding the Post Completion Works)] have been designed, constructed, remodelled or refurbished in the forms and materials described and as approved in any planning approvals and the Facilities Requirements, [Technical Specification] and Construction Proposals;

each Zone [(excluding any Zones that are the subject to Post Completion Works)] has been completed, finished and laid out in accordance with the standards and provisions set out in the Zone Data Sheets;

the Buildings have been located on [the/each] Site, together with landscaped areas [(excluding any Zones that are the subject to Post Completion Works)], and with the sports and recreational facilities as shown in the Facilities Requirements and the Construction Proposals and as approved in any planning approvals;

external fencing, gates, security equipment, vehicular and pedestrian access are complete as described in the Facilities Requirements, [Technical Specification] and the Construction Proposals;

the Buildings are weatherproof and watertight;

the building services, the drains, the fire and intruder alarm installations and any other security related equipment comply with the Facilities Requirements, [Technical Specification] and the Construction Proposals in all material respects;

the Buildings, and where relevant the Site[s], are clean and tidy and all debris, surplus material and rubbish has been removed;

[the Contractor has provided the Building Manual (including the health and safety file)] or [the Contractor has provided a draft copy of the Building Manual (such copy to include the health and safety file), the contents of such draft to be to the reasonable satisfaction of the Independent Certifier and the Contractor confirms that it will be able to provide a final and complete version of the Building Manual within twenty (20) Business Days following the date upon which the Acceptance Certificate is issued, the contents of any such version of the Building Manual to be to the reasonable satisfaction of the Independent Certifier];

the mechanical and electrical plant and equipment have been tested on Site to ascertain compliance with the Facilities Requirements, [Technical Specification] and the Construction Proposals and meet the standards set out in the Facilities Requirements, [Technical Specification] and the Construction Proposals;

all mechanical and electrical installation work is complete and the plant and equipment are safe for use;

the Collateral Warranties have been duly executed and delivered to the Authority.

Part 2 – [Post Completion Works Acceptance Requirements]

SCHEDULE 6

PAYMENT AND PERFORMANCE MONITORING SYSTEM

[Note: Two example Payment and Performance Monitoring schedules are included within this template:

- Option A is a standard Payment Mechanism - including reference to Performance Adjstment Points; and

- Option B is default notice system.

Local authorities should review the two template schedules to determine which approach suits their needs best, and ensure that their preferred option is included in the tender documents issued to bidders.]

option a – standard payment mechanism

CONTENTS

Definitions

- Introduction

- Monthly Payments

- Indexation

- Performance Standards and Performance Failures

- Rectification Periods

- Performance Adjustment Points

- [Performance Bonus Points]

- Performance Adjustments

- Excusing Causes

- Monitoring and Reporting

- Review of the Payment and Performance Monitoring System

Appendices

- Performance Standards and Priority Ratings and Urgency Weightings

- Worked Examples

Definitions

The terms and expressions used in this Schedule shall have the same meaning as set out in clause 1 (Definitions and Interpretation) of this Agreement. In addition, the following words and expressions shall have the meanings set out below:

Annual Payment

means the amount payable in respect of a Contract Year payable by the Authority to the Contractor where it is a Deficit Annual Payment or by the Contractor to the Authority where it is a Surplus Annual Payment as set out in the table at paragraph 2.5 below as may be adjusted in accordance with this Agreement

Annual Performance Adjustment or APA

means the fixed annual adjustment to be applied for failure to meet the Annual Performance Standards calculated in accordance with paragraphs 8.5−8.9 of this Schedule;

Annual Performance Failure

means non satisfaction of one or more of the Annual Performance Standards;

Annual Performance Standard

means the Performance Standards set out in Part 1B of the Services Specification and listed as such in Appendix A to this Schedule;

Authority's Outcomes

means the Performance Standards as set out in paragraph [1.5] of Part 1B of the Services Specification;

[Bedding-In Period

means in relation to [X Facility] the period commencing on the Services Availability Date and expiring at midnight six (6) calendar months after such date;]

Contract Day

means a period commencing on the opening of [the/such] Facility to the public and ending on the closing of [the/such] Facility to the public, such period being no less than that set out in the Minimum Opening Hours;

Critical Zone Multiplier

means a factor of [two (2)]

Current Indexation Date

has the meaning given to it in paragraph 3.1 of this Schedule;

Duty Manager

means the person or persons appointed as such by the Contractor, for the managing of the Facilities;

Excusing Cause

means the specific circumstances in which the Contractor could be relieved from Performance Adjustment Points, Performance Adjustments and Annual Performance Adjustments in accordance with paragraph 9 of this Schedule;

External Areas

means all access roads, hard standing, footpaths, car park areas and entrances external pitches and courts comprised in or serving the Facility;

Facility Performance Failure

means non satisfaction of one or more of the Facility Performance Standards;

Facility Performance Standard

means the facility performance standards for each Zone as set out in Part 1D and Appendix 4 (Zone Data Sheets) of the Services Specification and listed as such in Appendix A to this Schedule;

Help Desk

means the entrance area and reception made available by the Contractor at the relevant [Facility/Facilities] in accordance with Part 1B of the Services Specification;

Indexed Annual Payment or IAP

means the Annual Payment to be indexed in accordance with paragraph 3 of this Schedule;

Monthly Payment or MP

means the gross monthly payment calculated by the formula set out at paragraph 2.1 of this Schedule;

Monthly Performance Adjustment or MPA

means the adjustments made in respect of Performance Adjustment Points and calculated in accordance with paragraphs 8.1 and 8.5  of this Schedule;

Monthly Performance Failure

means either a Facility Performance Failure or Service Performance Failure

National Benchmarking Service

means the benchmarking service managed by Sport England that is a partnership approach to providing critical data on the performance of leisure facilities;

Non-rectified Performance Failures

has the meaning given to it in paragraph 6.2 of this Schedule

Original Zone

means a Zone which fails to meet a Facility Performance Standard and whose function may be transferred to a Replacement Zone in accordance with paragraph 6.6−6.13 of this Schedule;

Originating Zone

means a Zone that is identified as such in paragraph 6.5 of this Schedule;

Outcomes Scorecard

means the annual scorecard developed between both parties for the measurement of the Contractor's performance against the Authority's Outcomes in accordance with paragraph [1.5] of Part 1B of the Services Specification;

Participation Targets Annual Performance Standard

means those targets as set out in Part 1B, paragraph [1.7] of the Services Specification or as agreed between the parties;

Performance Adjustment

means the adjustments to be applied in respect of Monthly Performance Adjustments and/ or Annual Performance Adjustments and calculated in accordance with paragraph 8 of this Schedule;

Performance Adjustment Cap

has the meaning given to it in paragraph 2.6 of this Schedule;

Performance Adjustment Points

means the points awarded for each Non-rectified Performance Failure, depending on the Priority Rating applied and calculated in accordance with this Schedule;

[Performance Bonus Points]

[means the bonus points calculated in accordance with paragraphs 7.1 and 7.2];

Performance Failure

means any or all of a Facility Performance Failure, Service Performance Failure or an Annual Performance Failure as described in paragraph 4.3 of this Schedule;

Performance Monitoring Report

means the monthly report to be compiled by the Contractor in accordance with paragraph 10 of this Schedule and detailing all Performance Failures in the previous Contract Month and appropriate Rectification Periods or Rectification Periods rescheduled pursuant to paragraphs 5.5, 5.5A and/or 5.6 of this Schedule;

Performance Standard

means the performance standards set out in detail within the Services Specification and summarised in Appendix A to this Schedule and divided into the following categories;

(a)	Facility Performance Standards;

(b)	Service Performance Standards; and

(c)	Annual Performance Standards;

Priority Rating

means a Very High Priority Rating, High Priority Rating, Medium Priority Rating or Low Priority Rating, as appropriate, as determined in accordance with Appendix A of this Schedule;

Rectification

means subject to paragraph 5.4 making good a Service Performance Failure or a Facility Performance Failure so that the subject matter of such Service Performance Failure or Facility Performance Failure complies with the levels of Service required pursuant to this Agreement and shall without prejudice to the generality of the foregoing include:

(a) 	restoring all functional capability necessary to meet the Facility Performance Standard or Service Performance Standard;

(b) 	ensuring that any Zone which has been affected by the relevant Facility Performance Failure complies with the Facility Performance Standards; and

(c) 	(if applicable) complying with and making good the Monthly Performance Failure in accordance with Legislation and, where in relation to a matter there is no express obligation or standard imposed on the Contractor under this Agreement, in accordance with Good Industry Practice;

or as the context so requires where paragraph 5.4 applies

rectification shall mean taking all necessary actions to make the affected area safe and "Rectify" and "Rectified" shall be construed accordingly;

Rectification Period

means subject to extensions in accordance with paragraphs 5.5, 5.5A and/or 5.6 of this Schedule the time period set out in Appendix A in respect of the relevant Monthly Performance Failure or, if not set out therein, the time period referred to in paragraph 5.4 of this Schedule within which Rectification of the relevant Monthly Performance Failure must be completed;

Related Zone

means a Zone that is linked to an Originating Zone as set out in paragraph 6.5 of this Schedule;

Replacement Zone

means an appropriate alternative Zone provided by the Contractor when an Original Zone fails to meet a Facility Performance Standard as set out in paragraph 6.6−6.13 of this Schedule;

Service Performance Failure

means non satisfaction of one or more of the Service Performance Standards;

Service Performance Standard

means the service performance standards set out in Part 1C of the Services Specification and listed as such in Appendix A to this Schedule;

Sport England National Benchmarking Service Annual Performance Standard

means those targets as set out in Part 1B, paragraph [1.8] of the Services Specification or as agreed between the parties;

Total Performance Adjustment or TPA

has the meaning given to it in paragraph 2.1 of this Schedule;

Urgency Rating

means a Very High Urgency Rating, High Urgency Rating, Medium Urgency Rating or Low Urgency Rating, as appropriate, as determined in accordance with paragraph 5.4 and Appendix A of this Schedule;

Zone

means an area of the [Facility/ Facilities] as identified in the Zone Data Sheets;

Zone Data Sheets

means those data sheets in respect of each Zone as provided in Appendix 4 of the Services Specification.

Introduction

The Services Specification provides details of the Authority's requirements for the Services and sets out the Performance Standards in respect of the various elements of the Services.

The Services Specification is largely output-based and the Authority is keen to work in close partnership with the Contractor to ensure that the outcomes it requires from the Services are met and continuous improvement is achieved throughout the [Services Period/Contract Period].

To facilitate this aim, the Authority wishes to adopt a performance monitoring system that is both effective in helping to achieve the desired outcomes and efficient to operate.

Under this Payment and Performance Monitoring System, financial adjustments will apply for failure to achieve the required Performance Standards.

The Authority has taken care to ensure that as far as possible there are simple methods for measurement of the Performance Standards and that the reporting requirements and reporting frequency are not overly onerous.

In this way and through working together with the Contractor in a positive partnership, the Authority's intention is that this Payment and Performance Monitoring System will provide reasonable and prudent checks while focusing on demonstrating key performance indicators that confirm a high quality of service is being delivered and measuring the contribution of the Services to the Authority's Outcomes.

Applied effectively monitoring can be an important tool in demonstrating real service quality and recognising the wider benefits of service provision.

It should however be noted that the accumulation of financial adjustments for failure to achieve the required Performance Standards may lead to termination of this Agreement, subject to, and in accordance with the provisions of this Agreement.

Monthly Payments

The Monthly Payment shall be calculated in accordance with this paragraph 2.1 and:

where the Annual Payment is a Deficit Annual Payment, the Monthly Payment shall be paid by the Authority to the Contractor; or

where Annual Payment is a Surplus Annual Payment, the Monthly Payment shall be paid by the Contractor to the Authority,

such Monthly Payment to be paid monthly in arrears in accordance with, and subject to, the provisions of this Schedule and clause 37 (Payment during the Services Period) of this Agreement:-

- Monthly Payment (MP) = IAP (Indexed) /12

- where IAP = Indexed Annual Payment, calculated in accordance with paragraph 3.1 below for the relevant Contract Year.

Subject to paragraph 2.6 below and to the provisions of this Agreement, Performance Adjustment Points shall be accumulated in respect of Non-rectified Performance Failures for the preceding Contract Month and Monthly Performance Adjustments calculated pursuant to the number of Performance Adjustment Points awarded as set out in paragraph 8.1 [taking into account any Performance Bonus Points that apply in accordance with paragraph 8.2] below.  Annual Performance Adjustments shall be calculated as provided for in paragraphs 8.5 to 8.9 below and Total Performance Adjustments per Contract Month shall be calculated as follows:

- TPA = MPA + APA/12

where:

- TPA = the Total Performance Adjustment to be applied for a particular Contract Month;

- MPA = the Monthly Performance Adjustments calculated pursuant to paragraphs 8.1 to 8.5  below for the preceding Contract Month; and

- APA = the Annual Performance Adjustments calculated pursuant to paragraphs 8.6 −8.10 below for the preceding Contract Year.

Where [the Commencement Date/Services Availability Date] occurs, or this Agreement is terminated, part way through a Contract Month, the Monthly Payment shall be calculated pro rata to the number of days in such Contract Month.

The MP and TPA shall be paid in accordance with and subject to the provisions of Clause 37 (Payment during the Services Period) of this Agreement.

The Annual Payment at [the Commencement Date/Services Availability Date] is [£X,000]. [The profiled Annual Payment throughout the [Services Period/Contract Period] will be as follows]:[The profiled Annual Payment is based on an assumed Services Availability Date of [X January 20XX] in relation to [X Facility].]

| CONTRACT YEAR | ANNUAL PAYMENT |
| --- | --- |
| [Year 1] | [£X,000] |
| [Year 2] | [£X,000] |
| [Year 3] | [£X,000] |
| [Year 4 onwards] | [£X,000] |

Monthly Performance Adjustments and/or Annual Performance Adjustments applied cannot exceed [                              ] ("Performance Adjustment Cap") in respect of the relevant Contract Month and any Performance Adjustment in excess of the Performance Adjustment Cap shall not be carried forward to any subsequent Contract Month. There is no limit to the amount of Performance Adjustment Points that can be incurred (as these are linked to termination provisions in this Agreement).

Neither party shall be entitled to challenge the level of Performance Adjustments or Performance Adjustment Points applicable to a Contract Month after a period of twelve (12) months from the last day of the relevant Contract Month.

Indexation

The Annual Payment shall be adjusted in accordance with indexation on each anniversary of the Pricing Reference Date ("Current Indexation Date") in accordance with the formula at paragraph 3.2 below.

The Indexed Annual Payment shall be calculated as follows:

- I = X/Y

- IAP = I x Annual Payment

- where X = [CPI] at Current Indexation Date; and

- Y = [CPI] at the Pricing Reference Date.

For the purposes of paragraph 3.1 above the [CPI] at the Current Indexation Date means the [CPI] most recently published before the Current Indexation Date.

For the purposes of paragraph 3.1 above the [CPI] at the Pricing Reference Date means the [CPI] most recently published before the Pricing Reference Date.

For the avoidance of doubt, any periodic re-alignment of the [CPI] base should be correctly accounted for in the calculation.

Where prices are subject to indexation in accordance with paragraph [1.20] of the Services Specification, the indexed price shall be calculated as follows:

- I = X/Y

- Indexed price = I x price

- where X = [CPI] at Current Indexation Date; and

- Y = [CPI] at the Pricing Reference Date.

Performance Standards and Performance Failures

The Performance Standards are set out in detail within the Services Specification and summarised within the attached Appendix A.

The Performance Standards have been divided into three separate categories, namely:

Annual Performance Standards

Facility Performance Standards

Service Performance Standards.

A Performance Failure shall have occurred where the Contractor fails to meet the requirements of any of these Performance Standards.

Each Facility Performance Standard and Service Performance Standard has been allocated a Priority Rating, which will apply in the event of a Monthly Performance Failure occurring. The Priority Ratings are as follows:

- Very High

- High

- Medium

- Low.

Subject to paragraph 4.6, the Priority Rating that has been allocated to each of the Service Performance Standards and Facility Performance Standards is detailed within Appendix A.

For most Facility Performance Standards, details of the relevant Priority Rating can be found in the relevant Zone Data Sheets included at Appendix 4 of the Services Specification. Those Facility Performance Standards that are not covered within the Zone Data Sheets are allocated a generic Priority Rating, which is to be applied in accordance with Appendix A.

Rectification Periods

Where a Monthly Performance Failure has occurred, the Contractor shall be allowed a Rectification Period in which to rectify that Monthly Performance Failure.

For the avoidance of doubt, the Contractor shall not be entitled to a Rectification Period for an Annual Performance Failure.

When the Contractor or its' staff becomes aware of a Monthly Performance Failure it shall notify the Help Desk within the time periods specified in the table below:

|  | PERFORMANCE FAILURE | NOTIFICATION REQUIREMENT |
| --- | --- | --- |
| (1) | A Facility Performance Failure or a Service Performance Failure involving a risk to health and safety or a potential breach of Legislation or a potential threat of injury to persons or damage to property | Immediate notification |
| (2) | Subject to (1) above, a Facility Performance Failure or Service Performance Failure which occurs in a Zone which is being used for a programmed activity which is being supervised or carried out by a staff member (including lifeguards) and such supervision prevents that staff member from giving immediate notification of the failure | Notification at the end of the activity, or when the staff member is relieved of such supervision provided this is not a Very High Urgency Rating (in which case immediate notification is required) |
| (3) | Subject to (1) above, a Facility Performance Failure or a Service Performance Failure which is identified by a staff member during the Duty Manager's inspection in accordance with paragraph 10.3 of this Schedule | Within 1 hour of the end of the Duty Manager's inspection |
| (4) | Subject to (1) above, a Facility Performance Failure or Service Performance Failure which is reported to or identified by a staff member outside of a programmed activity or an inspection | Prompt notification with regard to operational circumstances |

The Rectification Period will run from the time the failure is logged at the Help Desk and will vary according to the Urgency Rating of the Facility Performance Failure or Service Performance Failure. Unless stated in the relevant Zone Data Sheet or in Appendix A, Rectification Periods are as follows:

| URGENCY RATING | RECTIFICATION PERIOD |
| --- | --- |
| Very High | [1 hour] |
| High | [4/6 hours] Hours] |
| Medium | [24/48 hours] |
| Low | [1 week] |

In circumstances of a Monthly Performance Failure where a Very High Urgency Rating or High Urgency Rating applies provided the Contractor has effected temporary rectification by taking all necessary actions to make the affected area safe, the Rectification Period for effecting permanent rectification within the meaning set out in the definition of Rectification paragraphs (a) to (c) shall, subject as may be extended pursuant to paragraphs 5.5, 5.5A and/or 5.6 of this Schedule, be the same period as for a Monthly Performance Failure with a Medium Urgency Rating.

The Rectification Period shall be extended to be included in the next period of planned preventative maintenance in accordance with the Schedule of Programmed Maintenance or at such other time or by such period as is reasonable if the Contractor can demonstrate to the Authority's satisfaction (the Authority acting reasonably) that:

the activity required to achieve Rectification is better carried out at that time; or

a part which is necessary to achieve Rectification is not in stock and it can be demonstrated that failure to have the necessary part in stock is in line with Good Industry Practice; or

the circumstances of the Monthly Performance Failure are such that Rectification within the scheduled Rectification Period cannot reasonably be achieved by the Contractor acting in accordance with Good Industry Practice and in accordance with its obligations under this Agreement.

## 6.5A	Without prejudice to Relief Events and the operation of clause 55 (Relief Events) of the Agreement, if a Performance Failure occurs due to failure by a utility supplier to supply utilities to a Facility through no fault of the Contractor, [or the [Leisure Operator] the Rectification Period shall be increased to seven (7) days and those Rectification Periods specified in Appendix A or in the table at paragraph 5.4 above shall not apply in such circumstances. Should the failure by a utility supplier to supply utilities to a Facility through no fault of the Contractor [or the Leisure Operator] continue for a period in excess of seven (7) days then the Contractor shall be entitled to apply for rescheduled Rectification pursuant to paragraph 5.6 below.

If the Contractor wishes to extend the Rectification Period, the Contractor shall apply to the Authority in writing requesting an extension of the Rectification Period and setting out the reasons for the request, an explanation of any steps already taken to resolve the failure and the proposed approach to seeking to avoid a similar situation arising in the future. Subject as set out below, the Rectification Period shall only be extended with the written consent of the Authority's Representative, such consent not to be unreasonably withheld or delayed, provided that where a Monthly Performance Failure occurs on a Contract Day other than a Business Day and the Contractor is not able to obtain Authority consent having taken reasonable endeavours to contact the Authority's Representative or other nominated officer on out of office hours contact numbers provided to the Contractor, the Rectification Period will commence at the start of the next Business Day. The Authority shall act in a reasonable and proportionate manner having regard to the circumstances arising. The Authority's Representative shall be entitled to withhold consent if there is a continuing contravention of Legislation or if there is a risk of death, personal injury or damage to the relevant [Facility/Facilities] provided that if Rectification cannot be completed within the applicable Rectification Period for any of the reasons set out in paragraph 5.5, the Contractor shall take all measures to temporarily rectify or make safe the area affected and the Authority shall nevertheless acting reasonably give all due consideration to the request for the extended period to enable the Contractor to permanently Rectify the circumstances or event giving rise to such Monthly Performance Failure.

Notwithstanding that the Contractor completes Rectification of the Monthly Performance Failure within the relevant Rectification Period, if the same Monthly Performance Failure arises again as a result of the same cause as the original Monthly Performance Failure during a period of seventy two (72) hours from the logging of the original Monthly Performance Failure then the Contractor shall be treated as if the original Monthly Performance Failure had never been Rectified and Performance Adjustment Points shall be allocated in relation to the subsequent Monthly Performance Failure from the time that the original Monthly Performance Failure was logged and shall continue until the subsequent Monthly Performance Failure is Rectified in accordance with the provisions of this Schedule.

Performance Adjustment Points

For the purpose of Performance Adjustment Point allocation, each Zone of [the/ each] Facility shall be treated as a single operation. For example, a cleaning failure in two of the Zones in the same Contract Day would lead to two Service Performance Failures. Where two different Facility Performance Failures or Service Performance Failures arising out of the same event or circumstances occur in the same Zone [in the same Facility], in the same Contract Day, only the Service Performance Failure or Facility Performance Failure with the higher associated Performance Adjustment Points shall apply.

Performance Adjustment Points shall be allocated per Contract Month where a Facility Performance Failure and/ or Service Performance Failure has not been Rectified within the allowed Rectification Period (as the same may be extended pursuant to paragraphs 5.5, 5.5A and/or 5.6 of this Schedule) ("Non-rectified Performance Failure") and such Performance Adjustment Points shall continue for each Contract Day (or part thereof) until such Non-rectified Performance Failure is Rectified.

The number of Performance Adjustment Points awarded will depend on the Priority Rating of the Non-rectified Performance Failure as set out in Appendix A or if not set out therein, as follows:

| PRIORITY RATING | PERFORMANCE ADJUSTMENT POINTS |
| --- | --- |
| Very High | [10] points |
| High | [5] points |
| Medium | [3] points |
| Low | [1] point |

Where a Facility Performance Failure occurs in one of the following list of Zones within the [Facility/ Facilities], a Critical Zone Multiplier shall be applied to the total number of Performance Adjustment Points;

[the Sports Hall; or

the Swimming Pool Hall].

Where the Non-rectified Performance Failure is a Facility Performance Failure in relation to certain Zones ("Originating Zones") then each Zone linked to that Originating Zone ("Related Zones") in the same Facility shall also be deemed to be the subject of the same Facility Performance Failure that has not been rectified.

| ORIGINATING ZONE | RELATED ZONE | COMMENT |
| --- | --- | --- |
| [To be inserted] | [To be inserted] | [[100%] of Zone to be accounted for] |
| [Sports Hall] | [Dry Changing] | [[25%] of Zone to be accounted for] |
| [Dry Changing] | [Sports Hall Squash Courts Dance Studio Fitness Suite] | [Unless other changing can be utilitised] |

Where a Zone fails to meet a Facility Performance Standard (the "Original Zone"), the Contractor shall be entitled (but not obliged) to utilise a Replacement Zone within the same Facility, for the function of the Original Zone.

Provided that the Facility Performance Standards applicable to the Original Zone are satisfied in the Replacement Zone no Performance Adjustment Points shall accrue in respect of the Original Zone.

Subject to paragraph 6.9, where a Replacement Zone is utilised then that Replacement Zone shall be deemed to have a Facility Performance Failure for its original purpose as designated in the Services Specification and for the avoidance of doubt, Performance Adjustment Points shall accrue in respect of the deemed Non-rectified Performance Failure in the Replacement Zone until the Replacement Zone is restored to the function required in the Services Specification and meets the Facility Performance Standards specified for that Replacement Zone.

Where a Replacement Zone is utilised, but is not pre-booked or included within the [Authority's Weekly Programming Requirements] as set out in the Services Specification or required by any User, the Performance Adjustment Points relating to the Replacement Zone shall be reduced by 50%. Where a Replacement Zone is used in place of an Original Zone, no Performance Adjustment Points shall be allocated in respect of any Related Zones to the Replacement Zone or to the Original Zone.

If the Original Zone subject to the Facility Performance Failure (which is having a Replacement Zone used in its place) is not restored to its function as set out in the Services Specification, so as to meet the Facility Performance Standards for that Zone within seven (7) Contract Days of the end of the Rectification Period (as may have been extended in accordance with this Schedule), then the Original Zone [and the Replacement Zone] shall accrue Performance Adjustment Points in accordance with this Schedule from the first Contract Day after the expiry of the seven (7) Contract Days and shall continue to so accrue for each Contract Day thereafter until the relevant Facility Performance Failure is Rectified.

The Contractor shall not be entitled to implement the Replacement Zone procedure again in respect of the same Zones within three (3) Contract Days of the Rectification of the Facility Performance Failure to which the use of the Replacement Zone procedure related.

For the avoidance of doubt, the Contractor shall be entitled to withdraw the Replacement Zone at any time, and in such circumstances (subject to the Replacement Zone meeting the Facility Performance Standards specified for that Replacement Zone in the Services Specification) Performance Adjustment Points shall [(subject to paragraph 6.10)] only accrue in respect of the Original Zone.

For the avoidance of doubt those Zones considered to be appropriate Replacement Zones for each Original Zone have been outlined in the table below.

| ORIGINAL ZONE | REPLACEMENT ZONE |
| --- | --- |
| [To be inserted] | [To be inserted] |
| [Wet Changing Facilities] | [Dry Changing Facilities] |
| [Multi-Use Zone] | [Sports Hall] |
| [Dry Changing Facilities] | [Wet Changing Facilities] |
| [Sports Hall] | [Multi-Use Zones] |

Should the same Non-rectified Performance Failure continue beyond ten (10) Contract Days from the date of expiry of the relevant Rectification Period (as the same may be extended pursuant to paragraphs 5.5, 5.5A and/or 5.6 of this Schedule), then the value of daily Performance Adjustment Points awarded shall be increased by 50% for all subsequent Contract Days until such Non-rectified Performance Failure has been Rectified.

Should the same Non-rectified Performance Failure continue beyond thirty (30) Contract Days from the date of expiry of the relevant Rectification Period (as the same may be extended pursuant to paragraphs 5.5, 5.5A and/or 5.6 of this Schedule), then the value of Performance Adjustment Points awarded from this point onwards shall be increased by 100% until such Non-rectified Performance Failure is Rectified. For the avoidance of doubt, this means 100% of the daily Performance Adjustment Points level as set out in paragraph 6.3 above.

Should the same Annual Performance Failure continue for two consecutive Contract Years then the value of the fixed Annual Performance Adjustment shall be multiplied by two (2) for all subsequent Contract Years (subject to paragraph 8.9) or part thereof until the Annual Performance Failure has been Rectified and paragraph 8.9 shall apply where Rectification occurs part way through a Contract Year with Annual Performance Adjustments calculated applying the multiple referred to above.

Performance Adjustment Points shall be accumulated in each Contract Month for Non-rectified Performance Failures and reportedly monthly and Monthly Performance Adjustments levied monthly.

[Performance Bonus Points

Performance Bonus Points will be awarded for over-delivery against the Authority’s Outcomes, as measured by the Outcomes Scorecard. The Authority expects all Outcomes to be ‘Green’ or ‘Amber’ in order to meet the Annual Performance Standards relating to the Authority’s Outcomes and Performance Bonus Points will be awarded for additional ‘Green’ scores as follows;

| AUTHORITY OUTCOME LEVELS | PERFORMANCE BONUS POINTS |
| --- | --- |
| More than 50% ‘Green’ | [25] points |
| More than 75% ‘Green’ | [50] points |
| More than 90% ‘Green’ | [75] points |
| 100% ‘Green’ | [100] points |

Performance Bonus Points shall be awarded annually and then used to offset any Performance Adjustments in the following Contract Year. The Performance Bonus Points shall not in any event become a cash alternative and in the event of termination or expiry of this Agreement during a year in which Performance Bonus Points have been accrued, those points shall be disregarded in any relevant termination payment or upon expiry in accordance with this Agreement.]

Performance Adjustments

In each Contract Month, Monthly Performance Adjustments relating to Non-rectified Performance Failures at [the/ each] Facility shall be calculated according to Performance Adjustment Points allocated in accordance with the table below:

| PERFORMANCE ADJUSTMENT POINTS (calculated on a Contract Month basis as per the Worked Example) | MONTHLY PERFORMANCE ADJUSTMENT (Indexed) (calculated on a Contract Month basis as per the Worked Example) |
| --- | --- |
| Up to [5] points | No adjustment |
| 6-10 points | [£x] |
| 11-20 points | [£x] |
| 21-30 points | [£x] |
| 31-40 points | [£x] |
| 41-50 points | [£x] |
| 51-75 points | [£x] |
| 76-100 points | [£x] |
| More than 100 points | [£x] plus [£x] for each additional point over 100 points |

[The Performance Adjustments Points (PAP) for a Contract Month shall be calculated as follows:

PAP = TPAP [– PBP/12]

Where:

TPAP = the total Performance Adjustment Points accrued for the relevant Contract Month before applying Performance Bonus Points;

PBP/12 = Performance Bonus Points for the previous Contract Year divided by twelve (12) (to represent a monthly amount of bonus points).]

[The  Performance Adjustment Points cannot be negative therefore in the event that Performance Bonus Points outweigh the total Performance Adjustment Points for the relevant Contract Month then the Performance Adjustment Points for that Contract Month shall be zero.]

Worked Examples are attached at Appendix B.

Monthly Performance Adjustments calculated pursuant to paragraph 8.1 [and paragraph 8.2] above are agreed to be a genuine pre-estimate of the Authority's loss and damage in relation to the subject matter thereof and shall:

where the Annual Payment is a Surplus Annual Payment, be paid at the same time as the Monthly Payment for the Contract Month next following the Contract Month in respect of which the Monthly Performance Adjustments apply; or

where the Annual Payment is a Deficit Annual Payment, be deducted from the calculation of the Monthly Payment for the Contract Month next following the Contract Month in respect of which the Monthly Performance Adjustments apply.

Failure to achieve the Annual Performance Standards may result in a fixed Annual Performance Adjustment in respect of [the/each] Facility as follows[]:

| Failure to achieve Annual Performance Standard as required in Appendix A | Annual Performance Adjustment per Contract Year [per Facility] (subject to paragraphs 8.8.and 8.9 |
| --- | --- |
| Authority's Outcomes | [£x] in relation to each agreed Authority Outcome provided that the Annual Performance Adjustment shall not exceed [£x] per Contract Year per Facility for failure to achieve the Authority's Outcomes Annual Performance Standard. |
| Quality Management Accreditation | [£x] |
| Participation Targets sub divided pro rata as set out in paragraph 8.8 | [£x] subject to paragraph 8.8 |
| Sport England National Benchmarking Service | [£x] or the cost of carrying out the National Benchmarking Service, whichever is the higher |
| [Inclusive Fitness Initiative] | [£x] |
| [other] | [£x] |

With regard to the Participation Targets Annual Performance Standard the fixed Annual Performance Adjustment will be sub-divided and allocated equally across the target groups with achievement of the Participation Targets Annual Performance Standard being assessed on a target group by target group basis.

With regard to the Sport England National Benchmarking Service Annual Performance Standard, the fixed Annual Performance Adjustment shall be the greater of the Annual Performance Adjustment relating to an Annual Performance Standard for the Facility or the cost of carrying out the National Benchmarking Service.

If the Annual Performance Standard that the Contractor has failed to achieve is subsequently achieved within the first six (6) months of the following Contract Year, the fixed Annual Performance Adjustment for the Annual Performance Failure (excluding the Participation Targets Annual Performance Standard) shall be pro-rated to only take into account the number of Contract Months of the Annual Performance Failure.

[Should the same Annual Performance Failure in respect of the same Facility continue for two consecutive Contract Years then the value of the fixed Annual Performance Adjustment for such Annual Performance Failure shall be multiplied by two (2) for all subsequent Contract Years or pro rata for part thereof until the relevant Annual Performance Standard has been achieved.]

For the avoidance of doubt, any breach which may be capable of being the subject of Performance Adjustments or the allocation of Performance Adjustment Points but do not give rise to Performance Adjustments or the allocation of Performance Adjustment Points because it is rectified or in respect of which relief is granted in accordance with this Agreement, or such Performance Adjustment or Performance Adjustment Points do not apply as permitted in this Schedule 6, shall not, for the purposes of clause 40 (Persistent Breach) of this Agreement be regarded as a Persistent Breach.

Excusing Causes

Provided that;

there has been no negligence, default or breach of this Agreement by the Contractor or any Contractor Related Party which has caused the Performance Failure;

the effect of such Excusing Cause is claimed within ten (10) Business Days of the date on which the Contractor became aware of such circumstance; and

the Excusing Cause has been the direct cause of the failure by the Contractor to perform in accordance with the required Performance Standards; then

Performance Adjustment Points and Performance Adjustments shall not be applied in the circumstances set out below and the Contractor shall be entitled to such relief from obligations as is reasonable:

- where the Performance Failure has been caused by a breach by the Authority or any Authority Related Party, of the performance of the Authority's obligations under this Agreement;

- where the Performance Failure has been caused by the proper carrying out and putting into effect of the Change Protocol;

- where the Authority's Representative has notified the Contractor in writing that a particular activity or particular activities to be performed pursuant to the Services Specification should cease to be performed as a direct result of which a Performance Failure occurs;

- where the Annual Performance Failure occurs as a consequence of a failure by an external Quest accreditor (to the extent not caused by an act or omission of the Contractor or a Contractor Related Party) to:

i) assess the relevant Facility within six (6) months of an initial application;

ii) award accreditation within three (3) months of assessment where such assessment was subsequently determined to be successful; or

iii) reassess the relevant Facility within six (6) months of a reapplication, following a failed assessment

if, following assessment, the Contractor successfully achieves Quest accreditation.

For the avoidance of doubt, this Excusing Cause will apply from the date of the application, assessment or reapplication referred to in paragraph (i), (ii) or (iii) above to the date that the relevant assessment award or reassessment occurs;

- upon the happening of a Force Majeure Event;

- where the Performance Failure occurs as a consequence of step-in by the Authority pursuant to Clause 58 (Authority Step-In);

- where the Performance Failure is a result of the proper implementation of Programmed Maintenance in accordance with the relevant Schedule of Programmed Maintenance or other such maintenance pre-agreed with the Authority;

- [where in respect of existing facilities a Facility Performance Failure occurs relating to a failure to meet a Performance Standard set out in the Zone Data Sheets if, [within the first 12 months following the [Commencement Date/Services Availability Date]], the Contractor is able to demonstrate to the satisfaction of the Authority (the Authority acting reasonably) that the requisite Performance Standard set out in the Zone Data Sheets cannot reasonably be met because of an inaccuracy in the relevant Zone Data Sheet or given the design and build of the Facility [(other than in respect of the Works)] or an inherent defect in the existing building systems [(other than those forming part of the Works)] and the relevant Zone Data Sheet has been amended accordingly (both parties acting reasonably as regards any such amendment)];

- any Facility Performance Failure or Service Performance Failure in the External Areas or inability to obtain access to a Facility, or any Performance Failure due to there not being sufficient minimum levels of staff required to satisfy health and safety requirements at a Facility due to extreme adverse snow, ice, storm or flooding ("Adverse Conditions") provided that the Contractor has taken all reasonable measures to mitigate the effects of such Adverse Conditions; and

- where the Performance Failure occurs as a consequence of the proper carrying out by the Contractor of the Authority's instructions on the occurrence of an Emergency pursuant to Clause 25 (Emergencies ).

The Contractor shall use all reasonable endeavours to mitigate the consequences of an Excusing Cause on the Contractor's ability to perform its obligations under this Agreement. To the extent that the Contractor does not use all such reasonable endeavours, the Contractor shall not be entitled to, and shall not receive the relief specified in paragraph 9.1 above and Performance Adjustment Points and/or Performance Adjustments will still accrue.

[During the Bedding-In Period, any failure to meet the Facility Performance Standards relating to pool water, internal temperature levels, lux levels, ventilation levels or any other element of the building fabric or systems shall not lead to a Facility Performance Failure in the affected Zone(s) during such period.]

Monitoring and Reporting

The Contractor shall monitor and maintain records of its performance against the Performance Standards.

The Authority and Users shall be entitled to report any Facility Performance Failures or Service Performance Failures to the Contractor.

The Duty Manager or his/her representative shall conduct a visual inspection and keep a log of such inspection of:

all Zones of [the/ each] Facility each Contract Day (to include before opening [the/ each] Facility and between the hours of 1pm and 5pm); and

all Performance Standards which would not be derived from an inspection of the Zones at appropriate times given the nature of the Performance Standard.

For the avoidance of doubt, this visual inspection will not involve undertaking the measured inspections in line with the measured inspection regime table set out in paragraph 10.4 below.

The Contractor will implement and record the following measured inspections in-line with the measured inspection regime table below.

| Service Spec Reference | Parameter | Inspection Timeframe |
| --- | --- | --- |
| [1.27] | Water Temp. Shower | Monthly |
| [1.27] | Water Temp. (Hand washing) | Monthly |
| [1.29] | Air Changes per hour – Mechanical Ventilation | Quarterly, or where new fan system is installed. |
| [1.30] | Air Temperatures | Weekly |
| [1.30] | Humidity (Pool Hall) | Weekly |
| [1.30] | Humidity (Other Areas) | Monthly |
| [1.31] | Illuminance Values (lux levels) | Monthly |
| [1.31] | Uniformity ratio | Monthly |
| [1.31] | Colour rendering index | Monthly |
| [1.32] | Pool Water Temperature | Twice Daily |
| [1.32] | pH and Chlorine | Every 4 hours during opening hours |
| [1.32] | Alkalinity | Weekly |
| [1.32] | Calcium Hardness | Weekly |
| [1.32] | Total Dissolved Solids | Weekly |
| [1.32] | Sulphate | Weekly |

Notwithstanding paragraphs 10.3 and 10.4 above, where the Contractor has been notified of an alleged failure of a Facility Performance Standard by either a User, the Authority's Representative or where following a visual inspection it is suspected that a Facility Performance Failure has occurred, then the Facility Performance Standard will be measured as soon as possible and within an hour as a minimum.

Within 10 (ten) Business Days of the end of each Contract Month the Contractor shall submit a monthly Performance Monitoring Report to the Authority showing for the previous Contract Month each instance of a Non-rectified Performance Failure giving rise to Performance Adjustment Points and the Performance Adjustment to be applied in respect of that Contract Month.

The Performance Monitoring Report shall provide the Authority with all the information set out in paragraph [1.19] (Reporting) of the Services Specification including an Outcomes Progress Update and Outcomes Scorecard as set out at Appendix [6] of the Services Specification. The Contractor shall also assess performance against the Key Performance Indicators within Appendix [7] of the Services Specification and include a completed Key Performance Indicator assessment as an appendix to the Performance Monitoring Report on a quarterly basis. The link between the specification, monitoring system and reporting requirements is summarised in figure 1 below.

Subject to paragraph 10.9, if the Contractor has erroneously failed to report a Performance Failure against a Performance Standard (Reporting Failure), Performance Adjustment Points in relation to any Non-rectified Performance Failure that was not reported will be allocated and an additional set of Performance Adjustment Points shall be applied equating to a further Non-rectified Performance Failure with a Low Priority Rating.

If the Contractor has wilfully and deliberately caused the non-reporting of a Non-rectified Performance Failure, double the Performance Adjustment Points in relation to such Non-rectified Performance Failure that was not reported will be allocated.

Review of the Payment and Performance Monitoring System

In consultation with the Contractor, the Authority at its discretion but acting reasonably, may undertake a full review of this Payment and Performance Monitoring System after the first six months of the [Services Period/Contract Period] and thereafter annually to include a review of Urgency Ratings, Priority Ratings, Rectification Periods, Performance Adjustment Points, Monthly Performance Adjustment levels and Annual Performance Adjustment levels.

Any amendments to this Payment and Performance Monitoring System must be agreed in writing by both the Authority and the Contractor or implemented through the Change Protocol as an Authority Change.

Figure 1: Link between the specification, monitoring system and reporting requirements

Appendix A – Performance Standards,

Priority Ratings and Urgency Ratings

APPENDIX A

PERFORMANCE STANDARDS, PRIORITY RATINGS AND URGENCY RATINGS

To be read in conjunction with the Services Specification and Zone Data Sheets.

| Services Specification Reference | Performance Standard | Priority Rating | Urgency Rating | Refer to Zone Data Sheet for Priority Rating and Rectification Periods relating to specific requirements |
| --- | --- | --- | --- | --- |
| Annual Performance Standard |  |  |  |
| [Part 1B paragraph 1.5] | Authority's Outcomes The Annual Performance Standard is met if either a 'Green' or 'Amber' rating is achieved in relation to all the performance measures within the Outcomes Scorecard or the Contractor is able to demonstrate that they have met the agreed action plan relating to any 'Red' performance measures within the following six month period. | Fixed Annual Performance Adjustment |
| [Part 1B paragraph 1.6] | Quality Management Accreditation The Annual Performance Standard is met if Quality Management Accreditation (e.g. Quest) is maintained and the score awarded is within the top 25% of all facilities assessed nationally. Where Quest is used as the Quality Management Accreditation a banded score of 'Good' is awarded. | Fixed Annual Performance Adjustment |
| [Part 1B paragraph 1.7] | Participation Targets The Annual Performance Standard is met if either the targets are achieved or the Contractor is able to demonstrate that they have met the agreed annual Marketing Plan within the previous twelve month period. | Fixed Annual Performance Adjustment |
| [Part 1B paragraph 1.8] | Sport England National Benchmarking Service The Annual Performance Standard is met if either the targets are achieved or the Contractor is able to demonstrate that they have met the agreed NBS action plan within the previous twelve month period. | Fixed Annual Performance Adjustment |
| [Part 1B paragraph 1.9] | [Inclusive Fitness Initiative] | Fixed Annual Performance Adjustment |
| [Part 1B paragraph 1.10] | [To be inserted] | Fixed Annual Performance Adjustment |
| Service Performance Standard |  |  |  |
| [Part 1B paragraph 1.11] | Cleaning | [High – 5 points] | [High - 4 hours] |  |
| [Part 1C paragraph 1.12] | Environmental and Energy Management | [High – 5 points] | [Low – 1 week] |  |
| [Part 1C paragraph 1.13] | Customer Service | [High – 5 points] | [Low – 1 week] |  |
| [Part 1C paragraph 1.14] | Catering and Vending | [High – 5 points] | [High - 4 hours] |  |
| [Part 1C paragraph 1.15] | IT Systems | [High – 5 points] | [Medium - 24 hours] |  |
| [Part 1C paragraph 1.16] | Maintenance of Buildings, Plant and Equipment | [High – 5 points] | [Low – 1 week] |  |
| [Part 1C paragraph 1.17] | [Grounds Maintenance] | [High – 5 points] | [Medium - 24 hours] |  |
| [Part 1C paragraph 1.18] | [Event Management] | [High – 5 points] | [High - 4 hours] |  |
| [Part 1C paragraph 1.19] | Reporting |  |  |  |
|  | - Sports & Activity Development Plan | [Medium – 3 points] | [Low – 1 week] |  |
|  | - Marketing and Publicity | [Medium – 3 points] | [Low – 1 week] |  |
|  | - Major Incident Reporting | [High – 5 points] | [High - 4 hours] |  |
|  | - Other Reporting | [Medium – 3 points] | [Low – 1 week] |  |
| Facility Performance Standard |  |  |  |
| [Part 1D paragraph 1.20] | Pricing Requirements | [High – 5 points] | [High - 4 hours] |  |
| [Part 1D paragraph 1.21] | Opening Hours | [High – 5 points] | [High - 4 hours] |  |
| [Part 1D paragraph 1.22] | Activity Programming | [Medium – 3 points] | [Medium - 24 hours] | Yes |
| [Part 1D paragraph 1.23] | Health and Safety Management | [Very High – 10 points] | [Very High - 1 hour] |  |
| [Part 1D paragraph 1.24] | Equipment | [Medium – 3 points] | [Medium - 24 hours] | Yes |
| [Part 1D paragraph 1.25] | Access | [High – 5 points] | [High - 4 hours] | Yes |
| [Part 1D paragraph 1.26] | Legislation and Policy | [Medium – 3 points] | [Medium - 24 hours] | Yes |
| [Part 1D paragraph 1.27] | Water (Hot and Cold) Installations | [High – 5 points] | [High - 4 hours] | Yes |
| [Part 1D paragraph 1.28] | Drainage | [Medium – 3 points] | [Medium - 24 hours] | Yes |
| [Part 1D paragraph 1.29] | Ventilation | [High – 5 points] | [High - 4 hours] | Yes |
| [Part 1D paragraph 1.30] | Heating (Thermal Comfort) | [High – 5 points] | [High - 4 hours] | Yes |
| [Part 1D paragraph 1.31] | Lighting | [High – 5 points] | [High - 4 hours] | Yes |
| [Part 1D paragraph 1.32] | Pool Water Quality | [High – 5 points] | [High – 4 hours] | Yes |
| [Part 1D paragraph 1.33] | CCTV & Security | [High – 5 points] | [High - 4 hours] | Yes |
| [Part 1D paragraph 1.34] | Staffing | [High – 5 points] | [High - 4 hours] | Yes |

Appendix B – Worked Examples

- Facility Performance Failure

The lights are not working over one of the badminton courts in the sports hall at [X Facility] when the Duty Manager completes their morning inspection of the Facility. The lights are still not fixed later in the afternoon when the local badminton club has a training session.

On the same Contract Day a customer reports that four of the treadmills, four steppers and two bikes are broken in the gym at [Y Facility]. They reported it yesterday as well and they are still not fixed. When the Duty Manager goes to look they also notice a pool of water on the floor by the entrance to the gym. It is dealt with within 75 minutes.

Badminton Court Lighting Failure:

Facility Performance Failure: Lighting (Services Specification Part 1D and Sports Hall Zone Data Sheet)

Priority Rating = [High] (Appendix A)

Rectification Period = [4 hours] (in accordance with the Sports Hall Zone Data Sheet and its Urgency Rating set out in Appendix A)

Assuming that the Facility Performance Failure is not Rectified within [four hours] of logging.

Performance Adjustment Points for failure to Rectify = [5] points

Equipment Failure:

Failure of Facility Performance Failure: Equipment (Services Specification Part 1D and Fitness Gym Zone Data Sheet that requires [90%] of equipment to be available = [81 of the 90] station gym)

Priority Rating = [Medium] (Appendix A)

Rectification Period = [24 hours] (in accordance with the Fitness Gym Zone Data Sheet and its Urgency Rating set out in Appendix A)

Assuming that the Facility Performance Failure has not been Rectified within [24 hours] of logging

Performance Adjustment Points for failure to Rectify = [3] points

Pool of Water

Facility Performance Failure: Health and Safety Management (Services Specification Part 1D)

Priority Rating = [Very High] (Appendix A)

Rectification Period = [1 hour] (in accordance with Appendix A)

The Performance Failure takes 75 minutes to Rectify

Performance Adjustment Points for failure to Rectify = [10] points

Total Performance Adjustment Points in Contract Day = [18] points

Monthly Performance Adjustment = [£1,000]

Service Performance Failure

On Monday morning, the quarterly sports & activity development plan update report was due to be submitted to the Authority in line with the reporting requirements set out in the Services Specification. The report is submitted a week later on the Tuesday afternoon.

Service Performance Failure - Reporting (Services Specification Part 1C)

Priority Rating = [Medium] (Appendix A)

Rectification Period = [1 week] (in accordance with Appendix A)

Total Performance Adjustment Points for failure to Rectify = [3] points x 9 Contract Days = [27] points

Monthly Performance Adjustment = [£2,000]

Annual Performance Failure

The Contractor fails to achieve Quest re-assessment at [X Facility].

Annual Performance Failure – Quality Management Accreditation (Services Specification Part 1B)

Fixed Annual Performance Adjustment = [£60,000]

Annual Performance Adjustment = [£60,000]

An adjustment of [£5,000] shall be made in each Contract Month during the following Contract Year.

[Performance Bonus Points

The Contractor has over-performed against the Authority’s Outcomes with more than 75% ‘Green’ outcomes as measured by the Outcomes Scorecard. This equates to [50] Performance Bonus Points.

Net Monthly Payment in the second Contract Month following the end of a Contract Year

Total Performance Adjustment Points (TPAP) = [45] (18 points relating to the Facility Performance Failures set out above plus 27 points relating to the Service Performance Failure set out above) accrued for the relevant Contract Month (assuming the Facility Performance Failure and Service Performance Failure set out above occur over the preceding Contract Month)

PAP = TPAP [-PBP/12]

Performance Adjustment Points (PAP ) = [45] – [50]/ 12 = [40.8]

Monthly Performance Adjustment = [£4,000] (based on [40.8] Performance Adjustment Points)

Annual Performance Adjustment (APA) = [£5,000] in each Contract Month assuming the Annual Performance Adjustment set out above occurs in the previous Contract Year.

TPA = MPA + APA/12

Total Performance Adjustment = [£4,000] + [£5,000] = [£9,000]]

Option B – default notice system

PERFORMANCE MONITORING SYSTEM

CONTENTS

Definitions

- Introduction

- Performance Standards and Performance Failures

- Rectification Periods

- Performance Failure Notices

- Excusing Causes

- Monitoring and Reporting

- Review of the Payment and Performance Monitoring System

Appendix A - Performance Standards, Priority Ratings and Urgency Weightings

Definitions

The terms and expressions used in this Schedule shall have the same meaning as set out in clause 1 (Definitions and Interpretation) of this Agreement. In addition, the following words and expressions shall have the meanings set out below:

Annual Performance Failure

means non satisfaction of one or more of the Annual Performance Standards;

Annual Performance Standard

means the Performance Standards set out in Part 1B of the Services Specification and listed as such in Appendix A to this Schedule;

Authority's Outcomes

means the Performance Standards as set out in paragraph [1.5] of Part 1B of the Services Specification;

[Bedding-In Period

means in relation to [X Facility], the period commencing on the [Services Availability Date] and expiring at midnight six (6) calendar months after such date;]

Contract Day

means a period commencing on the opening of [the/such] Facility to the public and ending on the closing of [the/such] Facility to the public, such period being no less than that set out in the Minimum Opening Hours;

[Contract Quarter

to be defined on a case by case basis, to meet the parties' requirements];

Default Notice

means a notice issued when a Service Performance Failure or Facility Performance Failure has not been Rectified within the Rectification Period or rescheduled Rectification Period pursuant to paragraph 3.5, 3.5A and/or 3.6;

Duty Manager

means the person or persons appointed as such by the Contractor for managing the Facilities;

Excusing Cause

means the specific circumstances in which the Contractor is entitled to relief from and may not be served with a Remedy Notice, Default Notice or Warning Notice in accordance with paragraph 5 of this Schedule;

External Areas

means all access roads, hard standing, footpaths, car park areas and entrances external pitches and courts comprised in or serving the Facility;

Facility Performance Failure

means non satisfaction of one or more of the Facility Performance Standards;

Facility Performance Standard

means the Performance Standards for each Zone as set out in Part 1D and Appendix 4 (Zone Data Sheets) of the Services Specification and listed as such in Appendix A to this Schedule;

Help Desk

means the entrance area and reception made available by the Contractor at the relevant [Facility/Facilities] in accordance with Part 1B of the Services Specification;

Monthly Performance Failure

means either a Facility Performance Failure or Service Performance Failure;

National Benchmarking Service

means the benchmarking service managed by Sport England that is a partnership approach to providing critical data on the performance of leisure facilities;

Notices

means either a Remedy Notice, Default Notice or Warning Notice;

Outcomes Scorecard

means the annual scorecard developed between both parties for the measurement of the Contractor's performance against the Authority's Outcomes in accordance with paragraph [1.5] of Part 1B of the Services Specification;

Participation Targets Annual Performance Standard

means those targets as set out in Part 1B, paragraph [1.7] of the Services Specification or as agreed between the parties;

Performance Failure

means any or all of a Facility Performance Failure, Service Performance Failure or an Annual Performance Failure as described in paragraph 2.3 of this Schedule;

Performance Monitoring Report

means the quarterly report to be compiled by the Contractor in accordance with paragraph 6 of this Schedule and detailing all Performance Failures in the previous Contract Quarter and appropriate Rectification Periods or Rectification Periods rescheduled pursuant to paragraphs 3.5, 3.5A or 3.6 of this Schedule;

Performance Standard

means the performance standards set out in detail within the Services Specification and summarised in Appendix A to this Schedule and divided into the following categories:

(a)	Facility Performance Standards;

(b)	Service Performance Standards; and

(c)	Annual Performance Standards;

Rectification

means, subject to paragraph 3.4, making good a Service Performance Failure or a Facility Performance Failure so that the subject matter of such Service Performance Failure or a Facility Performance Failure complies with the levels of Service required pursuant to this Agreement and shall without prejudice to the generality of the foregoing include:

(a)	restoring all functional capability necessary to meet the Facility Performance Standard or Service Performance Standard;

(b)	ensuring that any Zone which has been affected by the relevant Facility Performance Failure complies with the Facility Performance Standards; and

(c)	(if applicable) complying with and making good the Monthly Performance Failure in accordance with Legislation and, where in relation to a matter there is no express obligation or standard imposed on the Contractor under this Agreement, in accordance with Good Industry Practice;

or as the context so requires where paragraph 3.4 applies, "Rectification" shall mean taking all necessary actions to make the affected area safe and "Rectify" and "Rectified" shall be construed accordingly;

Rectification Period

means, subject to extension in accordance with paragraphs 3.5, 3.5A and/or 3.6 of this Schedule, the time period set out in Appendix A in respect of the relevant Monthly Performance Failure or if not set out therein, the time period set out in paragraph 3.4 of this Schedule within which Rectification of the relevant Monthly Performance Failure must be completed;

Remedy Notice

means a notice that is issued by the Authority upon discovery of a Services Performance Failure or a Facility Performance Failure;

Service Performance Failure

means non satisfaction of one or more of the Service Performance Standards;

Service Performance Standard

means the Performance Standards set out in [Part 1C of the Services Specification] and listed as such in Appendix A to this Schedule;

Sport England National Benchmarking Service Annual Performance Standard

means those targets as set out in [Part 1B, paragraph 1.8 of the Services Specification] or as agreed between the parties;

Urgency Rating

means a Very High Urgency Rating, High Urgency Rating, Medium Urgency Rating or Low Urgency Rating, as appropriate, as determined in accordance with paragraph 3.4 and Appendix A of this Schedule;

Warning Notice

means a notice that is issued by the Authority under paragraphs 4.5 or 4.7

Zone

means an area of the Facility as identified in the Services Specification.

Zone Data Sheets

means those data sheets in respect of each Zone as provided in Appendix 4 of the Services Specification.

- Introduction

The Services Specification provides details of the Authority's requirements for the Services and set out the Performance Standards in respect of the various elements of the Services.

The Services Specification is largely output-based and the Authority is keen to work in close partnership with the Contractor to ensure that the outcomes it requires from the Services are met and continuous improvement is achieved throughout the [Services Period/Contract Period].

To facilitate this aim, the Authority wishes to adopt a performance monitoring system that is both effective in helping to achieve the desired outcomes and efficient to operate.

Under this Performance Monitoring System, notices will be issued when the Authority discovers a failure to achieve the required Performance Standards either by discovery of the failure itself or through a User or by the Performance Monitoring Report.

The Authority has taken care to ensure that as far as possible there are simple methods for measurement of the Performance Standards and that the reporting requirements and reporting frequency are not overly onerous.

In this way and through working together with the Contractor in a positive partnership, the Authority's intention is that this Performance Monitoring System will provide reasonable and prudent checks while focusing on demonstrating key performance indicators that confirm a high quality of service is being delivered and measuring the contribution of the Services to the Authority's Outcomes.

Applied effectively monitoring can be an important tool in demonstrating real service quality and recognising the wider benefits of service provision.

It should however be noted that the accumulation of Warning Notices for failure to achieve the required Performance Standards may lead to termination of this Agreement, subject to, and in accordance with the provisions of this Agreement.

Performance Standards and Performance Failures

The Performance Standards are set out in detail within the Services Specification and summarised within the attached Appendix A.

The Performance Standards have been divided into three separate categories, namely:

Annual Performance Standards

Facility Performance Standards

Service Performance Standards.

A Performance Failure shall have occurred where the Contractor fails to meet the requirements of any of these Performance Standards.

Rectification Periods

Where a Monthly Performance Failure has occurred, the Contractor shall be allowed a Rectification Period in which to rectify that Monthly Performance Failure.

For the avoidance of doubt, the Contractor shall not be entitled to a Rectification Period for an Annual Performance Failure.

When the Contractor or its’ staff becomes aware of a Facility Performance Failure or a Service Performance Failure it shall notify the Help Desk within the time periods specified in the table below:

|  | PERFORMANCE FAILURE | NOTIFICATION REQUIREMENT |
| --- | --- | --- |
| (1) | A Facility Performance Failure or a Service Performance Failure involving a risk to health and safety or a potential breach of Legislation or a potential threat of injury to persons or damage to property | Immediate notification |
| (2) | Subject to (1) above, a Facility Performance Failure or Service Performance Failure which occurs in a Zone which is being used for a programmed activity which is being supervised or carried out by a staff member (including lifeguards) and such supervision prevents that staff member from giving immediate notification of the failure | Notification at the end of the activity, or when the staff member is relieved of such supervision provided this is not a Very High Urgency Rating (in which case immediate notification is required) |
| (3) | Subject to (1) above, a Facility Performance Failure or a Service Performance Failure which is identified by a staff member during the Duty Manager's inspection in accordance with paragraph 6.3 of this Schedule | Within 1 hour of the end of the Duty Manager's inspection |
| (4) | Subject to (1) above, a Facility Performance Failure or Service Performance Failure which is reported to or identified by a staff member outside of a programmed activity or an inspection | Prompt notification with regard to operational circumstances |

The Rectification Period will run from the time the failure is logged at the Help Desk and will vary according to the Urgency Rating of the Facility Performance Failure or Service Performance Failure. Unless stated in the relevant Zone Data Sheet or in Appendix A, Rectification Periods are as follows:

| URGENCY RATING | RECTIFICATION PERIOD |
| --- | --- |
| Very High | [1 hour] |
| High | [4/6 hours] Hours] |
| Medium | [24/48] hours |
| Low | [1 week] |

In circumstances of a Monthly Performance Failure where a Very High Urgency Rating or High Urgency Rating applies, provided the Contractor has effected temporary rectification by taking all necessary actions to make the affected area safe, the Rectification Period for effecting permanent rectification within the meaning set out in the definition of Rectification paragraphs (a) to (c) shall, subject as may be extended pursuant to paragraphs 3.5, 3.5A or 3.6 of this Schedule, be the same period as for a Monthly Performance Failure with a Medium Urgency Rating.

The Rectification Period shall be extended to be included in the next period of planned preventative maintenance in accordance with the Schedule of Programmed Maintenance or at such other time or by such period as is reasonable if the Contractor can demonstrate to the Authority's satisfaction (the Authority acting reasonably) that:

the activity required to achieve Rectification is better carried out at that time; or

a part which is necessary to achieve Rectification is not in stock and it can be demonstrated that failure to have the necessary part in stock is in line with Good Industry Practice; or

the circumstances of the Monthly Performance Failure are such that Rectification within the scheduled Rectification Period cannot reasonably be achieved by the Contractor acting in accordance with Good Industry Practice or in accordance with its obligations under this Agreement.

3.5A	Without prejudice to Relief Events and the operation of Clause 55 (Relief Events) of the Agreement, if a Performance Failure occurs due to failure by a utility supplier to supply utilities to a Facility through no fault of the Contractor [or the [Leisure Operator], the Rectification Period shall be increased to seven (7) days and those Rectification Periods specified in or in Appendix A or in the table at paragraph 3.4 above shall not apply in such circumstances. Should the failure by a utility supplier to supply utilities to a Facility through no fault of the Contractor [or the [Leisure Operator] continue for a period in excess of seven (7) days then the Contractor shall be entitled to apply for rescheduled Rectification pursuant to paragraph 3.6 below.

If the Contractor wishes to extend the Rectification Period, the Contractor shall apply to the Authority in writing requesting an extension of the Rectification Period and setting out the reasons for the request, an explanation of any steps already taken to resolve the failure and the proposed approach to seeking to avoid a similar situation arising in the future. Subject as set out below, the Rectification Period shall only be extended with the written consent of the Authority's Representative, such consent not to be unreasonably withheld provided that where a Monthly Performance Failure occurs on a Contract Day other than a Business Day and the Contractor is not able to obtain Authority consent having taken reasonable endeavours to contact the Authority's Representative or other nominated officer on out of office hours contact numbers provided to the Contractor, the Rectification Period will commence at the start of next Business Day. The Authority shall act in a reasonable and proportionate manner having regard to the circumstances arising. The Authority's Representative shall be entitled to withhold consent if there is a continuing contravention of Legislation or if there is a risk of death, personal injury or damage to the Facility provided that if Rectification cannot be completed within the applicable Rectification Period for any of the reasons set out in paragraph 3.5, the Contractor shall take all measures to temporarily rectify or make safe the area affected and the Authority shall nevertheless, acting reasonably, give all due consideration to the request for the extended period to enable the Contractor to permanently Rectify the circumstances or event giving rise to such Monthly Performance Failure.

Performance Failure Notices

For the purpose of managing the contract and monitoring performance, each Zone of [the/ each] Facility shall be treated as a single operation. For example a cleaning failure in two of the Zones in the same Contract Day would lead to two Service Performance Failures. Where two different Facility Performance Failures or Service Performance Failures arising out of the same event or circumstances occur in the same Zone [in the same Facility] in the same Contract Day, (“Originating Event”) a Remedy Notice for each Facility Performance Failure or Service Performance Failure arising out of that Originating Event may be issued, provided that:

if the Originating Event has not been Rectified within the relevant Rectification Period for the Monthly Performance Failure comprised in the Originating Event with the highest Urgency Rating set out in Appendix A (as such period may be extended in accordance with paragraphs 3.5, 3.5A and/or 3.6 of this Schedule) then the Authority may only issue one Default Notice in respect of that one Monthly Performance Failure resulting from that Originating Event; and

once the Originating Event has been Rectified but any consequent Facility Performance Failures or Service Performance Failures the subject of a Remedy Notice referred to above have not been Rectified within the relevant Rectification Period (as such period may be extended in accordance with paragraphs 3.5, 3.5A and/or 3.6 of this Schedule), then the Authority may issue Default Notices in respect of each such non -rectified Facility Performance Failure or Service Performance Failure.

A Remedy Notice may be issued by the Authority to the Contractor where a Facility Performance Failure or a Service Performance Failure has been discovered by or reported to the Authority.

Where Remedy Notices are issued these shall be logged at the Help Desk and categorised in accordance with paragraph 3.4.

A Default Notice may be issued by the Authority to the Contractor in the following circumstances:

where a Remedy Notice has been issued and the Monthly Performance Failure the subject of the Remedy Notice has not been Rectified within the allowed Rectification Period (as the same may be extended pursuant to paragraphs 3.5, 3.5A and/or 3.6 of this Schedule);

where a Performance Monitoring Report identifies that a Service Performance Failure or a Facility Performance Failure was not Rectified within the allowed Rectification Period (as the same may be extended pursuant to paragraphs 3.5, 3.5A and/or 3.6 of this Schedule).

Should the same Monthly Performance Failure the subject of a Default Notice issued under paragraph 4.4.1 continue beyond seven (7) Contract Days from the date of the expiry of the relevant Rectification Period (as the same may be extended pursuant to paragraphs 3.5, 3.5A and/or 3.6 of this Schedule), then a Warning Notice may be issued by the Authority.

Should the same Monthly Performance Failure the subject of the Warning Notice issued under paragraph 4.5 continue beyond fourteen (14) Contract Days from the date of the expiry of the relevant Rectification Period (as the same may be extended pursuant to paragraphs 3.5, 3.5A and/or 3.6 of this Schedule), then a further Warning Notice may be issued and further Warning Notices may be issued at the expiry of each subsequent period of fourteen (14) Contract Days until such Monthly Performance Failure is Rectified.

Where a Default Notice is issued under paragraph 4.4.2 because a Performance Monitoring Report identifies that a Service Performance Failure or Facility Performance Failure has not been Rectified within the Rectification Period (as the same may be extended pursuant to paragraphs 3.5, 3.5A and/or 3.6 of this Schedule) and the same Monthly Performance Failure is reported in the next Performance Monitoring Report as never having been Rectified then the Authority may issue a Warning Notice.

Should the same Annual Performance Failure continue for two consecutive Contract Years then the Authority may issue a Warning Notice.

Warning Notices will be monitored each Contract Year and if [     ] or more Warning Notices are issued during a Contract Year is respect of non-rectified Monthly Performance Failures the Authority may consider terminating the Agreement under Clause 39.3 (Termination on Contractor Default).

Excusing Causes

Provided that:

there has been no negligence, default or breach of this Agreement by the Contractor or any Contractor Related Party which has caused the Performance Failure;

the effect of such Excusing Cause is claimed within ten (10) Business Days of the date on which the Contractor became aware of such circumstance; and

the Excusing Cause has been the direct cause of the failure by the Contractor to perform in accordance with the required Performance Standards; then

Remedy Notices, Default Notices or Warning Notices shall not be applied in the circumstances set out below and the Contractor shall be entitled to such relief from obligations as is reasonable:

      - where the Performance Failure has been caused by a breach by the Authority or any Authority Related Party, of the performance of the Authority's obligations under this Agreement;

      - where the Performance Failure has been caused by the proper carrying out and putting into effect of the Change Protocol;

      - where the Authority's Representative has notified the Contractor in writing that a particular activity or particular activities to be performed pursuant to the Services Specification should cease to be performed as a direct result of which a Performance Failure occurs;

      - where an Annual Performance Failure occurs as a consequence of a failure by an external Quest accreditor (to the extent not caused by an act or omission of the Contractor or a Contractor Related Party) to:

#### (i)	assess the relevant Facility within six (6) months of an initial application;

#### (ii)	award accreditation within three (3) months of assessment where such assessment was subsequently determined to be successful; or

#### (iii)	reassess the relevant Facility within six (6) months of a reapplication, following a failed assessment;

### if, following assessment, the Contractor successfully achieves Quest accreditation;

### For the avoidance of doubt, this Excusing Cause will apply from the date of the application, assessment or reapplication referred to in paragraph (i), (ii) or (iii) above to the date that the relevant assessment award or reassessment occurs;

      - upon the happening of a Force Majeure Event;

      - where the Performance Failure occurs as a consequence of step-in by the Authority pursuant to Clause 58 (Authority Step-In);

      - where the Facility Performance Failure or Service Performance Failure is a result of the proper implementation of Programmed Maintenance in accordance with the relevant Schedule of Programmed Maintenance or other such maintenance pre-agreed with the Authority;

      - [where in respect of existing facilities a Facility Performance Failure occurs relating to a failure to meet a Performance Standard set out in the Zone Data Sheets if, [within the first 12 months following the [Commencement Date/Services Availability Date]], the Contractor is able to demonstrate to the satisfaction of the Authority (the Authority acting reasonably) that the requisite Performance Standard set out in the Zone Data Sheets cannot reasonably be met because of an inaccuracy in the relevant Zone Data Sheet or given the design and build of the Facility [(other than in respect of the Works)] or an inherent defect in the existing building systems [(other than those forming part of the Works)] and the relevant Zone Data Sheet has been amended accordingly (both parties acting reasonably as regards any such amendment)]

      - any Facility Performance Failure or Service Performance Failure in the External Areas or inability to obtain access to a Facility, or any Performance Failure due to there not being sufficient minimum levels of staff required to satisfy health and safety requirements for the Facility due to extreme adverse snow, ice, storm or flooding ("Adverse Conditions") provided that the Contractor has taken all reasonable measures to mitigate the effects of such Adverse Conditions; and

      - where the Performance Failure occurs as a consequence of the proper carrying out by the Contractor of the Authority's instructions on the occurrence of an Emergency pursuant to Clause 25 (Emergencies).

The Contractor shall use all reasonable endeavours to mitigate the consequences of an Excusing Cause on the Contractor's ability to perform its obligations under this Agreement. To the extent that the Contractor does not use all such reasonable endeavours, Remedy Notices, Default Notices or Warning Notices may still be issued.

[During the Bedding-In Period, any failure to meet the Facility Performance Standards relating to pool water, internal temperature levels, ventilation levels or any other element of the building fabric or systems shall not lead to a Facility Performance Failure in the affected Zone(s) during such period].

Monitoring and Reporting

The Contractor shall monitor and maintain records of its performance against the Performance Standards.

The Authority and Users shall be entitled to report any Facility Performance Failures or Service Performance Failures to the Contractor.

The Duty Manager or his/her representative shall conduct a visual inspection and keep a log of such inspection of:

all Zones of [the/each] Facility each Contract Day (to include before opening [the/each] Facility and between the hours of 1pm and 5pm); and

all Performance Standards which would not be derived from an inspection of the Zones at appropriate times given the nature of the Performance Standard.

For the avoidance of doubt, this visual inspection will not involve undertaking the measured inspections in line with the measured inspection regime table set out in paragraph 6.4 below.

The Contractor will implement and record the following measured inspections in-line with the measured inspection regime table below.

| Service Spec Reference | Parameter | Inspection Timeframe |
| --- | --- | --- |
| [1.27] | Water Temp. Shower | Monthly |
| [1.27] | Water Temp. (Hand washing) | Monthly |
| [1.29] | Air Changes per hour – Mechanical Ventilation | Quarterly, or where new fan system is installed. |
| [1.30] | Air Temperatures | Weekly |
| [1.30] | Humidity (Pool Hall) | Weekly |
| [1.30] | Humidity (Other Areas) | Monthly |
| [1.31] | Illuminance Values (lux levels) | Monthly |
| [1.31] | Uniformity ratio | Monthly |
| [1.31] | Colour rendering index | Monthly |
| [1.32] | Pool Water Temperature | Twice Daily |
| [1.32] | pH and Chlorine | Every 4 hours during opening hours |
| [1.32] | Alkalinity | Weekly |
| [1.32] | Calcium Hardness | Weekly |
| [1.32] | Total Dissolved Solids | Weekly |
| [1.32] | Sulphate | Weekly |

Notwithstanding paragraphs 6.3 and 6.4 above, where the Contractor has been notified of an alleged failure of a Facility Performance Standard by either a User, the Authority's Representative or where following a visual inspection it is suspected that a Facility Performance Failure has occurred, then the Facility Performance Standard will be measured as soon as practicable and within an hour as a minimum.

Within 10 (ten) Business Days of the end of each Contract Quarter the Contractor shall submit a Performance Monitoring Report showing for the previous Contract Quarter each instance of a Monthly Performance Failure  and the time period in which the Monthly Performance Failure was Rectified.

The Performance Monitoring Report shall provide the Authority with all the information set out in paragraph [1.19] (Reporting) of the Services Specification. The Contractor shall also assess performance against the Key Performance Indicators within the attached Appendix [7] of the Services Specification and include a completed Key Performance Indicator assessment as an appendix to the Performance Monitoring Report on a quarterly basis. The link between the specification, monitoring system and reporting requirements is summarised in figure 1 below.

If the Contractor has wilfully or deliberately caused the non-reporting of a non-rectified Performance Failure, the Authority may issue a Default Notice.

Review of the Performance Monitoring System

In consultation with the Contractor, the Authority at its discretion but acting reasonably, may undertake a full review of this Performance Monitoring System after the first six months of the [Services Period/Contract Period] and thereafter annually to include a review of the Rectification Periods and time periods for the issuing of notices.

Any amendments to this Performance Monitoring System must be agreed in writing by both the Authority and the Contractor or implemented through the Change Protocol as an Authority Change.

Figure 1: Link between the specification, monitoring system and reporting requirements

## Appendix A – Performance Standards and Urgency Ratings

APPENDIX A

PERFORMANCE STANDARDS AND URGENCY RATINGS

To be read in conjunction with the Services Specification.

| Services Specification Reference | Performance Standard | Urgency Rating | Refer to Zone Data Sheet for Priority Rating and Rectification Periods relating to specific requirements |
| --- | --- | --- | --- |
| Annual Performance Standard |  |  |
| [Part 1B paragraph 1.5] | Authority's Outcomes The Annual Performance Standard is met if either a 'Green' or 'Amber' rating is achieved in relation to all the performance measures within the Outcomes Scorecard or the Contractor is able to demonstrate that they have met the agreed action plan relating to any 'Red' performance measures within the following six month period |  |
| [Part 1B paragraph 1.6] | Quality Management Accreditation The Annual Performance Standard is met if Quality Management Accreditation (e.g. Quest) is maintained and the score awarded is within the top 25% of all facilities assessed nationally. Where Quest is used as the Quality Management Accreditation a banded score of 'Good' is awarded |  |
| [Part 1B paragraph 1.7] | Participation Targets The Annual Performance Standard is met if either the targets are achieved or the Contractor is able to demonstrate that they have met the agreed annual Marketing Plan within the previous twelve month period |  |
| [Part 1B paragraph 1.8] | Sport England National Benchmarking Service The Annual Performance Standard is met if either the targets are achieved or the Contractor is able to demonstrate that they have met the agreed NBS action plan within the previous twelve month period |  |
| [Part 1B paragraph 1.9] | [Inclusive Fitness Initiative] |  |
| [Part 1B paragraph 1.10] | [To be inserted] |  |
| Service Performance Standard |  |  |
| [Part 1B paragraph 1.11] | Cleaning | [High – 4 hours] |  |
| [Part 1C paragraph 1.12] | Environmental and Energy Management | [Low – 1 week] |  |
| [Part 1C paragraph 1.13] | Customer Service | [Low – 1 week] |  |
| [Part 1C paragraph 1.14] | Catering and Vending | [High – 4 hours] |  |
| [Part 1C paragraph 1.15] | IT Systems | [Medium – 24 hours] |  |
| [Part 1C paragraph 1.16] | Maintenance of Buildings, Plant and Equipment | [Low – 1 week] |  |
| [Part 1C paragraph 1.17] | [Grounds Maintenance] | [Medium - 24 hours] |  |
| [Part 1C paragraph 1.18] | [Event Management] | [High – 4 hours] |  |
| [Part 1C paragraph 1.19] | Reporting – Sports & Activity Development Plan | [Low – 1 week] |  |
|  | – Marketing and Publicity | [Low – 1 week] |  |
|  | – Major Incident Reporting | [High – 4 hours] |  |
|  | – Other Reporting | [Low – 1 week] |  |
| Facility Performance Standard |  |  |
| [Part 1D paragraph 1.20] | Pricing Requirements | [High – 4 hours] | Yes |
| [Part 1D paragraph 1.21] | Opening Hours | [High – 4 hours] | Yes |
| [Part 1D paragraph 1.22] | Activity Programming | [Medium – 24 hours] | Yes |
| [Part 1D paragraph 1.23] | Health and Safety Management | [Very High – 1 hour] | Yes |
| [Part 1D paragraph 1.24] | Equipment | [Medium – 24 hours] | Yes |
| [Part 1D paragraph 1.25] | Access | [High – 4 hours] | Yes |
| [Part 1D paragraph 1.26] | Legislation and Policy | [Medium – 24 hours] | Yes |
| Part 1D paragraph 1.27 | Water (Hot and Cold) Installations | [High – 4 hours] | Yes |
| Part 1D paragraph 1.28 | Drainage | [Medium – 24 hours] | Yes |
| Part 1D paragraph 1.29 | Ventilation | [High – 4 hours] | Yes |
| Part 1D paragraph 1.30 | Heating (Thermal Comfort) | [High – 4 hours] | Yes |
| Part 1D paragraph 1.31 | Lighting | [High – 4 hours] | Yes |
| Part 1D paragraph 1.32 | Pool Water Quality | [High – 4 hours] | Yes |
| Part 1D paragraph 1.33 | CCTV & Security | [High – 4 hours] | Yes |
| Part 1D paragraph 1.34 | Staffing | [High – 4 hours] | Yes |

SCHEDULE 7

COLLATERAL WARRANTIES

SCHEDULE 7 – COLLATERAL WARRANTIES

Part 1

Warranty from the Contractor's Building Contractor

Dated 20 [CONTRACTOR'S BUILDING CONTRACTOR] (1) [AUTHORITY] (2) [CONTRACTOR] (3) DUTY OF CARE DEED relating to

THIS DEED is made on  						20

BETWEEN:

(1)	[CONTRACTOR'S BUILDING CONTRACTOR] (Company No.                 ), whose registered office is at                                                        (the Building Contractor);

(2)	[AUTHORITY] of                        (the Authority), which expression includes its permitted successors in title and assigns); and

(3)	CONTRACTOR (Company No.                 ), whose registered office is at                                    (the Contractor).

BACKGROUND

(A) 	By a design, build, operate and maintain agreement dated [                                   ] (the Agreement) the Authority has appointed the Contractor to carry out, in relation to the Site[s], the provision of serviced accommodation to the Authority at each and every Facility as contemplated by the Agreement including the carrying out of the Works and the provision of the Services and the design and construction of the Works.

(B)	By a design and build contract dated [                ] (the Building Contract) the Contractor has appointed the Building Contractor to carry out, in relation to the Site[s], the design and construction of the Works.

(C)	The Building Contractor is obliged under the Building Contract to give a warranty in this form in favour of the Authority.

(D)	The Building Contractor and the Contractor have agreed to execute this Deed in favour of the Authority.

- DEFINITIONS AND INTERPRETATIONS

Unless expressly defined otherwise in this Deed any defined term in this Deed shall have the same meaning given to such term in the Building Contract.

Intellectual Property Rights

any and all patents, trade marks, service marks, copyright, database rights, moral rights, rights in design, know how, confidential information and all or any other intellectual or industrial property rights whether or not registered or capable of registration and whether subsisting in the United Kingdom or any other part of the world together with all or any goodwill relating or attaching thereto which is created, brought into existence, acquired, used or intended to be used by the Building Contractor for the purpose of carrying out the Works;

Project Data

(i)	all drawings, reports, documents, plans, software, formulae, calculations and other data relating to the design, construction, testing or operation of the [Facility/Facilities] (as defined in the Agreement) in each case that is used by or on behalf of the Building Contractor in connection with the provision of the Works or the performance of the Building Contractor's obligations under the Building Contract; and

(ii)	any other materials, documents or data acquired or brought into existence or used in relation to the Works or the Building Contract by or on behalf of the Building Contractor in connection with the provision of the Works or the performance of the Building Contractor's obligations under the Building Contract.

OPERATIVE PROVISIONS

In consideration of the payment of one pound (£1.00) by the Authority to the Building Contractor, receipt of which the Building Contractor acknowledges:

BUILDING CONTRACTOR'S WARRANTY AND LIABILITY

The Building Contractor warrants to the Authority that it has carried out and will continue to carry out its duties under the Building Contract in accordance with the Building Contract and that it has exercised and will continue to exercise, in carrying out the design of the Works, the level of skill and care reasonably to be expected from an appropriately qualified and competent professional designer providing those services in relation to a project of a similar size and scope to the Works. In particular and without limiting the generality of the foregoing the Building Contractor covenants with the Authority that it has carried out and will carry out and complete the Works in accordance with the Building Contract and duly observe and perform all its duties and obligations thereunder;

The Building Contractor shall have no liability under clause 3.1 or clause 11 of this Deed that is greater or of longer duration than it would have had as if in lieu of this Deed the Authority had been a party to the Building Contract as joint employer and the Building Contractor shall be entitled in any action or proceedings by the Authority to raise equivalent rights in defence of liability (except for set off or counterclaim). Upon the expiration of twelve (12) years from the date of Services Availability in accordance with the Agreement, the liability of the Building Contractor under this Deed shall cease and determine, save in relation to any claims made by the Authority against the Building Contractor where proceedings have commenced prior to such date.

The Building Contractor shall have no liability to the Authority in respect of any delay in the completion of the Works howsoever caused save to the extent that the liability arises under the Building Contract and the Authority shall have exercised its right to step in under clause 10 of this Deed. Any claim in relation to a delay in completion of the Works but not otherwise will be extinguished to the extent that the Building Contractor has had deducted liquidated damages under the relevant clause of the Building Contract.

Nothing in this Deed shall entitle the Authority to exercise its rights under this clause 3 unless:

the Agreement (or the Contractor's employment under it) has been terminated; or, in the absence of such termination

the Contractor has not (either itself or through its supply chain (whether through the Building Contractor or an FM Contractor or otherwise)) satisfied the potential claim by the Authority under this clause 3, including addressing and/or remedying the matter or circumstance giving rise to such claim, within a reasonable time of such matter or circumstance arising,

provided that this clause 3.4 shall not apply where any delay in the exercise of the Authority's rights under Deed might otherwise lead to their becoming statute-barred.

INTELLECTUAL PROPERTY

The Building Contractor shall make available to the Authority free of charge (and hereby irrevocably licences the Authority to use) all Project Data that might reasonably be required by the Authority. The Building Contractor shall obtain all necessary licences, permissions and consents necessary for it to make the Project Data available to the Authority on these terms, for the purposes of:

the Authority using the Works for the provision of Services (as defined in the Agreement) and for ancillary purposes, its duties under the Agreement and/or any statutory duties that the Authority may have; and

following termination of the Agreement or of the Contractor's employment under it, the design or construction of the Works and/or the operation, maintenance or improvement of the Works,

(together, the Approved Purposes), and in this clause 4 "use" shall include the acts of copying, modifying, adapting and translating the material in question and/or incorporating them with other materials and the term "the right to use" shall be construed accordingly. The Authority will not hold the Building Contractor liable for any use it may make of the Project Data for any purpose other than the Approved Purposes.

The Building Contractor:

hereby grants to the Authority, free of charge, an irrevocable non-exclusive and transferable (subject to the restrictions continued in clause 7 of this Deed) licence to use the Intellectual Property Rights that are or become vested in the Building Contractor for the Approved Purposes; and

shall (where any Intellectual Property Rights are or become vested in a third party) use all reasonable endeavours to procure the grant of a like licence to that referred to in clause 4.2.1 to the Authority,

in both cases, solely for the Approved Purposes.

The Building Contractor warrants to the Authority that it has used the standard of skill, care and diligence as set out in clause 3.1 to see that the Project Data (save to the extent duly appointed sub-contractors have been used to prepare the same) are its own original work and that in any event their use in connection with the Works will not infringe the rights of any third party.

Where a claim or proceeding is made or brought against the Authority that arises out of the infringement of any Intellectual Property Rights or because the use of any materials, plant, machinery or equipment in connection with the Works infringes or the Works themselves infringe any Intellectual Property Rights of a third party then, unless such infringement has arisen out of the use of any Intellectual Property Rights by or on behalf of the Authority otherwise than in accordance with this Deed, the Building Contractor shall indemnify the Authority at all times from and against all Direct Losses and Indirect Losses (as defined in the Agreement) arising as a result of such claims and proceedings.

INSURANCE

The Building Contractor hereby covenants with the Authority to:

take out and maintain professional indemnity insurance cover with a limit of indemnity that shall be a minimum of [ten million pounds (£10,000,000)] either each and every loss or in the aggregate in relation to the Works (if in the aggregate then in any one (1) year of insurance a minimum of one (1) automatic reinstatement of the aggregate indemnity limit is required) (PI Insurance) and that it will maintain such insurance with reputable insurers carrying on business in the European Union from the date hereof until twelve (12) years after Services Availability pursuant to the Agreement, provided that such insurance is generally available in the market to design and build contractors at commercially reasonable rates and terms and provided further that payment of any increased or additional premiums or more onerous terms required by insurers by reason of the Building Contractor's own claims record or other acts, omissions, matters or things peculiar to the Building Contractor will be deemed to be within the commercially reasonable rates and terms;

provide evidence (as and when reasonably required by the Authority) satisfactory to the Authority of the PI Insurance being in full force and effect from the date of the Building Contract (such evidence to include details of the cover);

provide the Authority with notice of:

any cancellation of the PI Insurance not less than thirty (30) days prior to the relevant cancellation date; and

any adverse material change to or suspension of cover relevant to the Works not less than thirty (30) days prior to such relevant change or suspension;

inform the Authority as soon as reasonably practicable of any claim under the PI Insurance in respect of the Works in excess of one million pounds (£1,000,000) and provide such information to the Authority as the Authority may reasonably require in relation to such claim and provide notice of any potential breach of the aggregate limit of the policy; and

indemnify the Authority in respect of any subrogation claim by the insurers brought in connection with any claim made under the PI Insurance.

NOTICES

Any notice to be given by any party will be sufficiently served if sent by hand, by facsimile transmission or by post to the registered office or if there is none the last known address of the party to be served. Any notice sent by hand will be deemed to be served on the date of delivery and any notice sent by facsimile transmission will be deemed to be served in full at the time recorded on the facsimile report sheet, provided that if any notice sent by hand or facsimile is sent after 4.45 pm on any day it will be deemed to be served on the next Business Day. Any notice sent by post will be deemed to have been duly served at the expiration of forty-eight (48) hours after the time of posting if the end of that period falls before 4.45pm on a Business Day and otherwise on the next Business Day.

ASSIGNMENT

The benefit of and the rights of the Authority under this Deed may be assigned without the consent of the Building Contractor on two (2) occasions only and the Authority will notify the Building Contractor in writing following any such assignment specifying the name and address of the assignee and the date of the assignment. The Building Contractor will not contend that any such assignee is precluded from recovering any loss resulting from any breach of this Deed (whatever the date of such breach) by reason only that that person is an assignee and not the original beneficiary hereunder or by reason that the original beneficiary or any intermediate beneficiary escaped any loss resulting from such breach by reason of the disposal of any interest in the Site[s] or that the original beneficiary or any intermediate beneficiary has not suffered any, or as much, loss.

AUTHORITY'S REMEDIES

The rights and benefits conferred upon the Authority by this Deed are in addition to any other rights and remedies it may have against the Building Contractor including without prejudice to the generality of the foregoing any remedies in negligence.

INSPECTION OF PROJECT DATA

The Building Contractor's liabilities under this Deed will not be in any way reduced or extinguished by reason of any inspection or approval of the Project Data or attendance at site meetings or other enquiry or inspection which the Authority may make or procure to be made for its benefit or on its behalf.

STEP-IN RIGHTS IN FAVOUR OF THE AUTHORITY

The Building Contractor will not exercise or seek to exercise any right which may be or become available to it to terminate or treat as terminated or repudiated the Building Contract or its engagement under it or discontinue or suspend the performance of any duties or obligations thereunder without first giving to the Authority not less than twenty (20) Business Days' prior written (seven (7) days' prior written notice of suspension in the event of non-payment under the Building Contract) notice specifying the Building Contractor's ground for terminating or treating as terminated or repudiated the Building Contract or its engagement under it or discontinuing or suspending its performance thereof and stating the amount (if any) of monies outstanding under the Building Contract. Within such period of notice:

the Authority may give written notice to the Building Contractor that the Authority will thenceforth become the client under the Building Contract to the exclusion of the Contractor and thereupon the Building Contractor will admit that the Authority is its client under the Building Contract and the Building Contract will be and remain in full force and effect notwithstanding any of the said grounds;

if the Authority has given such notice as aforesaid or under clause 10.3, the Authority shall accept liability for the Contractor's obligations under the Building Contract and will as soon as practicable thereafter remedy any outstanding breach by the Contractor that properly has been included in the Building Contractor's specified grounds and which is capable of remedy by the Authority; and

if the Authority has given such notice as aforesaid or under clause 10.3, the Authority will from the service of such notice become responsible for all sums properly payable to the Building Contractor under the Building Contract accruing due after the service of such notice but the Authority will in paying such sums be entitled to the same rights of set-off and deduction as would have applied to the Contractor under the Building Contract.

Notwithstanding anything contained in this Deed and notwithstanding any payments which may be made by the Authority to the Building Contractor, the Authority will not be under any obligation to the Building Contractor nor will the Building Contractor have any claim or cause of action against the Authority unless and until the Authority has given written notice to the Building Contractor pursuant to clause 10.1.1 or clause 10.3 of this Deed.

The Building Contractor further covenants with the Authority that if the employment of the Contractor under the Agreement is terminated or if the Agreement is terminated by the Authority the Building Contractor, if requested by the Authority by notice in writing and subject to clause 10.1.2 and clause 10.1.3, will accept the instructions of the Authority to the exclusion of the Contractor in respect of its duties under the Building Contract upon the terms and conditions of the Building Contract and will if so requested in writing enter into a novation agreement in the form set out in Appendix 1 to this Deed whereby the Authority is substituted for the Contractor under the Building Contract.

If the Building Contractor is requested to enter into a novation agreement pursuant to clause 10.3, the Contractor agrees to enter into the same at the request of the Authority.

The Contractor acknowledges that the Building Contractor will be entitled to rely on a notice given to the Building Contractor by the Authority under clause 10.3 as conclusive evidence that the employment of the Contractor under the Agreement has been terminated or that the Agreement has been terminated.

The Authority may by notice in writing to the Building Contractor appoint another person to exercise its rights under this clause 10 subject to the Authority remaining liable to the Building Contractor as guarantor for its appointee in respect of its obligations under this Deed.

As from the date of service of notice under clauses 10.1.1 or 10.3 to the extent that the Building Contract operates by reference to the existence and application of the Agreement, the Building Contract shall be administered and construed as though the Agreement were continuing and the Building Contract shall therefore continue, subject to amendment only as necessary to reflect the fact that the Agreement may in fact have been terminated and the Authority has undertaken the obligations set out in clause 10.1.2.

Upon request by the Authority the Building Contractor agrees to co-operate with the Authority in determining the duties performed or to be performed by the Building Contractor and to provide a copy of the Building Contract and any variations thereto and details of all monies paid and due under the Building Contract.

STANDARDS OF PRODUCTS AND MATERIALS

The Building Contractor warrants that it has only used and will only use new materials in carrying out the Works unless the Authority agrees otherwise in writing or the contrary is set out in the Authority's Requirements (as defined in the Agreement)) and all goods used or included in the Works shall be of satisfactory quality, and the Building Contractor warrants that it has not used or included and will not use or include in the Works any of those products and materials listed in Schedule 9 (Prohibited Materials) of the Agreement nor any products or materials not in conformity with relevant British or European Union standards or codes of practice or which, at the time of use, are widely known to building contractors, contractors or members of the relevant design profession within the European Union to be deleterious to health and safety or to the durability of buildings and/or other structures and/or finishes and/or plant and machinery in the particular circumstances in which they are used.

SUB-CONTRACTORS

Following a written request from the Authority the Building Contractor will (unless it has already done so) and/ or procure that its Principal Building Sub-Contractors (as defined in the Agreement) and members of the Professional Team (as defined in the Agreement) each execute a deed of collateral warranty in the relevant form specified in the Building Contract in favour of any person in whose favour the Building Contract obliges the Building Contractor to give or procure the giving of such a warranty.

SEVERABILITY

If any term, condition or provision of this Deed shall be held to be invalid, unlawful or unenforceable to any extent, such term, condition or provision shall not affect the validity, legality and enforceability of the other provisions of or any other documents referred to in this Agreement.

WAIVER

No term or provision of this Deed shall be considered as waived by any party to this Deed unless a waiver is given in writing by that party.

No waiver under clause 14.1 shall be a waiver of a past or future default or breach, nor shall it amend, delete or add to the terms, conditions or provisions of this Deed unless (and only to the extent) expressly stated in that waiver.

THIRD PARTY RIGHTS

No term of this Deed is enforceable under the Contracts (Rights of Third Parties) Act 1999 by a person who is not party to this Deed. This clause 15 does not affect any right or remedy of any person that exists or is available otherwise than pursuant to that Act.

GOVERNING LAW AND JURISDICTION

This Deed and all non-contractual obligations in connection with this Deed shall be governed by and construed in all respects in accordance with the laws of England and Wales. The English Courts shall have exclusive jurisdiction to settle any disputes that may arise out of or in connection with this Deed.

CONTRACTOR ACKNOWLEDGEMENT

The Contractor has entered into this Deed in order to acknowledge the arrangements effected hereby and undertakes to each of the Authority and the Building Contractor to observe the provisions of this Deed at all times and not in any way to prejudice or affect the enforcement hereof or to do or permit to be done anything which would be a breach hereof.

COUNTERPARTS

This Deed may be executed in one or more counterparts. Any single counterpart or a set of counterparts executed, in either case, by all the parties shall constitute a full and original instrument for all purposes.

IN WITNESS of which this document is executed as a deed and is delivered on the date first set out above

| Executed as a deed, but not delivered until the first date specified on page 1, by BUILDING CONTRACTOR acting by a director in the presence of a witness: | )))) | Signature |  |
| --- | --- | --- | --- |
|  |  | Name (block capitals) |  |
|  |  |  | Director |
| Witness signature |  |  |
| Witness name |  |  |
| (block capitals) |  |  |
| Witness address |  |  |

| Executed as a deed, but not delivered until the first date specified on page 1, by CONTRACTOR acting by a director in the presence of a witness: | )))) | Signature |  |
| --- | --- | --- | --- |
|  |  | Name (block capitals) |  |
|  |  |  | Director |
| Witness signature |  |  |
| Witness name |  |  |
| (block capitals) |  |  |
| Witness address |  |  |

| Executed as a deed, but not delivered until the first date specified on page 1, by AUTHORITY acting by: | )))) |  |  |
| --- | --- | --- | --- |
| Authorised Signatory |  |  |  |
| Authorised Signatory |  |  |  |

Appendix 1

Form of Deed of Novation

THIS DEED is made on  						20

BETWEEN:

(1)	[CONTRACTOR'S BUILDING CONTRACTOR] (Company No.                 ), whose registered office is at                                                        (the Building Contractor);

(2)	[AUTHORITY] of                        (the Authority), which expression includes its permitted successors in title and assigns); and

(3)	[CONTRACTOR] (Company No.                 ), whose registered office is at                                    (the Contractor).

WHEREAS

(A)	By a design, build, operate and maintain agreement dated [                                   ] (the Agreement) the Authority has appointed the Contractor to carry out in relation to [		] (the Sites) the design and construction of the Works (as defined in the Agreement).

(B)	By a design and build contract dated [	] (the Building Contract) the Contractor has appointed the Building Contractor to carry out in relation to the Sites the design and construction of the Works.

(C)	[The employment of the Contractor under the Agreement has been terminated] [the Agreement has been terminated by the Authority].

(D)	The Contractor has transferred or agreed to transfer its interest in (or granted or agreed to grant a subordinate interest in) the Sites to the Authority.

(E)	The parties have agreed to novate the Building Contract to the Authority on the terms set out below.

IT IS AGREED

- Novation of Building Contract

The Building Contract is hereby novated from the Contractor and the Building Contractor to the Authority and the Building Contractor.

- Release of the Contractor

The Contractor shall no longer owe any duty or obligation to the Building Contractor under or in respect of the Building Contract whether by virtue of its terms or by virtue of any breach or otherwise.

- Release of the Building Contractor

The Building Contractor shall no longer owe any duty or obligation to the Contractor under or in respect of the Building Contract whether by virtue of its terms or by virtue of any breach or otherwise.

- Binding of the Building Contractor to the Authority

  - The Building Contractor binds itself to the Authority in the terms of the Building Contract as if the Authority were and always had been named in the Building Contract in place of the Contractor.

  - The Building Contractor warrants to the Authority that prior to the date of this Deed it has performed and that it will continue to perform its duties and obligations as required by and in accordance with the terms of the Building Contract.

  - The Authority shall not be precluded from recovering any losses incurred by the Authority or the Contractor resulting from any breach of clause 4.2 by reason that (if it be the case) the acts or omissions causing such breach occurred before this Deed took effect, or that the Contractor will not incur or has not or would not have incurred any such losses. No waiver by the Contractor, either express or implied, will affect the Building Contractor's liability to the Authority pursuant to this clause 4.

  - Upon the expiration of twelve (12) years from the date of completion of the Works in accordance with the Building Contract, the liability of the Building Contractor under this Deed shall cease and determine, save in relation to any claims made by the Authority against the Building Contractor and notified by the Authority to the Building Contractor in writing prior thereto.

- Binding of the Authority to the Building Contractor

The Authority binds itself to the Building Contractor in the terms of the Building Contract as if the Authority were and always had been named in the Building Contract in place of the Contractor and as if all acts and omissions of the Contractor (including any wrongful acts or omissions) under and in respect of the Building Contract were the acts and omissions of the Authority.

- Vesting of remedies in the Authority

All rights of action and remedies vested in the Contractor against the Building Contractor under and in respect of the Building Contract shall hereupon vest in the Authority.

- Vesting of remedies against the Authority

All rights of action and remedies vested in the Building Contractor against the Contractor under and in respect of the Building Contract shall hereinafter lie against the Authority.

- Amendment of the Building Contract

The Authority and the Building Contractor agree that the terms of the Building Contract shall be and are varied in the manner set out in Schedule 1.

- Affirmation of the Building Contract

Subject to the terms of this Deed the Building Contract shall remain in full force and effect.

- Third Party Rights

No term of this Deed is enforceable under the Contracts (Rights of Third Parties) Act 1999 by a person who is not party to this Deed. This clause 10 does not affect any right or remedy of any person that exists or is available otherwise than pursuant to that Act.

- Governing Law and Interpretation

This Deed and all non-contractual obligations in connection with this Deed shall be governed by and construed in all respects in accordance with the laws of England and Wales. The English Courts shall have exclusive jurisdiction to settle any disputes that may arise out of or in connection with this Deed.

IN WITNESS of which this document is executed as a deed and is delivered on the date first set out above

SCHEDULE 7

COLLATERAL WARRANTIES

Part 2

Warranty from Principal Building Sub-Contractors

Dated 20 [PRINCIPAL BUILDING SUB-CONTRACTOR] (1) [AUTHORITY] (2) [CONTRACTOR'S BUILDING CONTRACTOR] (3) DUTY OF CARE DEED relating to

THIS DEED is made on  						20

BETWEEN:

(1)	[PRINCIPAL BUILDING SUB-CONTRACTOR] (Company No.                 ), whose registered office is at 										(the Principal Building Sub-Contractor);

(2)	[AUTHORITY] of [									] (the Authority), (which expression includes its permitted successors in title and assigns); and

(3)	BUILDING CONTRACTOR ((Company No.                 ), whose registered office is at [	                                                  ] (the Building Contractor).

BACKGROUND

(A)	By a design, build, operate and maintain agreement dated [                             ] (the Agreement) the Authority has appointed the Contractor to carry out, in relation to the Site[s], the provision of serviced accommodation to the Authority at each and every Facility as contemplated by the Agreement including the carrying out of the Works and the provision of the Services and the design and construction of the Works.

(B)	By a design and build contract dated [                          ] (the Building Contract) the Contractor has appointed the Building Contractor to carry out in relation to the Site[s] the design and construction of the Works.

(C)	The Principal Building Sub-Contractor has been appointed by the Building Contractor under a contract dated [                    ] (the Subcontract) in relation to the [  ] element of the Works (the Subcontract Works).

(D)	The Principal Building Sub-Contractor and the Building Contractor have agreed to execute this Deed in favour of the Authority.

- DEFINITIONS AND INTERPRETATIONS

Unless expressly defined otherwise in this Deed, any defined term in this Deed shall have the same meaning given to such term in the [Building Contract/Subcontract].

Intellectual Property Rights

any and all patents, trade marks, service marks, copyright, database rights, moral rights, rights in a design, know how, confidential information and all or any other intellectual or industrial property rights whether or not registered or capable of registration and whether subsisting in the United Kingdom or any other part of the world together with all or any goodwill relating or attaching thereto which is created, brought into existence, acquired, used or intended to be used by the Principal Building Sub-Contractor for the purpose of carrying out the Subcontract Works;

Project Data

(i)	all drawings, reports, documents, plans, software, formulae, calculations and other data relating to the design, construction, testing or operation of the [Facility/Facilities] (as defined in the Agreement) in each case used by or on behalf of the Principal Building Sub-Contractor in connection with the provision of the Works or the performance of the Principal Building Sub-Contractor's obligations under the Subcontract; and

(ii)	any other materials, documents or data acquired or brought into existence or used in relation to the Works or the Subcontract by or on behalf of the Principal Building Sub-Contractor in connection with the provision of the Works or the performance of the Principal Building Sub-Contractor's obligations under the Subcontract.

- OPERATIVE PROVISIONS

In consideration of the payment of one pound (£1.00) by the Authority to the Principal Building Sub-Contractor, receipt of which the Principal Building Sub-Contractor acknowledges:

- PRINCIPAL BUILDING SUB-CONTRACTOR'S WARRANTY AND LIABILITY

  - The Principal Building Sub-Contractor warrants to the Authority that it has carried out and will continue to carry out its duties under the Subcontract in accordance with the Subcontract and that it has exercised and will continue to exercise, in carrying out the design of the Subcontract Works, the level of skill and care reasonably to be expected from an appropriately qualified and competent professional designer providing those services in relation to a project of a similar size and scope to the Works. In particular and without limiting the generality of the foregoing the Principal Building Sub-Contractor covenants with the Authority that it has carried out and will carry out and complete the Subcontract Works in accordance with the Subcontract and duly observe and perform all its duties and obligations thereunder;

  - The Principal Building Sub-Contractor shall have no liability under clause 3.1 or clause 11 of this Deed that is greater or of longer duration than it would have had as if in lieu of this Deed the Authority had been a party to the Subcontract as joint employer and the Principal Building Sub-contractor shall be entitled in any action or proceedings by the Authority to raise equivalent rights in defence of liability (except for set off or counterclaim). Upon the expiration of twelve (12) years from the date of Services Availability in accordance with the Agreement, the liability of the Principal Building Sub-Contractor under this Deed shall cease and determine, save in relation to any claims made by the Authority against the Principal Building Sub-Contractor where proceedings have commenced prior to such date.

  - Nothing in this Deed shall entitle the Authority to exercise its rights under this clause 3 unless:

    - the Agreement (or the Contractor's employment under it) has been terminated; or, in the absence of such termination

    - the Contractor has not (either itself or through its supply chain (whether through the Building Contractor or an FM Contractor or otherwise)) satisfied the potential claim by the Authority under this clause 3, including addressing and/or remedying the matter or circumstance giving rise to such claim, within a reasonable time of such matter or circumstance arising,

provided that this clause 3.3 shall not apply where any delay in the exercise of the Authority's rights under Deed might otherwise lead to their becoming statute-barred.

- INTELLECTUAL PROPERTY

  - The Principal Building Sub-Contractor shall make available to the Authority free of charge (and hereby irrevocably licences the Authority to use) all Project Data that might reasonably be required by the Authority. The Principal Building Sub-Contractor shall obtain all necessary licences, permissions and consents necessary for it to make the Project Data available to the Authority on these terms, for the purposes of:

    - the Authority using the Works for the provision of Services (as defined in the Agreement) and for ancillary purposes, its duties under the Agreement and/or any statutory duties the Authority may have; and

    - following termination of the Subcontract or of the Principal Building Sub-Contractor's employment under it, the design or construction of the Works and/or the operation, maintenance or improvement of the Works,

(together, the Approved Purposes), and in this clause 4 "use" shall include the acts of copying, modifying, adapting and translating the material in question and/or incorporating them with other materials and the term "the right to use" shall be construed accordingly. The Authority will not hold the Principal Building Sub-Contractor liable for any use it may make of the Project Data for any purpose other than the Approved Purposes.

  - The Principal Building Sub-Contractor:

    - hereby grants to the Authority, free of charge, an irrevocable, non-exclusive and transferable (subject to the restrictions contained in clause 7 of this Deed) licence to use the Intellectual Property Rights which are or become vested in the Principal Building Sub-Contractor for the Approved Purposes; and

    - shall (where any Intellectual Property Rights are or become vested in a third party) use all reasonable endeavours to procure the grant of a like licence to that referred to in clause 4.2.1 to the Authority,

in both cases, solely for the Approved Purposes.

  - The Principal Building Sub-Contractor warrants to the Authority that he has used the standard of skill, care and diligence as set out in clause 3.1 to see that the Project Data (save to the extent duly appointed sub contractors have been used to prepare the same) are its own original work and that in any event their use in connection with the Works will not infringe the rights of any third party.

  - Where a claim or proceeding is made or brought against the Authority which arises out of the infringement of any Intellectual Property Rights or because the use of any materials, plant, machinery or equipment in connection with the Works infringes or the Works themselves infringe any Intellectual Property Rights of a third party then, unless such infringement has arisen out of the use of any Intellectual Property Rights by or on behalf of the Authority otherwise than in accordance with this Deed, the Principal Building Sub-Contractor shall indemnify the Authority at all times from and against all Direct Losses and Indirect Losses (as defined in the Agreement) arising as a result of such claims and proceedings.

- INSURANCE

  - The Principal Building Sub-Contractor hereby covenants with the Authority to:

    - take out and maintain [professional indemnity/product liability] insurance cover with a limit of indemnity that shall be a minimum of [                                                            ] pounds (£[                    ])] either each and every loss or in the aggregate in relation to the Subcontract Works (if in the aggregate then in any one (1) year of insurance a minimum of one (1) automatic reinstatement of the aggregate indemnity limit is required) ([PI Insurance/Product Liability Insurance]) and that it will maintain such insurance with reputable insurers carrying on business in the European Union from the date hereof until twelve (12) years after Services Availability pursuant to the Agreement, provided that such insurance is generally available in the market to members of the Principal Building Sub-Contractor's profession at commercially reasonable rates and terms and provided further that payment of any increased or additional premiums or more onerous terms required by insurers by reason of the Principal Building Sub-Contractor's own claims record or other acts, omissions, matters or things peculiar to the Principal Building Sub-Contractor will be deemed to be within the commercially reasonable rates and terms;

    - provide evidence (as and when reasonably required by the Authority) satisfactory to the Authority of the [PI Insurance/Product Liability Insurance] being in full force and effect from the date of the Subcontract (such evidence to include details of the cover);

    - provide the Authority with notice of:

      - any cancellation of the [PI Insurance/Product Liability Insurance] not less than thirty (30) days prior to the relevant cancellation date; and

      - any adverse material changes to or suspension of cover relevant to the Subcontract Works not less than thirty (30) days prior to the relevant change or suspension;

    - inform the Authority as soon as reasonably practicable of any claim under the [PI Insurance/Product Liability Insurance] in respect of the Subcontract Works in excess of one million pounds (£1,000,000) and provide such information to the Authority as the Authority may reasonably require in relation to such claim and provide notice of any potential breach of the aggregate limit of the policy; and

    - indemnify the Authority in respect of any subrogation claim by the insurers brought in connection with any claim made under the PI Insurance/Product Liability Insurance.

- NOTICES

Any notice to be given by any party hereunder will be sufficiently served if sent by hand, by facsimile transmission or by post to the registered office or if there is none the last known address of the party to be served. Any notice sent by hand will be deemed to be served on the date of delivery and any notice sent by facsimile transmission will be deemed to be served in full at the time recorded on the facsimile report sheet, provided that if any notice sent by hand or facsimile is sent after 4.45 pm on any day it will be deemed to be served on the next Business Day. Any notice sent by post will be deemed to have been duly served at the expiration of forty-eight (48) hours after the time of posting if the end of that period falls before 4.45pm on a Business Day and otherwise on the next Business Day.

- ASSIGNMENT

The benefit of and the rights of the Authority under this Deed may be assigned without the consent of the Principal Building Sub-Contractor on two (2) occasions only and the Authority will notify the Principal Building Sub-Contractor in writing following any such assignment specifying the name and address of the assignee and the date of the assignment. The Principal Building Sub-Contractor will not contend that any such assignee is precluded from recovering any loss resulting from any breach of this Deed (whatever the date of such breach) by reason only that that person is an assignee and not the original beneficiary hereunder or by reason that the original beneficiary or any intermediate beneficiary escaped any loss resulting from such breach by reason of the disposal of any interest in the Site[s] or that the original beneficiary or any intermediate beneficiary has not suffered any, or as much, loss.

- AUTHORITY'S REMEDIES

The rights and benefits conferred upon the Authority by this Deed are in addition to any other rights and remedies it may have against the Principal Building Sub-Contractor including without prejudice to the generality of the foregoing any remedies in negligence.

- INSPECTION OF PROJECT DATA

The Principal Building Sub-Contractor's liabilities under this Deed will not be in any way reduced or extinguished by reason of any inspection or approval of the Project Data or attendance at site meetings or other enquiry or inspection which the Authority may make or procure to be made for its benefit or on its behalf.

- STEP-IN RIGHTS IN FAVOUR OF THE AUTHORITY

  - The Principal Building Sub-Contractor will not exercise or seek to exercise any right which may be or become available to it to terminate or treat as terminated or repudiated the Subcontract or its engagement under it or discontinue or suspend the performance of any duties or obligations thereunder without first giving to the Authority not less than twenty (20) Business Days' prior written notice (and seven (7) days' prior written notice of suspension in the event of non-payment under the Subcontract) specifying the Principal Building Sub-Contractor's ground for terminating or treating as terminated or repudiated the Subcontract or its engagement under it or discontinuing or suspending its performance thereof and stating the amount (if any) of monies outstanding under the Subcontract. Within such period of notice:

    - the Authority may give written notice to the Principal Building Sub-Contractor that the Authority will thenceforth become the client under the Subcontract to the exclusion of the Building Contractor and thereupon the Principal Building Sub-Contractor will admit that the Authority is the client under the Subcontract and the Subcontract will be and remain in full force and effect notwithstanding any of the said grounds;

    - if the Authority has given such notice as aforesaid or under clause 10.3, the Authority shall accept liability for the Building Contractor's obligations under the Subcontract and will as soon as practicable thereafter remedy any outstanding breach by the previous client which properly has been included in the Principal Building Sub-Contractor's specified grounds and which is capable of remedy by the Authority; and

    - if the Authority has given such notice as aforesaid or under clause 10.3, the Authority will from the service of such notice become responsible for all sums properly payable to the Principal Building Sub-Contractor under the Subcontract accruing due after the service of such notice but the Authority will in paying such sums be entitled to the same rights of set-off and deduction as would have applied to the Building Contractor under the Subcontract.

  - Notwithstanding anything contained in this Deed and notwithstanding any payments which may be made by the Authority to the Principal Building Sub-Contractor, the Authority will not be under any obligation to the Principal Building Sub-Contractor nor will the Principal Building Sub-Contractor have any claim or cause of action against the Authority unless and until the Authority has given written notice to the Principal Building Sub-Contractor pursuant to clause 10.1.1 or clause 10.3 of this Deed.

  - The Principal Building Sub-Contractor further covenants with the Authority that if the employment of the Building Contractor under the Building Contract is terminated or if the Building Contract is terminated or the Building Contract is terminated the Principal Building Sub-Contractor, if requested by the Authority by notice in writing and subject to clause 10.1.2 and clause 10.1.3, will accept the instructions of the Authority to the exclusion of the Building Contractor in respect of its duties under the Subcontract upon the terms and conditions of the Subcontract and will if so requested in writing enter into a novation agreement in the form set out in Appendix 1 to this Deed whereby the Authority is substituted for the Building Contractor under the Subcontract.

  - The Building Contractor acknowledges that the Principal Building Sub-Contractor will be entitled to rely on a notice given to the Principal Building Sub-Contractor by the Authority under clause 10.3 as conclusive evidence that the employment of the Building Contractor under the Building Contract has been terminated.

  - The Authority may by notice in writing to the Principal Building Sub-Contractor appoint another person to exercise its rights under this clause 10 subject to the Authority remaining liable to the Principal Building Sub-Contractor as guarantor for its appointee in respect of its obligations under this Deed.

  - Upon request by the Authority the Principal Building Sub-Contractor agrees to co-operate with the Authority in determining the duties performed or to be performed by the Principal Building Sub-Contractor and to provide a copy of the Subcontract and any variations thereto and details of all monies paid and due under the Subcontract.

  - As from the date of service of notice under clauses 10.1.1 or 10.3  to the extent that the Subcontract operates by reference to the existence and application of the Building Contract and/or the Agreement, the Subcontract shall be administered and construed as though the Building Contract and the Agreement were continuing and the Subcontract shall therefore continue, subject to amendment only as necessary to reflect the fact that the Building Contract and the Agreement may in fact have been terminated and the Authority has undertaken the obligations set out in clause 10.1.2.

- STANDARDS OF PRODUCTS AND MATERIALS

  - The Principal Building Sub-Contractor warrants that it has not specified for use or used and it will not specify for use or use and (as appropriate) it has not authorised or approved and it will not authorise or approve the use by others, of any products or materials not in conformity with relevant British or European Union Standards or Codes of Practice or which at the time of specification are widely known to members of the Principal Building Sub-Contractor's profession within the European Union to be deleterious to health and safety or to the durability of buildings and/or other structures and/or finishes and/or plant and machinery in the particular circumstances in which they are used.

  - If in the performance of its duties under the Subcontract the Principal Building Sub-Contractor becomes aware that it or any other person has specified or used, or authorised or approved the specification or use by others of any such products or materials the Principal Building Sub-Contractor will notify the Authority in writing forthwith. This clause does not create any additional duty for the Principal Building Sub-Contractor to inspect or check the work of others which is not required by the Subcontract.

- SUB-CONTRACTORS

Following a written request from the Authority the Principal Building Sub-Contractor will (unless it has already done so) and/ or procure that its sub-contractors execute a deed of collateral warranty in the relevant form specified in the Subcontract in favour of any person in whose favour the Subcontract obliged the Principal Building Sub-Contractor to give or procure the giving of such a warranty.

- SEVERABILITY

If any term, condition or provision of this Deed shall be held to be invalid, unlawful or unenforceable to any extent, such term, condition or provision shall not affect the validity, legality and enforceability of the other provisions of or any other documents referred to in this Deed.

- WAIVER

  - No term or provision of this Deed shall be considered as waived by any party to this Deed unless a waiver is given in writing by that party.

  - No waiver under clause 14.1 shall be a waiver of a past or future default or breach, nor shall it amend, delete or add to the terms, conditions or provisions of this Deed unless (and only to the extent) expressly stated in that waiver.

- THIRD PARTY RIGHTS

No term of this Deed is enforceable under the Contracts (Rights of Third Parties) Act 1999 by a person who is not party to this Deed. This clause 15 does not affect any right or remedy of any person that exists or is available otherwise than pursuant to that Act.

- GOVERNING LAW AND JURISDICTION

This Deed and all non-contractual obligations in connection with this Deed shall be governed by and construed in all respects in accordance with the laws of England and Wales. The English Courts shall have exclusive jurisdiction to settle any disputes which may arise out of or in connection with this Deed.

- BUILDING CONTRACTOR ACKNOWLEDGEMENT

The Building Contractor has entered into this Deed in order to acknowledge the arrangements effected hereby and undertakes to each of the Authority and the Principal Building Sub-Contractor to observe the provisions of this Deed at all times and not in any way to prejudice or affect the enforcement hereof or to do or permit to be done anything which would be a breach hereof.

- COUNTERPARTS

This Deed may be executed in one or more counterparts. Any single counterpart or a set of counterparts executed, in either case, by all the parties shall constitute a full and original instrument for all purposes.

IN WITNESS of which this document is executed as a deed and is delivered on the date first set out above

| Executed as a deed, but not delivered until the first date specified on page 1, by PRINCIPAL BUILDING CONTRACTOR acting by a director in the presence of a witness: | )))) | Signature |  |
| --- | --- | --- | --- |
|  |  | Name (block capitals) |  |
|  |  |  | Director |
| Witness signature |  |  |
| Witness name |  |  |
| (block capitals) |  |  |
| Witness address |  |  |

| Executed as a deed, but not delivered until the first date specified on page 1, by BUILDING CONTRACTOR acting by a director in the presence of a witness: | )))) | Signature |  |
| --- | --- | --- | --- |
|  |  | Name (block capitals) |  |
|  |  |  | Director |
| Witness signature |  |  |
| Witness name |  |  |
| (block capitals) |  |  |
| Witness address |  |  |

| Executed as a deed, but not delivered until the first date specified on page 1, by AUTHORITY acting by: | )))) |  |  |
| --- | --- | --- | --- |
| Authorised Signatory |  |  |  |
| Authorised Signatory |  |  |  |

Appendix 1

Form of Deed of Novation

THIS DEED is made on  						20

BETWEEN:

(1)	[PRINCIPAL BUILDING SUB-CONTRACTOR] (Company No.                 ), whose registered office is at                                                        (the Principal Building Sub-Contractor);

(2)	[AUTHORITY] of                        (the Authority), which expression includes its permitted successors in title and assigns); and

(3)	BUILDING CONTRACTOR (Company No.                 ), whose registered office is at               (the Building Contractor).

WHEREAS

(A)	By a design, build, operate and maintain agreement dated [	] (the Agreement) the Authority has appointed the Contractor to carry out in relation to [		] (the Sites) the design and construction of the Works (as defined in the Agreement).

(B)	By a design and build contract dated [	] (the Building Contract) the Contractor has appointed the Building Contractor to carry out in relation to the Sites the design and construction of the Works.

(C)	The Principal Building Sub-Contractor has been appointed by the Building Contractor under a contract dated [                    ] (the Subcontract) in relation to the [  ] element of the Works (the Subcontract Works).

(C)	[The employment of the Building Contractor under the Building Contract has been terminated] [the Building Contract has been terminated].

(D)	The Building Contractor has transferred or agreed to transfer its interest in (or granted or agreed to grant a subordinate interest in) the Sites to the Authority.

(E)	The parties have agreed to novate the Subcontract to the Authority on the terms set out below.

IT IS AGREED

- Novation of the Subcontract

The Subcontract is hereby novated from the Principal Building Sub-Contractor and the Building Contractor to the Principal Building Sub-Contractor and the Authority.

Release of the Principal Building Sub-Contractor

The Principal Building Sub-Contractor shall no longer owe any duty or obligation to the Building Contractor under or in respect of the Subcontract whether by virtue of its terms or by virtue of any breach or otherwise.

Release of the Building Contractor

The Building Contractor shall no longer owe any duty or obligation to the Principal Building Sub-Contractor under or in respect of the Subcontract whether by virtue of its terms or by virtue of any breach or otherwise.

Binding of the Principal Building Sub-Contractor to the Authority

The Principal Building Sub-Contractor binds itself to the Authority in the terms of the Subcontract as if the Authority were and always had been named in the Subcontract in place of the Building Contractor.

The Principal Building Sub-Contractor warrants to the Authority that prior to the date of this Deed it has performed and that it will continue to perform its duties and obligations as required by and in accordance with the terms of the Building Contract.

The Authority shall not be precluded from recovering any losses incurred by the Authority resulting from any breach of clause 4.2 by reason that (if it be the case) the acts or omissions causing such breach occurred before this Deed took effect, or that the Building Contractor will not incur or has not or would not have incurred any such losses. No waiver by the Building Contractor, either express or implied, will affect the Principal Building Sub-Contractor's liability to the Authority pursuant to this clause 4.

Upon the expiration of twelve (12) years from the date of completion of the Works in accordance with the Building Contract, the liability of the Principal Building Sub-Contractor under this Deed shall cease and determine, save in relation to any claims made by the Authority against the Principal Building Sub-Contractor and notified by the Authority to the Principal Building Sub-Contractor in writing prior thereto.

Binding of the Authority to the Principal Building Sub-Contractor

The Authority binds itself to the Principal Building Sub-Contractor in the terms of the Subcontract as if the Authority were and always had been named in the Subcontract in place of the Contractor and as if all acts and omissions of the Contractor (including any wrongful acts or omissions) under and in respect of the Subcontract were the acts and omissions of the Authority.

Vesting of remedies in the Authority

All rights of action and remedies vested in the Building Contractor against the Principal Building Sub-Contractor under and in respect of the Subcontract shall hereupon vest in the Authority.

Vesting of remedies against the Authority

All rights of action and remedies vested in the Principal Building Sub-Contractor against the Building Contractor under and in respect of the Subcontract shall hereinafter lie against the Authority.

Amendment of the Subcontract

The Authority and the Principal Building Sub-contractor agree that the terms of the Subcontract shall be and are varied in the manner set out in Schedule 1.

Affirmation of the Subcontract

Subject to the terms of this Deed the Subcontract shall remain in full force and effect.

Third Party Rights

No term of this Deed is enforceable under the Contracts (Rights of Third Parties) Act 1999 by a person who is not party to this Deed. This clause 10 does not affect any right or remedy of any person that exists or is available otherwise than pursuant to that Act.

Governing Law and Interpretation

This Deed and all non-contractual obligations in connection with this Deed shall be governed by and construed in all respects in accordance with the laws of England and Wales. The English Courts shall have exclusive jurisdiction to settle any disputes which may arise out of or in connection with this Deed.

IN WITNESS of which this document is executed as a deed and is delivered on the date first set out above

SCHEDULE 7

COLLATERAL WARRANTIES

Part 3

Warranty from members of the Professional Team

Dated 20 [CONSULTANT] (1) [AUTHORITY] (2) [CONTRACTOR'S BUILDING CONTRACTOR] (3) DUTY OF CARE DEED relating to

THIS DEED is made on  						20

BETWEEN

(1)	THE PARTNERS IN [INSERT NAME OF PARTNERSHIP] (being the persons listed in the Schedule hereto), whose principal place of business is at																	 OR 				 LIMITED/PLC (Company No.                 ), whose registered office is at 					(the Consultant);

(2)	[AUTHORITY] of 	                                                         (the Authority), which expression includes its permitted successors in title and assigns); and

(3)	[BUILDING CONTRACTOR] (Company No.                 ), whose registered office is at                                         (the Building Contractor).

BACKGROUND

(A)	By a design, build, operate and maintain agreement dated [			] (the Agreement) the Authority has appointed the Contractor to carry out, in relation to the Site[s], the provision of serviced accommodation to the Authority at each and every Facility as contemplated by the Agreement including the carrying out of the Works (as defined in the Agreement) and the provision of the Services and design and construction of the Works.

(B)	By a design and build contract dated [                             ] (the Building Contract) the Contractor has appointed the Building Contractor to carry out in relation to the Site[s] the design and construction of the Works.

(C)	The Consultant has been appointed by the Building Contractor under a [letter/deed] of appointment dated [                             ] (the Appointment) to provide services in relation to the Works.

(D)	The Consultant is obliged under the Appointment to give a warranty in this form in favour of the Authority.

(E)	The Consultant and the Building Contractor have agreed to execute this Deed in favour of the Authority.

- DEFINITIONS AND INTERPRETATIONS

Unless expressly defined otherwise in this Deed, any defined term in this Deed shall have the same meaning given to such term in the Appointment.

Intellectual Property Rights

any and all patents, trade marks, service marks, copyright, database rights, moral rights, rights in a design, know how, confidential information and all or any other intellectual or industrial property rights whether or not registered or capable of registration and whether subsisting in the United Kingdom or any other part of the world together with all or any goodwill relating or attaching thereto which is created, brought into existence, acquired, used or intended to be used by the Consultant for the purpose of carrying out the Works;

Project Data

i)	all drawings, reports, documents, plans, software, formulae, calculations and other data relating to the design, construction, testing or operation of the [Facility/Facilities] (as defined in the Agreement) in each case that is used by or on behalf of the Consultant in connection with the provision of the Works or the performance of the Consultant's obligations under the Appointment; and

ii)	any other materials, documents or data acquired or brought into existence or used in relation to the Works and or the Appointment by or on behalf of the Consultant in connection with the provision of the Works and or the performance of the Consultant's obligations under the Appointment.

- OPERATIVE PROVISIONS

In consideration of the payment of one pound (£1.00) by the Authority to the Consultant, receipt of which the Consultant acknowledges:

- CONSULTANT'S WARRANTY AND LIABILITY

  - The Consultant warrants to the Authority that it has carried out and will continue to carry out its duties under the Appointment in accordance with the Appointment and that it has exercised and will continue to exercise in the performance of those duties the reasonable skill care and diligence to be expected of a properly qualified member of its profession experienced in carrying out duties such as its duties under the Appointment in relation to works of similar scope, nature and complexity to the Works.

  - The Consultant shall have no liability under clause 3.1 or clause 11 of this Deed that is greater or of longer duration than it would have had as if in lieu of this Deed the Authority had been a party to the Appointment as joint employer and the Consultant shall be entitled in any action or proceedings by the Authority to raise equivalent rights in defence of liability (except for set off or counterclaim). Upon the expiration of twelve (12) years from the date of Services Availability in accordance with the Agreement, the liability of the Consultant under this Deed shall cease and determine, save in relation to any claims made by the Authority against the Consultant where proceedings have commenced prior to such date.

  - Nothing in this Deed shall entitle the Authority to exercise its rights under this clause 3 unless:

    - the Agreement (or the Contractor's employment under it) has been terminated; or, in the absence of such termination;

    - the Contractor has not (either itself or through its supply chain (whether through the Building Contractor or an FM Contractor or otherwise)) satisfied the potential claim by the Authority under this clause 3, including addressing and/or remedying the matter or circumstance giving rise to such claim, within a reasonable time of such matter or circumstance arising,

provided that this clause 3.3 shall not apply where any delay in the exercise of the Authority's rights under Deed might otherwise lead to their becoming statute-barred.

- INTELLECTUAL PROPERTY

  - The Consultant shall make available to the Authority free of charge (and hereby irrevocably licences the Authority to use) all Project Data that might reasonably be required by the Authority. The Consultant shall obtain all necessary licences, permissions and consents necessary for it to make the Project Data available to the Authority on these terms, for the purposes of:

    - the Authority using the Works for the provision of Services (as defined in the Agreement) and for ancillary purposes, its duties under the Agreement and/or any statutory duties which the Authority may have; and

    - following termination of the Appointment or of the Consultant's employment under it, the design or construction of the Works and/or the operation, maintenance or improvement of the Works,

(together, the Approved Purposes), and in this clause 4 "use" shall include the acts of copying, modifying, adapting and translating the material in question and/or incorporating them with other materials and the term "the right to use" shall be construed accordingly. The Authority will not hold the Consultant liable for any use it may make of the Project Data for any purpose other than the Approved Purposes.

  - The Consultant:

    - hereby grants to the Authority, free of charge, an irrevocable, non-exclusive and transferable (subject to the restrictions contained in clause 8 of this Deed) licence to use the Intellectual Property Rights which are or become vested in the Consultant for the Approved Purposes; and

    - shall (where any Intellectual Property Rights are or become vested in a third party) use all reasonable endeavours to procure the grant of a like licence to that referred to in clause 4.2.1 above to the Authority,

in both cases, solely for the Approved Purposes.

  - The Consultant warrants to the Authority that it has used the standard of skill, care and diligence as set out in clause 3.1 to see that the Project Data (save to the extent duly appointed sub contractors have been used to prepare the same) are its own original work and that in any event their use in connection with the Works will not infringe the rights of any third party.

  - Where a claim or proceeding is made or brought against the Authority that arises out of the infringement of any Intellectual Property Rights or because the use of any materials, plant, machinery or equipment in connection with the Works infringes or the Works themselves infringe any Intellectual Property Rights of a third party then, unless such infringement has arisen out of the use of any Intellectual Property Rights by or on behalf of the Authority otherwise than in accordance with this Deed, the Consultant shall indemnify the Authority at all times from and against all Direct Losses and Indirect Losses (as defined in the Agreement) arising as a result of such claims and proceedings.

- INSURANCE

  - The Consultant hereby covenants with the Authority to:

    - take out and maintain professional indemnity insurance cover with a limit of indemnity that shall be a minimum of [                                                            ] pounds (£[                    ]) either each and every loss or in the aggregate in relation to the Works (if in the aggregate then in any one (1) year of insurance a minimum of one (1) automatic reinstatement of the aggregate indemnity limit is required) (PI Insurance) and that it will maintain such insurance with reputable insurers carrying on business in the European Union from the date hereof until twelve (12) years after Services Availability pursuant to the Agreement, provided that such insurance is generally available in the market to members of the Consultant's profession at commercially reasonable rates and terms and provided further that payment of any increased or additional premiums or more onerous terms required by insurers by reason of the Consultant's own claims record or other acts, omissions, matters or things peculiar to the Consultant will be deemed to be within the commercially reasonable rates and terms;

    - provide evidence (as and when reasonably required by the Authority) satisfactory to the Authority of the PI Insurance being in full force and effect from the date of the Appointment (such evidence to include details of the cover);

    - provide the Authority with notice of:

      - any cancellation of the PI Insurance not less than thirty (30) days prior to the relevant cancellation date; and

      - any adverse material changes to or suspension of cover relevant to the Works not less than thirty (30) days prior to the relevant change or suspension;

    - inform the Authority as soon as reasonably practicable of any claim under the PI Insurance in respect of the Works in excess of one million pounds (£1,000,000) and provide such information to the Authority as the Authority may reasonably require in relation to such claim and provide notice of any potential breach of the aggregate limit of the policy; and

    - indemnify the Authority in respect of any subrogation claim by the insurers brought in connection with any claim made under the PI Insurance.

- LIABILITY OF PARTNERS

Where the Consultant is a partnership, references in this Deed to the "Consultant" will be deemed to include reference to each and every present and future partner of such partnership and the liability of each and every such partner under this Deed will be deemed to be joint and several.

- NOTICES

Any notice to be given by any party to this Deed will be sufficiently served if sent by hand, by facsimile transmission or by post to the registered office or if there is none the last known address of the party to be served. Any notice sent by hand will be deemed to be served on the date of delivery and any notice sent by facsimile transmission will be deemed to be served in full at the time recorded on the facsimile report sheet, provided that if any notice sent by hand or facsimile is sent after 4.45 pm on any day it will be deemed to be served on the next Business Day. Any notice sent by post will be deemed to have been duly served at the expiration of forty-eight (48) hours after the time of posting if the end of that period falls before 4.45pm on a Business Day and otherwise on the next Business Day.

- ASSIGNMENT

The benefit of and the rights of the Authority under this Deed may be assigned without the consent of the Consultant on two (2) occasions only and the Authority will notify the Consultant in writing following any such assignment specifying the name and address of the assignee and the date of the assignment. The Consultant will not contend that any such assignee is precluded from recovering any loss resulting from any breach of this Deed (whatever the date of such breach) by reason only that that person is an assignee and not the original beneficiary hereunder or by reason that the original beneficiary or any intermediate beneficiary escaped any loss resulting from such breach by reason of the disposal of any interest in the Site[s] or that the original beneficiary or any intermediate beneficiary has not suffered any or as much loss.

- AUTHORITY'S REMEDIES

The rights and benefits conferred upon the Authority by this Deed are in addition to any other rights and remedies it may have against the Consultant including without prejudice to the generality of the foregoing any remedies in negligence.

- INSPECTION OF PROJECT DATA

The Consultant's liabilities under this Deed will not be in any way reduced or extinguished by reason of any inspection or approval of the Project Data or attendance at site meetings or other enquiry or inspection which the Authority may make or procure to be made for its benefit or on its behalf.

- STANDARDS OF PRODUCTS AND MATERIALS

  - The Consultant warrants that it has exercised and will exercise reasonable skill, care and diligence in accordance with this Deed to see that it has not specified for use and it will not specify for use and (as appropriate) it has not authorised or approved and it will not authorise or approve the specification or use by others, of any products or materials not in conformity with relevant British or European Union Standards or Codes of Practice or which at the time of specification are widely known to members of the Consultant's profession within the European Union to be deleterious to health and safety or to the durability of buildings and/or other structures and/or finishes and/or plant and machinery in the particular circumstances in which they are used.

  - If in the performance of its duties under the Appointment the Consultant becomes aware that it or any other person has specified or used, or authorised or approved the specification or use by others of any such products or materials the Consultant will notify the Authority in writing forthwith. This clause does not create any additional duty for the Consultant to inspect or check the work of others which is not required by the Appointment.

- STEP-IN RIGHTS IN FAVOUR OF THE AUTHORITY

  - The Consultant will not exercise or seek to exercise any right which may be or become available to it to terminate or treat as terminated or repudiated the Appointment or its engagement under it or discontinue or suspend the performance of any duties or obligations thereunder without first giving to the Authority not less than twenty (20) Business Days' prior written notice (and seven (7) days' prior written notice of suspension in the event of non-payment under the Appointment) specifying the Consultant's ground for terminating or treating as terminated or repudiated the Appointment or its engagement under it or discontinuing or suspending its performance thereof and stating the amount (if any) of monies outstanding under the Appointment. Within such period of notice:

    - the Authority may give written notice to the Consultant that the Authority will thenceforth become the client under the Appointment to the exclusion of the Building Contractor and thereupon the Consultant will admit that the Authority is its client under the Appointment and the Appointment will be and remain in full force and effect notwithstanding any of the said grounds;

    - if the Authority has given such notice as aforesaid or under clause 12.3 the Authority shall accept liability for the Building Contractor's obligations under the Appointment and will as soon as practicable thereafter remedy any outstanding breach by the previous client [which properly has been included in the Consultant's specified grounds and] which is capable of remedy by the Authority; and

    - if the Authority has given such notice as aforesaid or under clause 12.3 the Authority will from the service of such notice become responsible for all sums properly payable to the Consultant under the Appointment accruing due after the service of such notice but the Authority will in paying such sums be entitled to the same rights of set-off and deduction as would have applied to the previous client under the Appointment.

  - Notwithstanding anything contained in this Deed and notwithstanding any payments which may be made by the Authority to the Consultant, the Authority will not be under any obligation to the Consultant nor will the Consultant have any claim or cause of action against the Authority unless and until the Authority has given written notice to the Consultant pursuant to clause 12.1.1 or clause 12.3 of this Deed.

  - The Consultant further covenants with the Authority that if the employment of the Building Contractor under the Building Contract is terminated or if the Building Contract is terminated the Consultant, if requested by the Authority by notice in writing and subject to clause 12.1.2 and clause 12.1.3, will accept the instructions of the Authority to the exclusion of the Building Contractor in respect of its duties under the Appointment upon the terms and conditions of the Appointment and will if so requested in writing enter into a novation agreement in the form set out in Appendix 1 to this Deed whereby the Authority is substituted for the Building Contractor under the Appointment.

  - If the Consultant is requested to enter into a novation agreement pursuant to clause 12.3, the Building Contractor agrees to enter into the same at the request of the Authority.

  - The Building Contractor acknowledges that the Consultant will be entitled to rely on a notice given to the Consultant by the Authority under clause 12.3 as conclusive evidence that the employment of the Building Contractor under the Building Contract has been terminated or the Building Contract has been terminated.

  - The Authority may by notice in writing to the Consultant appoint another person to exercise its rights under this clause 12 subject to the Authority remaining liable to the Consultant as guarantor for its appointee in respect of its obligations under this Deed.

  - As from the date of service of notice under clauses 12.1.1 or 12.3 to the extent that the Appointment operates by reference to the existence and application of the Agreement and the Building Contract, the Appointment shall be administered and construed as though the Agreement and Building Contract were continuing and the Appointment shall therefore continue, subject to amendment only as necessary to reflect the fact that the Agreement and the Building Contract may in fact have been terminated and the Authority has undertaken the obligations set out in clause 12.1.2.

- SUB-CONSULTANTS

Following a written request from the Authority the Consultant will (unless it has already done so) and/or procure that its sub-consultants execute a deed of collateral warranty in the relevant form specified in the Appointment in favour of any person in whose favour the Appointment obliged the Consultant to give or procure the giving of such a warranty.

- SEVERABILITY

If any term, condition or provision of this Deed shall be held to be invalid, unlawful or unenforceable to any extent, such term, condition or provision shall not affect the validity, legality and enforceability of the other provisions of or any other documents referred to in this Deed.

- WAIVER

  - No term or provision of this Deed shall be considered as waived by any party to this Deed unless a waiver is given in writing by that party.

  - No waiver under clause 15.1 shall be a waiver of a past or future default or breach, nor shall it amend, delete or add to the terms, conditions or provisions of this Deed unless (and only to the extent) expressly stated in that waiver.

- THIRD PARTY RIGHTS

No term of this Deed is enforceable under the Contracts (Rights of Third Parties) Act 1999 by a person who is not party to this Deed. This clause 16 does not affect any right or remedy of any person that exists or is available otherwise than pursuant to that Act.

- GOVERNING LAW AND JURISDICTION

This Deed and all non-contractual obligations in connection with this Deed shall be governed by and construed in all respects in accordance with the laws of England and Wales. The English Courts shall have exclusive jurisdiction to settle any disputes which may arise out of or in connection with this Deed.

- BUILDING CONTRACTOR ACKNOWLEDGEMENT

The Building Contractor has entered into this Deed in order to acknowledge the arrangements effected hereby and undertakes to each of the Authority and the Consultant to observe the provisions of this Deed at all times and not in any way to prejudice or affect the enforcement hereof or to do or permit to be done anything which would be a breach hereof.

- COUNTERPARTS

This Deed may be executed in one or more counterparts. Any single counterpart or a set of counterparts executed, in either case, by all the parties shall constitute a full and original instrument for all purposes.

IN WITNESS of which this document is executed as a deed and is delivered on the date first set out above

| Executed as a deed, but not delivered until the first date specified on page 1, by CONSULTANT acting by a director in the presence of a witness: | )))) | Signature |  |
| --- | --- | --- | --- |
|  |  | Name (block capitals) |  |
|  |  |  | Director |
| Witness signature |  |  |
| Witness name |  |  |
| (block capitals) |  |  |
| Witness address |  |  |

| Executed as a deed, but not delivered until the first date specified on page 1, by BUILDING CONTRACTOR acting by a director in the presence of a witness: | ))))) | Signature |  |
| --- | --- | --- | --- |
|  |  | Name (block capitals) |  |
|  |  |  | Director |
| Witness signature |  |  |
| Witness name |  |  |
| (block capitals) |  |  |
| Witness address |  |  |

| Executed as a deed, but not delivered until the first date specified on page 1, by AUTHORITY acting: | ))) | Signature |  |
| --- | --- | --- | --- |
|  |  | Name (block capitals) |  |
|  |  |  | Authorised Signatory |
|  |  | Signature |  |
|  |  | Name (block capitals) |  |
|  |  |  | Authorised Signatory |

Appendix 1

Form of Deed of Novation

BETWEEN:

(1)	[CONSULTANT] (Company No.                 ), whose registered office is at                                                        (the Consultant);

(2)	[AUTHORITY] of                        (the Authority), which expression includes its permitted successors in title and assigns); and

(3)	[BUILDING CONTRACTOR] (Company No.                 ), whose registered office is at               (the Building Contractor).

WHEREAS

(A)	By a design, build, operate and maintain agreement dated [	] (the Agreement) the Authority has appointed the Contractor to carry out in relation to [		] (the Sites) the design and construction of the Works (as defined in the Agreement).

(B)	By a design and build contract dated [	] (the Building Contract) the Contractor has appointed the Building Contractor to carry out in relation to the Sites the design and construction of the Works.

(C)	The Consultant has been appointed by the Building Contractor under a [letter/deed] of appointment dated [                             ] (the Appointment) to provide services in relation to the Works.

(C)	[The employment of the Building Contractor under the Building Contract has been terminated] [the Building Contract has been terminated].

(D)	The Building Contractor has transferred or agreed to transfer its interest in (or granted or agreed to grant a subordinate interest in) the Sites to the Authority.

(E)	The parties have agreed to novate the Appointment to the Authority on the terms set out below.

IT IS AGREED

- Novation of the Appointment

The Appointment is hereby novated from the Consultant and the Building Contractor to the Consultant and the Authority.

- Release of the Consultant

The Consultant shall no longer owe any duty or obligation to the Building Contractor under or in respect of the Appointment whether by virtue of its terms or by virtue of any breach or otherwise.

- Release of the Building Contractor

The Building Contractor shall no longer owe any duty or obligation to the Consultant under or in respect of the Appointment whether by virtue of its terms or by virtue of any breach or otherwise.

- Binding of the Consultant to the Authority

  - The Consultant binds itself to the Authority in the terms of the Appointment as if the Authority were and always had been named in the Appointment in place of the Building Contractor.

  - The Consultant warrants to the Authority that prior to the date of this Deed it has performed and that it will continue to perform its duties and obligations as required by and in accordance with the terms of the Appointment.

  - The Authority shall not be precluded from recovering any losses incurred by the Authority resulting from any breach of clause 4.2 by reason that (if it be the case) the acts or omissions causing such breach occurred before this Deed took effect, or that the Building Contractor will not incur or has not or would not have incurred any such losses. No waiver by the Building Contractor, either express or implied, will affect the Consultant's liability to the Authority pursuant to this clause 4.

  - Upon the expiration of twelve (12) years from the date of completion of the Works in accordance with the Appointment, the liability of the Consultant under this Deed shall cease and determine, save in relation to any claims made by the Authority against the Consultant and notified by the Authority to the Consultant in writing prior thereto.

- Binding of the Authority to the Consultant

The Authority binds itself to the Consultant in the terms of the Appointment as if the Authority were and always had been named in the Appointment in place of the Building Contractor and as if all acts and omissions of the Building Contractor (including any wrongful acts or omissions) under and in respect of the Appointment were the acts and omissions of the Authority.

- Vesting of remedies in the Authority

All rights of action and remedies vested in the Building Contractor against the Consultant under and in respect of the Appointment shall hereupon vest in the Authority.

- Vesting of remedies against the Authority

All rights of action and remedies vested in the Consultant against the Building Contractor under and in respect of the Appointment shall hereinafter lie against the Authority.

- Amendment of the Appointment

The Authority and the Consultant agree that the terms of the Appointment shall be and are varied in the manner set out in Schedule 1.

- Affirmation of the Appointment

Subject to the terms of this Deed the Appointment shall remain in full force and effect.

- Third Party Rights

No term of this Deed is enforceable under the Contracts (Rights of Third Parties) Act 1999 by a person who is not party to this Deed. This clause 10 does not affect any right or remedy of any person that exists or is available otherwise than pursuant to that Act.

- Governing Law and Interpretation

This Deed and all non-contractual obligations in connection with this Deed shall be governed by and construed in all respects in accordance with the laws of England and Wales. The English Courts shall have exclusive jurisdiction to settle any disputes which may arise out of or in connection with this Deed.

IN WITNESS of which this document is executed as a deed and is delivered on the date first set out above

SCHEDULE 7

COLLATERAL WARRANTIES

Part 4

Warranty from the Contractor's FM Contractor

DATED                                                                              20

[FM CONTRACTOR]  (1)

[AUTHORITY]  (2)

[CONTRACTOR]  (3)

DUTY OF CARE DEED

relating to

THIS DEED OF WARRANTY is made on the 	day of 	                               20

BETWEEN:

- [FM CONTRACTOR] (Company No.                             ) whose registered office is at										  (the FM Contractor);

- [AUTHORITY] of 						                  (the Authority), (which expression includes its permitted successors in title and assigns); and

- [CONTRACTOR] (Company No.			) whose registered office is at						 (the Contractor).

BACKGROUND

(A) 	By a design, build, operate and maintain agreement dated [			] (the Agreement) the Authority has appointed the Contractor to carry out, in relation to the Facility, the provision of serviced accommodation to the Authority at each and every Facility as contemplated by the Agreement including the carrying out of the Works and the provision of the Services design and construction of the Works.

(B)	The FM Contractor has been appointed by the Contractor under a contract dated [           ] (the FM Agreement) to carry out the Maintenance Services.

(C)	The FM Contractor is obliged under the FM Agreement to give a warranty in this form in favour of the Authority.

(D)	The FM Contractor and the Contractor have agreed to execute this Deed in favour of the Authority.

- DEFINITIONS AND INTERPRETATIONS

Unless expressly defined otherwise in this Deed any defined term in this Deed shall have the same meaning given to such term in the FM Agreement.

Intellectual Property Rights

any and all patents, trade marks, service marks, copyright, database rights, moral rights, rights in design, know how, confidential information and all or any other intellectual or industrial property rights whether or not registered or capable of registration and whether subsisting in the United Kingdom or any other part of the world together with all or any goodwill relating or attaching thereto which is created, brought into existence, acquired, used or intended to be used by the FM Contractor for the purpose of carrying out the Maintenance Services;

Project Data

(i)	all drawings, reports, documents, plans, software, formulae, calculations and other data relating to the design, construction, testing or operation of the [Facility/Facilities] (as defined in the Agreement) in each case that is used by or on behalf of the FM Contractor in connection with the Maintenance Services or the performance of the FM Contractor's obligations under the FM Agreement; and

(ii)	any other materials, documents or data acquired or brought into existence or used in relation to the Maintenance Services or the FM Agreement by or on behalf of the FM Contractor in connection with the provision of the Maintenance Services or the performance of the FM Contractor's obligations under the FM Agreement.

- OPERATIVE PROVISIONS

In consideration of the payment of one pound (£1.00) by the Authority to the FM Contractor, receipt of which the FM Contractor acknowledges:

- WARRANTY

  - The FM Contractor warrants to the Authority that it has carried out and will continue to carry out all its obligations and duties under the FM Agreement in accordance with and to the standard required by the FM Agreement, provided always that the FM Contractor has no liability hereunder which is greater or of a longer duration than that it owes to the Contractor under the FM Agreement.

  - The FM Contractor shall have no liability under clauses 3.1 and 11 of this Deed that is greater or of longer duration than it would have had, and shall be entitled in any proceedings by the Authority to rely on any limitation in the FM Agreement and to raise equivalent rights in defence of liability as it would have against the Contractor under the FM Agreement.

  - Notwithstanding anything in this Deed and not withstanding any payments which may be made by the Authority to the FM Contractor, the Authority and the FM Contractor will not be under any obligation to each other nor will any party have any claim or cause of action against the others unless and until the Authority has given written notice to the FM Contractor pursuant to clause 7.1.1 or clause 7.3.

- INTELLECTUAL PROPERTY

  - The FM Contractor shall make available to the Authority free of charge (and hereby irrevocably licences the Authority to use) all Project Data that might reasonably be required by the Authority. The FM Contractor shall obtain all necessary licences, permissions and consents necessary for it to make the Project Data available to the Authority on these terms, for any purpose whatsoever connected with the Project and such other purposes as are reasonably foreseeable, (the Approved Purposes), and in this clause 4 "use" shall include the acts of copying, modifying, adapting and translating the material in question and/or incorporating them with other materials and the term "the right to use" shall be construed accordingly. The Authority will not hold the FM Contractor liable for any use it may make of the Project Data for any purpose other than the Approved Purposes unless the FM Contractor authorises such use and confirms that the Project Data is suitable for it.

  - The FM Contractor:

    - hereby grants to the Authority, free of charge, an irrevocable non-exclusive and transferable (subject to the restrictions continued in clause 5 of this Deed) licence to use the Intellectual Property Rights that are or become vested in the FM Contractor for the Approved Purposes;

    - shall (where any Intellectual Property Rights are or become vested in a third party) use all reasonable endeavours to procure the grant of a like licence to that referred to in clause 4.2.1 above to the Authority,

in both cases, solely for the Approved Purposes.

  - The FM Contractor agrees on reasonable request at any time and following reasonable written prior notice to give the Authority or those authorised by it access to the Project Data and to provide copies (including copy negatives and CAD disks) thereof at the Authority's expense.

  - The FM Contractor warrants to the Authority that the Project Data (save to the extent duly appointed sub-contractors have been used to prepare the same) is its own original work and that in any event their use in connection with the Project will not infringe the rights of any third party.

  - Where a claim or proceeding is made or brought against the Authority that arises out of the infringement of any Intellectual Property Rights or because the use of any materials, plant, machinery or equipment in connection with the Maintenance Services infringes any Intellectual Property Rights of a third party then, unless such infringement has arisen out of the use of any Intellectual Property Rights by or on behalf of the Authority otherwise than in accordance with this Deed, the FM Contractor shall indemnify the Authority at all times from and against all Direct Losses and Indirect Losses (as defined in the Agreement) arising as a result of such claims and proceedings.

- ASSIGNMENT

The benefit of and the rights of the Authority under this Deed may be assigned without the consent of the FM Contractor on two (2) occasions only and the Authority will notify the FM Contractor in writing following any such assignment specifying the name and address of the assignee and the date of the assignment. The FM Contractor will not contend that any such assignee is precluded from recovering any loss resulting from any breach of this Deed (whatever the date of such breach) by reason only that that person is an assignee and not the original beneficiary hereunder or by reason that the original beneficiary or any intermediate beneficiary escaped any loss resulting from such breach by reason of the disposal of any interest in the Site[s] or that the original beneficiary or any intermediate beneficiary has not suffered any, or as much, loss.

- AUTHORITY'S REMEDIES

The rights and benefits conferred upon the Authority by this Deed are in addition to any other rights and remedies it may have against the FM Contractor including without prejudice to the generality of the foregoing any remedies in negligence.

- STEP-IN RIGHTS IN FAVOUR OF THE AUTHORITY

  - The FM Contractor will not exercise or seek to exercise any right which may be or becomes available to it to terminate or treat as terminated or repudiated the FM Agreement or its employment under it or discontinue or suspend the performance of any duties or obligations thereunder without first giving to the Authority not less than thirty (30) Business Days' prior written notice specifying the FM Contractor's ground for terminating or treating as terminated or repudiated the FM Agreement or its employment under it or discontinuing or suspending its performance thereof and stating the amount (if any) of monies outstanding under the FM Agreement. Within such period of notice:

    - the Authority may give written notice to the FM Contractor that the Authority will thenceforth become the client under the FM Agreement to the exclusion of the Contractor and thereupon the FM Contractor will admit that the Authority is its client under the FM Agreement and the FM Agreement will be and remain in full force and effect notwithstanding any of the said grounds;

    - if the Authority has given such notice as aforesaid or under clause 7.3, the Authority shall accept liability for the Contractor's obligations under the FM Agreement and will as soon as practicable thereafter remedy any outstanding breach by the Contractor including for the avoidance of doubt any non-payment of sums due to the FM Contractor that properly has been included in the FM Contractor's specified grounds pursuant to this clause 7.1 (and which has been notified to the Authority) and which is capable of remedy; and

    - if the Authority has given such notice as aforesaid or under clause 7.3, the Authority will from the service of such notice become responsible for all sums properly payable to the FM Contractor under the FM Agreement accruing due after the service of the FM Contractor's notice but the Authority will in paying such sums be entitled to the same rights of set-off and deduction as would have applied to the Contractor under the FM Agreement.

  - Notwithstanding anything contained in this Deed and notwithstanding any payments which may be made by the Authority to the FM Contractor, the FM Contractor will not be under any duty to obey any direction or instruction from the Authority unless and until the Authority has given notice under clauses 7.1.1 and 7.3.

  - The FM Contractor further covenants with the Authority that if the employment of the Contractor under the Agreement is terminated or if the Agreement is terminated by the Authority the FM Contractor, if requested by the Authority by notice in writing and subject to clause 7.1.2 and clause 7.1.3, will accept the instructions of the Authority to the exclusion of the Contractor in respect of the Maintenance Services upon the terms and conditions of the FM Agreement and will if so requested in writing enter into a novation agreement in the form set out in Appendix 1 to this Deed whereby the Authority is substituted for the Contractor under the FM Agreement.

  - If the FM Contractor is requested to enter into a novation agreement pursuant to clause 7.3, the Contractor agrees to enter into the same at the request of the Authority.

  - The Contractor acknowledges that the FM Contractor will be entitled to rely on a notice given to the FM Contractor by the Authority under clause 7.3 as conclusive evidence that the Contractor's employment under the Agreement has been terminated or that the Agreement has been terminated by the Authority.

  - The Authority may by notice in writing to the FM Contractor appoint another person to exercise its rights under this clause 7 subject to the Authority remaining liable to the FM Contractor as guarantor for its appointee in respect of its obligations under this Deed.

- LIMITATION

Without prejudice to the provisions of clause 7.1, the Authority shall not be entitled to take any action or proceedings against the FM Contractor pursuant to this Deed unless and until the Agreement has been terminated.

- INDEPENDENT ENQUIRY CLAUSE

The liability of the FM Contractor under this Deed shall not be modified released, diminished or in any way affected by any independent inspection investigation or enquiry into any relevant matter which may be made or carried out by or for the Authority nor by any failure or omission to carry out any such inspection, investigation or enquiry nor by the appointment by the Authority of any independent firm, company or party whatsoever to review the progress of or otherwise report to the Authority in respect of the Maintenance Services nor by any action or omission of any such firm, company or party whether or not such action or omission might give rise to any independent liability of such firm, company or party to the Authority provided always that nothing in this clause 9 shall modify or affect any rights which the FM Contractor might have but for the existence of this clause 9 to claim contribution from any third party whether under statute or at common law.

- NO VARIATION TO FM AGREEMENT WITHOUT AUTHORITY'S CONSENT

The Contractor and the FM Contractor undertake with the Authority not to vary or depart from the terms and conditions of the FM Agreement without the prior written consent of the Authority (such consent to be sought in accordance with the Review Procedure where that procedure applies to the variation or departure in question), and agree that no such variation or departure made without such consent shall be binding upon the Authority, or affect or prejudice the Authority's rights hereunder, or under the FM Agreement or in any other way.

- SEVERABILITY

If any term, condition or provision of this Deed shall be held to be invalid, unlawful or unenforceable to any extent, such term, condition or provision shall not affect the validity, legality and enforceability of the other provisions of or any other documents referred to in this Agreement.

- WAIVER

  - No term or provision of this Deed shall be considered as waived by any party to this Deed unless a waiver is given in writing by that party.

  - No waiver under clause 12.1 shall be a waiver of a past or future default or breach, nor shall it amend, delete or add to the terms, conditions or provisions of this Deed unless (and only to the extent) expressly stated in that waiver.

- THE CONTRACTOR'S INCLUSION AS PARTY

The Contractor has agreed to be a party to this Deed for the purpose of clause 8 and for acknowledging that the FM Contractor shall not be in breach of the FM Agreement by complying with the obligations imposed on it by this Deed.

- COUNTERPARTS

This Deed may be executed in one or more counterparts. Any single counterpart or a set of counterparts executed, in either case, by all the parties shall constitute a full and original instrument for all purposes.

- GOVERNING LAW AND JURISDICTION

This Deed and all non-contractual obligations in connection with this Deed shall be governed by and construed in all respects in accordance with the laws of England and Wales. The English Courts shall have exclusive jurisdiction to settle any disputes which may arise out of or in connection with this Deed.

- THIRD PARTY RIGHTS

No term of this Deed is enforceable under the Contracts (Rights of Third Parties) Act 1999 by a person who is not party to this Deed. This clause 16 does not affect any right or remedy of any person that exists or is available otherwise than pursuant to that Act.

- NOTICES

Any notice to be given by either party hereunder will be sufficiently served if  sent by hand, by facsimile transmission or by post to the registered office or if there is none the last known address of the party to be served. Any notice sent by hand will be deemed to be served on the date of delivery and any notice sent by facsimile transmission will be deemed to be served in full at the time recorded on the facsimile report sheet, provided that if any notice sent by hand or facsimile is sent after 4.45 pm on any day it will be deemed to be served on the next Business Day. Any notice sent by post will be deemed to have been duly served at the expiration of forty-eight (48) hours after the time of posting if the end of that period falls before 4.45pm on a Business Day and otherwise on the next Business Day.

IN WITNESS whereof this document is executed by the parties as a Deed and delivered on the date stated at the beginning of this Deed

EXECUTED as a Deed by the FM CONTRACTOR

acting by two of its directors or a

director and its secretary:

……………………………….

Director

………………………………..

Director/Secretary

EXECUTED AS A DEED by the Authority acting by two authorised signatories:

…………………………………

Authorised Signatory

…………………………………

Authorised Signatory

EXECUTED as a Deed by

[CONTRACTOR]

acting by two of its directors or a

director and its secretary:

…………………………………

Director

…………………………………

Director/Secretary

Appendix 1

Form of Deed of Novation

THIS DEED is made on  						20

BETWEEN:

(1)	[CONTRACTOR'S FM CONTRACTOR] (Company No.                 ) whose registered office is at                                                        (the FM Contractor);

(2)	[AUTHORITY] of                        (the Authority), which expression includes its permitted successors in title and assigns); and

(3)	CONTRACTOR (Company No.                 ) whose registered office is at               (the Contractor).

WHEREAS

(A)	By a design, build, operate and maintain agreement dated [	] (the Agreement) the Authority has appointed the Contractor to carry out in relation to [		] (the Sites) the design and construction of the Works (as defined in the Agreement).

(B)	The FM Contractor has been appointed by the Contractor under a contract dated [           ] (the FM Agreement) to carry out the Maintenance Services.

(C)	[The employment of the Contractor under the Agreement has been terminated] [The Agreement has been terminated by the Authority].

(D)	The Contractor has transferred or agreed to transfer its interest in (or granted or agreed to grant a subordinate interest in) the Sites to the Authority.

(E)	The parties have agreed to novate the FM Agreement to the Authority on the terms set out below.

IT IS AGREED

- Novation of FM Agreement

The FM Agreement is hereby novated from the Contractor and the FM Contractor to the Authority and the FM Contractor.

- Release of the Contractor

The Contractor shall no longer owe any duty or obligation to the FM Contractor under or in respect of the FM Agreement whether by virtue of its terms or by virtue of any breach or otherwise.

- Release of the FM Contractor

The FM Contractor shall no longer owe any duty or obligation to the Contractor under or in respect of the FM Agreement whether by virtue of its terms or by virtue of any breach or otherwise.

- Binding of the FM Contractor to the Authority

  - The FM Contractor binds itself to the Authority in the terms of the FM Agreement as if the Authority were and always had been named in the FM Agreement in place of the Contractor.

  - The FM Contractor warrants to the Authority that prior to the date of this Deed it has performed and that it will continue to perform its duties and obligations as required by and in accordance with the terms of the FM Agreement.

  - The Authority shall not be precluded from recovering any losses incurred by the Authority or the Contractor resulting from any breach of clause 4.2 by reason that (if it be the case) the acts or omissions causing such breach occurred before this Deed took effect, or that the Contractor will not incur or has not or would not have incurred any such losses. No waiver by the Contractor, either express or implied, will affect the FM Contractor's liability to the Authority pursuant to this clause 4.

- Binding of the Authority to the FM Contractor

The Authority binds itself to the FM Contractor in the terms of the FM Agreement as if the Authority were and always had been named in the FM Agreement in place of the Contractor and as if all acts and omissions of the Contractor (including any wrongful acts or omissions) under and in respect of the FM Agreement were the acts and omissions of the Authority.

- Vesting of remedies in the Authority

All rights of action and remedies vested in the Contractor against the FM Contractor under and in respect of the FM Agreement shall hereupon vest in the Authority.

- Vesting of remedies against the Authority

All rights of action and remedies vested in the FM Contractor against the Contractor under and in respect of the FM Agreement shall hereinafter lie against the Authority.

- Affirmation of FM Agreement

Subject to the terms of this Deed the FM Agreement shall remain in full force and effect.

- Third Party Rights

No term of this Deed is enforceable under the Contracts (Rights of Third Parties) Act 1999 by a person who is not party to this Deed. This clause 9 does not affect any right or remedy of any person that exists or is available otherwise than pursuant to that Act.

- Governing Law and Interpretation

This Deed and all non-contractual obligations in connection with this Deed shall be governed by and construed in all respects in accordance with the laws of England and Wales. The English Courts shall have exclusive jurisdiction to settle any disputes which may arise out of or in connection with this Deed.

IN WITNESS of which this document is executed as a deed and is delivered on the date first set out above

SCHEDULE 7

COLLATERAL WARRANTIES

Part 5

Warranty from the Contractor's Leisure Operator

DATED                                                                              20

[LEISURE OPERATOR]  (1)

[AUTHORITY]  (2)

[CONTRACTOR]  (3)

DUTY OF CARE DEED

relating to

THIS DEED OF WARRANTY is made on the 	day of 	                               20

BETWEEN:

- [LEISURE OPERATOR] (Company No.                             ) whose registered office is at										  (the Leisure Operator);

- [AUTHORITY] of 						                  (the Authority), (which expression includes its permitted successors in title and assigns); and

- [CONTRACTOR] (Company No.			) whose registered office is at						 (the Contractor).

BACKGROUND

(A) 	By a design, build, operate and maintain agreement dated [			] (the Agreement) the Authority has appointed the Contractor to carry out, in relation to the Facility, the provision of serviced accommodation to the Authority at each and every Facility as contemplated by the Agreement including the carrying out of the Works and the provision of the Services design and construction of the Works.

(B)	The Leisure Operator has been appointed by the Contractor under a contract dated [           ] (the Leisure Contract) to carry out the Leisure Services.

(C)	The Leisure Operator is obliged under the Leisure Contract to give a warranty in this form in favour of the Authority.

(D)	The Leisure Operator and the Contractor have agreed to execute this Deed in favour of the Authority.

- DEFINITIONS AND INTERPRETATIONS

Unless expressly defined otherwise in this Deed any defined term in this Deed shall have the same meaning given to such term in the Leisure Contract.

Intellectual Property Rights

any and all patents, trade marks, service marks, copyright, database rights, moral rights, rights in design, know how, confidential information and all or any other intellectual or industrial property rights whether or not registered or capable of registration and whether subsisting in the United Kingdom or any other part of the world together with all or any goodwill relating or attaching thereto which is created, brought into existence, acquired, used or intended to be used by the Leisure Operator for the purpose of carrying out the Leisure Services;

Project Data

(i)	all drawings, reports, documents, plans, software, formulae, calculations and other data relating to the design, construction, testing or operation of the [Facility/Facilities] (as defined in the Agreement) in each case that is used by or on behalf of the Leisure Operator in connection with the Leisure Services or the performance of the Leisure Operator's obligations under the Leisure Contract; and

(ii)	any other materials, documents or data acquired or brought into existence or used in relation to the Leisure Services or the Leisure Contract by or on behalf of the Leisure Operator in connection with the provision of the Leisure Services or the performance of the Leisure Operator's obligations under the Leisure Contract.

- OPERATIVE PROVISIONS

In consideration of the payment of one pound (£1.00) by the Authority to the Leisure Operator, receipt of which the Leisure Operator acknowledges:

- WARRANTY

  - The Leisure Operator warrants to the Authority that it has carried out and will continue to carry out all its obligations and duties under the Leisure Contract in accordance with and to the standard required by the Leisure Contract, provided always that the Leisure Operator has no liability hereunder which is greater or of a longer duration than that it owes to the Contractor under the Leisure Contract.

  - The Leisure Operator shall have no liability under clauses 3.1 and 11 of this Deed that is greater or of longer duration than it would have had, and shall be entitled in any proceedings by the Authority to rely on any limitation in the Leisure Contract and to raise equivalent rights in defence of liability as it would have against the Contractor under the Leisure Contract.

  - Notwithstanding anything in this Deed and not withstanding any payments which may be made by the Authority to the Leisure Operator, the Authority and the Leisure Operator will not be under any obligation to each other nor will any party have any claim or cause of action against the others unless and until the Authority has given written notice to the Leisure Operator pursuant to clause 7.1.1 or clause 7.3.

- INTELLECTUAL PROPERTY

  - The Leisure Operator shall make available to the Authority free of charge (and hereby irrevocably licences the Authority to use) all Project Data that might reasonably be required by the Authority. The Leisure Operator shall obtain all necessary licences, permissions and consents necessary for it to make the Project Data available to the Authority on these terms, for any purpose whatsoever connected with the Project and such other purposes as are reasonably foreseeable, (the Approved Purposes), and in this clause 4 "use" shall include the acts of copying, modifying, adapting and translating the material in question and/or incorporating them with other materials and the term "the right to use" shall be construed accordingly. The Authority will not hold the Leisure Operator liable for any use it may make of the Project Data for any purpose other than the Approved Purposes unless the Leisure Operator authorise such use and confirms that the Project Data is suitable for it.

  - The Leisure Operator:

    - hereby grants to the Authority, free of charge, an irrevocable non-exclusive and transferable (subject to the restrictions continued in clause 5 of this Deed) licence to use the Intellectual Property Rights that are or become vested in the Leisure Operator for the Approved Purposes;

    - shall (where any Intellectual Property Rights are or become vested in a third party) use all reasonable endeavours to procure the grant of a like licence to that referred to in clause 4.2.1 above to the Authority,

in both cases, solely for the Approved Purposes.

  - The Leisure Operator agrees on reasonable request at any time and following reasonable written prior notice to give the Authority or those authorised by it access to the Project Data and to provide copies (including copy negatives and CAD disks) thereof at the Authority's expense.

  - The Leisure Operator warrants to the Authority that the Project Data (save to the extent duly appointed sub-contractors have been used to prepare the same) is its own original work and that in any event their use in connection with the Project will not infringe the rights of any third party.

  - Where a claim or proceeding is made or brought against the Authority that arises out of the infringement of any Intellectual Property Rights or because the use of any materials, plant, machinery or equipment in connection with the Leisure Services infringes any Intellectual Property Rights of a third party then, unless such infringement has arisen out of the use of any Intellectual Property Rights by or on behalf of the Authority otherwise than in accordance with this Deed, the Leisure Operator shall indemnify the Authority at all times from and against all Direct Losses and Indirect Losses (as defined in the Agreement) arising as a result of such claims and proceedings.

- ASSIGNMENT

The benefit of and the rights of the Authority under this Deed may be assigned without the consent of the Leisure Operator on two (2) occasions only and the Authority will notify the Leisure Operator in writing following any such assignment specifying the name and address of the assignee and the date of the assignment. The Leisure Operator will not contend that any such assignee is precluded from recovering any loss resulting from any breach of this Deed (whatever the date of such breach) by reason only that that person is an assignee and not the original beneficiary hereunder or by reason that the original beneficiary or any intermediate beneficiary escaped any loss resulting from such breach by reason of the disposal of any interest in the Site[s] or that the original beneficiary or any intermediate beneficiary has not suffered any, or as much, loss

- AUTHORITY'S REMEDIES

The rights and benefits conferred upon the Authority by this Deed are in addition to any other rights and remedies it may have against the Leisure Operator including without prejudice to the generality of the foregoing any remedies in negligence.

- STEP-IN RIGHTS IN FAVOUR OF THE AUTHORITY

  - The Leisure Operator will not exercise or seek to exercise any right which may be or becomes available to it to terminate or treat as terminated or repudiated the Leisure Contract or its employment under it or discontinue or suspend the performance of any duties or obligations thereunder without first giving to the Authority not less than thirty (30) Business Days' prior written notice specifying the Leisure Operator's ground for terminating or treating as terminated or repudiated the Leisure Contract or its employment under it or discontinuing or suspending its performance thereof and stating the amount (if any) of monies outstanding under the Leisure Contract. Within such period of notice:

    - the Authority may give written notice to the Leisure Operator that the Authority will thenceforth become the client under the Leisure Contract to the exclusion of the Contractor and thereupon the Leisure Operator will admit that the Authority is its client under the Leisure Contract and the Leisure Contract will be and remain in full force and effect notwithstanding any of the said grounds;

    - if the Authority has given such notice as aforesaid or under clause 7.3, the Authority shall accept liability for the Contractor's obligations under the Leisure Contract and will as soon as practicable thereafter remedy any outstanding breach by the Contractor including for the avoidance of doubt any non-payment of sums due to the Leisure Operator that properly has been included in the Leisure Operator's specified grounds pursuant to this clause 7.1 (and which has been notified to the Authority) and which is capable of remedy; and

    - if the Authority has given such notice as aforesaid or under clause 7.3, the Authority will from the service of such notice become responsible for all sums properly payable to the Leisure Operator under the Leisure Contract accruing due after the service of the Leisure Operator's notice but the Authority will in paying such sums be entitled to the same rights of set-off and deduction as would have applied to the Contractor under the Leisure Contract.

  - Notwithstanding anything contained in this Deed and notwithstanding any payments which may be made by the Authority to the Leisure Operator, the Leisure Operator will not be under any duty to obey any direction or instruction from the Authority unless and until the Authority has given notice under clauses 7.1.1 and 7.3.

  - The Leisure Operator further covenants with the Authority that if the employment of the Contractor under the Agreement is terminated or if the Agreement is terminated by the Authority the Leisure Operator, if requested by the Authority by notice in writing and subject to clause 7.1.2 and clause 7.1.3, will accept the instructions of the Authority to the exclusion of the Contractor in respect of the Leisure Services upon the terms and conditions of the Leisure Contract and will if so requested in writing enter into a novation agreement in the form set out in Appendix 1 to this Deed whereby the Authority is substituted for the Contractor under the Leisure Contract.

  - If the Leisure Operator is requested to enter into a novation agreement pursuant to clause 7.3, the Contractor agrees to enter into the same at the request of the Authority.

  - The Contractor acknowledges that the Leisure Operator will be entitled to rely on a notice given to the Leisure Operator by the Authority under clause 7.3 as conclusive evidence that the Contractor's employment under the Agreement has been terminated or that the Agreement has been terminated by the Authority.

  - The Authority may by notice in writing to the Leisure Operator appoint another person to exercise its rights under this clause 7 subject to the Authority remaining liable to the Leisure Operator as guarantor for its appointee in respect of its obligations under this Deed.

- LIMITATION

Without prejudice to the provisions of clause 7.1, the Authority shall not be entitled to take any action or proceedings against the Leisure Operator pursuant to this Deed unless and until the Agreement has been terminated.

- INDEPENDENT ENQUIRY CLAUSE

The liability of the Leisure Operator under this Deed shall not be modified, released, diminished or in any way affected by any independent inspection investigation or enquiry into any relevant matter which may be made or carried out by or for the Authority nor by any failure or omission to carry out any such inspection, investigation or enquiry nor by the appointment by the Authority of any independent firm, company or party whatsoever to review the progress of or otherwise report to the Authority in respect of the Leisure Services nor by any action or omission of any such firm, company or party whether or not such action or omission might give rise to any independent liability of such firm, company or party to the Authority provided always that nothing in this clause 9 shall modify or affect any rights which the Leisure Operator might have but for the existence of this clause 9 to claim contribution from any third party whether under statute or at common law.

- NO VARIATION TO LEISURE CONTRACT WITHOUT AUTHORITY'S CONSENT

The Contractor and the Leisure Operator undertake with the Authority not to vary or depart from the terms and conditions of the Leisure Contract without the prior written consent of the Authority (such consent to be sought in accordance with the Review Procedure where that procedure applies to the variation or departure in question), and agree that no such variation or departure made without such consent shall be binding upon the Authority, or affect or prejudice the Authority's rights hereunder, or under the Leisure Contract or in any other way.

- SEVERABILITY

If any term, condition or provision of this Deed shall be held to be invalid, unlawful or unenforceable to any extent, such term, condition or provision shall not affect the validity, legality and enforceability of the other provisions of or any other documents referred to in this Agreement.

- WAIVER

  - No term or provision of this Deed shall be considered as waived by any party to this Deed unless a waiver is given in writing by that party.

  - No waiver under clause 12.1 shall be a waiver of a past or future default or breach, nor shall it amend, delete or add to the terms, conditions or provisions of this Deed unless (and only to the extent) expressly stated in that waiver.

- THE CONTRACTOR'S INCLUSION AS PARTY

The Contractor has agreed to be a party to this Deed for the purpose of clause 8 and for acknowledging that the Leisure Operator shall not be in breach of the Leisure Contract by complying with the obligations imposed on it by this Deed.

- COUNTERPARTS

This Deed may be executed in one or more counterparts. Any single counterpart or a set of counterparts executed, in either case, by all the parties shall constitute a full and original instrument for all purposes.

- GOVERNING LAW AND JURISDICTION

This Deed and all non-contractual obligations in connection with this Deed shall be governed by and construed in all respects in accordance with the laws of England and Wales. The English Courts shall have exclusive jurisdiction to settle any disputes which may arise out of or in connection with this Deed.

- THIRD PARTY RIGHTS

No term of this Deed is enforceable under the Contracts (Rights of Third Parties) Act 1999 by a person who is not party to this Deed. This clause 16 does not affect any right or remedy of any person that exists or is available otherwise than pursuant to that Act.

- NOTICES

Any notice to be given by either party hereunder will be sufficiently served if  sent by hand, by facsimile transmission or by post to the registered office or if there is none the last known address of the party to be served. Any notice sent by hand will be deemed to be served on the date of delivery and any notice sent by facsimile transmission will be deemed to be served in full at the time recorded on the facsimile report sheet, provided that if any notice sent by hand or facsimile is sent after 4.45 pm on any day it will be deemed to be served on the next Business Day. Any notice sent by post will be deemed to have been duly served at the expiration of forty-eight (48) hours after the time of posting if the end of that period falls before 4.45pm on a Business Day and otherwise on the next Business Day.

IN WITNESS whereof this document is executed by the parties as a Deed and delivered on the date stated at the beginning of this Deed

EXECUTED as a Deed by the LEISURE OPERATOR

acting by two of its directors or a

director and its secretary:

……………………………….

Director

………………………………..

Director/Secretary

EXECUTED AS A DEED by the Authority acting by two authorised signatories:

…………………………………

Authorised Signatory

…………………………………

Authorised Signatory

EXECUTED as a Deed by

[CONTRACTOR]

acting by two of its directors or a

director and its secretary:

…………………………………

Director

…………………………………

Director/Secretary

Appendix 1

Form of Deed of Novation

THIS DEED is made on  						20

BETWEEN:

(1)	[CONTRACTOR'S LEISURE OPERATOR] (Company No.                 ) whose registered office is at                                                        (the Leisure Operator);

(2)	[AUTHORITY] of                        (the Authority), which expression includes its permitted successors in title and assigns); and

(3)	CONTRACTOR (Company No.                 ) whose registered office is at               (the Contractor).

WHEREAS

(A)	By a design, build, operate and maintain agreement dated [	] (the Agreement) the Authority has appointed the Contractor to carry out in relation to [		] (the Sites) the design and construction of the Works (as defined in the Agreement).

(B)	The Leisure Operator has been appointed by the Contractor under a contract dated [           ] (the Leisure Contract) to carry out the Leisure Services.

(C)	[The employment of the Contractor under the Agreement has been terminated] [The Agreement has been terminated by the Authority].

(D)	The Contractor has transferred or agreed to transfer its interest in (or granted or agreed to grant a subordinate interest in) the Sites to the Authority.

(E)	The parties have agreed to novate the Leisure Contract to the Authority on the terms set out below.

IT IS AGREED

- Novation of Leisure Contract

The Leisure Contract is hereby novated from the Contractor and the Leisure Operator to the Authority and the Leisure Operator.

- Release of the Contractor

The Contractor shall no longer owe any duty or obligation to the Leisure Operator under or in respect of the Leisure Contract whether by virtue of its terms or by virtue of any breach or otherwise.

- Release of the Leisure Operator

The Leisure Operator shall no longer owe any duty or obligation to the Contractor under or in respect of the Leisure Contract whether by virtue of its terms or by virtue of any breach or otherwise.

- Binding of the Leisure Operator to the Authority

  - The Leisure Operator binds itself to the Authority in the terms of the Leisure Contract as if the Authority were and always had been named in the Leisure Contract in place of the Contractor.

  - The Leisure Operator warrants to the Authority that prior to the date of this Deed it has performed and that it will continue to perform its duties and obligations as required by and in accordance with the terms of the Leisure Contract.

  - The Authority shall not be precluded from recovering any losses incurred by the Authority or the Contractor resulting from any breach of clause 4.2 by reason that (if it be the case) the acts or omissions causing such breach occurred before this Deed took effect, or that the Contractor will not incur or has not or would not have incurred any such losses. No waiver by the Contractor, either express or implied, will affect the Leisure Operator's liability to the Authority pursuant to this clause 4.

- Binding of the Authority to the Leisure Operator

The Authority binds itself to the Leisure Operator in the terms of the Leisure Contract as if the Authority were and always had been named in the Leisure Contract in place of the Contractor and as if all acts and omissions of the Contractor (including any wrongful acts or omissions) under and in respect of the Leisure Contract were the acts and omissions of the Authority.

- Vesting of remedies in the Authority

All rights of action and remedies vested in the Contractor against the Leisure Operator under and in respect of the Leisure Contract shall hereupon vest in the Authority.

- Vesting of remedies against the Authority

All rights of action and remedies vested in the Leisure Operator against the Contractor under and in respect of the Leisure Contract shall hereinafter lie against the Authority.

- Affirmation of Leisure Contract

Subject to the terms of this Deed the Leisure Contract shall remain in full force and effect.

- Third Party Rights

No term of this Deed is enforceable under the Contracts (Rights of Third Parties) Act 1999 by a person who is not party to this Deed. This clause 9 does not affect any right or remedy of any person that exists or is available otherwise than pursuant to that Act.

- Governing Law and Interpretation

This Deed and all non-contractual obligations in connection with this Deed shall be governed by and construed in all respects in accordance with the laws of England and Wales. The English Courts shall have exclusive jurisdiction to settle any disputes which may arise out of or in connection with this Deed.

IN WITNESS of which this document is executed as a deed and is delivered on the date first set out above

SCHEDULE 8

REVIEW PROCEDURE

- REVIEW PROCEDURE

The provisions of this Schedule 8 shall apply whenever any item, documents or course of action are required to be reviewed, approved or otherwise processed in accordance with the Review Procedure.

Each submission under the Review Procedure shall be accompanied by a copy of the document to be reviewed (including, where applicable, any Reviewable Design Data) or a statement of the proposed course of action (the entire contents of a submission being referred to in this Schedule 8 as a Submitted Item). In relation to each Submitted Item, the following procedure shall apply:

as soon as possible and, if the Submitted Item comprises:

an item of Reviewable Design Data;

a revised Construction Programme; or

a document or proposed course of action submitted in the case of an emergency,

within ten (10) Business Days of the date of receipt of a submission (or re-submission, as the case may be) of the Submitted Item to the Authority's Representative (or such other period as the parties may agree), the Authority's Representative shall return one (1) copy of the relevant Submitted Item to the Contractor endorsed "no comment" or (subject to and in accordance with paragraph 1.3) "comments" as appropriate; and

if the Authority's Representative fails to return a copy of any Submitted Item (including any re-submitted Submitted Item) duly endorsed in accordance with this paragraph 1.2, within ten (10) Business Days (or within such other period as the parties may agree in writing) of the date of its submission to the Authority's Representative, then the Authority's Representative shall be deemed to have returned the Submitted Item to the Contractor endorsed "no comment" (and, in the case of the Reviewable Design Data, endorsed "Level A - no comment").

If the Authority's Representative raises comments on any Submitted Item in accordance with this paragraph 1.3 he shall state the ground upon which such comments are based and the evidence or other information necessary to substantiate that ground. To the extent that the Authority's Representative comments on a Submitted Item other than on the basis set out in this Schedule 8, or fails to comply with the provisions of this paragraph 1.3, the Contractor may, in its discretion, either:

request written clarification of the basis for such comments and, if clarification is not received within five (5) Business Days of such request by the Contractor, refer the matter for determination in accordance with the Dispute Resolution Procedure; or

at its own risk, and without prejudice to clause 14 (Design Development) proceed with further design or construction disregarding such comments.

FURTHER INFORMATION

The Contractor shall submit any further or other information, data and documents that the Authority's Representative reasonably requires in order to determine whether he has a basis for raising comments or making objections to any Submitted Item in accordance with this Schedule 8. If the Contractor does not submit any such information, data and documents, the Authority's Representative shall be entitled to:

comment on the Submitted Item on the basis of the information, data and documents which have been provided; or

object to the Submitted Item on the grounds that insufficient information, data and documents have been provided to enable the Authority's Representative to determine whether he has a legitimate basis for commenting or objecting in accordance with this Schedule 8.

GROUNDS OF OBJECTION

The expression "raise comments" in this paragraph 3 shall be construed to mean "raise comments or make objections" unless the contrary appears from the context. The Authority's Representative may raise comments in relation to any Submitted Item on the grounds set out in the paragraph above or on the grounds that the Submitted Item would (on the balance of probabilities) breach any Legislation or not be in accordance with any Necessary Consent, but otherwise may raise comments in relation to a Submitted Item only as follows:

in relation to any Submitted Item:

the Contractor's ability to perform its obligations under this Agreement would (on the balance of probabilities) be adversely affected by the implementation of the Submitted Item; or

the implementation of the Submitted Item would (on the balance of probabilities) adversely affect any right of the Authority under this Agreement or its ability to enforce any such right;

in relation to any Submitted Item submitted pursuant to clause 7.1 (Ancillary Documents):

the Authority's ability to perform its obligations under this Agreement would be adversely affected by the proposed course of action;

the Authority's ability to carry out any of its statutory functions would (on the balance of probabilities) be adversely affected by the proposed course of action;

the proposed course of action would be likely to result in an increase to the Authority's liabilities or potential or contingent liabilities under this Agreement;

the proposed course of action would adversely affect any right of the Authority under this Agreement or its ability to enforce any such right; or

the Contractor's ability to perform its obligations under this Agreement would be materially adversely affected by the proposed course of action;

in relation to Reviewable Design Data submitted pursuant to clause 14 (Design Development):

the Submitted Item is not in accordance with the Authority's Requirements; or

the Submitted Item is not in accordance with the Construction Proposals;

in relation to any proposed variation to the Construction Proposals relating to the Works:

the Submitted Item would increase the likelihood of Performance Adjustment Points and/or Performance Adjustments being applied pursuant to clause 37 (Payment during the Services Period) and Schedule 6 (Payment and Performance Monitoring System) following the [relevant] Services Availability Date;

would result in a decrease or worsening of the quality of the Site[s] following the [relevant] Services Availability Date; or

save where such proposed variation is necessitated due to a Qualifying Change in Law, a Compensation Event or an Authority Change, would lead to an increase in the Annual Payment where it is a Deficit Annual Payment or a decrease in the Annual Payment where it is a Surplus Annual Payment;

in relation to the submission of any revised Construction Programme on the ground that the revised Construction Programme:

would not (on the balance of probabilities) enable any part of the Works to be completed by the [relevant] Planned Services Availability Date;

in relation to the submission of any proposed revision or substitution for the Service Delivery Proposals on the grounds that:

the proposed revision or substitution is not in accordance with Good Industry Practice;

the performance of the relevant Services in accordance with the proposed revision or substitution would (on the balance of probabilities):

be less likely to achieve compliance with relevant parts of the Authority's Requirements;

have an adverse effect on the provision by the Contractor of the Services or on the safety of any Users of the [Facility/Facilities]; or

would cause the Authority to incur material additional expense; or

the proposed revision or substitution would (on the balance of probabilities) result in an inferior standard of performance of the relevant Services to the standard of performance in accordance with the Service Delivery Proposals prior to such proposed revision or substitution;

in relation to the submission of any Schedule of Programmed Maintenance, any revision to any Schedule of Programmed Maintenance on the grounds that:

carrying out the programmed maintenance in the period or at the times suggested would (on the balance of probabilities) interfere with the operations of the [Facility/Facilities] and such interference could be avoided or mitigated by the Contractor rescheduling the Programmed Maintenance;

the safety of Users or staff would (on the balance of probabilities) be adversely affected; or

the period for carrying out the Programmed Maintenance would (on the balance of probabilities) exceed the period reasonably required for the relevant works;

in relation to any Submitted Item submitted pursuant to clause 28 (Use of the [Facility/Facilities] [and Surplus Share]), the proposed use of the Facilities by third parties:

could reasonably be expected to impair the provision of the Services or such use is not compatible with the use of the [Facility][Facilities] as [a] community leisure centre[s];

the use is one which the Authority (acting reasonably) has objected to;

the use involves the sponsorship, advertisement or other direct involvement by an organisation, entity or person engaged in, or with substantial interest in the production or sale of products containing or derived from tobacco or the manufacture of sale of arms and weapons;

the use could be expected to involve undue violence (provided that the provision of organised sport shall not be considered undue violence) or otherwise be incompatible with the ethos of the Authority;

in relation to any submission to defer the replacement of any part of the [Facility/Facilities] made pursuant to clause 23.6 (Programmed Replacement) on the grounds that:

the proposed deferral is not in accordance with Good Industry Practice;

the performance of the relevant Services in accordance with the proposed deferral would (on the balance of probabilities):

be less likely to achieve compliance with relevant parts of the Authority's Requirements;

have an adverse effect on the provision of the Services or on the safety of any Users; or

would cause the Authority to incur material additional expense;

the proposed deferral would (on the balance of probabilities) result in an inferior standard of performance of the relevant Services to the standard of performance in accordance with the Service Delivery Proposals prior to such proposed revision or substitution; or

would result in a decrease or worsening of the quality of the Sites;

EFFECT OF REVIEW

Any Submitted Item which is returned or deemed to have been returned by the Authority's Representative endorsed "no comment" (and in the case of Reviewable Design Data, endorsed "Level A - no comment") may be complied with or implemented (as the case may be) by the Contractor.

In the case of any Submitted Item other than Reviewable Design Data, if the Authority's Representative returns the Submitted Item to the Contractor endorsed "comments", the Contractor shall comply with such Submitted Item after amendment in accordance with the comments unless the Contractor disputes that any such comment is on grounds permitted by this Agreement, in which case the Contractor or the Authority's Representative may refer the matter for determination in accordance with clause 64 (Dispute Resolution).

In the case of a Submitted Item comprising Reviewable Design Data, if the Authority's Representative returns the Submitted Item endorsed other than "Level A - no comment", the Contractor shall:

where the Authority's Representative has endorsed the Submitted Item "Level B - proceed subject to amendment as noted", either proceed to construct or proceed to the next level of design of the part of the Works to which the Submitted Item relates but take into account any amendments required by the Authority's Representative in his comments;

where the Authority's Representative has endorsed the Submitted Item "Level C - subject to amendment as noted", not act upon the Submitted Item, amend the Submitted Item in accordance with the Authority's Representative's comments and re-submit the same to the Authority's Representative in accordance with paragraph 4.4.

where the Authority's Representative has endorsed  the Submitted  Item  "Level D - rejected" not act upon the Submitted Item, amend the Submitted Item and re-submit the Submitted Item to the Authority's Representative in accordance with paragraph 4.4,

unless the Contractor disputes that any such comment or proposed amendment is on grounds permitted by this Agreement, in which case the Contractor or the Authority's Representative may refer the matter for determination in accordance with the Dispute Resolution Procedure and, save as permitted by the provisions of clause 14.3, the Contractor shall not act on the Submitted Item until such matter is so determined or otherwise agreed.

Within ten (10) Business Days of receiving the comments of the Authority's Representative on any Submitted Item comprising Reviewable Design Data, the Contractor shall (except in the case contemplated in paragraph 4.3.1) send a copy of the Submitted Item as amended to the Authority's Representative pursuant to paragraph 4.3 and the provisions of this Schedule 8 (Review Procedure) shall apply (changed according to context) to such re-submission.

The return or deemed return of any Submitted Item endorsed "no comment" (or in the case of Reviewable Design Data endorsed "Level A - no comment" or otherwise endorsed in accordance with paragraphs 4.3.1 or 4.3.2) shall mean that the relevant Submitted Item may be used or implemented for the purposes for which it is intended but, save to the extent expressly stated in this Agreement such return or deemed return of any Submitted Item shall not otherwise relieve the Contractor of its obligations under this Agreement nor is it an acknowledgement by the Authority that the Contractor has complied with such obligations.

DOCUMENT MANAGEMENT

The Contractor shall issue [NUMBER] copies of all Submitted Items to the Authority's Representative and compile and maintain a register of the date and contents of the submission of all Submitted Items.

The Contractor shall compile and maintain a register of the date of receipt and content of all Submitted Items that are returned or deemed to be returned by the Authority's Representative.

No review, comment or approval by the Authority shall operate to exclude or limit the Contractor's obligations or liabilities under this Agreement (or the Authority's rights under this Agreement).

VARIATIONS

Subject to paragraph 6.2, no approval or comment or any failure to give or make an approval or comment under this Schedule 8 shall constitute an Authority Change save to the extent provided in this Schedule 8.

If, having received comments from the Authority's Representative, the Contractor considers that compliance with those comments would amount to an Authority Change, the Contractor shall, before complying with the comments, notify the Authority of the same and, if it is agreed by the parties or determined pursuant to the Dispute Resolution Procedure that an Authority Change would arise if the comments were complied with, the Authority may, if it wishes, implement the Authority Change and it shall be dealt with in accordance with Schedule 24 (Change Protocol). Any failure by the Contractor to notify the Authority that it considers compliance with any comments of the Authority's Representative would amount to an Authority Change shall constitute an irrevocable acceptance by the Contractor that any compliance with the Authority's comments shall be without cost to the Authority and without any extension of time.

No alteration or modification to the design, quality and quantity of the Works arising from the development of detailed design or from the co-ordination of the design shall, subject to paragraph 6.1, be construed or regarded as an Authority Change.

REVIEWABLE DESIGN DATA

[LIST TO BE INSERTED]

SCHEDULE 9

Part 1 – Prohibited Materials

Materials which are generally known at the time of specification to be deleterious to health and safety or to the durability of works or of any part thereof in the particular circumstances in which they are used or are not in accordance with British or European standard or codes of practice current at the time of specification, (or where no such standard exists do not conform with a British Board of Agrément Certificate), or which do not comply with the guidance set out in "Good Practice in the Selection of Construction Materials 2011" published by the British Council of Offices.

Part 2 – Works Stipulations

During the carrying out of the Works the Contractor shall (or shall procure that those carrying out the Works shall):

- not use or occupy or permit the Site[s] to be used or occupied for any purpose other than for the carrying out of the Works;

- not deposit or manufacture or permit to be deposited or manufactured on the Site[s], any materials which are not required for the carrying out of the Works and not deposit or manufacture on the Site[s] any materials;

- not sell or dispose of any earth, clay, sand, gravel, chalk or other material from the Site[s] or permit or suffer the same to be removed, except so far as shall be necessary for the proper execution of the Works, without the consent of the Authority (which shall not be unreasonably withheld);

- transport all surplus materials arising from the Works and arrange for the tipping of the same at such places as may lawfully be used for tipping and the Contractor shall ensure that (until such time as such material is lawfully tipped) such materials shall not cause or give rise to pollution of the environment as defined by Section 29(3) of the Environmental Protection Act 1990;

- [not permit the storage of materials or the parking of vehicles in the immediate external vicinity of the boundaries of the Site[s] by the Contractor or those involved in the carrying out of the Works other than for reasonable periods necessary for loading and unloading or as set out in the Construction Proposals;]

- ensure that all vehicles leaving the Site[s] are adequately cleaned to prevent the deposit of waste materials, dust and debris on any Adjoining Property and/or the Buildings;

- not gain access to or egress from the Site[s] except via such access points and access ways included in the grant of the Ancillary Rights; and

- not permit any oil, grease or deleterious, dangerous, poisonous, explosive or radioactive matter to be discharged from the Site[s] into any ditches or Services Media on the Site[s] and/or any Adjoining Property and/or the Buildings and shall not permit or suffer the blockage of any such ditches and Services Media by reason of anything done or omitted to be done on the Site[s], and in the event of any such discharge or blockage shall comply with any requirements of the Environment Agency or any other Relevant Authority in so far as such requirements relate to or affect the Works.

SCHEDULE 10

LIAISON PROCEDURE

- PROJECT LIAISON GROUP

The Authority and the Contractor shall establish and maintain throughout the Contract Period a project liaison group (the Project Liaison Group), consisting of [three (3)] members from the Authority, [three (3)] members from the Contractor, a chairman (the Chairman), and, where a majority of the Project Liaison Group so determines, additional members being properly qualified to participate in discussions relating to any particular matter, these members having no voting rights, which shall have the functions described below.

The Contractor and the Authority agree that for the duration of the Works the Contractor shall procure the attendance of the Building Contractor during such parts of meetings of the Project Liaison Group as the parties shall agree. The Contractor and the Authority agree that during the Services Period the Contractor shall procure the attendance of the Leisure Operator and the FM Contractor during such parts of meetings of the Project Liaison Group as the parties shall agree.

Each party will have the right to make reasonable objections to the other party's proposed members or the Chairman but not so as to frustrate the rotation of the chairmanship.

Should the Authority and the Contractor agree that the best interests of the Project would be served by the removal of one or more members of the Project Liaison Group, they may so direct in writing and the Authority or the Contractor, as the case may be, will put forward to the Authority and Contractor the name of a substitute member of the Project Liaison Group.

The relevant person shall with the consent of the other party, such consent not to be unreasonably withheld or delayed, become a member of the Project Liaison Group as from the date of its next meeting.

FUNCTIONS

The functions of the Project Liaison Group shall be:

to provide a means for the joint review of all aspects of the performance of this Agreement;

to provide a forum for joint strategic discussion and consideration of all aspects with regard to this Agreement including ensuring dissemination of information and consideration of the views of all the stakeholders connected with the Project; and

consideration of issues relating to:

Necessary Consents;

the Construction Programme;

provision of the Services;

Authority Changes; and

[others to be listed].

ROLE

The role of the Project Liaison Group is to make recommendations to the Authority and to the Contractor, which the Authority and the Contractor may accept or reject at their complete discretion. Neither the Project Liaison Group itself, nor its members acting in that capacity, shall have any authority to vary any of the provisions of this Agreement or to make any decision binding on the parties. The Authority and the Contractor shall not rely on any act or omission of the Project Liaison Group, or any members of the Project Liaison Group acting in that capacity, so as to give rise to any waiver or personal bar in respect of any right, benefit or obligation of the Authority or of the Contractor under this Agreement. No discussion, review or recommendation by the Project Liaison Group shall relieve the Authority or the Contractor of any liability or vary any such liability or any right or benefit.

REPRESENTATIVES

The Authority and the Contractor may appoint their representatives on the Project Liaison Group and remove those representatives and appoint replacements, by written notice delivered to the other at any time. A representative on the Project Liaison Group may appoint and remove an alternate (who may be another representative of that party) in the same manner. If a representative is unavailable (and the other parties' representative may rely on the alternate's statement that the representative is unavailable) his alternate shall have the same rights and powers as the representative.

PRACTICES AND PROCEDURES

Subject to the provisions of this Schedule 10, the members of the Project Liaison Group may adopt such procedures and practices for the conduct of the activities of the Project Liaison Group as they consider appropriate, from time to time, provided that the quorum for a meeting of the Project Liaison Group shall be [four (4)] (with at least [two (2)] members of the Authority and [two (2)] members of the Contractor present).

RECOMMENDATIONS

Recommendations and other decisions of the Project Liaison Group must have the affirmative vote of all those voting on the matter, which must include not less than one (1) representative of the Authority and not less than one (1) representative of the Contractor.

VOTING

Each member of the Project Liaison Group shall have one (1) vote.

CHAIRMAN

The Chairman of the Project Liaison Group shall be nominated by the Authority and by the Contractor alternately every six (6) months during the Contract Period (commencing with the Authority). The Chairman shall be in addition to each party's representatives on the Project Liaison Group. The Chairman shall not have a vote.

FREQUENCY OF MEETINGS

The Project Liaison Group shall meet at least once every month during the Works Period and thereafter at least once every quarter.

CONVENING OF MEETINGS

Any member of the Project Liaison Group may convene a meeting of the Project Liaison Group at any time.

NOTICES OF MEETINGS

Not less than ten (10) Business Days' notice (identifying the agenda items to be discussed at the meeting) shall be given to convene a meeting of the Project Liaison Group, except that in emergencies, a meeting may be called at any time on such notice as may be reasonable in the circumstances.

ATTENDANCE AT MEETINGS

Meetings of the Project Liaison Group should normally involve the attendance (in person or by alternative) of representatives at the meeting. Where the representatives of the Project Liaison Group consider it appropriate (by affirmative vote of all those voting on the matter which must include not less than one (1) representative of the Authority and one (1) representative of the Contractor) meetings may also be held by telephone or another form of telecommunication by which each participant can hear and speak to all other participants at the same time.

MINUTES

Minutes of all decisions (including those made by telephone or other telecommunication form) and meetings of the Project Liaison Group shall be kept by the Contractor and copies circulated promptly to the Authority, normally within ten (10) Business Days of the making of the decision or the holding of the meeting. A full set of minutes shall be kept by the Contractor and shall be open to inspection by the Authority at any time, upon request.

[PARTNERING CHARTER

The Partnering Charter appended at Appendix 1 of this Schedule 10 (Liaison Procedure) shall take effect.]

APPENDIX 1

Partnering Charter

- For the duration of the Agreement, this "Partnering Charter" will apply. The parties shall each work cooperatively with each other to discharge their respective responsibilities under this Agreement and to provide strategic direction for the provision of the Services and the operation of the [Facility/Facilities]. The parties will provide support to the Project Liaison Group and its functions shall include:-

  - Considering and agreeing annual participation targets- establish and agree appropriate targets on an annual basis in accordance with the Agreement and monitor effectiveness for collating data and reporting against selected targets

  - Monitoring  Service performance - ensure the Services are delivered to the standards required by the Agreement, in particular by commissioning qualitative and quantitative reports on performance and implementing/reviewing procedures for self-monitoring and reporting through the use of the agreed key performance indicators.

  - Creating and monitoring a Risk and Project Register - establish a joint approach to risk and project management by creating and regularly reviewing a register of the risks and projects associated with the implementation and on-going Service delivery and determining which of the parties should assume responsibility/are responsible for the risk(s) and project actions.

  - Being Innovative - develop and/or consider proposals for continuous service improvement and for greater cost-effectiveness in the delivery of the Services. This may be implemented by studying examples of best practice elsewhere, implementing studies, reports and projects managed by the Authority and the Contractor.

  - Being Proactive - anticipate and consider proposals for any change in the Services that may be required, for example, by any change in law or policy, or by any change in economic or social circumstances or expectations.

  - Ensuring a partnering ethos – fully and properly consider any representations that may be made by either party concerning any matter that appears to be inconsistent with the parties commitment to work cooperatively.

  - Resolving Differences - seek the rapid and fair resolution of any differences between the parties. The parties commit to discuss problems as soon as they arise and to work together in a no blame culture.

  - Reviewing Service performance – review monthly/annual reports prepared and consider/discuss openly the parties' opinions on the state of the partnering relationship, successes and shortcomings over a Contract Year, and proposals for improvement in the future.

- The Authority's Representative and the Contractor's Representative will meet regularly to ensure that the day-to-day operational requirements of the Agreement are being met. The dates for these meetings will be agreed between the parties and will vary according to operational requirements.

- Furthermore, the parties each accept a duty to:

  - make a sincere effort to understand the other party's obligations, goals, expectations, duties and objectives in the performance of the Services and operation of the [Facility/Facilities];

  - be just and faithful in all dealings in respect of the relationship between the parties, the Agreement and the Project, and to give a true account of such dealings;

  - work at all times within a spirit of co-operation to ensure the delivery of the Services to the required standard;

  - resolve differences that may arise in relation to the Agreement by good faith discussions and negotiations wherever possible;

  - communicate clearly and effectively, and in a timely manner, on all matters relating to the Agreement;

  - make the most efficient use of resources, and seek to achieve cost effective savings and to enhance User participation and revenue to the benefit of both parties;

  - make every reasonable endeavour to ensure that all persons engaged on the Project diligently and faithfully employ themselves to bring about its performance to a high standard;

  - give an early warning to the other party of any material mistakes, discrepancies or omissions of which either party becomes aware within the Agreement, and offer fair and reasonable solutions where practicable; and

  - give an early warning to the other party of any matter that they become aware of that could affect the achievement of any obligations, goals, expectations, duties and objectives in the performance of the Services and operation of the [Facility/Facilities].

SCHEDULE 11

[WARRANTED] DATA

SCHEDULE 11 – [WARRANTED] DATA

Part 1 – Authority Data

Authority employees

| STAFF REF NO | CONTRACT HOURS | WTE | SEX (M/F) | AGE | D.O.B | DATE OF COMMENCEMENT | CONTINUOUS SERVICE START DATE | GRADE | CONTRACTED HOURS INC WHETHER FULL OR PART TIME | RATE/ HOUR (£) INC SCALE AND POINT | N.I. CODE LETTER (A OR D) | SUPERANNUABLE (Y/N) AND COMMENCEMENT OF PENSIONABLE SERVICE | EMPLOYER AND EMPLOYEE CONTRIBUTION RATES | ALLOWANCE/ DEDUCTION CODE | JOB TITLE AND DESCRIPTION | SITE AND DEPARTMENT IN WHICH EMPLOYED | NOTICE PERIOD | ACCOMMODATION PROVIDED | HOLIDAY PAY | NOTICE ENTITLEMENT | REDUNDANCY PAY | BONUS ENTITLEMENT(S) | CONTRACTUAL REMUNERATION OR OTHER BENEFITS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 12 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 13 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 14 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 15 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 16 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 17 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 19 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Third Party Relevant Employees

| STAFF REF NO | CONTRACT HOURS | WTE | SEX (M/F) | AGE | D.O.B | DATE OF COMMENCEMENT | CONTINUOUS SERVICE START DATE | GRADE | CONTRACTED HOURS INC WHETHER FULL OR PART TIME | RATE/ HOUR (£) INC SCALE AND POINT | N.I. CODE LETTER (A OR D) | SUPERANNUABLE (Y/N) AND COMMENCEMENT OF PENSIONABLE SERVICE | EMPLOYER AND EMPLOYEE CONTRIBUTION RATES | ALLOWANCE/ DEDUCTION CODE | JOB TITLE AND DESCRIPTION | SITE AND DEPARTMENT IN WHICH EMPLOYED | NOTICE PERIOD | ACCOMMODATION PROVIDED | HOLIDAY PAY | NOTICE ENTITLEMENT | REDUNDANCY PAY | BONUS ENTITLEMENT(S) | CONTRACTUAL REMUNERATION OR OTHER BENEFITS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 12 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 13 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 14 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 15 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 16 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 17 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 19 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Part 2 – Contractor Warranted Data

- Registered Name of Contractor:

[PREFERRED BIDDER TO COMPLETE]

Registered Office of Contractor:

[PREFERRED BIDDER TO COMPLETE]

Company Registration Number of Contractor:

[PREFERRED BIDDER TO COMPLETE]

Directors of Contractor:

[PREFERRED BIDDER TO COMPLETE]

Shareholders of Contractor (with respective shareholdings):

[PREFERRED BIDDER TO COMPLETE]

Registered Name of Holdco:

[PREFERRED BIDDER TO COMPLETE]

Registered Office of Holdco:

[PREFERRED BIDDER TO COMPLETE]

Company Registration Number of Holdco:

[PREFERRED BIDDER TO COMPLETE]

Directors of Holdco:

[PREFERRED BIDDER TO COMPLETE]

Shareholders of Holdco (with respective shareholdings):

[PREFERRED BIDDER TO COMPLETE]

Part 3 – Proposed Workforce Information

SCHEDULE 12

INDICATIVE PAYMENT SCHEDULE

- CONTRACT SUM

| The Contract Sum for the provision of the Works is: | £ |
| --- | --- |

PAYMENT PROFIELE

| Month 1 (etc.) | Value | Cumulative Value |
| --- | --- | --- |

SCHEDULE 13

TITLE MATTERS

Part 1 – Title Warranties

Save as disclosed in the Disclosed Title Matters, the Replies to Enquiries and the Disclosed Searches the Authority warrants that for the period of this Agreement:

- each and every Site is in the sole legal and beneficial ownership of the Authority;

the Site[s] are not subject to any Adverse Rights;

no one is in adverse possession of the Site[s] or has acquired or is acquiring any Adverse Rights affecting the Site[s];

there are no disputes, claims, actions, demands or complaints in respect of the Site[s] that are outstanding or that are expected by the Authority and that would prevent or disrupt the carrying out of the Works and/or the provision of Services;

from the Commencement Date no person, other than [the Authority], has any right (actual or contingent) to possession, occupation or use of or interest in the Site[s];

the information set out or described in the Replies to Enquiries has been prepared after due and careful enquiry and is true, accurate and complete as at the date of this Agreement; and

the Disclosed Title Matters comprise all of the documents relating to the title to the Site[s].

Part 2 – Disclosed Title Matters

Per Site:

Official Copies and plan (where registered land) / epitome of title (where land is unregistered) and copies of any title documents.

Part 3 – Replies to Enquiries

Per Site:

Replies to relevant Standard Pre-contract Enquiries (CPSE).

Replies to Standard Pre-contract Enquiries (Supplemental) Property subject to tenancies (commercial) (CPSE.2 v2.2).

Part 4 – Disclosed Searches

Per Site:

Search:

Date:

Official search in the Index Map (SIM).

Local search certificate and replies to enquiries in CON29R Enquiries of Local Authority (2007) and any other relevant enquiries in CON29O Optional Enquiries of Local Authority (2007).

Commercial drainage and water enquiries.

Common land and town and village greens search.

Enquiries of The Coal Authority as to past, present and future mining operations in proximity to the Site.

Where title to the Site is not registered, Land Charges Act searches against every estate owner who was a party to any transaction, or concerned in any event, comprised in the relevant title (see Section 25 of the Law of Property Act 1969) where there is no clear search with the title deeds.

Land Registry search (whether of whole or part), date of expiry of priority and name of party having benefit of priority period.

Where title to the Site is not registered, date of search at the Companies Registry of the file of all companies disclosed by the documents of title as estate owners of the Site since the root of title.

Enquiries of the Highways Authority to ascertain the boundaries of publicly maintainable highways abutting, and any footpaths or rights of way affecting, the Site.

Details of other searches or enquiries we considered to be appropriate:

- BT;

Gas Utility Search;

Electricity Company Search;

Highways (including footpaths);

London Transport:

Dockland Light Railway;

London Underground Search;

British Waterways – Commercial (canals/lakes etc.);

Chancel Liability Search;

Cheshire Brine Subsidence Compensation Board (re salt extraction in Cheshire area);

Radon;

Clay (Ball/China);

Tin Mining;

Limestone; and

Forestry.

SCHEDULE 14

Insurances

This Schedule 14 comprises five Parts:

PART 1: Policies to be taken out by the Contractor and maintained during the Works Period

PART 2: Policies to be taken out by the Contractor and maintained during the Services Period

PART 3: Endorsements

PART 4: Broker's Letter of Undertaking

PART 5: Definitions

Part 1

Policies to be taken out by the Contractor and maintained during the Works Period

Common to each policy in Part 1 (unless stated otherwise):

Insureds

- Authority;

Contractor;

Building Contractor;

FM Contractor;

Sub-contractors to Insureds 2, 3 and 4, of any tier;

[lenders]; and

Consultants - for their site activities only,

each for their respective rights and interests in the Project.

- Contractors' "All Risks" Insurance

Insured Property

The permanent and temporary works, materials (including but not limited to equipment supplied by the Authority), goods, plant and equipment for incorporation in the Works (other than constructional plant, tools, accommodation and equipment belonging to or the responsibility of the Contractor or the Building Contractor or its or their sub-contractors) and all other property used or for use in connection with the Works.

Coverage

"All risks" of physical loss or damage to the Insured Property unless otherwise excluded.

Sum Insured

At all times an amount not less than the full reinstatement or replacement value of the Insured Property, but not less than the value specified in the Building Contract, plus provision to include Principal Extensions as appropriate.

Maximum Deductible

£ [      ]

Territorial Limits

United Kingdom, including offsite storage and whilst in transit.

Period of Insurance

From the date of the Agreement until the Services Availability Date and thereafter in respect of defects liability until expiry of the 12 months' defects liability period.

Cover Features and Extensions

Terrorism.

Munitions of war clause.

Professional fees clause (including Authority's advisers' fees incurred during any period of reinstatement).

Debris removal clause.

72 hour clause.

European Union local authorities clause.

Free issue materials clause.

[115]% increase clause.

Additional costs of completion clause.

Automatic reinstatement of sum insured clause.

Plans and documents clause.

Loss minimisation.

Testing/commissioning period clause.

Principal Exclusions

War and related perils (UK market agreed wording).

Nuclear/radioactive risks (UK market agreed wording).

Pressure waves caused by aircraft and other aerial devices travelling at sonic or supersonic speeds.

Wear, tear and gradual deterioration.

Consequential financial losses.

Cyber risks.

Delay in Start Up Insurance

Insureds

Contractor;

[FM Contractor;] and

[Leisure Operator],

each for their respective rights and interests in the Project.

Indemnity

In respect of:

loss of anticipated Revenue (as defined in Part 5 of this Schedule) during the Minimum Indemnity Period arising from a delay in completion of the Project as a result of loss or damage covered under the Contractors' All Risks' Insurance effected in accordance with paragraph 1 of Part 1 of this Schedule, including physical loss or damage which would be indemnifiable but for the application of any deductible; and

the additional expenditure necessarily and reasonably incurred for the purpose of avoiding or reducing the loss of Revenue (as defined in Part 5 of this Schedule) of the Contractor which without such expenditure would have taken place, during the Minimum Indemnity Period.

Sum Insured

An amount sufficient to cover the sums the subject of the Indemnity for the Minimum Indemnity Period.

Maximum Excess

[   ] days.

Minimum Indemnity Period

[12] months.

Period of Insurance

As per the Contractors' "All Risks" Insurance, excluding the defects liability period.

Cover Features and Extensions

Denial of access.

Utilities.

Terrorism.

Subrogation waiver and non-vitiation clause.

Professional fees.

Automatic reinstatement of sum insured.

Principal Exclusions

To follow the Contractors' 'All Risks' Insurance, other than for consequential losses.

Construction Third Party Liability Insurance

Interest

To indemnify the Insured in respect of all sums that they may become legally liable to pay (including claimant's costs and expenses) as damages in respect of accidental:

death, or bodily injury, illness, disease contracted by any person;

loss or damage to property;

interference to property or any easement right of air, light, water or way or the enjoyment or use thereof by obstruction, trespass, nuisance, loss of amenities, or any like cause,

happening during the Period of Insurance and arising out of or in connection with the Works.

Limit of Indemnity

Not less than £[ ] mn in respect of any one occurrence, the number of occurrences being unlimited, but in the aggregate in respect of pollution and products liability.

Maximum Deductible

£[      ] for each and every occurrence of property damage. (Personal injury claims will be paid in full.)

Territorial Limits

[United Kingdom but worldwide in respect of non-manual visits.] OR [Worldwide excluding USA, Canada and Australia.]

Jurisdiction

Worldwide excluding USA, Canada and Australia.

Period of Insurance

As per the Contractor's "All Risks" Insurance, including the defects liability period.

Cover Features and Extensions

Munitions of war.

Cross liability clause.

Contingent motor.

Principal Exclusions

Liability for death, illness, disease or bodily injury sustained by employees of the Insured.

Liability arising out of the use of mechanically propelled vehicles whilst required to be compulsorily insured by Legislation in respect of such vehicles.

Liability in respect of predetermined penalties or liquidated damages imposed under any contract entered into by the Insured.

Liability in respect of loss or damage to property in the care, custody and control of the insured but this exclusion is not to apply to all property belonging to the Authority that is in the care, custody and control of another Insured.

Liability arising out of technical or professional advice (given for a fee) other than in respect of death or bodily injury to persons or damage to third party property.

Losses indemnified under the insurances referred to in paragraphs 1 and 2 of this Part 1 of Schedule 14.

Liability arising from the ownership, possession or use of any aircraft or marine vessel.

Liability arising from seepage and pollution unless caused by a sudden, unintended and unexpected occurrence.

Part 2

Policies to be taken out by the Contractor and maintained during the Services Period

Common to all policies in Part 2 (unless stated otherwise):

Insureds

- Authority;

Contractor;

FM Contractor;

Sub-contractors to Insureds 2 and 3, of any tier; and

[lenders],

each for their respective rights and interests in the Project.

- Property Damage Insurance

Insured Property

Any property of whatsoever nature or description associated with the Project that is the property of the Contractor or for which the Contractor may be responsible under this Agreement including but not limited to the new facilities.

Coverage

"All risks" of physical loss or damage to the Insured Property from any cause not excluded, including machinery breakdown and computer breakdown in respect of appropriate equipment.

Sum Insured

At all times an amount not less than the total reinstatement or replacement value of the Insured Property plus provision to include other Principal Extensions as appropriate (escalated periodically as appropriate in accordance with clause 63.4).

Maximum Deductible

£[      ] each and every claim, escalated periodically as appropriate in accordance with clause 63.4.

Territorial Limits

United Kingdom.

Period of Insurance

From the first Services Availability Date or as otherwise specified in the Agreement for the duration of this Agreement and renewable on an annual basis unless agreed otherwise by the parties.

Cover Features and Extensions

Terrorism.

Pollution and contamination to the Insured Property arising from an event which itself is not otherwise excluded. To include pollution or contamination resulting from accidental damage.

Insured Property whilst in transit.

Automatic reinstatement of sum insured.

Capital additions clause.

72 hour clause.

European Union local authorities clause.

Replacement of computer records.

Professional fees.

Debris removal.

Repair / reinstatement basis of claims settlement with cash option for non-reinstatement.

Principal Exclusions

War and related perils (UK market agreed wording).

Nuclear/radioactive risks (UK market agreed wording).

Pressure waves caused by aircraft and other aerial devices travelling at sonic or supersonic speeds.

Wear, tear and gradual deterioration.

Consequential financial losses.

Cyber risks.

Business Interruption Insurance

Insureds

Contractor;

[FM Contractor]; and

[Leisure Operator],

each for their respective rights and interests in the Project.

Indemnity

In respect of:

loss of anticipated Revenue (as defined in Part 5 of this Schedule) during the Minimum Indemnity Period arising from an interruption or interference in the operation the Project as a result of loss or damage covered under Property Damage Insurance effected in accordance with paragraph 1 of Part 2 of this Schedule 14 including physical loss or damage which would be indemnifiable but for the application of any deductible; and

the additional expenditure necessarily and reasonably incurred for the purpose of avoiding or reducing the loss of Revenue (as defined in Part 5 of this Schedule) of the Contractor which without such expenditure would have taken place, during the Minimum Indemnity Period.

Sum Insured

An amount sufficient to cover the sums the subject of the Indemnity for the Minimum Indemnity Period.

Maximum Excess

[   ] days.

Minimum Indemnity Period

[12] months.

Period of Insurance

From the Services Availability Date for the duration of this Agreement and renewable on an annual basis unless agreed otherwise by the parties.

Cover Features and Extensions

Denial of access.

Utilities.

Terrorism.

Subrogation waiver and non vitiation clause.

Accountants clause.

Automatic reinstatement of Sum Insured and Indemnity Period.

Principal Exclusions

To follow the Contractors' 'All Risks' Insurance, other than for consequential losses.

Third Party Public and Products Liability Insurance

Interest

To indemnify the Insured in respect of all sums that they may become legally liable to pay (including claimant's costs and expenses) as damages in respect of accidental:

death, or bodily injury, illness, disease contracted by any person;

loss or damage to property; or

interference to property or any easement right of air, light, water or way or the enjoyment or use thereof by obstruction, trespass, nuisance, loss of amenities, or any like cause,

happening during the Period of Insurance and arising out of or in connection with the Project and the provision of the Services.

Limit of Indemnity

Not less than £[      ]mn  (escalated periodically as appropriate in accordance with clause 63.4)  in respect of any one occurrence, the number of occurrences being unlimited, but in the aggregate in respect of pollution and products liability.

Maximum Deductible

£[      ] for each and every occurrence of property damage, escalated periodically as appropriate. (Personal injury claims will be paid in full.)

Territorial Limits

[United Kingdom but worldwide in respect of non-manual visits.] OR [Worldwide excluding USA, Canada and Australia.]

Jurisdiction

Worldwide excluding USA, Canada and Australia.

Period of Insurance

From the first Services Availability Date or as otherwise specified in this Agreement for the duration of this Agreement and renewable on an annual basis unless agreed otherwise by the parties.

Cover Features and Extensions

Munitions of war.

Cross liability clause.

Contingent motor liability.

Subrogation waiver and non vitiation clause.

Principal Exclusions

Liability for death, illness, disease or bodily injury sustained by employees of the Insured.

Liability arising out of the use of mechanically propelled vehicles whilst required to be compulsorily insured by Legislation in respect of such vehicles.

Liability in respect of predetermined penalties or liquidated damages imposed under any contract entered into by the Insured.

Liability in respect of loss or damage to property in the care, custody and control of the insured but this exclusion is not to apply to all property belonging to the Authority that is in the care, custody and control of another Insured.

Liability arising out of technical or professional advice (given for a fee) other than in respect of death or bodily injury to persons or damage to third party property.

Liability arising from the ownership, possession or use of any aircraft or marine vessel.

Liability arising from seepage and pollution unless caused by a sudden, identifiable, unintended and unexpected occurrence.

Losses under the insurances referred to in paragraphs 1 and 2 of this Part 2 of Schedule 14.

Part 3

Endorsements

Unless the context otherwise requires defined terms set out in the following endorsements shall have the meaning set out in the Agreement.

Endorsement 1

Cancellation

This policy shall not be cancelled or terminated before the original expiry date is to take effect except in respect of non-payment of premium.

The insurer shall by written notice advise the Authority:

(a)	at least thirty (30) Business Days before any such cancellation or termination is to take effect

(b)	at least thirty (30) Business Days before any reduction in limits or coverage or any increase in deductibles is to take effect; and

(c)	of any act or omission or any event of which the insurer has knowledge and which might invalidate or render unenforceable in whole or in part this policy

Endorsement 2

Multiple Insured/Subrogation/Non-Vitiation Clause

Each of the parties comprising the insured shall for the purpose of this policy be considered a separate co-insured entity, insured on a composite basis, with the words "the insured" applying to each as if they were separately and individually insured provided that the total liability of the insurers under each section of this policy to the insured collectively shall not (unless the policy specifically permits otherwise) exceed the limit of indemnity or amount stated to be insured under that section or policy. Accordingly, the liability of the insurers under this policy to any one insured shall not be conditional upon the due observance and fulfilment by any other insured party of the terms and conditions of this policy or of any duties imposed upon that insured party relating thereto, and shall not be affected by any failure in such observance or fulfilment by any such other insured party.

It is understood and agreed that any payment or payments by insurers to any one or more of the insureds shall reduce, to the extent of that payment, insurers' liability to all such parties arising from any one event giving rise to a claim under this policy and (if applicable) in the aggregate.

Insurers shall be entitled to avoid liability to or (as may be appropriate) claim damages from any insured party in circumstances of fraud misrepresentation non-disclosure or material breach of warranty or condition of this policy (each referred to in this clause as a Vitiating Act) committed by that insured party save where such misrepresentation non-disclosure or breach of warranty or condition was committed innocently and in good faith.

For the avoidance of doubt it is however agreed that a Vitiating Act committed by one insured party shall not prejudice the right to indemnity of any other insured who has an insurable interest and who has not committed the Vitiating Act.

Insurers hereby agree to waive all rights of subrogation and/or recourse which they may have or acquire against any insured party (together with their employees and agents) except where the rights of subrogation or recourse are acquired in consequence of a Vitiating Act in which circumstances insurers may enforce such rights against the insured responsible for the Vitiating Act notwithstanding the continuing or former status of the vitiating party as an insured.

Notwithstanding any other provision of this policy or any other document or any act and/or omission by any insured party insurers agree that:

(1)	no party other than the Authority has any authority to make any warranty, disclosure or representation in connection with this policy on behalf of the Authority;

(2)	where any warranty, disclosure or representation is required from the Authority in connection with this policy insurers will contact the Authority in writing (in accordance with Endorsement 3 to the Agreement) and set out expressly the warranty, disclosure and/or representation required within a reasonable period of time from the Authority (regarding itself); and

(3)	save as set out in a request from insurers to the Authority in accordance with (2) above, the Authority shall have no duty to disclose any fact or matter to insurers in connection with this policy save to the extent that for the Authority not to disclose a fact or matter would constitute fraudulent misrepresentation and/or fraudulent non-disclosure.

Endorsement 3

Communications

All notices or other communications under or in connection with this policy shall be given to each insured (and the Authority) in writing or by facsimile. Any such notice will be deemed to be given as follows:

(a)	if in writing, when delivered;

(b)	if by facsimile, when transmitted but only if, immediately after transmission, the sender's facsimile machine records a successful transmission has occurred.

The address and facsimile number of the Authority for all notices under or in connection with this policy are those notified from time to time by the Authority for this purpose to the Contractor's insurance broker at the relevant time. The initial address and facsimile number of the Authority is as follows:

The Authority:

Address:

Facsimile No:	[     ]

Attention:

It is further agreed that a notice of claim given by the Authority or any other insured shall in the absence of any manifest error be accepted by the insurer as a valid notification of a claim on behalf of all insureds.

Endorsement 4

Loss Payee (applicable only to the Physical Damage Policies)

All proceeds of this policy shall be payable without deduction or set-off to the Joint Insurance Account.

Endorsement 5

Primary Insurance

It is expressly understood and agreed that this policy provides primary cover for the insured parties and that in the event of loss destruction damage or liability covered by this policy which is covered either in whole or in part under any other policy or policies of insurance effected by or on behalf of any of the insured parties the insurers will indemnify the insured parties as if such other policy or policies of insurance were not in force and the insurers waive their rights of recourse if any against the insurers of such other policy or policies of insurance.

Endorsement 6

Claims Negotiation Rights

Notwithstanding any claim conditions contained herein insurers agree that the Authority has the right to settle and negotiate any claims received from third parties subject to prior consent of insurers. If an Authority takes or fails to take any action as a direct result of which insurers' liability is increased then the liability of insurers to provide an indemnity is reduced to such an extent.

Endorsement 7

Ringfencing

The level of any indemnity available to an insured party under this policy in relation to any claim(s) concerning the Project shall not be affected and/or reduced by any claim(s) unrelated to the Project.

Part 4

Broker's Letter of Undertaking

Any one of the following three broker's letters of undertaking should be used.

Broker's Letter of Undertaking [A]

To: [             ] Council

Dear Sirs

Agreement dated on or about [      ] entered into between [                             ] (the "Contractor") and [           ] Council (the "Authority") (the "Agreement")

- We refer to the Agreement. Unless the context otherwise requires, terms defined in the Agreement shall have the same meaning in this letter.

We act as insurance broker to the Contractor in respect of the Required Insurances and in that capacity we confirm that the Required Insurances which are required to be procured pursuant to clause 61 and Schedule 14 of the Agreement:

where appropriate name you and such other persons as are required to be named pursuant to the Agreement for their respective interests;

are, in our reasonable opinion as insurance brokers, as at today's date, in full force and effect;

all premiums due to date in respect of the Required Insurances are paid and the Required Insurances are, to the best of our knowledge and belief, placed with insurers which, as at the time of placement, are reputable and financially sound. We do not, however, make any representations regarding such insurers' current or future solvency or ability to pay claims; and that

the endorsements set out in Part 3 to Schedule 14 of the Agreement are as at today's date in full force and effect in respect of the Required Insurances.

We further confirm that the attached cover notes confirm this position.

Pursuant to instructions received from the Contractor and in consideration of your approving our appointment [or continuing appointment] as brokers in connection with the Required Insurances, we hereby undertake in respect of the interests of the Authority  in relation to the Required Insurances:

Notification Obligations

To notify you at least thirty (30) days prior to the expiry of any of the Required Insurances if we have not received instructions from the Contractor to negotiate renewal and in the event of our receiving instructions to renew, to advise you promptly of the details thereof.

To notify you at least thirty (30) days prior to ceasing to act as brokers to the Contractor unless, due to circumstances beyond our control, we are unable to do so in which case we shall notify you as soon as practicable.

To pay into the Joint Insurance Account without set off or deduction of any kind for any reason all payments in respect of claims received by us from insurers in relation to the Required Insurances specified in clause 62.2 of the Agreement.

Advisory Obligations

To notify you as soon as practicable of any default in the payment of any premium for any of the Required Insurances.

To notify you if any insurer cancels or gives notification of cancellation of any of the Required Insurances, at least thirty (30) days before such cancellation is to take effect or as soon as reasonably practicable in the event that notification of cancellation takes place less than thirty (30) days before it is to take effect.

To notify you as soon as reasonably practicable of any act or omission, breach or default of the Contractor or any other insured under the Required Insurances of which those of our employees directly involved with the placement or administration of the Insurances become aware and which acting reasonably they consider may invalidate any Insurance or render it void, avoidable or unenforceable in whole or in part or which may otherwise materially impact on the extent of cover provided under the Required Insurances.

In accordance with our duty to the Contractor to notify the Contractor of its pre-contractual duties of disclosure to insurers including the duty to disclose all information that would be considered material in the context of such duty.

Disclosure Obligations

disclose to insurers all information and any fact, change of circumstance or occurrence made available to us by the Contractor; or

disclose, with the approval of the Contractor (such approval not to be unreasonably withheld), all information and any fact, change of circumstance or occurrence made available to us by the Authority,

which in our reasonable opinion is material to the risks insured against under the Required Insurances and which properly should be disclosed to insurers in accordance with the insurers' relevant policy terms and conditions as soon as reasonably practicable after we are in receipt from the Contractor of such information or of the approval of the Contractor in respect of such information and become aware of such information, fact, change of circumstance or occurrence whether prior to inception or renewal or otherwise.

To treat as confidential all information so marked or otherwise stated to be confidential and supplied to us by or on behalf of the Contractor or the Authority and not to disclose such information, without the prior written consent of the supplier of the information, to any third party other than those persons who, in our reasonable opinion have a need to have access to such information from time to time, and for the purpose of disclosure to the insurers or their agents in respect of the Required Insurances in discharge of our obligation set out at clause 4.3.1 of this letter. Our obligations of confidentiality shall not conflict with our duties owed to the Contractor and shall not apply to disclosure required by an order of a court of competent jurisdiction, or pursuant to any applicable law, governmental or regulatory authority having the force of law or to information which is in the public domain.

Administrative Obligations

To hold copies of all documents relating to or evidencing the Required Insurances, including but without prejudice to the generality of the foregoing, insurance slips, contracts, policies, endorsements and copies of all documents evidencing renewal of the Required Insurances, payment of premiums and presentation and receipt of claims.

To supply to the Authority and/or its insurance advisers (or the Authority's or its insurance advisers' authorised representatives) promptly on written request copies of the documents set out in clause 4.4.1 of this letter, and to the extent available, to make available to such persons promptly upon the Authority's request the originals of such documents.

To administer the payment of premiums due pursuant to the Required Insurances such that, insofar as we hold appropriate funds, all such premiums shall be paid to insurers in accordance with the terms of the Required Insurances.

To administer the payment of claims from insurers in respect of the Required Insurances (the Insurance Claims) including:

negotiating settlement of Insurance Claims presented in respect of the Required Insurances;

collating and presenting all information required by insurers in relation to Insurance Claims presented in respect of the Required Insurances; and

insofar as it is relevant and practicable, liaising with and reporting to the Authority throughout the settlement, payment and administration of such Insurance Claims.

To advise the Authority promptly upon receipt of notice of any material changes which we are instructed to make in the terms of the Required Insurances and which, if effected, in our opinion as Insurance Brokers would result in any material reduction in limits or coverage or in any increase in deductibles, exclusions or exceptions.

To advise the Authority in advance of any lapse or non-renewal of any policy maintained in respect of the Required Insurances.

To use our reasonable endeavours to have endorsed on each and every policy evidencing the Required Insurances (when the same is issued) endorsements substantially in the form set out in Part 3 to Schedule 14 of the Agreement.

Insurance Cost Reporting Procedures

to prepare following request, at the expense of the Contractor, a Joint Insurance Cost Report on behalf of both the Contractor and the Authority in accordance with the Insurance Review Procedure as set forth in clause 61.15 of the Agreement. We shall ensure that the information in the Joint Insurance Cost Report is fairly represented, based on the information available to us.

Notification Details

Our obligations at clause 4 of this letter to notify or inform you shall be discharged by providing the requisite information in hard copy to:

[                    ] Council

[Address]

General

For the avoidance of doubt, the undertakings and confirmations given in this letter relate solely to the Required Insurances. They do not apply to any other insurances and nothing in this letter should be taken as providing any undertakings or confirmations in relation to any insurance (other than the Required Insurances) that ought to have been placed or may at some future date be placed by ourselves or by other brokers.

Following termination of our appointment as broker to the Contractor, on written notice to the Authority we are released from all ongoing obligations set forth in this letter.

Nothing in this letter shall prejudice insurers' right to cancel the Required Insurances in accordance with their terms and the undertakings and confirmations set out in this letter are given subject to such right.

This letter is given by us on the instructions of the Contractor and with the Contractor's full knowledge and consent as to its terms as evidenced by the Contractor's signature below. Accordingly, the Contractor hereby waives any potential liability we might otherwise have had to it arising from actions taken by us to comply with the terms of this letter (including, without limitation, any particular liability relating to any conflict of interest).

This letter shall be governed by and construed in accordance with English law.

Yours faithfully

-------------------------------------------------------------

For and on behalf of [Contractor's broker]

-------------------------------------------------------------

For and on behalf of the [Authority]

-------------------------------------------------------------

For and on behalf of the [Contractor]

Broker's Letter of Undertaking [B]

To:	The Authority

Dear Sirs

Agreement dated [	] entered into between [                                  ] Limited (the "Contractor") and [                                   ] (the "Authority") (the "Agreement")

- We refer to the Agreement. Unless the context otherwise requires, terms defined in the Agreement shall have the same meaning in this letter.

We act as insurance broker to the Contractor in respect of the Required Insurances and in that capacity we confirm that the Required Insurances which are required to be procured pursuant to clause 61 and Schedule 14 of the Agreement:

where appropriate name you and such other persons as are required to be named pursuant to the Agreement for their respective interests;

are, in our reasonable opinion as insurance brokers, as at today's date, in full force and effect;

all premiums due to date in respect of the Required Insurances are paid and the Required Insurances are, to the best of our knowledge and belief, placed with insurers which, as at the time of placement, are reputable and financially sound. We do not however make any representations regarding such insurers' current or future solvency, or ability to pay claims; and that

the endorsements set out in Part 3 to Schedule 14 of the Agreement which is attached hereto are in our reasonable opinion as at today's date in full force and effect in respect of the Required Insurances.

We further confirm that the attached cover notes confirm this position.

Pursuant to instructions received from the Contractor and in consideration of your approving our appointment [or continuing appointment] as brokers in connection with the Required Insurances, we hereby undertake in relation to the Required Insurances:

Notification Obligations

To notify you at least thirty (30) days prior to the expiry of any of the Required Insurances if we have not received instructions from the Contractor to negotiate renewal and in the event of our receiving instructions to renew, to advise you promptly of the details thereof.

To notify you at least thirty (30) days prior to ceasing to act as brokers to the Contractor unless, due to circumstances beyond our control, we are unable to do so in which case we shall notify you as soon as practicable.

To pay into the Joint Insurance Account without set off or deduction of any kind for any reason all payments in respect of claims received by us from insurers in relation to the Required Insurances specified in clause 62.2 of the Agreement.

Advisory Obligations

To notify you as soon as reasonably practicable of any default in the payment of any premium for any of the Required Insurances.

To notify you if any insurer cancels or gives notification of cancellation of any of the Required Insurances to us, at least thirty (30) days before such cancellation is to take effect or as soon as reasonably practicable in the event that notification of cancellation takes place less than thirty (30) days before it is to take effect.

To notify you as soon as reasonably practicable of any act or omission, breach or default of which we have been notified which in our reasonable opinion would  either, invalidate or render unenforceable in whole or in part any of the Required Insurances or, would otherwise materially impact on the extent of cover provided under the Required Insurances.

In accordance with our duty to the Contractor to notify the Contractor of its pre-contractual duties of disclosure to insurers, including the duty to disclose all information that would be considered material in the context of such duty.

Disclosure Obligations

Subject to the prior written consent of the Contractor (and we undertake to notify you as soon as reasonably practicable if such consent is withheld) to disclose to insurers all information provided to those of our employees directly involved with the placement of the Required Insurances in our capacity as insurance broker to the Contractor, including any fact, change of circumstance or occurrence notified to such employees, which in our reasonable opinion is material to the risks insured against under the Required Insurances and which properly should be disclosed to insurers, or in accordance with the policy terms and conditions of the relevant Required Insurance, as soon as reasonably practicable after we are in receipt of such information, fact, change of circumstance or occurrence whether prior to inception or renewal or otherwise.

To treat as confidential all information so marked or otherwise stated to be confidential and supplied to us by or on behalf of the Contractor or the Authority and not to disclose such information, without the prior written consent of the supplier, to any third party other than those persons who, in our reasonable opinion have a need to have access to such information from time to time, and for the purpose of disclosure to the insurers or their agents in respect of the Required Insurances. Our obligations of confidentiality shall not conflict with our duties owed to the Contractor and shall not apply to disclosure required by an order of a court of competent jurisdiction, or pursuant to any applicable law, governmental or regulatory authority having the force of law or to information which is in the public domain.

Administrative Obligations

To hold copies of all documents relating to or evidencing the Required Insurances, including but without prejudice to the generality of the foregoing, insurance slips, contracts, policies, endorsements and copies of all documents evidencing renewal of the Required Insurances, payment of premiums and presentation and receipt of claims.

To supply to the Authority and/or its insurance advisers (or the Authority's or its insurance advisers' authorised representatives) promptly on written request copies of the documents set out in clause 4.4.1 of this letter, and to the extent available, to make available to such persons promptly upon the Authority's request the originals of such documents.

To administer the payment of premiums due pursuant to the Required Insurances such that, insofar as we hold appropriate funds, all such premiums shall be paid to insurers in accordance with the terms of the Required Insurances.

[To administer the payment of claims from insurers in respect of the Required Insurances (the Insurance Claims) including:

negotiating settlement of Insurance Claims presented in respect of the Required Insurances;

collating and presenting all information required by insurers in relation to Insurance Claims presented in respect of the Required Insurances, and

insofar as it is relevant and practicable, liaising and reporting to the Authority throughout the settlement, payment and administration of such Insurance Claims.]

To advise the Authority as soon as reasonably practicable upon receipt of notice of any material changes which we are instructed by the Contractor to make in the terms of the Required Insurances and which, if effected, in our reasonable opinion as Insurance Brokers would result in any material reduction in limits or coverage or increase in deductibles, exclusions or exceptions.

To use our reasonable endeavours to have endorsed on each and every policy evidencing the Required Insurances (when the same is issued) endorsements substantially in the form set out in Part 3 to Schedule 14 of the Agreement.

Insurance Cost Reporting Procedures

to prepare, at the expense of the Contractor, a Joint Insurance Cost Report on behalf of both the Contractor and the Authority in accordance with the Insurance Review Procedure as set forth in 61.15 of the Agreement. We shall ensure that the information in the Joint Insurance Cost Report is fairly represented, based on the information available to us.

Notification Details

Our obligations at clause 4 of this letter to notify or inform you shall be discharged by providing the requisite information in hard copy to:

[  ]  Authority

Save insofar as we have given agreements or representations in this letter, it is to be understood by the Authority that they may not rely on any advice which we have given to the Contractor, and we do not represent that the Required Insurances are suitable or sufficient to meet the needs of the Authority which must take steps and advice of its own as it considers necessary in order to protect its own position.

The representations and obligations set out in this letter are subject to our continuing appointment as insurance brokers to the Contractor in relation to the Required Insurances concerned, and following termination of such appointment our immediate release from all our obligations set out in this letter to the extent those obligations arise on or after the termination, and subject to any right of lien we may have over the policy and policy documents regarding the Required Insurances, arising through common law or otherwise.

Our aggregate liability to any persons companies or organisation who acts in reliance on this letter, or on any other broker's letter of undertaking issued by us in respect of the Required Insurances for this Project, for any and all matters arising from them and the contents thereof shall in any and all events be limited to the sum of £[           ], even if we are negligent. We do not limit liability for our fraud.

This letter is given by us on the instructions of the Contractor and with their full knowledge and consent as to its terms.

Yours faithfully

-------------------------------------------------------------

For and on behalf of [Contractor's broker]

We consent to the giving of this Letter of Undertaking by our insurance brokers

-------------------------------------------------------------

For and on behalf of

[Contractor]

Broker's Letter of Undertaking [C]

The Authority

Dear Sirs

Agreement dated [	] entered into between [                      ] Limited (the "Contractor") and [                       ] (the "Authority") (the "Agreement")

- We refer to the Agreement. Unless the context otherwise requires, terms defined in the Agreement shall have the same meaning in this letter.

We act as insurance broker to the Contractor in respect of the insurances (which are defined in clause 61 and schedule 14 of the Agreement attached hereto as Appendix A) evidenced by the cover notes attached hereto as Appendix B (Required Insurances) and in that capacity we confirm that the Required Insurances:

where appropriate name you and such other persons as are required to be named pursuant to the Agreement for their respective interests;

are, to the best of our knowledge and belief (after making all reasonable enquiries), as at today's date, in full force and effect; and that

all premiums due as at today's date in respect of the Required Insurances are paid and the Required Insurances are, to the best of our knowledge and belief, placed with insurers which, as at the time of placement, are reputable and financially sound. We do not, however, make any representations regarding such insurers' current or future solvency or ability to pay claims; and that

the endorsements set out in Part 3 to Schedule 14 of the Agreement attached hereto as Appendix C are to the best of our knowledge and belief as at today's date in full force and effect.

We further confirm that the cover notes attached hereto as Appendix B confirm this position.

Pursuant to instructions received from the Contractor and in consideration of your approving our appointment or continuing appointment as brokers in connection with the Required Insurances, we hereby undertake in respect of the interests of the Authority  in relation to the Required Insurances:

Notification Obligations

To notify you at least thirty (30) days prior to the expiry of any of the Required Insurances if we have not received instructions from the Contractor to negotiate renewal and in the event of our receiving instructions to renew, to advise you as soon as reasonably practicable, and in any event within three (3) business days, of the details thereof.

To notify you at least thirty (30) days prior to ceasing to act as brokers to the Contractor unless, due to circumstances beyond our control, we are unable to do so in which case we shall notify you as soon as reasonably practicable and in any event within three (3) business days.

To pay into the Joint Insurance Account without set off or deduction of any kind or for any reason, all payments in respect of claims received by us from insurers in relation to the Required Insurances specified in clause 62.2 of the Agreement attached hereto as Appendix D.

Advisory Obligations

To notify you as soon as reasonably practicable, and in any event within three (3) business days, of any default in the payment of any premium by the Contractor to us for any of the Required Insurances.

To notify you if any insurer cancels or gives notification of cancellation of any of the Required Insurances, at least thirty (30) days before such cancellation is to take effect or as soon as reasonably practicable in the event that notification of cancellation takes place less than thirty (30) days before it is to take effect.

To notify you as soon as reasonably practicable of any act or omission, breach or default of the Contractor of which those of our employees directly involved with the placement or administration of the Relevant Insurances becomes actually aware in their capacity as brokers to the Contractor which acting reasonably they consider may  invalidate or render unenforceable in whole or in part any of the Required Insurances or which may otherwise materially impact on the extent of cover provided under the Required Insurances.

In accordance with our duty to the Contractor, to advise the Contractor of its duties of disclosure to insurers including:

the types of facts, circumstances and beliefs that should generally be disclosed to insurers; and

the obligation not to misrepresent any facts, matters or beliefs to insurers.

Disclosure Obligations.

subject to the prior written consent of the Contractor (and we undertake to notify you as soon as reasonably practicable if such consent is withheld) to disclose to insurers all information  made available to those of our employees directly involved with the placement of the Relevant Insurances in their capacity as brokers to the Contractor and any fact, change of circumstances or occurrence made known to such employees which in our reasonable opinion is material to the risks insured against under the Required Insurances and which properly should be disclosed to insurers (in accordance with the Contractor's duty of disclosure to insurers) as soon as practicable after we are in receipt of such information; and become aware of such information, fact, change of circumstance or occurrence whether prior to inception or renewal or otherwise.

To treat as confidential all information so marked or otherwise stated to be confidential and supplied to us by or on behalf of the Contractor or the Authority and not to disclose such information, without the prior written consent of the supplier, to any third party other than those persons who, in our reasonable opinion have a need to have access to such information from time to time, and for the purpose of disclosure to the insurers or their agents in respect of the Required Insurances in discharge of our obligation set out at clause 4.3.1 of this letter. Our obligations of confidentiality shall not conflict with our duties owed to the Contractor and shall not apply to disclosure required by an order of a court of competent jurisdiction, or pursuant to any applicable law, governmental or regulatory authority having the force of law or to information which is in the public domain.

Administrative Obligations

To hold copies of all documents relating to or evidencing the Required Insurances, including but without prejudice to the generality of the foregoing, insurance slips, contracts, policies, endorsements and copies of all documents evidencing renewal of the Required Insurances, payment of premiums and presentation and receipt of claims.

Subject to our lien over the Policies for premiums and/or commissions due, to supply to the Authority and/or its insurance advisers (or the Authority's authorised representatives) as soon as reasonably practicable, on written request copies of the documents set out in clause 4.3.1 of this letter, and to the extent available, to make available to such persons as soon as reasonably practicable, upon the Authority's request the originals of such documents.

To administer the payment of premiums due pursuant to the Required Insurances such that, insofar as we hold appropriate cleared funds from the Contractor, all such premiums shall be paid to insurers in accordance with the terms of the Required Insurances.

To administer the payment of claims from insurers in respect of the Required Insurances (the Insurance Claims) including:

negotiating settlement of Insurance Claims presented in respect of the Required Insurances;

collating and presenting all information required by insurers in relation to Insurance Claims presented in respect of the Required Insurances; and

insofar as it is relevant and practicable, liaising with and reporting to each Authority throughout the settlement, payment and administration of such Insurance Claims. [Broker to ensure this section complies with claims procedure agreed with Insured before signing letter.]

To advise the Authority as soon as reasonably practicable upon receipt of notice of any material changes from the Contractor which we are instructed to make in the terms of the Required Insurances and which, if effected, in our reasonable opinion as insurance brokers would result in any material reduction in limits or coverage or in any material increase in deductibles, exclusions or exceptions.

To advise the Authority in advance, to the extent we are actually aware in advance, of any material change to the terms of, or any lapse, non-renewal and/or cancellation of Required Insurances.

Insurance Cost Reporting Procedures

to prepare following request, at the expense of the Contractor, a Joint Insurance Cost Report on behalf of both the Contractor and the Authority in accordance with the Insurance Review Procedure as set forth in 61.15 of the Agreement attached hereto as Appendix E. We shall ensure that the information in the Joint Insurance Cost Report is fairly represented, based on the information available to us.

Notification Details

Our obligations at clause 4 of this letter to notify or inform you shall be discharged by providing the requisite information in hard copy to:

[  ]  Authority

The undertakings given and obligations set out in this letter are given subject to any liability we may incur to you arising out of or in connection with this letter whether in contract, tort (including but not limited to negligence) or otherwise being limited in aggregate to £[	].

All liability we may incur to you, whether in contract, tort (including but not limited to negligence) or otherwise for loss of profit, loss of savings, loss of opportunity or any indirect or consequential loss is hereby expressly excluded.

No limit of liability shall apply in the case of death or personal injury caused by our negligence, or in respect of any loss caused by our fraud.

The undertakings given and obligations set out in this letter are given subject to insurers' right to cancel the Relevant Insurances, are given solely in our capacity as broker to the Contractor, relate only to the Relevant Insurances and are subject to our continuing appointment as broker to the Contractor. Following termination of such appointment, we are, for the avoidance of doubt and without prejudice to your accrued rights, released from all our ongoing obligations set out in this letter.

You may not rely on any advice which we have given to the Contractor and we do not represent that any of the Relevant Insurances are suitable or sufficient to meet your needs and you must take steps and advice of your own as you consider necessary in order to protect your own position.

In the event that this letter is disclosed to any third party, any and all liability howsoever arising to such third party is hereby expressly excluded to the extent permitted in law.

No person, except you, has any rights arising out of this letter under the Contracts (Rights of Third Parties) Act 1999.

This letter shall be governed by and construed in all respects in accordance with the laws of England and Wales.

This letter is given by us at the request of the Contractor and with the Contractor's full knowledge and consent as to its terms, who confirms that we are authorised to give and comply with the undertakings and acknowledges that compliance with the undertakings may be in conflict with the interests of the Contractor, as evidenced by the Contractor's signature below.

Yours faithfully

-------------------------------------------------------------

For and on behalf of [Contractor's broker]

Accepted for and on behalf of the Contractor

-------------------------------------------------------------

Part 5

Definitions

The following definitions apply to the terms used in this Schedule 14:

Revenue

the projected Unavoidable Fixed Costs of the Contractor/[loss of Revenue];

[Unavoidable Fixed Costs

the fixed costs incurred by the Contractor which first fall due for payment by the Contractor during the period of indemnity but excluding:

(a)	costs which could have reasonably been mitigated or avoided by the Contractor;

(b)	payments to the Contractor's Affiliates;

(c)	payments which are not entirely at arm's length;

(d)	indirect losses suffered or allegedly suffered by any person;

(e)	fines, penalties or damages for unlawful acts, breaches of contract or other legal obligations;

(f)	payments the Contractor can recover under contract or in respect of which the Contractor has a remedy against another person in respect of the same liability; and

(g)	payments to the extent that the Contractor has available to it:

(i)	standby or contingent facilities or funds of senior debt or equity which the Contractor is entitled to have available; and

(ii)	payments representing any profits of the Project (to the extent not already excluded in (d) above).]

SCHEDULE 15

AUTHORITY'S POLICIES

The Authority’s Policies are the principles reflected in the policies listed below and attached.

SCHEDULE 16

[AUTHORITY PLANNING CONDITIONS]

SCHEDULE 17

PROJECT DOCUMENTS AND ANCILLARY DOCUMENTS

Part 1

Project Documents

| Document | Parties |
| --- | --- |

Part 2

Ancillary Documents

| Document | Parties |
| --- | --- |

SCHEDULE 18

BENCHMARKING

Part 1

Definitions

The terms and expressions used in this Schedule shall have the same meaning as set out in Clause 1 (Definitions and Interpretation). The following words and expressions shall have the meanings set out below:

Actual Income

means the annual operating income of the Contractor [and/or without double counting the Leisure Operator] in relation to the [Facility/ Facilities] [(and excluding any actual Excluded Items (Income)] where the Actual Leisure Management Amount is a deficit figure)], generated through the provision of the Benchmarked Services in relation to the [Facility/ Facilities] after adding back in any monies not received by the Contractor [and/or without double counting the Leisure Operator] due to any fraudulent or criminal act or omission and the amount of loss of operating income due to Non-Rectified Performance Failures as defined in and referred to in Schedule 6 (Payment and Performance Monitoring System);

Actual Operating Cost

means the annual actual operating costs as such cost headings are identified in the LOBTA, to include the Head Office Costs and Profit and cost of goods sold, that are incurred by the Contractor [or (without double counting) the Leisure Operator] in providing the Benchmarked Services in relation to the [Facility/ Facilities] [(but excluding Excluded Costs)];

Actual Leisure Management Amount

means the Actual Income less the Actual Operating Costs (where Actual Income is greater than the Actual Operating Costs this shall be a surplus (positive number); where Actual Income is less than Actual Operating Cost this shall be a deficit (negative number)) in relation to the [Facility/ Facilities];

Actual Utility Cost

means the actual cost of the Benchmarked Utilities actually consumed or used at each Facility using the Target Consumption Level for the relevant Facility;

Assessment Year

has the meaning given to it in paragraph 6.1 of Part 5 of this Schedule;

Authority Sponsored Facility

means where the Authority has taken steps to procure subsidise or commission a facility which meets the criteria specified in the definition of a Competing Facility (except item iv) provided always that the following shall not constitute the Authority having taken positive steps to procure, commission or subsidise a Competing Facility:

- any facilities which do not qualify as sports or leisure facilities at the time such facilities are commissioned, procured or subsidised by the Authority but where such facilities subsequently become sports or leisure facilities and the Authority has no control in respect of such change of use;

- the granting by the Authority in its capacity as a planning authority of any permission or consent to any third party to undertake the development of new leisure facilities;

- the disposal (on arms length commercial terms) of any interest the Authority may have in any land to any third party to undertake the development of new competing leisure facilities whether by way of freehold sale, lease, underlease or sub-lease;

- the granting of NNDR relief (or its successor) (if applicable);

- the granting to any organisation by the Authority of:

  - capital funds for the sole purpose of new building works or refurbishment for an amount equal to or less than [fifty thousand pounds (£50,000)] (Indexed) per annum, provided that any subsequent capital funds grant following an initial grant of up to [fifty thousand pounds (£50,000)] (Indexed) is not in respect of the same facility and that no amount of grant or funds is used to secure or procure any further capital funding; or

  - additional community grants or leisure revenue support for an amount equal to or less than [twenty thousand pounds (£20,000)] (Indexed) per annum, provided such community grant or leisure revenue support is not given in relation to any capital support and is limited to revenue expenditure excluding debt financing,

at the date that this test is being applied

- the provision of revenue, capital, sponsorship or subsidy ("Support") to:

  - a facility or organisation pursuant to a statutory duty of the Authority; or

  - a facility or organisation in circumstances where the Authority has no discretion as to whether to provide such Support; or

  - a school or college (which contains leisure facilities) where the Authority does have discretion as to whether to provide such Support; provided that the school or college does not allow community use of the leisure facilities and/or

- the paying of any money to a user group or entity where such money is paid by the Authority as a conduit in its capacity as an accountable body to the provider of such money;

Base Head Office Costs

means in relation to the [Facility/ Facilities] an amount (Indexed) which is a percentage of the Base Modelled Income profiled on an annual basis for which the annual percentage profile [shown as a percentage of Base Modelled Income] is shown in row [X] of the ‘summary’ worksheet of the LOBTA;

Base Leisure Management Amount

means the Base Modelled Income less the Base Modelled Costs shown in row [X] of ‘summary’ worksheet of the LOBTA (which at the date of this Agreement for the first year following [the Commencement Date/ Services Availability] gives rise to a [Deficit/Surplus] Annual Payment];

Base Modelled Income

means the annual operating income (Indexed) that is projected to be earned in relation to the [Facility/ Facilities] by the Contractor [and/or without double counting the Leisure Operator] in providing the Benchmarked Services as the same are identified in the LOBTA [(and excluding any Excluded Items (Income) projected in the LOBTA where the Base Leisure Management Amount is a deficit figure)], as adjusted in accordance with this Agreement;

Base Modelled Costs

means the annual operating costs (Indexed) that are projected to be incurred in relation to the [Facility/ Facilities] by the Contractor [and/or without double counting the Leisure Operator] in providing the Benchmarked Services as the same are identified in the LOBTA (to include the Base Head Office Costs and Base Profit and cost of goods sold [but excluding Excluded Costs projected in the LOBTA]), as adjusted in accordance with this Agreement;

Base Profit

means in relation to the [Facility/ Facilities] an amount (Indexed) which is [X%] of the Base Modelled Income shown in row [X] of the ‘summary’ worksheet of the LOBTA;

Base Utility Cost

means the cost of the Benchmarked Utilities projected to be consumed or used at [the/each] Facility and included within the table[s] at Appendix 1 to Part 2 of this Schedule, as may be amended at each Cost Benchmarking Date pursuant to paragraph 3.2 of Part 2 of this Schedule;

Benchmark Consultant

means:

an expert appointed by agreement between the parties who:-

- possesses at least five (5) years’ experience of operating in, or as a consultant to, the leisure and sports facilities management industries;

- possesses at least five (5) years’ experience of valuing services provided in the aforementioned industries; and

- is engaged or employed by a reputable independent leisure organisation which is independent of the parties and of any other operator,

or in the absence of any such agreement:-

  - a person appointed by such other mutually agreed professional body; or where the parties cannot agree on such person;

  - such other competent person who is appointed by an Adjudicator;

provided that the person appointed is independent of the parties and satisfies the criteria set out in (a) to (c) of this definition;

Benchmarked Services

means the Services to be procured at the [Facility/ Facilities] by the Contractor to satisfy the Services Specification [excluding Hard FM];

Benchmarked Utilities

the provision of gas and electricity at the [Facility/ Facilities] and Benchmarked Utility shall be construed accordingly;

Comparable Market

means the market for sports facilities of similar content to the [Facility/Facilities] operated by Reputable Operators provided that at least three such facilities are considered and at least one of the three facilities is operated by a different Reputable Operator to the other two);

Compensatory Amount

means:

- the Actual Leisure Management Amount for the Tested Period of the immediately preceding Net Income Benchmarking Process (Indexed up to the Income Benchmarking Date) or if none the Base Leisure Management Amount for the Tested Period (Indexed up to the Income Benchmarking Date);

LESS:

- the Actual Leisure Management Amount for the Tested Period adjusted to take account of the duty to mitigate as set out in paragraph 1.4 of Part 3 of this Schedule;

if this figure is a negative number;

Compensatory Amount Increase

has the meaning given to it in paragraph 4.1.2(a) of Part 3 of this Schedule;

"Compensatory Amount Decrease"

has the meaning given to it in paragraph 4.1.2(b) of Part 3 of this Schedule;

"Competing Facility"

means the provision of sports or leisure activities to Users resulting from:

- the construction of new facilities; or

- the improvement of existing facilities (excluding essential lifecycle or planned preventative maintenance); or

- the carrying out of new leisure activities or different leisure activities at an existing facility (excluding off-site activities in relation to the Government's healthy living agenda) which are not in the form of the activities provided at such facilities at the Commencement Date;

and which meet all of the following criteria:

- provide additional or new competition for the Services (or part thereof) carried out at the [Facility/Facilities];

- provide areas of accommodation similar to or better than the [Facility/Facilities];

- are at a facility which is within the a [two] mile radius of [one of] the [Facility/Facilities];

- are at a facility which is an Authority Sponsored Facility;

- are not operated by the Contractor or any Affiliate of any of them; and

- the new or improved facility or activity was not under active consideration and known (or ought to have been known) to the Contractor as at the date of this Agreement (the Contractor having made all reasonable enquiries);

Competing Facility Assessment Period

means the period of one (1) complete Contract Year commencing at the beginning of the Contract Year immediately following the Contract Year in which the later of the following events to occur occurs

- the date on which the Contractor or the Authority reports the Competing Facility to the other pursuant to paragraph 1 of Part 5 of this Schedule;

- the date on which the Competing Facility commences competing activities; and

- the Services Availability Date;

Competing Facility Benchmarking Process

means the process set out in Part 5 of this Schedule;

Competing Facility Report

means the report to be produced by the Benchmark Consultant pursuant to Part 5 of this Schedule;

Competition Information Notice

has the meaning given in paragraph 1 of Part 5 of this Schedule;

Cost Benchmarking Date

means, subject to paragraph 1.3 of Part 2 of this Schedule, the date which is [two] years after [the Commencement Date/Services Availability] and thereafter on each anniversary of the last Cost Benchmarking Date;

Cost Benchmarking Procedure

means the procedure to establish the Cost Figure as set out and described in Part 2 of this Schedule;

Cost Benchmarking Proposal

means the proposal produced pursuant to paragraph 2 of Part 2 of this Schedule;

Cost Figure

means, subject to the operation of Paragraph 5 of Part 2 of this Schedule:

where:

A = the Actual Utility Cost of the Benchmarked Utilities at the Target Consumption Levels (or the actual consumption levels, if lower) since the last Cost Benchmarking Date; and

B = for the first Cost Benchmarking Procedure, the Base Utility Cost at the Target Consumption Levels and for each Cost Benchmarking Procedure thereafter, the updated Base Utility Cost at the Target Consumption Levels (or the actual consumption levels, if lower) agreed or determined at the previous Cost Benchmarking Procedure.

Deficit Payment Increase

has the meaning given to it in paragraph 4.1.1(a) of Part 3 of this Schedule;

[Excluded Costs

means all costs payable by the Contractor in relation to [insurance], Utilities, NNDR, [Hard FM] and any Performance Adjustments payable in accordance with Schedule 6 (Payment and Performance Monitoring System);]

[Excluded Items (Income)

means receipt of payment on a pass through basis by the Contractor in respect of all relevant elements of the Annual Payment (to include any management fee payable to the Contractor) and the Benchmarked Utilities;]

Hard FM

means any maintenance of a lifecycle nature provided by the Contractor;

Head Office Costs

means an amount which is a percentage of the Actual Income profiled on an annual basis for which the annual percentage profile is shown in row [X] of the ‘summary’ worksheet of the LOBTA;

Income Benchmarking Date

means the date, subject to paragraph 1.1.1 and paragraph 1.1.2 of Part 3 of this Schedule, on which either party serves a notice on the other party pursuant to paragraph 1.2 of Part 3 of this Schedule;

Income Benchmarking Report

means the report to be produced by the Benchmark Consultant pursuant to paragraph 3 of Part 3 of this Schedule;

Income Proposal

means the report to be supplied by the Contractor to the Authority pursuant to paragraph 1.3 of Part 3 of this Schedule;

[Key User

means [            ]];

[Key User Facilities

means that part of the [Facility/Facilities] or Services being used by a Key User;]

[Key User Assessment Period

means the period of twelve months from the date on which a Special Benchmarking Warning Notice is issued pursuant to paragraph 2 of Part 4 of this Schedule;]

[Key User Base Modelled Income

means the annual income (Indexed) that is projected to be earned from the Key User by the Contractor [and/or the Leisure Operator] (without double counting) as set out in the ‘key user income’ worksheet of the LOBTA;]

[Key User Information Notice

means the notice to be served in accordance with paragraph 6 of Part 4 of this Schedule;]

Net Income Benchmarking Process

means the procedure to establish the Net Income Figure or Compensatory Amount as set out and described in Part 3 of this Schedule;

Net Income Figure

means:

(a)	the Actual Leisure Management Amount for the Tested Period of the immediately preceding Net Income Benchmarking Process (Indexed up to the Income Benchmarking Date) or if none the Base Leisure Management Amount for the Tested Period (Indexed up to the Income Benchmarking Date);

LESS:

(b)	the Actual Leisure Management Amount for the Tested Period, adjusted to take account of the duty to mitigate as set out in this Schedule;

if this figure is a positive number;

Net Income Figure (Competing Facility)

means:

(a)	the Base Leisure Management Amount for the Competing Facility Assessment Period (Indexed up to the Competing Facility income benchmarking date);

LESS:

(b)	the Actual Leisure Management Amount for the Competing Facility Assessment Period;

if this figure is a positive number;

New Supplier

has the meaning given to it in paragraph 4.1 of Part 2 of this Schedule;

Profit

means an amount which is [X%] of the Actual Income;

Receiving Party

has the meaning given to it in paragraph 2.1 of Part 2;

[Reduced Actual Income

means the reduced annual operating income of the Contractor [and/or the Leisure Operator] in relation to that part of the [Facility/ Facilities] or Services which is no longer used by a Key User (without double counting [and excluding any Excluded Items (Income)] where the Actual Leisure Management Amount is a deficit figure), after adding back in any revenue actually received by the Contractor [and/or the Leisure Operator] and any monies not received by the Contractor [and/or the Leisure Operator] due to any failure to mitigate the circumstances of the loss of the Key User including reasonable steps to generate more income];

Reputable Operator

means a reputable private sector leisure/sports facilities operator or trust leisure/sports facilities operator possessing a broadly comparable degree of skill, resources and financial standing as the Contractor;

Requesting Party

has the meaning given to it in paragraph 2.1 of Part 2;

"Special Benchmarking Process

has the meaning given in paragraph 1 of Part 4 of this Schedule;]

[Special Benchmarking Warning Notice

has the meaning given in paragraph 2 of Part 4 of this Schedule;]

[Special Benchmarking Compensation Payment

means the agreed amount to be invoiced by the Contractor to the Authority following a Special Benchmarking Process in accordance with Part 4 of this Schedule;]

Surplus Payment Increase

has the meaning given to it in paragraph 4.1.1(b) of Part 3 of this Schedule;

Target Consumption Level

means the target consumption levels of Benchmarked Utilities at the [Facility/ Facilities] as shown in Appendix 1 of Part 2 as may be adjusted in accordance with paragraph 2 of Appendix 1 of this Schedule;

Tested Period

means the [five (5) years] immediately preceding the Income Benchmarking Date;

[Trigger Date

has the meaning given in paragraph 7 of Part 5 of this Schedule].

Part 2

Utility Cost Benchmarking Procedure

- Utility Cost Benchmarking Procedure

In respect of Benchmarked Utilities, a Cost Benchmarking Procedure may be carried out to determine the Cost Figure in accordance with this Schedule on each Cost Benchmarking Date.

If either party wishes to submit a Benchmarked Utility to a Cost Benchmarking Procedure it must issue a notice in writing to that effect to the other party no later than five (5) Business Days before a Cost Benchmarking Date.

If a Cost Benchmarking Procedure is scheduled to occur within twelve months of a Net Income Benchmarking Process, then the Authority may opt to delay or bring forward the Cost Benchmarking Procedure to be carried out at the same time as the Net Income Benchmarking Process, in which case such alternative date shall be regarded as the Cost Benchmarking Date.

[If, away from the Cost Benchmarking Date, either party believes that extraordinary fluctuations in the utility market have resulted in the requirement for a Cost Benchmarking Procedure, it may issue a notice in writing to that effect to the other party. Both parties must meet (but with no obligation to act) within ten (10) Business Days of the date of the notice to discuss the extraordinary utility market fluctuations and the possibility of agreeing a Cost Benchmarking Procedure away from the Cost Benchmarking Date at each party’s discretion. For the avoidance of doubt, the Cost Benchmarking Procedure will not take place if both parties are not in agreement that it should take place away from the Cost Benchmarking Date.]

Cost Benchmarking Proposal

Within two (2) months of the Cost Benchmarking Date, the party requesting the Cost Benchmarking Procedure (the "Requesting Party") shall carry out at its own cost a benchmarking procedure with a view to establishing the information set out in paragraph 2.2 and the Cost Figure and shall by the end of the same two (2) month period, deliver to the other party (the "Receiving Party") its proposals for the Cost Figure (the "Cost Benchmarking Proposal").

The Cost Benchmarking Proposal shall be in a report containing all of the following information on a per Facility basis provided by the Requesting Party:

the Base Utility Cost (Indexed) and Actual Utility Cost for the period since the last Cost Benchmarking Date (or for the first Cost Benchmarking Procedure, since [the Commencement Date/Services Availability]);

in addition to the Actual Utility Cost, any supporting evidence relevant to the particular Benchmarked Utility including invoices paid and actual consumption levels at the Facility with reference to the applicable Target Consumption Level;

any efficiency steps which the Contractor has taken to reduce the impact of higher utility costs;

any mitigatory steps which might reasonably be taken to reduce the future impact of increased utility costs;

details of any tendering for supply of Benchmarked Utilities recently undertaken, including brokerage arrangements;

details and an analysis of tariff changes, charges and structures of four natural gas and electricity suppliers or alternatively the details and an analysis of tariff charges and structures tendered by natural gas and electricity suppliers for any portfolios to which the Contractor has access since the last Cost Benchmarking Date where gas or electricity is being benchmarked;

the proposed Cost Figure for the relevant Benchmarked Utility and the proposed consequential adjustment to the Annual Payment;

the methodology and all assumptions by which the Cost Figure has been determined;

assessments made in respect of the Benchmarked Utilities by a Comparable Market (in so far as such information is available after having made reasonable enquiry);

evidence in support of each of the criteria used to determine the Cost Figure and proposed consequential adjustment to the Annual Payment;

full details of sources of information used in establishing the Cost Figure and proposed consequential adjustment to the Annual Payment;

in respect of each component of the Cost Figure and proposed consequential adjustment to the Annual Payment, a breakdown of how each is comprised;

any other evidence required (so as to provide further evidence to that already provided) to support the proposed consequential adjustment to the Annual Payment and enable a decision to be made by the other party;

such other details as the parties may agree at the time.

The parties shall meet within 1 month of the Receiving Party receiving the Cost Benchmarking Proposal to review and discuss the Cost Benchmarking Proposal taking into account the following:

any above [CPI] change relating to price movement since the last Cost Benchmarking Date (or for the first Cost Benchmarking Procedure, since the Pricing Reference Date) as identified through enquiries with local and national providers in accordance with paragraph 2.2.6 and taking into account utility prices paid by the Authority; and

actual consumption levels at the [Facility/Facilities] in comparison to the applicable Target Consumption Level[s].

For the avoidance of doubt, subject to paragraph 2 of Appendix 1 of this Schedule, the unit cost of the Benchmarked Utilities shall only be negotiated by the parties and not consumption levels. The consumption levels applied to such unit costs will be the actual consumption levels up to but no greater than the relevant Target Consumption Levels. For the avoidance of doubt, subject to the other terms of this Agreement, where the Benchmarked Utility consumption level is above the relevant Target Consumption Level, any cost associated with such excess shall be met by the Contractor.

By a date that is no more than two (2) months after receipt of the Cost Benchmarking Proposal the Receiving Party shall respond to the Requesting Party in writing indicating whether or not it accepts the Cost Benchmarking Proposal.  If the Receiving Party agrees the content of the Cost Benchmarking Proposal and the proposed variation to the Annual Payment, paragraph 3 of this Part 2 shall apply.  If the Receiving Party rejects the Cost Benchmarking Proposal the matter shall be determined by the Dispute Resolution Procedure.

If the Receiving Party fails to respond to the Cost Benchmarking Proposal within the period referred to in paragraph 2.5 above, it shall be deemed to have approved the Cost Benchmarking Proposal and the proposed variation to the Annual Payment and paragraph 3 of this Part 2 shall apply.

Implementation

When the Cost Figure is agreed or determined pursuant to Part 2 of this Schedule the Annual Payment shall be adjusted by the full amount of the Cost Figure and such adjustment shall be effective from the Cost Benchmarking Date, and, as appropriate, backdated to such date. For the avoidance of doubt, the Annual Payment:

where it is a Surplus Annual Payment:

shall be decreased where the Cost Figure is positive; or

subject to clause 69.4.3 shall be increased where the Cost Figure is negative; or

where it is a Deficit Annual Payment;

shall be increased where the Cost Figure is positive; or

shall be decreased where the Cost Figure is negative.

For the avoidance of doubt the Base Utility Cost will be rebased at the end of each Cost Benchmarking Procedure to reflect the price payable per unit as a result of that Cost Benchmarking Procedure. Accordingly, the parties agree that following agreement or determination of the Actual Utility Cost in accordance with paragraph 3.1 above, the Actual Utility Cost (for that period) becomes the Base Utility Cost for the next Cost Benchmarking Procedure.

Appendix 2 to this part of this Schedule comprises a worked example of how the Cost Figure is established and the adjustment to the Annual Payment.

Choice of Supplier

Subject to paragraph 4.2 of this Part 2, if prior to the Contractor [or Leisure Operator] entering into a contract with its utility supplier, the Authority provides to the Contractor a detailed written quotation which identifies a cheaper appropriately regulated utility supplier than that proposed by the Contractor, then the Contractor shall [or shall require the Leisure Operator to] contract with the supplier identified by the Authority. The Authority shall have no responsibility for or liability in respect of the identified or any other supplier. Any comparison should be on a like for like basis. For the avoidance of doubt, the requirement for the Contractor [or the Leisure Operator] to enter into contract with the supplier identified by the Authority ("New Supplier") shall only apply where the Contractor’s [or Leisure Operator's] existing contract with its existing supplier expires following a fixed term product or otherwise on the Authority’s instruction and only to the extent that the contract with the New Supplier is not on any materially more onerous terms than the Contractor’s [or Leisure Operator’s] contract with its current supplier at that time.

The Contractor shall have the option for it [or the Leisure Operator] to contract with its own choice of utility supplier provided that any cheaper tariff (which is available to the Contractor [or as applicable the Leisure Operator] (whether they take it or not)) identified by this Cost Benchmarking Procedure shall be the unit cost used to calculate the Actual Utility Cost and the Cost Figure.

CRC Scheme

To the extent the Contractor’s liabilities under the CRC Scheme as referred to in clause 10.3.2.4 of this Agreement increase or will increase as a result of any adjustment to the Base Utility Costs or Target Consumption Levels in accordance with this Schedule, any such increase shall be taken into account for the purposes of calculating the Cost Figure.

PART 2 - APPENDICES

Appendix 1 		Target Consumption Levels

Appendix 2		Worked example of Cost Figure

Appendix 3		Utilities Benchmarking – Process Diagram

PART 2 – Appendix 1

- The following Table 1 shall apply for each relevant year of the [Contract Period/Services Period] for the [Facility/ Facilities].

Table 1 – Target Consumption Levels

| Benchmarked Utility | Facility | Target Consumption Level Per Annum | Unit of Measurement | Base Benchmarked Utility Cost Per Unit (£)* | Total Base Utility Cost at Target Consumption Level (£) |
| --- | --- | --- | --- | --- | --- |

*For the avoidance of doubt, the cost per unit shall include all relevant fixed costs/ standing charges relating to that utility.

- The Target Consumption Level for each of the Benchmarked Utilities [at Facility X] as set out in the table above shall be substituted with the actual annual consumption levels (taking into account consumption in accordance with Good Industry Practice for a leisure operator) for each of the Benchmarked Utilities [at the relevant Facility] measured over the first two years from the [Commencement Date] [Services Availability Date] and (subject to as may be determine in respect of any dispute between the parties as referred to below) such substituted consumption levels shall become the Target Consumption Levels for the purpose of subsequent Cost Benchmarking Procedures under Part 2 of this Schedule. In the absence of agreement as to the average of the annual consumption levels either party may refer the matter to the Dispute Resolution Procedure.

PART 2 – Appendix 2

Worked example of Cost Figure

See separate excel document [Note: this is at Appendix G of the toolkit]

PART 2 - Appendix 3

Utilities Benchmarking – Process Diagram

PART 3

Net Income Benchmarking Process

- Net Income Benchmarking Process

Either party shall be entitled to undertake a Net Income Benchmarking Process as follows:

The Contractor shall be entitled to undertake a Net Income Benchmarking Process if:-

at least [five (5)] years have passed since the Income Benchmarking Date applicable to the last Net Income Benchmarking Process (and for the first Net Income Benchmarking Process only at least [five (5)] years have passed since [the Commencement Date/Services Availability]; and

the Contractor has, on average, not suffered Performance Adjustment Points greater than [    ] in the immediately preceding [five (5)] year period; and

        - [Actual Income (expressed as a 12 month average) earned during the Tested Period has decreased by [5%] or more by comparison to the Actual Income (Indexed and expressed as a 12 month average) for the Tested Period of the immediately preceding Net Income Benchmarking Process or if none, the Base Modelled Income (expressed as a 12 month average) for the Tested Period; 
or Actual Operating Cost (expressed as a 12 month average) incurred during the Tested Period has increased by [5%] or more by comparison to the Actual Operating Cost (Indexed and expressed as a 12 month average) for the Tested Period of the immediately preceding Net Income Benchmarking Process or if none, the Base Modelled Cost (expressed as a 12 month average) for the Tested Period; and

when taking into account Actual Income (expressed as a 12 month average) during the Tested Period and deducting Actual Operating Costs (expressed as a 12 month average) incurred during the Tested Period and comparing that to the figure calculated by deducting the Actual Operating Costs (Indexed) expressed as a 12 month average from the Actual Income (Indexed and expressed as a 12 month average) in both cases for the Tested Period of the immediately preceding Net Income Benchmarking Process or if none, the Base Modelled Costs (expressed as a 12 month average) from Base Modelled Income (expressed as a 12 month average) for the Tested Period; the Net Income Figure has a differential of the equivalent of or greater than [X%] of the Base Head Office Costs plus Base Profit (Indexed and expressed as a 12 month average) during the Tested Period;] or

        - when taking into account Actual Income (expressed as a 12 month) average during the Tested Period and deducting Actual Operating Costs (expressed as a 12 month average) incurred during the Tested Period and comparing that to the figure calculated by deducting the Actual Operating Costs (Indexed and expressed as a 12 month average) from the Actual Income (Indexed and expressed as a 12 month average) in both cases for the Tested Period of the immediately preceding Net Income Benchmarking Process or if none, the Base Modelled Costs (expressed as a 12 month average) from Base Modelled Income (expressed as a 12 month average) for the Tested Period; the Net Income Figure has a differential of the equivalent of or greater than [X%] of the Base Head Office Costs plus Base Profit (Indexed and expressed as a 12 month average) during the Tested Period.

The Authority shall be entitled to request a Net Income Benchmarking Process if at least [five (5)] years have passed since the Income Benchmarking Date applicable to the last Net Income Benchmarking Process (and for the first Net Income Benchmarking Process only at least [five (5)] years have passed since [the Commencement Date/Services Availability].

If either party is entitled to and wishes to commence a Net Income Benchmarking Process, it shall serve a written notice to this effect on the other party within one (1) month of the Net Income Benchmarking Date.

Within (two) 2 months of the Income Benchmarking Date if either party has submitted a notice pursuant to paragraph 1.2 above, the Contractor shall supply an Income Proposal which shall be a proposal containing the following information on a per Facility basis:

details of all Actual Income and Actual Operating Costs for the Tested Period broken down into the categories defined in the LOBTA;

full details set out on a monthly basis for the Tested Period and on an annual basis for the immediately preceding [five (5)] year period of the Performance Adjustment Points under Schedule 6 (Payment and Performance Monitoring System) and all mitigatory steps that have been taken by the Contractor pursuant to its obligations at paragraph 1.4 of this Part 3;

the proposed Net Income Figure or Compensatory Amount and the proposed revised Annual Payment requested from the Income Benchmarking Date;

details of the assumptions used in calculating the Base Modelled Income and Base Modelled Cost and the current status of those assumptions; and

details of the anticipated Actual Income and anticipated Actual Cost for the remainder of the Contract Period where the Contractor, exercising its reasonable skill and care, believes that such anticipated figures differ from Base Modelled Income and Base Modelled Costs for the remainder of the Contract Period and the assumptions used in calculating such anticipated Actual Income and anticipated Actual Cost.

The Contractor must on a continuous basis:

take reasonable steps to mitigate all losses; and

do all things reasonably necessary or desirable as would a prudent leisure operator performing to a standard consistent with the proper performance of the Contractor’s obligations hereunder in so mitigating all losses,

including without prejudice to the generality of the foregoing considering the amendment of the Service Delivery Proposals and Services Specification applicable to the Benchmarked Services and reviewing core pricing, provided always that any amendment to the Services Specification or this Agreement shall be subject to the Change Protocol. Where it is agreed by both parties or determined by the Benchmark Consultant that the Contractor has failed to carry out its duty to mitigate, a cost adjustment shall be made as part of the Net Income Benchmarking Process.

By a date that is two (2) months after receipt of the Income Proposal, or such longer period as the parties, acting reasonably, shall agree, the Authority shall respond to the Contractor stating either:

that it requires further information which is reasonably required to enable the Authority to have a clear understanding of how the proposed revised Annual Payment has been calculated and including steps taken by the Contractor in accordance with paragraph 1.4 of this Part 3 above in which case the Contractor shall issue such information in the form reasonably required by the Authority within a reasonable time having regard to the nature of the information requested as agreed with the Authority.  If within fifteen (15) Business Days of the Authority’s response the parties are unable to agree further information requested, either party may appoint a Benchmark Consultant in accordance with the provisions of this Part 3.  Upon receipt of such further information the Authority shall assess the details and respond to the Contractor pursuant to paragraph 1.5.2 of this Part 3 within twenty (20) Business Days of receipt of such information; or

that:

it accepts the Income Proposal (together with further information provided by the Contractor pursuant to paragraph 1.5.1, if applicable) and that it will amend the Annual Payment in accordance with the provisions of paragraph 4 of this Part 3; or

it does not accept the Income Proposal (together with further information provided by the Contractor pursuant to paragraph 1.5.1, if applicable) giving full and particularised reasons why it does not and the parties shall consult in good faith in an attempt to come to an agreement in relation to the Income Proposal within twenty (20) Business Days of the date of the Authority’s response. If following such consultation an agreement is reached by the parties, the Annual Payment shall, [subject to clause 69.4.3], be adjusted in accordance with the provisions of paragraph 4 of this Part 3. If the parties have not come to an agreement, the Authority shall notify the Contractor that it does not accept the Income Proposal and the parties shall appoint a Benchmark Consultant in accordance with the provisions of this Part 3 of this Schedule. Nothing shall prevent either party from seeking to agree a change to the Services Specification applicable to the Benchmarked Services in accordance with the Change Protocol in which case such process shall run concurrently with this process.

If the Authority fails to respond to the Contractor within the relevant time prescribed by paragraph 1.5 of this Part 3 the Authority shall be deemed to have accepted the Income Proposal and the Annual Payment shall be adjusted in accordance therewith.

Any failure by the Contractor to issue an Income Proposal will be deemed to mean that:

if the Contractor served the notice at paragraph 1.2 of this Part 3, that there is a zero Net Income Figure; or

if the Authority served the notice at paragraph 1.2 of this Part 3, the Contractor does not agree that any Net Income Benchmarking Process is necessary and a Benchmark Consultant can be appointed to conduct the Net Income Benchmarking Process by either party and the procedure in paragraphs 2 and 3 of this Part 3 shall apply and in such circumstances, the Contractor shall be responsible for all of the costs in respect of the Benchmark Consultant.

Benchmark Consultant

At the same time as seeking to agree the appointment of the Benchmark Consultant pursuant to this Part 3, the parties shall:

obtain a cost estimate from the prospective Benchmark Consultant prior to the appointment of the same;

notify the Benchmark Consultant that it is to act fairly and reasonably as between the Contractor and the Authority;

ensure that all parties are aware of the date(s) by which decisions and reports are required; and

agree the terms of reference for the Net Income Benchmarking Process based on those set out in paragraph 2.3 of this Part 3

and any failure to do so shall entitle either party to submit the dispute to the Dispute Resolution Procedure.

The Benchmark Consultant shall take into account the terms of reference for the Net Income Benchmarking Process based on the criteria and factors set out in paragraph 2.3 of this Part 3. The Benchmark Consultant shall benchmark on a like for like comparison basis supported wherever possible by actual inputs from the Comparable Market with the objective being in each case to determine what the Benchmark Consultant concludes the Net Income Figure or Compensatory Amount should be for the purposes of any adjustment to the Annual Payment pursuant to paragraph 4 of this Part 3.

The Benchmark Consultant shall determine the Net Income Figure or Compensatory  Amount taking into account the following considerations over the Tested Period:

the Services Specification in relation to the Benchmarked Services;

socio-economic groups within a catchment area and the demographics of that area;

accessibility to [each of] the [Facility/Facilities] including [its/their] location, public transport to [each of] the [Facility/Facilities] and available car parking;

the Authority’s strategic objectives, social and leisure policies;

the Authority’s pricing policy and other prices for similar services within the Comparable Market;

competition in the catchment area of [the/ each] Facility and from similar facilities to [each of] the [Facility/ Facilities] nationally;

current labour rates and staffing costs at all levels (allowing for any regional variations) for the time being applying within the Comparable Market;

cost variations in consumables and other materials used in the provision of the Benchmarked Services;

the age, specification and condition of the buildings comprising the [Facility/ Facilities] and quality and availability of any on site hotel/ serviced accommodation serving the [Facility/ Facilities] (based upon the assumption that they are being maintained in accordance with the Services Specification);

the cost of any changes in work methods necessary for conformity with Quest accreditation (or equivalent or successor accreditation requirements), Good Industry Practice or Legislation including the impact of consequential additional capital investment;

the terms and provisions of this Agreement and other agreements to which the Contractor is a party in relation to this Project;

the range of services available within [the/ each] [Facility/ Facilities];

information on the legal and taxation status of the organisations running leisure centres within the Comparable Market (including without limitation information as to whether the entities are not for profit organisations);

information available from benchmark data collectors and distributors;

details of any steps taken by the Contractor to mitigate the effects of decreases in Actual Income or increases in Actual Operating Costs particularly any changes to the Services Specification or Service Delivery Proposals in relation to the Benchmarked Services or prices for the activities that the Contractor implemented with a view to complying with its obligations under paragraph 1.4 of this Part 3;

the proposal to adjust the Annual Payment by taking into account the proposed Net Income Figure or Compensatory Amount;

the level of costs that ought to have been incurred in relation to the provision of the Benchmarked Services pursuant to the terms of this Agreement by comparison to the standards, prices and levels of projected income, subsidy and costs in relation to substantially similar services provided in the Comparable Market and bodies requiring similar services on a similar basis by reputable organisations possessing a broadly comparable degree of skill, resources and financial standing relative to the provision of the Benchmarked Services;

the level of income that should be achievable for [the/each] Facility assuming a range of activities and programming were employed when considering the capabilities of [the/each] Facility and the requirements of the market with reference to the relevant Marketing Plan in accordance with the Services Specification; and

such other criteria or terms of reference as the parties may agree (acting reasonably) when appointing and instructing the Benchmark Consultant;

provided always that all changes to be measured by the Benchmark Consultant pursuant to this paragraph 2 shall be measured with reference to other local authority facilities offering similar services to the Benchmarked Services in the Comparable Market during the time of the Tested Period and any other relevant resources.

All discussions with the Benchmark Consultant will be attended by a representative from each party.

Subject to paragraph 1.7.2 of this Part 3, the parties shall bear their own costs, fees and expenses associated with the preparation, review and analysis of the Net Income Benchmarking Process provided always that the Benchmark Consultant shall be paid his reasonable and proper costs in connection with the carrying out of his duties pursuant to the terms of his appointment and subject to paragraph 1.7.2 of this Part 3 such costs shall be borne equally between the parties.

Benchmarking Report

The Benchmark Consultant shall provide his final report (the "Income Benchmarking Report") as soon as is reasonably practicable and, in any event, within not more than three (3) months of his appointment and shall deliver a copy of the Income Benchmarking Report to each of the Authority and the Contractor.

The Benchmark Consultant shall provide in the Income Benchmarking Report full supporting evidence of the assumptions, source of market pricing information and conclusions reached.

The Income Benchmarking Report shall contain as a minimum details of:

the proposed Net Income Figure or Compensatory Amount for [each/ the] [Facility/Facilities] showing income and costs and net profit or net loss  separately and specifying the proposed consequential adjustment to the Annual Payment;

the methodology and all assumptions by which the Net Income Figure or Compensatory Amount was determined;

assumptions made in respect of the Comparable Market;

how the representations made by each party have been taken into account in determining the Net Income Figure or Compensatory Amount and shall include full details of issues and comments raised by both parties;

full evidence to support the difference between:

Actual Income and Base Modelled Income or Actual Income for the Tested Period of the immediately preceding Net Income Benchmarking Process; and

Actual Operating Costs and Base Modelled Costs or Actual Operating Costs of the Tested Period of the immediately preceding Net Income Benchmarking Process;

to arrive at the Net Income Figure or Compensatory Amount (as the case may be);

full evidence to support the difference between the previous income and costs of providing the Benchmarked Services and mitigation in such respect and in respect of each component a breakdown of how each is comprised;

full evidence in support of each of the criteria used to determine the Net Income Figure or Compensatory Amount;

full details of sources of information used in establishing the Net Income Figure or Compensatory Amount;

in respect of each component of the Net Income Figure or Compensatory Amount a breakdown of how each is comprised;

costs of the Contractor’s staff including management or otherwise;

details of the Contractor’s management and head office overhead costs;

any efficiencies and innovations in Good Industry Practice and Sport England Guidance relevant to the delivery of the Benchmarked Services at [the/ each] Facility; and

such other details as the parties may agree when appointing and instructing the Benchmark Consultant or which the Benchmark Consultant considers relevant.

The Authority and the Contractor shall use reasonable endeavours to ensure the Benchmark Consultant complies with its obligations under its appointment and, in particular, to produce the Income Benchmarking Report on the due date under the appointment.

If the Benchmark Consultant fails to produce an Income Benchmarking Report by the due date without good cause, then (subject to paragraph 3.6) either party may require the Benchmark Consultant to be replaced and the parties shall reserve the right in the appointment of the Benchmark Consultant to withhold payment of the remaining elements of payment due to the Benchmark Consultant in such circumstances. If the Benchmark Consultant fails to complete on time and he is to be replaced, the parties shall ensure the Benchmark Consultant agrees to return all the information provided by the Authority and the Contractor and to provide the incomplete Income Benchmarking Report to the Authority and the Contractor.

In circumstances where a Benchmark Consultant fails to deliver an Income Benchmarking Report and the parties reasonably believe that no Benchmark Consultant is likely to produce an adequate Income Benchmarking Report, the provisions of paragraph 3.11 of this Part 3 below shall apply.

Both parties shall within twenty (20) Business Days of receiving the Income Benchmarking Report serve notice on the other party setting out whether or not it agrees with the Net Income Figure or Compensatory Amount.

In the event that the parties agree with the Net Income Figure or Compensatory Amount the Annual Payment will be adjusted in accordance with paragraph 4 of this Part 3.

In the event that neither party issues a notice disagreeing with the Net Income Figure or Compensatory Amount within twenty (20) Business Days of receiving the Income Benchmarking Report, unless either party requests in writing to the other that such period be extended, both parties shall be deemed to have approved the Net Income Figure or Compensatory Amount and the Annual Payment will be adjusted in accordance with paragraph 4 of this Part 3.

In the event that either party disagrees with the Net Income Figure or Compensatory Amount within the prescribed time period (or as extended by agreement between the parties) it shall include in its notice to the other party its reasons for disputing such Net Income Figure or Compensatory Amount and paragraph 3.11 of this Part 3 shall apply.

f paragraph 3.6 or paragraph 3.10 of this Part 3 applies and/or where the Benchmark Consultant fails to establish the Net Income Figure or Compensatory Amount acceptable to both parties, the Authority and the Contractor shall meet as soon as practicable and negotiate in good faith to agree the appropriate Net Income Figure or Compensatory Amount.  In such circumstances if the parties have been unable to agree an appropriate Net Income Figure or Compensatory Amount within fifteen (15) Business Days of first meeting, then the parties shall use all reasonable endeavours for a further period of up to thirty (30) Business Days to agree the contents of a Change pursuant to the Change Protocol with a view to a change to the Services Specification, the Facilities and/or the Method Statements, the effect of which would be to mitigate the negative or adverse implications to both parties of any adjustment to the Annual Payment which would otherwise result from the Net Income Benchmarking Process.

In circumstances where, notwithstanding the parties’ efforts pursuant to paragraph 3.11 of this Part 3 above, the parties have been unable to agree the Net Income Figure or Compensatory Amount within the fifteen (15) Business Day period above (or where the parties have endeavoured to agree a Change in accordance with the Change Protocol but have failed to do so, then within fifteen (15) Business Days of expiry of the aforementioned thirty (30) Business Day period or where such Change  has been agreed but the implementation of the Change has not been agreed or determined in accordance with the Change Protocol, then within fifteen (15) Business Days of the exhaustion of the procedure in the Change Protocol), either party may refer the matter for determination by the Dispute Resolution Procedure. For the purposes of this paragraph 3.12, the party referring the dispute shall instruct the Adjudicator (as defined in Clause 64 (Dispute Resolution)) to determine the dispute in accordance with the terms of this Part 3.

Once the Net Income Figure or Compensatory Amount is agreed or determined in accordance with this Schedule, the provisions of paragraph 4 of this Part 3 below shall apply in relation to adjustment of the Annual Payment.

Implementation

Subject to paragraph 4.3, when the Net Income Figure or Compensatory Amount is agreed or determined in accordance with Part 3 of this Schedule any increase or decrease in the Annual Payment shall be calculated as follows and shall be effective from the Income Benchmarking Date, and, as appropriate, backdated to such date:

[X%] of the Net Income Figure shall be applied in full:

where a Surplus Annual Payment applies to decrease the Annual Payment to the Authority ("Surplus Payment Decrease") unless and until such Surplus Payment Decrease is replaced pursuant to a further Net Income Benchmarking Process; or

where a Deficit Annual Payment applies to increase the Annual Payment to the Contractor ("Deficit Payment Increase") unless and until such Deficit Payment Increase is replaced pursuant to a further Net Income Benchmarking Process; or

[X%] of the Compensatory Amount shall be applied in full:

where a Surplus Annual Payment applies to increase the Annual Payment to the Authority (“Compensatory Amount Increase”) unless and until such Compensatory Amount Increase is replaced pursuant to a further Net Income Benchmarking Process or Competing Facility Benchmarking Process; or

where a Deficit Annual Payment applies to decrease the Annual Payment to the Contractor (“Compensatory Amount Decrease”) unless and until such Compensatory Amount Decrease is replaced pursuant to a further Net Income Benchmarking Process or Competing Facility Benchmarking Process.

[Without prejudice to the adjustment of the Base Case and the Annual Payment as permitted under this Agreement, the LOBTA shall not be amended by the Net Income Figure or Compensatory Amount.]

There shall be no double counting or double recovery by the Contractor.

Appendix 1 to this Part 3 comprises a worked example of how the Net Income Benchmarking Process is intended to work.

Information

Within three (3) months of the end of the first year following [the Commencement Date/Services Availability] and within three (3) months of the end of each subsequent year the Contractor shall, in addition to its obligations under Clause 78 (Contractor’s Records) provide to the Authority such information as the Contractor would use for the purposes of calculating the Net Income Figure or Compensatory Amount for that year for [the/ each] Facility notwithstanding that the Net Income Benchmarking Process is not being conducted in respect of that year.

PART 3 – Appendix 1

Worked example Net Income Benchmarking

See separate excel document [Note: this is at Appendix G of the toolkit]

PART 3 – Appendix 2

Net Income Benchmarking – Process Diagram

[PART 4

Special Benchmarking Process

Where a Key User permanently ceases to use the Key User Facilities for which it was paying a rental fee (and ceases paying a rental fee) or was making payments for use of the Key User Facilities and reduces use by more than [X%] when compared to the Key User Base Modelled Income, other than as a result of a Force Majeure Event or Relief Event or due to the default or failure in performance of the Contractor or any Contractor Related Party, the Contractor shall promptly notify the Authority in accordance with paragraph 2 below and may request in such notice that the provisions of this Part 4 shall apply ("Special Benchmarking Process"). For the avoidance of doubt, where it is determined that a Key User has ceased to use the Key User Facilities or reduced its use by more than [X%] when compared to the Key User Base Modelled Income as a result of a compensatory increase in the use of an alternative facility managed or operated by the Contractor, the provisions of this Part 4 shall not apply.

The Contractor is entitled to issue a Special Benchmarking Warning Notice to the Authority where the loss of a Key User has been notified to the Authority as part of the monthly Performance Monitoring Report in accordance with Schedule 6 (Payment and Performance Monitoring System) in each and every month of the previous three (3) month period. For the purposes of this paragraph, loss of a Key User means:

where notification has been given by the Key User to the Contractor that they will no longer be using the [Facility/Facilities]; or

where the Key User permanently ceases to use the Key User Facilities for which it was previously paying a rental fee or making user income payments (and ceases paying a rental fee or making user income payments); or

where the Key User reduces use of the Key User Facilities for which it was previously paying a rental fee or making user income payments by more than [X%] when compared to the Key User Base Modelled Income;

other than due to the default or failure in performance of the Contractor or any Contractor Related Party or other than as a result of a Force Majeure Event or Relief Event.

In the instance of a Special Benchmarking Warning Notice where a Key User is no longer able to pay the rental fee at the required level of the Key User Modelled Income, then in order for this Part 4 to apply the Contractor must be able to demonstrate that it has worked with the Key User to mitigate the issue.

The Contractor shall keep the Authority informed, following issue of the Special Benchmarking Warning Notice pursuant to paragraph 2 of this Part 4, as to the circumstances of the Key User ceasing to use the Key User Facilities or reducing use of the Key User Facilities by more than [X%] when compared to the Key User Base Modelled Income and at the same time shall inform the Authority as to its proposals to mitigate any adverse affect of any reduced income.

The Contractor shall, on a continuous basis, seek to mitigate its losses by doing all things reasonably necessary or desirable as would a prudent leisure operator consistent with the proper performance of the Contractor's obligations under this Agreement to minimise the effect of the loss or reduction in use of the Key User. The Contractor shall demonstrate that it has followed a clear mitigation action plan following the issue of a Special Benchmarking Warning Notice and during the Key User Assessment Period. Any failure to do so shall mean the Contractor shall not be entitled to any compensation for net income loss in respect of the period for which it did not properly mitigate the effects of the loss of the Key User (as appropriate).

Within two (2) months following the expiry of the Key User Assessment Period, the Contractor shall (if it wishes to apply for compensation pursuant to this Special Benchmarking Process) provide the Authority with a notice in relation to the loss of the Key User (the "Key User Information Notice") which must:

identify the Key User Base Modelled Income assumed for the Key User Assessment Period;

confirm the Reduced Actual Income for the Key User Assessment Period together with supporting evidence including details of the actual numbers of Users in relation to the Key User Facilities on a monthly basis during the same period;

confirm that, when taking into account Reduced Actual Income during the Key User Assessment Period (taking into account any costs savings made or which ought to have been made as a result of any reduced use of the Key User Facilities) the Reduced Actual Income is lower than the Key User Base Modelled Income (taking into account adjustments for any cost savings) by [X%] or more;

provide details of the steps taken by the Contractor to mitigate the effects of the loss of a Key User in complying with its obligations under paragraph 5 of this Part 4;

confirm that the Contractor has performed its obligations in this Agreement and Services Specification; and

provide details of the proposed Special Benchmarking Compensation Payment in accordance with paragraph 9.

As soon as practicable after the Authority receives a Key User Information Notice the parties shall discuss and agree the matters set out in the Key User Information Notice. In such discussions the Contractor shall promptly respond to any reasonable requests for additional information made by the Authority to enable the parties to agree the Special Benchmarking Compensation Payment. The Authority will take into account the relevant criteria set out in paragraph 2.3 of Part 3 of this Schedule in so far as they are relevant to the Key User Facilities affected by the loss of the Key User and to assess the loss of income (and any cost savings that ought to be achievable) resulting from the loss of the Key User and income generated or which ought to have been generated by the Contractor from other Users of the Key User Facilities. If the parties cannot agree the Special Benchmarking Compensation Payment in respect of any Key User Information Notice then the dispute will be determined in accordance with the Dispute Resolution Procedure.

For the avoidance of doubt if a Key User ceases to use the Key User Facilities or reduces its use by more than [X%] of the Key User Base Modelled Income twelve (12) months or less prior to the next Income Benchmarking Date, then the procedure set out in this Part 4 shall be carried out at the next Income Benchmarking Date provided that any rent or income received in the twelve (12) month period during which the Key User ceases to use or reduces use of the Key User Facilities by more than [X%] shall not be taken into account in calculating the Actual Income for that period. In addition, if the Contractor has been entitled to an Average Excess Surplus share in accordance with paragraph 7 of Schedule 19 (Surplus Share) any Average Excess Surplus achieved shall be taken into account when carrying out the procedure set out in this Part 4 and deducted from any Special Benchmark Compensation Payment.

In order to ensure that the Contractor continues to mitigate the impact of a loss of a Key User following the implementation of the Special Benchmarking Process, the level of Special Benchmarking Compensation Payment made available by the Authority to the Contractor shall be reduced over the subsequent [four (4)] year period following completion of the Key User Assessment Period and Special Benchmarking Process in accordance with the following profile:

[x%] of the agreed Special Benchmarking Compensation Payment shall be made available to the Contractor during the first Contract Year following completion of the Key User Assessment Period and Special Benchmarking Process;

a maximum of [x%] of the agreed Special Benchmarking Compensation Payment shall be made available to the Contractor during the second Contract Year following completion of the Key User Assessment Period and Special Benchmarking Process;

a maximum of [x%] of the agreed Special Benchmarking Compensation Payment shall be made available to the Contractor during the third Contract Year following completion of the Key User Assessment Period and Special Benchmarking Process;

a maximum of [x%] of the agreed Special Benchmarking Compensation Payment shall be made available to the Contractor during the fourth Contract Year following completion of the Key Users Assessment Period and Special Benchmarking Process; and

no further Special Benchmarking Compensation Payment shall be made available to the Contractor from the end of the [fourth] Contract Year following completion of the Key User Assessment Period and Special Benchmarking Process and for the remainder of the Contract Period in relation to the same or materially similar issue or event that led to the Special Benchmarking Process.

As soon as practicable after the Special Benchmarking Compensation Payment is agreed or otherwise determined pursuant to the Dispute Resolution Procedure the Contractor shall submit to the Authority an invoice for the amount of that Special Benchmarking Compensation Payment for the relevant Contract Year in accordance with the agreed Key User Information Notice and for any VAT payable by the Authority in respect of that amount. The Authority will pay the amount of such invoice by the date thirty (30) Business Days after the receipt by the Authority of that invoice.]

PART 5

Competing Facility Benchmarking Process

- Competing Facility Process

Where either party has reason to believe that a Competing Facility is likely to arise or has arisen the provisions of this Part 5 shall apply ("Competing Facility Benchmarking Process") and such party shall notify the other party as soon as reasonably practicable.

The Contractor shall:

as soon as reasonably practicable following issue or receipt of the notice referred to in paragraph 1.1 of this Part 5 notify the Authority of the implications (or likely implications) of the Competing Facility and its impact (or likely impact) on this Agreement and at the same time shall inform the Authority as to its proposals to mitigate any adverse affect of the Competing Facility on income from Users; and

keep the Authority informed, following issue or receipt of the notice pursuant to paragraph 1.1 of this Part 5, as to the development of the Competing Facility and when the Competing Facility actually commences operations,

and the parties shall, as soon as reasonably practicable after issue of such notices meet to discuss the content of such notices and any measures to be taken by either party as a result of such notices.

The Contractor shall, on a continuous basis, use all reasonable endeavours to mitigate its losses by doing all things reasonably necessary or desirable as would a prudent leisure operator consistent with the proper performance of the Contractor's obligations under this Agreement to minimise the effect of a Competing Facility on the [Facility/Facilities] and the Service[s].

Within two (2) months following the expiry of the Competing Facility Assessment Period, the Contractor shall (if it wishes to implement this Competing Facility Benchmarking Process) provide the Authority with a notice (the "Competition Information Notice") which must:

identify the Base Modelled Income assumed for the Competing Facility Assessment Period together with details of the assumed number of Users at the [Facility/Facilities] on a monthly basis during the same period;

confirm the Actual Income for the Competing Facility Assessment Period together with supporting evidence including details of the actual numbers of Users at the [Facility/Facilities] on a monthly basis during the same period;

confirm that, when taking into account Actual Income during the Competing Facility Assessment Period and deducting Actual Operating Costs incurred during the Competing Facility Assessment Period, the Net Income Figure has a differential of [X%] or more by comparison to the figure calculated by deducting Base Modelled Costs (Indexed) from Base Modelled Income (Indexed) for the same Competing Facility Assessment Period AND the Net Income Figure has a differential of the equivalent or greater than [X%] of the Base Head Office Costs plus Base Profit;

describe the nature of the Competing Facility that has had an adverse impact on the activities carried out at the [Facility/Facilities] including (to the extent that such information is in the public domain or either the Contractor has such information or through reasonable enquiry can obtain such information) the nature and programming of the activities, services specification and prices charged in respect of the Competing Facility compared to the[Facility/Facilities];

provide full details of the steps taken by the Contractor to mitigate the effects of the Competing Facility; and

provide details of the proposed Net Income Figure (Competing Facility) and any proposed adjustment to the Annual Payment.

Upon receipt of the Competition Information Notice, the Authority shall assess the details and the provisions of paragraph 2 of Part 5 of this Schedule shall apply.

If either party disagrees that a Competing Facility is likely to arise or has arisen or as to the impact of the Competing Facility (including any impact on the Actual Income), the parties shall appoint a Benchmark Consultant in accordance with the provisions of paragraph 3 of Part 5 of this Schedule.

The parties agree and acknowledge that the aim and purpose of Part 5 of this Schedule shall be to ensure that the Contractor is left in no better or no worse position than it would have been in had the Competing Facility not operated and, notwithstanding the provisions of Clause 69 (Financial Adjustments), references in this Schedule to the Contractor being left in "no better and no worse position" shall be construed to refer to the Contractor's financial position as contemplated in the LOBTA (having due regard to the operation of the Competing Facility).

Response to Competition Information Notice

As soon as reasonably practicable, but in any event not later than thirty (30) Business Days following receipt of the Competition Information Notice from the Contractor, the Authority shall respond to the Contractor stating either:

that it requires further information which is reasonably required to enable the Authority to assess the information and/or the proposals contained in the Competition Information Notice (including how the proposed Net Income Figure (Competing Facility) and any consequential proposed adjustment to the Annual Payment has been calculated and including steps taken by the Contractor to mitigate the effects of the Competing Facility) in which case the Contractor shall issue such information in the form reasonably required by the Authority within a reasonable time having regard to the nature of the information requested.  Upon receipt of such further information, the Authority shall assess the details and respond to the Contractor pursuant to paragraph 2.1.2 of this Part 5 within thirty (30) Business Days of receipt of such information; or

that:

it accepts the Competition Information Notice (as supplemented or amended, where appropriate, with any additional information provided pursuant to paragraph 2.1.1) and that (where appropriate) adjustment to the Annual Payment will be made in accordance with the provisions of paragraph 5 of this Part 5; or

it does not accept the Competition Information Notice, giving particularised reasons why it does not and the parties shall consult in good faith in an attempt to come to an agreement in relation to the Competition Information Notice within thirty (30) Business Days of the date of the Authority's response. If following such consultation an agreement is reached by the parties, the Authority will (where appropriate) be required to adjust the Annual Payment in accordance with the provisions of paragraph 5 of this Part 5. If the parties have not come to an agreement within such thirty (30) Business Day period, the Authority shall notify the Contractor that it does not accept the Competition Information Notice and the parties shall appoint a Benchmark Consultant in accordance with the provisions of this paragraph 3 of Part 5 of this Schedule.

If the Authority fails to respond to the Contractor within the relevant time prescribed by paragraph 2.1 of this Part 5, the Authority shall be deemed to have accepted the Competition Information Notice and the adjustment to the Annual Payment proposed.

Benchmark Consultant

At the same time as seeking to agree the appointment of the Benchmark Consultant pursuant to this Part 5, the parties shall:

obtain a cost estimate from the prospective Benchmark Consultant prior to the appointment of the same; and

agree the terms of reference for the Benchmark Consultant, based on those set out in paragraph 3.2 of this Part 5,

and any failure to do so shall entitle either party to submit the dispute to the Dispute Resolution Procedure.

The Benchmark Consultant shall determine the impact of the Competing Facility (if any) and calculate the Net Income Figure (Competing Facility) taking into account the following considerations:

the quality, nature and extent of the Services as against the services provided at the Competing Facility;

socio-economic groups within the catchment area and the demographics of that area for each of the [Facility/Facilities] and the Competing Facility;

accessibility to each of the [Facility/Facilities] and the Competing Facility including location, public transport and available car parking;

the Authority's social and sports and leisure policies;

the pricing policy applied at the Competing Facility as against the pricing policy applied at the[Facility/Facilities];

other competition in the catchment area of the[Facility/Facilities];

current labour rates at the Competing Facility and at the[Facility/Facilities];

the cost of any changes in work methods or other costs reasonably incurred by the Contractor in attempting to increase User numbers or revenue in response to the impact of the Competing Facility including the cost of consequential additional capital investment;

any other factors reasonably considered to be affecting the number of Users using the [Facility/Facilities] (not caused by the Competing Facility);

details of any steps taken by the Contractor to mitigate the effects of any adverse impact of the Competing Facility (including any decrease in Actual Income) particularly any proposed Changes to the Services Specification or the Service Delivery Proposal in relation to the Services or prices for services or Changes that the Contractor has implemented with a view to complying with its' obligations to seek to mitigate;

such other criteria or terms of reference as the parties may agree (acting reasonably) when appointing and instructing the Benchmark Consultant;

the proposed adjustment to the Annual Payment by taking into account the proposed Net Income Figure (Competing Facility); and

the level of income that should be achievable for the [Facility/Facilities] (assuming the Contractor was complying with all of its obligations under this Agreement and assuming an appropriate range of activities/services/programming are employed, taking into account the capabilities of the [Facility/Facilities] and the expertise in relation to the Services contemplated by this Agreement).

All discussions with the Benchmark Consultant will be attended by representatives from each party.

The parties shall bear their own costs, fees and expenses associated with the preparation, review and analysis of the Competing Facility Benchmarking Process, provided always that the Benchmark Consultant shall be paid his reasonable and proper costs in connection with the carrying out of his duties pursuant to the terms of his appointment and such costs shall be borne equally between the parties.

Competing Facility Report

The Benchmark Consultant shall be required to provide his final report (the "Competing Facility Report") as soon as is reasonably practicable and, in any event, within not more than two (2) months of his appointment and to deliver a copy of the Competing Facility Report to each of the Authority and the Contractor.

The Benchmark Consultant shall provide in the Competing Facility Report full supporting evidence of the assumptions, source of market pricing information and conclusions reached.

The Competing Facility Report shall contain as a minimum details of:

the proposed Net Income Figure (Competing Facility) showing income and costs and net profit or net loss separately and specifying any proposed consequential adjustment to the Annual Payment;

the methodology and all assumptions by which the Net Income Figure (Competing Facility) and any proposed adjustment to the Annual Payment was determined;

assumptions made in respect of the impact of the Competing Facility on the [Facility/Facilities] (including any assumptions made in respect of other factors affecting the number of Users at the [Facility/Facilities] not caused by the Competing Facility);

how the representations made by each party have been taken into account in determining:

the Net Income Figure (Competing Facility) and any proposed adjustment to the Annual Payment; and

the impact of the Competing Facility,

and shall include full details of issues and comments raised by both parties;

full evidence to support:

the difference between Actual Income and Base Modelled Income (Indexed) in relation to the Competing Facility Assessment Period; and

details of Actual Costs for the Competing Facility Assessment Period;

to arrive at the Net Income Figure (Competing Facility) and any proposed adjustment to the Annual Payment;

in respect of each component of the Net Income Figure (Competing Facility), a breakdown of how each is comprised; and

such other details as the parties may agree when appointing and instructing the Benchmark Consultant or which the Benchmark Consultant considers relevant.

The Authority and the Contractor shall use reasonable endeavours to ensure the Benchmark Consultant complies with its obligations under its appointment and, in particular, to produce the Competing Facility Report on the due date under the appointment.

If the Benchmark Consultant fails to produce a Competing Facility Report by the due date without good cause, then either party may require the Benchmark Consultant to be replaced and the parties shall reserve the right in the appointment of the Benchmark Consultant to withhold payment of the remaining elements of payment due to the Benchmark Consultant in such circumstances. If the Benchmark Consultant fails to complete on time and he is to be replaced, the parties shall ensure the Benchmark Consultant agrees to return all the information provided by the Authority and the Contractor and to provide the incomplete Competing Facility Report to the Authority and the Contractor.

In circumstances where a Benchmark Consultant fails to deliver a Competing Facility Report with due cause and the parties reasonably believe that no Benchmark Consultant is likely to produce an adequate Competing Facility Report, the provisions of paragraph 4.11 below shall apply.

Each party shall within twenty (20) Business Days of receiving the Competing Facility Report serve notice on the other party setting out whether or not it agrees with the contents of the Competing Facility Report (including the proposed Net Income Figure (Competing Facility) and/or any proposed adjustment to the Annual Payment).

In the event that the parties agree with the contents of the Competing Facility Report and any proposed adjustment to the Annual Payment, this shall be implemented in accordance with paragraph 5 of this Part 5.

In the event that neither party issues a notice disagreeing with the Net Income Figure (Competing Facility) within twenty (20) Business Days of receiving the Competing Facility Report, unless either party requests in writing to the other that such period be extended, both parties shall be deemed to have approved the Competing Facility Report, the Net Income Figure (Competing Facility) and the proposed adjustment to the Annual Payment and the Annual Payment will be adjusted in accordance with paragraph 5 of this Part 5.

In the event that either party disagrees with the contents of the Competing Facility Report, the Net Income Figure (Competing Facility) and/or any proposed adjustment to the Annual Payment within the prescribed time period (or as extended by agreement) it shall include in its notice to the other party its reasons for disputing such Competing Facility Report, Net Income Figure (Competing Facility) and/or proposed adjustment to the Annual Payment and paragraph 4.11 of this Part 5 shall apply.

If paragraph 4.6 or 4.10 applies and/or where the Benchmark Consultant fails to establish the Net Income Figure (Competing Facility) and proposed adjustment to the Annual Payment acceptable to both parties, the Authority and the Contractor shall meet as soon as practicable and negotiate in good faith to agree the impact of the Competing Facility and/or an appropriate Net Income Figure (Competing Facility) and/or an appropriate adjustment to the Annual Payment. In circumstances where the parties have been unable to agree the impact of the Competing Facility and/or an appropriate Net Income Figure (Competing Facility) and/or an appropriate adjustment to the Annual Payment within fifteen (15) Business Days of first meeting, then the parties shall use all reasonable endeavours for a further period of up to fifteen (15) Business Days to agree the impact of the Competing Facility and/or an appropriate Net Income Figure (Competing Facility) and/or an appropriate adjustment to the Annual Payment and in circumstances where, notwithstanding the parties' efforts pursuant to this paragraph 4.11, the parties have been unable to so agree within such fifteen (15) Business Day period, either party may within a further fifteen (15) Business Days refer the matter to the Dispute Resolution Procedure.

Implementation

When the Net Income Figure (Competing Facility) and any consequential adjustment to the Annual Payment is agreed by the parties or determined pursuant to this Schedule, [X%] of the Net Income Figure (Competing Facility) shall be applied in full:

where a Surplus Annual Payment applies to decrease the Annual Payment to the Authority; or

where a Deficit Annual Payment applies to increase the Annual Payment to the Contractor,

for the period from the end of the Competing Facility Assessment Period to the Expiry Date (unless and until the Annual Payment is adjusted pursuant to any subsequent Competing Facility Benchmarking Process, Net Income Benchmarking Process or pursuant to paragraph 6 below).

Without prejudice to the adjustment of the Base Case and the Annual Payment as permitted under this Agreement, the LOBTA shall not be amended by the Net Income Figure (Competing Facility).

There shall be no double counting or double recovery by the Contractor.

Ongoing assessment

Where the Annual Payment is adjusted pursuant to paragraph 5.1 above, for the period of twelve (12) months from the end of the Competing Facility Assessment Period, and each subsequent period of twelve (12) months from the anniversary thereof (an "Assessment Year") the Contractor shall (subject to paragraph 6.2) within three (3) months of the end of an Assessment Year issue a notice to the Authority which shall identify:

the Actual Income and Actual Operating Costs for the relevant Assessment Year;

the Base Modelled Income (Indexed) and Base Modelled Costs (Indexed) for the relevant Assessment Year; and

the differential between the Actual Leisure Management Amount by comparison to the Base Leisure Management Amount (Indexed) for the relevant Assessment Year.

Where despite the impact of the Competing Facility, the Actual Leisure Management Amount is equal to or greater than the Base Leisure Management Amount (Indexed) for the relevant Assessment Year, the adjustment to the Annual Payment made in accordance with paragraph 5.1 above shall cease to apply so that for each year following the Assessment Year (subject to any further operation of this Schedule as result of any subsequent Competing Facility) there shall be no further requirement on the part of the Contractor to comply with this paragraph 6 and/or for the Authority to pay any Net Income Figure (Competing Facility) in respect of that Assessment Year and/or any subsequent Assessment Year.

Losses prior to Competing Facility Assessment Period

Where the period of one (1) complete year (as referred to in the definition of Competing Facility Assessment Period) commences six (6) or more months after the later of the dates referred to in paragraphs (a) to (c) of the definition of Competing Facility Assessment Period (such date being used to determine the trigger date for the Competing Facility Assessment Period (the "Trigger Date") then, in addition to the amount (if any) payable by the Authority in accordance with paragraph 5 (Implementation), the Authority shall pay to the Contractor a fair and reasonable amount to reflect any loss of Revenue arising from the Competing Facility in respect of the period from the Trigger Date until the commencement of the Competing Facility Assessment Period, such fair and reasonable amount being determined in accordance with the principles of this Schedule.

SCHEDULE 19

SURPLUS SHARE

    - This Schedule shall be applied to calculate the overall Excess Surplus/Deficit generated as a result of the management of the [Facility/Facilities] [the following [Facility/Facilities] only: [insert names of Facilities this schedule applies to].

    - Subject to paragraph 6, within three (3) months of the end of each Contract Year [following Services Availability] the Contractor shall provide to the Authority a calculation of the Operating Surplus/Deficit, Excess Surplus/Deficit and Average Excess Surplus for the previous Contract Year, subject to the calculation being audited by the Contractor’s auditors if an audited calculation cannot be provided within the required timescale. The calculation shall be in the form of a statement and certificate signed by the Contractor’s auditors or another registered auditor (the "Operating Surplus Statement") confirming the figures for Income and Expenditure and presented in the same format as in the [[Base Case] [LOBTA]] and setting out details of the Operating Surplus/Deficit, Excess Surplus/Deficit and Average Excess Surplus/Deficit for that previous Contract Year.

    - The Operating Surplus/Deficit for each Contract Year, as set out in each Operating Surplus Statement, shall be calculated in accordance with the formula:

OS/D = A – B, where

OS/D	means the Operating Surplus/Deficit for the relevant Contract Year.

A	means the Income received by and/or due to the Contractor in relation to the Services during the relevant Contract Year.

B	means all the Expenditure actually paid (or incurred but not paid) by the Contractor during the relevant Contract Year.

    - The Excess Surplus/Deficit (ES/D) shall be calculated in accordance with the formula:

ES/D = OS/D – the Contractor’s Projected Surplus

    - The Average Excess Surplus (AES) attributable to a Contract Year shall be calculated by the Contractor in accordance with the provisions of this paragraph 5 on the dates specified at paragraph 6 of this Schedule. The AES shall be the total ES/D for the preceding three (3) Contract Years divided by the number of Contract Years and shall be calculated using the following formula:

AES = (ES/D1 + ES/D2 + ES/D3), where

3

ES/D1	means the ES/D for the Contract Year ending immediately before the Contract Year during which the calculation is taking place

ES/D2	means the ES/D for the Contract Year immediately preceding ES/D1

ES/D3	means the ES/D for the Contract Year immediately preceding ES/D2

    - The first Average Excess Surplus calculation shall be undertaken by the Contractor at the same time as the Excess Surplus/Deficit calculation following the expiry of the third (3rd) Contract Year following [the Commencement Date] [Services Availability]. Subsequent Average Excess Surplus calculations shall be undertaken annually by the Contractor at the same time as the Excess Surplus/Deficit Calculation for the relevant Contract Year.

    - Where the Operating Surplus Statement shows a positive Average Excess Surplus, the Average Excess Surplus shall be divided between the parties according to the following table.

| Contractor's share of the Average Excess Surplus | Authority's share of the Average Excess Surplus |
| --- | --- |
| [X%] | [X%] |

    - Any dispute between the parties regarding the Operating Surplus Statement shall be dealt with in accordance with the Dispute Resolution Procedure.

    - Following agreement or as determined in accordance with paragraph 8, the Authority’s share of any Average Excess Surplus shall be used at the discretion of the Authority.

    - The Contractor shall pay the Authority’s share of the Average Excess Surplus to the Authority within thirty (30) Business Days of agreement or determination.

    - For the purpose of this Schedule the following terms shall have the following meanings:

"Average Excess Surplus" or "AES"

means the average excess profit to be shared between the Contractor and the Authority, calculated in accordance with paragraphs 5, 6 and 7;

"Base Modelled Income"

means the annual operating income (Indexed) that is projected to be earned in relation to the [Facility/ Facilities] by the Contractor as shown in row [X] of the ‘summary’ worksheet of the [[Base Case] [LOBTA]];

"Base Head Office Costs"

means in relation to the [Facility/ Facilities] an amount (Indexed) which is [X%] of the Base Modelled Income shown in row [X] of the ‘summary’ worksheet of the [[Base Case] [LOBTA]];

"Base Profit"

means in relation to the [Facility/ Facilities] an amount (Indexed) which is [X%] of the Base Modelled Income shown in row [X] of the ‘summary’ worksheet of the [[Base Case] [LOBTA]]);

"Contractor Profit"

means an amount which is a fixed amount of the income received by the Contractor in respect of the Services, calculated as [X%] of the Income for the relevant Contract Year;

"Contractor’s Projected Surplus"

means the greater of the amount projected in the [Base Case][LOBTA], calculated in accordance with the definition of “Base Profit” plus “Base Head Office Costs” and the sum of “Contractor Profit” plus “Head Office Costs” for the relevant Contract Year;

"Excess Surplus/Deficit" or "ES/D"

means the excess profit or deficit for the year, calculated as per paragraph 4;

"Expenditure"

means the amount of direct costs and expenditure actually paid (or incurred but not paid) by the Contractor during the relevant Contract Year in respect of the Services [including any Surplus Annual Payment] but excluding:

(a)	any sums paid in respect of a previous Contract Year

(b)	any Performance Adjustments levied through the terms of Schedule 6 (Payment and Performance Monitoring System);

(c)	any Contractor Profit; and

(d)	any Head Office Costs;

"Head Office Costs"

means an amount which is a fixed amount of the income received by the Contractor in respect of the Services, calculated as [X%]7 of the Income for the relevant Contract Year;

"Income"

means the actual operating income of the Contractor (or its Sub-Contractor (without double counting)) in the operation of the [Facility][Facilities] [(for the avoidance of doubt including any Annual Payment where it is a Deficit Annual Payment actually received by the Contractor in respect of the Services in respect of the relevant Contract Year)] but excluding any sums received in respect of a previous Contract Year;

"Operating Surplus/Deficit" or "OS/D"

has the meaning ascribed to it in paragraph 3.

"Operating Surplus Statement"

has the meaning ascribed to it in paragraph 2.

[Part A -] Worked Example (excluding any inflationary impacts)

The following worked example assumes a Deficit Annual Payment of £1,000,000 when taking into account total modelled income (£2,000,000) less total modelled expenditure (£3,000,000). Total modelled expenditure includes Base Profit costs of £100,000 (5% of total operating income) and Base Head Office Costs of £100,000 (5% of total operating income.

Income (A) = £3,000,000 (all income including the Deficit Annual Payment)

Expenditure (B) = £2,800,000 (all expenditure excluding Base Profit of £100,000 and Base Head Office Costs of £100,000)

In the base model, the Operating Surplus/Deficit is £200,000 surplus which is equal to the Contractor’s Projected Surplus (Base Profit plus Base Head Office Costs = £200,000) i.e. no Excess Surplus.

OS/D = A – B = £3,000,000 - £2,800,000 = £200,000 Operating Surplus

ES/D = £200,000 - £200,000 = £0

If at the end of Year 1 there has been an increase in income:

Income (A) = £3,300,000 (all income including the Deficit Annual Payment)

Expenditure (B) = £2,800,000 (all expenditure excluding Contractor’s Profit of £115,000 (5% of total operating income) and Head Office Costs of £115,000 (5% of total operating income)

OS/D = A – B = £3,300,000 – £2,800,000 = £500,000 Operating Surplus

ES/D1 = OS/D (£500,000) – the Contractor’s Projected Surplus (£230,000) = £270,000 Excess Surplus

To note; the Contractor’s Projected Surplus is the greater of Base Profit plus Base Head Office Costs (£200,000) and Contractor’s Profit and Head Office Costs (£230,000)

If at the end of Year 2 there have been savings in expenditure:

Income (A) = £3,300,000 (all income including the Deficit Annual Payment)

Expenditure (B) = £2,700,000 (all expenditure excluding Contractor’s Profit of £115,000 (5% of total operating income) and Head Office Costs of £115,000 (5% of total operating income)

OS/D = A – B = £3,300,000 – £2,700,000 = £600,000 Operating Surplus

ES/D2 = OS/D (£600,000) – the Contractor’s Projected Surplus (£230,000) = £370,000 Excess Surplus

To note; the Contractor’s Projected Surplus is the greater of Base Profit plus Base Head Office Costs (£200,000) and Contractor’s Profit and Head Office Costs (£230,000)

If at the end of Year 3 there has been a decrease in income:

Income (A) = £2,950,000 (all income including the Deficit Annual Payment)

Expenditure (B) = £2,700,000 (all expenditure excluding Contractor’s Profit of £97,500 (5% of operating income) and Head Office Costs of £97,500 (5% of operating income)

OS/D = A – B = £2,950,000 – £2,700,000 = £250,000 Operating Surplus

ES/D3 = OS (£250,000) – the Contractor’s Projected Surplus (£200,000) = £50,000 Excess Surplus

To note; the Contractor’s Projected Surplus is the greater of Base Profit plus Base Head Office Costs (£200,000) and Contractor’s Profit and Head Office Costs (£195,000)

The AES for this period is = (ES/D1 +ES/D2 + ES/D3) = (£270,000 + £370,000 + £50,000) = £230,000

3			3

shared between the Contractor and Authority on a [50:50] basis

Contractor – [£115,000]

Authority – [£115,000]

[Part B -] Worked Example (excluding any inflationary impacts)

The following worked example assumes a Surplus Annual Payment of £200,000 when taking into account total modelled income (£2,500,000) less total modelled expenditure (£2,300,000). Total modelled expenditure includes Base Profit costs of £125,000 (5% of total operating income) and Base Head Office Costs of £125,000 (5% of total operating income.

Income (A) = £2,500,000 (all income)

Expenditure (B) = £2,250,000 (all expenditure excluding Base Profit of £125,000 and Base Head Office Costs of £125,000 but including the Surplus Annual Payment)

In the base model, the Operating Surplus/Deficit is £250,000 surplus which is equal to the Contractor’s Projected Surplus (Base Profit plus Base Head Office Costs = £250,000) i.e. no Excess Surplus.

OS/D = A – B = £2,500,000 - £2,250,000 = £250,000 Operating Surplus

ES/D = £250,000 - £250,000 = £0

If at the end of Year 1 there has been an increase in income:

Income (A) = £2,800,000 (all income)

Expenditure (B) = £2,250,000 (all expenditure excluding Contractor’s Profit of £140,000 (5% of total operating income) and Head Office Costs of £140,000 (5% of total operating income) but including the Surplus Annual Payment

OS/D = A – B = £2,800,000 – £2,250,000 = £550,000 Operating Surplus

ES/D1 = OS/D (£550,000) – the Contractor’s Projected Surplus (£280,000) = £270,000 Excess Surplus

To note; the Contractor’s Projected Surplus is the greater of Base Profit plus Base Head Office Costs (£250,000) and Contractor’s Profit and Head Office Costs (£280,000)

If at the end of Year 2 there have been savings in expenditure:

Income (A) = £2,800,000 (all income)

Expenditure (B) = £2,150,000 (all expenditure excluding Contractor’s Profit of £140,000 (5% of total operating income) and Head Office Costs of £140,000 (5% of total operating income) but including the Surplus Annual Payment

OS/D = A – B = £2,800,000 – £2,150,000 = £650,000 Operating Surplus

ES/D2 = OS/D (£650,000) – the Contractor’s Projected Surplus (£280,000) = £370,000 Excess Surplus

To note; the Contractor’s Projected Surplus is the greater of Base Profit plus Base Head Office Costs (£250,000) and Contractor’s Profit and Head Office Costs (£280,000)

If at the end of Year 3 there has been a decrease in income:

Income (A) = £2,450,000 (all income)

Expenditure (B) = £2,150,000 (all expenditure excluding Contractor’s Profit of £122,500 (5% of operating income) and Head Office Costs of £122,500 (5% of operating income) but including the Surplus Annual Payment

OS/D = A – B = £2,450,000 – £2,150,000 = £300,000 Operating Surplus

ES/D3 = OS (£300,000) – the Contractor’s Projected Surplus (£250,000) = £50,000 Excess Surplus

To note; the Contractor’s Projected Surplus is the greater of Base Profit plus Base Head Office Costs (£250,000) and Contractor’s Profit and Head Office Costs (£245,000)

The AES for this period is = (ES/D1 +ES/D2 + ES/D3) = (£270,000 + £370,000 + £50,000) = £230,000

3			3

shared between the Contractor and Authority on a [50:50] basis

Contractor – [£115,000]

Authority – [£115,000]

SCHEDULE 20

EQUALITY REQUIREMENTS

The Contractor (including its agents and employees) shall not, and shall procure that any Contractor Related Party shall not:

discriminate directly or indirectly, or by way of victimisation or harassment, against any person on Protected Characteristics; and/or

contravene Sections 39, 108 to 109 and 111 to 112 of the Equality Act 2010 and Section 24A of the Equality Act 2006 (or any of them),

where appropriate.

The Contractor (including its agents and employees) shall, and shall procure that any Contractor Related Party shall, for purposes of ensuring compliance with paragraphs 1.1.1 to 1.1.2, in relation to staff engaged in the provision of Works, [Initial Services] or Services observe as far as possible the provisions of:

the Equality and Human Rights Commission Code of Practice on Employment;

the Equality and Human Rights Commission's Statutory Code of Practice on Equal Pay; and

any other relevant code of practice introduced by a commission or other body set up by Parliament to promote, monitor and enforce Equalities Legislation,

including, but not limited to, those provisions recommending the adoption, implementation and monitoring of an equal opportunities policy.

The Contractor shall, and shall procure that any Contractor Related Party shall, in performing its/their obligations under this Agreement, comply (to the extent permitted by law) with the provisions of sections 149 and 150 of the Equality Act 2010 as if they were a body within the meaning of Schedule 19 to the Equality Act 2010.

[Where in connection with this Agreement the Contractor (including its agents and employees) or any Contractor Related Party are required to carry out work on the Authority's premises or alongside the Authority's employees on any other premises, they shall comply with the Authority's own employment policy and codes of practice relating to discrimination and equal opportunities.]

The Contractor shall, and shall procure that any Contractor Related Party shall, notify the Authority's Representative forthwith in writing as soon as it becomes aware of any investigation of or proceedings brought against the Contractor or any Contractor Related Party under the Equalities Legislation.

Where any investigation is undertaken by a person or body empowered to conduct such investigation and/or proceedings are instituted in connection with any matter relating to the Contractor's performance of its obligations under this Agreement being in contravention of the Equalities Legislation, the Contractor shall, and shall procure that any Contractor Related Party shall, free of charge:

provide any information requested in the timescale allotted;

attend any meetings as required and permit any of its staff to attend;

promptly allow access to and investigation of any documents or data deemed to be relevant;

allow itself and any of its staff to appear as witness in any ensuing proceedings; and

co-operate fully and promptly in every way required by the person or body conducting such investigation during the course of that investigation.

SCHEDULE 21

CONFIDENTIAL INFORMATION

Part 1 – Commercially Sensitive Contractual Provisions

| Column 1 - Commercially Sensitive Contractual Provisions | Column 2 - For period ending on date below: |
| --- | --- |

Part 2 – Commercially Sensitive Material

| Column 1 - Commercially Sensitive Material | Column 2 - For period ending on date below: |
| --- | --- |

SCHEDULE 22

BULK TRANSFER TERMS

- Interpretation And Definitions

In this Schedule, unless the context otherwise requires, the following terms shall have the meanings given to them below:

Actuary's Letter

means the letter from the Administering Authority's Actuary, a copy of which has been attached to this Schedule 22 (Bulk Transfer Terms);

Administering Authority's Actuary

means [name of actuary] of [name of firm], or another actuary appointed by the Administering Authority for the purposes of this Schedule 22 (Bulk Transfer Terms);

AVCs

means AVCs or SCAVCs as defined in the LGPS Regulations;

Contractor's Actuary

means [name of actuary] of [name of firm], or another actuary appointed by the Contractor and/or relevant Sub-Contractor for the purposes of this Schedule 22 (Bulk Transfer Terms);

Contractor's Scheme

means the pension scheme or schemes nominated by the Contractor and/or relevant Sub-Contractor in accordance with clause 30.7 (Contractor Scheme) of this Agreement;

Due Date

means the date [  ] days after the last of the conditions in paragraph 3.6 of this Schedule 22 (Bulk Transfer Terms) has been satisfied;

Fund

means the [                           ] Fund within the LGPS;

Transfer Amount

means the amount or amounts referred to in paragraph 3.1 of this Schedule 22 (Bulk Transfer Terms);

Transferring Member

means an Eligible Employee who agrees to a transfer of benefits being made for him or her from the Fund to the Contractor's Scheme under paragraph 2 of this Schedule 22 (Bulk Transfer Terms).

The Contractor's Scheme

The Contractor shall (and shall procure that each relevant Sub-Contractor shall) invite each Eligible Employee who joins the Contractor's Scheme in accordance with clause 30.7 (Contractor's Scheme) of this Agreement to consent to a transfer of benefits being made for him from the Fund to the Contractor's Scheme. The Contractor and/or relevant Sub-Contractor must issue this invitation no later than [one] month after the Relevant Transfer Date. The invitation must be in a form acceptable to the Authority and the Administering Authority (such acceptance not to be unreasonably withheld or delayed by the Authority) and which complies with any requirements of the LGPS Regulations. Any Eligible Employee wishing to consent to a transfer of benefits must notify the Contractor and/or relevant Sub-Contractor of this consent in writing no later than [three] months after the date of the invitation. The Contractor shall (and shall procure that each relevant Sub-Contractor shall) provide the Authority and the Administering Authority with the names of the Transferring Members no later than [four] months after the Relevant Transfer Date.

Transfer payment from the Fund

The Authority shall use reasonable endeavours to ensure that the Administering Authority transfers from the Fund to the Contractor's Scheme on the Due Date an amount in respect of the relevant Transferring Members' service in the Fund before the Relevant Transfer Date calculated in accordance with the Actuary's Letter and the LGPS Regulations.

As soon as reasonably practicable following the Relevant Transfer Date, the Contractor shall (and shall procure that each relevant Sub-Contractor shall) promptly provide all data within its possession or under its control which the Administering Authority and the Administering Authority's Actuary may require for the calculation of the Transfer Amount and shall warrant that this data is in all material respects true, complete and accurate.

As soon as reasonably practicable following the Relevant Transfer Date, the Authority shall promptly provide all data within its possession or under its control which the Administering Authority and the Administering Authority's Actuary may require for the calculation of the Transfer Amount and shall warrant that this data is in all material respects true, complete and accurate.

The Authority shall use its reasonable endeavours to procure that:

as soon as reasonably practicable after the Administering Authority's Actuary has been provided with the necessary data and information, the Administering Authority's Actuary shall calculate the Transfer Amount in accordance with the Actuary's Letter and the LGPS Regulations; and

within [one week] of completing this calculation, the Administering Authority's Actuary shall notify the Contractor's Actuary in writing of the particulars of the calculation and the data on which the calculation is based.

The Contractor's Actuary will then have [one month] (or such longer period as the parties may agree) from the date on which those particulars and data have been supplied to him in which to object in writing that the calculation is incorrect or not in accordance with the Actuary's Letter. The calculation shall be final and binding on the parties if the Contractor's Actuary raises no objection within this stated period.

If the Contractor's Actuary objects in writing under paragraph 3.4 of this Schedule 22 (Bulk Transfer Terms) and the Administering Authority's Actuary and the Contractor's Actuary cannot subsequently agree the Transfer Amount within [one] month (or such longer period as shall be agreed between the parties) of the objection, then the amount shall be determined by an independent actuary to be nominated by the Administering Authority and the Contractor and/or relevant Sub-Contractor jointly or, if they cannot agree, by the President of the Institute of Actuaries on application by either party. The independent actuary shall act as an expert and not as an arbitrator, and his decision shall be final and binding on the parties. The independent actuary's costs shall be payable equally by the Administering Authority and the Contractor and/or relevant Sub-Contractor.

Payment to the Contractor's Scheme of the Transfer Amount shall only be made on the following conditions:

the Transfer Amount has been agreed or determined under paragraph 3.4 or 3.5 of this Schedule 22 (Bulk Transfer Terms) and in accordance with the LGPS Regulations;

the Contractor and/or relevant Sub-Contractor has complied with all its obligations under this Schedule 22 (Bulk Transfer Terms); and

the trustees of the Contractor's Scheme have confirmed in writing that:

a payment should be made in accordance with the LGPS Regulations and that they shall accept payment on the terms set out in paragraph 4 of this Schedule 22 (Bulk Transfer Terms);

they shall accept liability for each Transferring Member's accrued contracted out rights under the Fund; and

they shall accept the Transfer Amount in full and final settlement of all claims against the Fund in respect of each Transferring Member.

[The payment of the Transfer Amount shall be satisfied by the transfer of readily marketable stocks and shares of the Fund as agreed by the Administering Authority and the trustees of the Contractor's Scheme having a mid-market value on the day before the Due Date equal to the Transfer Amount. If the Administering Authority and the trustees of the Contractor's Scheme are not able to agree some or all of the particular assets to be transferred, or the mid-market value of any such assets, the payment of the Transfer Amount (or the appropriate part of it) shall be satisfied by the Fund transferring cash equal to [  ]% of that part of the Transfer Amount in respect of which there has been no agreement as to the assets to be transferred.]

Past Service Benefits

The Contractor shall (and shall procure that each relevant Sub-Contractor shall) ensure that the Contractor's Scheme provides in respect of each Transferring Member such benefits as the Administering Authority's Actuary certifies to be of actuarial equivalence [(in accordance with the Actuary's Letter)] to the benefits which would have been payable under the LGPS in respect of the Transferring Member's service before the Relevant Transfer Date if he had remained a member of the LGPS.

Additional Voluntary Contributions

Nothing in this Schedule 22 (Bulk Transfer Terms) shall apply to AVCs or to benefits secured by them. However, the Authority must ensure that the assets representing each Transferring Member's AVCs in the Fund (if any) shall be transferred to the Contractor's Scheme. The Contractor shall (and shall procure that each relevant Sub-Contractor shall) ensure that the Contractor's Scheme provides benefits for each relevant Transferring Member which are equivalent to the assets transferred.

No Assistance

The Contractor shall not (and shall procure that each relevant Sub-Contractor shall not) encourage or initiate or assist or facilitate any action or provide any financial assistance for the purpose of requiring the Fund to pay an amount larger than the Transfer Amount to the Contractor's Scheme in respect of the Transferring Members.

[Exit Provisions

The Contractor undertakes to the Authority (for the benefit of the Authority itself and for the Authority as agent and trustee for the benefit of the [Eligible Employees] that on:

the expiry or termination of this Agreement; or

the expiry or termination of any Sub-Contract in the case of a relevant Sub-Contractor; or

the employment of any [Eligible Employee] transferring to a New Employer in accordance with clause 30.13 (Transfer to another Employer) of this Agreement (or otherwise),

the Contractor shall (and shall procure that each relevant Sub-Contractor shall) procure that the trustees of the Contractor's Scheme offer bulk transfer terms in respect of the relevant [Eligible Employees'] service in the Contractor's Scheme to the pension scheme of the Authority, any Future Contractor (or their sub-contractors), any new Sub-Contractor or any new employer (as applicable) which are no less favourable (in the opinion of the Administering Authority's Actuary or an actuary appointed by the Authority) than the bulk transfer terms set out in the Actuary's Letter.

If the transfer payment paid by the trustees of the Contractor's Scheme is less (in the opinion of the Administering Authority's Actuary or an actuary appointed by the Authority) than the transfer payment which would have been paid had paragraph 7.1 of this Schedule 22 (Bulk Transfer Terms) been complied with, the Contractor shall (and/or shall procure that each relevant Sub-Contractor shall) pay to the Authority, any Future Contractor (or their sub-contractor), any new Sub-Contractor or any new employer (as appropriate) (or as such person shall direct) the amount of the difference.]

Authority's Costs

Any costs of the Authority necessarily and reasonably incurred in connection with this Schedule 22 (Bulk Transfer Terms) shall be borne by the Contractor.

SCHEDULE 23

[Note: In order to assist parties for the duration of the Agreement, two alternatives of the Loss of Revenue Schedule are included in this draft contract:

- Option A – Reflects the form of the Loss of Revenue schedule included in the previous iteration of the Sport England template documents; and

- Option B - a simplified version of the Loss of Revenue schedule. Drawing on the principles contained in Part A, the simplified schedule contained in Part B does not differentiate between high, medium and low seasons – and instead applies an averaged figure across the year.

Local Authorities should decide whether to include Part A or Part B of this schedule]

[Option A

LOSS OF REVENUE,

- Subject to the provisions of this Schedule 23 (Loss of Revenue), any Loss of Revenue shall be calculated in respect of each relevant activity by determining the anticipated daily Revenue for the relevant activity in question for the period in question (the Anticipated Daily Revenue) and deducting from that sum the actual daily revenue received for the relevant activity in question for the period in question.

The Authority shall be entitled to audit, at frequent intervals, actual Revenue received by the Leisure Operator at the [Facility/ Facilities].

The Anticipated Daily Revenue for each activity shall vary between seasons (as set out in paragraphs 4 and 5 of this Schedule 23 (Loss of Revenue)), and are set out:

[in respect of the Initial Phase in the table at paragraph 11 of this Schedule 23 (Loss of Revenue); and]

in respect of the Service Period (or any delay in the commencement of the Services Period), in the table at paragraph 12 of this Schedule 23 (Loss of Revenue).

In respect of [Swimming/Gym and Memberships]:

The High Season rate shall apply in [May, June, July and August];

The Mid Season rate shall apply in [February, March, April, September and October]; and

The Low Season rate shall apply in [January, November and December].

In respect of all activities except for [Swimming/Gym and Memberships]:

The High Season rate shall apply in [January, February, March, April, May, June, September and October];

The Mid Season rate shall apply in [July, August and November]; and

The Low Season rate shall apply in [December].

The Anticipated Daily Revenue rates set out in the table[s] in paragraph[s 11 and] 12 of this Schedule 23 (Loss of Revenue) are daily and shall be Indexed. The Anticipated Daily Revenue rates will be adjusted by agreement between the parties [at each Income Benchmarking Date (as defined in Schedule 18 (Benchmarking)) to reflect the Anticipated Daily Revenue at such date].

The Contractor shall and shall procure that the Leisure Operator shall at all times use all endeavours to minimise and mitigate any Loss of Revenue and the consequences of any Relevant Event or Loss of Revenue Event which shall include addressing variable costs and making appropriate cost adjustments. For the avoidance of doubt mitigation shall not include a reduction in Loss of Revenue based on an assessment of whether the prescribed rate for each area would have actually been achieved during the closure period in question.

In calculating any Loss of Revenue, the Contractor shall not be entitled to recover, as Loss of Revenue, any greater amount than the level of Revenue which it is projected to recover as set out in the table[s] at paragraph[s] [11 and] 12 of this Schedule 23 (Loss of Revenue).

[For the avoidance of doubt, the loss of membership revenue shall be equivalent to the price reduction given to the User in lieu of the relevant closures, to be agreed between the Contractor and the Authority in line with sensible commercial practice, plus the loss of membership revenue caused by membership cancellations during the closure period that are not replaced by membership revenue from new sales.]

[In the circumstances where the Loss of Revenue is triggered by a Relevant Event or Loss of Revenue Event and a period of six (6) months has elapsed from the occurrence of such Relevant Event or Loss of Revenue Event, the amounts set out in the table[s] at paragraph[s 11 and] 12 of this Schedule 23 (Loss of Revenue) shall be reduced by [X%] to remove the Contractor's profit from the calculation of the Loss of Revenue.]

[Initial Phase]

[XYZ] FACILITY

| Revenue Area/Service | Daily Rates (£) |
| --- | --- |
|  | Low Season | Mid Season | High Season |
| Swimming – Admissions |  |  |  |
| Swimming – Clubs Hire |  |  |  |
| Swimming – Schools Hire |  |  |  |
| Swimming – Lessons |  |  |  |
| Fitness Suite – Casual |  |  |  |
| Fitness Suite – Memberships | [See para 9] | [See para 9] | [See para 9] |
| Fitness Suite – Joining Fees |  |  |  |
| Dance Studios – Casual |  |  |  |
| Dance Studios – Membership | [See para 9] | [See para 9] | [See para 9] |
| Sale of Goods |  |  |  |
| Sport Card Income |  |  |  |
| Room Hire/Functions |  |  |  |
| Sports Hall – Casuals, Contracts & Schools |  |  |  |
| Sports Hall – Sessions |  |  |  |
| Sports Hall – Clubs |  |  |  |
| Crèche |  |  |  |
| The Zone |  |  |  |
| Squash (per court) |  |  |  |
| Health Suite |  |  |  |
| Total Income excl catering etc |  |  |  |
| Catering |  |  |  |
| Bar |  |  |  |
| Vending |  |  |  |
| Total Income catering etc |  |  |  |
| Grand Total |  |  |  |

Services Period

[XYZ] FACILITY

| Revenue Area/Service | Daily Rates (£) |
| --- | --- |
|  | Low Season | Mid Season | High Season |
| Swimming – Admissions |  |  |  |
| Swimming – Clubs Hire |  |  |  |
| Swimming – Schools Hire |  |  |  |
| Swimming – Lessons |  |  |  |
| Fitness Suite – Casual |  |  |  |
| Fitness Suite – Memberships | [See para 9] | [See para 9] | [See para 9] |
| Fitness Suite – Joining Fees |  |  |  |
| Dance Studios – Casual |  |  |  |
| Dance Studios – Membership | [See para 9] | [See para 9] | [See para 9] |
| Sale of Goods |  |  |  |
| Sport Card Income |  |  |  |
| Room Hire/Functions |  |  |  |
| Sports Hall – Casuals, Contracts & Schools |  |  |  |
| Sports Hall – Sessions |  |  |  |
| Sports Hall – Clubs |  |  |  |
| Crèche |  |  |  |
| The Zone |  |  |  |
| Squash (per court) |  |  |  |
| Health Suite |  |  |  |
| Total Income excl catering etc |  |  |  |
| Catering |  |  |  |
| Bar |  |  |  |
| Vending |  |  |  |
| Total Income catering etc |  |  |  |
| Grand Total |  |  |  |

Compensation

The financial consequences of any Relevant Event or Loss of Revenue Event shall be calculated pursuant to clause 69 (Financial Adjustments).

Notes

- The daily rate represents the maximum amount that will be charged for the full day in the (relevant high, medium or low season/relevant month), subject to mitigation in line with paragraph 7 of this Schedule 23 (Loss of Revenue). The hourly rate will not always be a simple calculation of daily rate divided by hours in the day but should reflect the time of day when the loss of revenue occurs. For example loss of revenue in the dance studio will be greater in the evening than in the morning. The booking programme or historical usage patterns may be used to calculate the hourly rate for different times of day and the Authority will have the certainty that the loss per day will not exceed the daily rate (listed in the schedule/as calculated by reference to Appendix A and divided by the relevant number of calendar days).

The loss of revenue associated with Bar, Catering and Vending Sales (above/as listed in Appendix A) will be apportioned in direct relation to the revenue loss attributable to the affected Revenue area, over the total revenue excluding Bar, Catering and Vending Sales.]

[OR Option B

- Subject to the provisions of this Schedule 23 (Loss of Revenue), any Loss of Revenue shall be calculated in respect of each relevant activity by determining the anticipated daily Revenue for the relevant activity in question for the period in question (the "Anticipated Daily Revenue") and deducting from that sum the actual daily revenue received for the relevant activity in question for the period in question.

The Authority shall be entitled to audit, at frequent intervals, actual Revenue received by the [Contractor/Leisure Operator] at the Facilities.

The Anticipated Daily Revenue for each activity in respect of the Service Period can be calculated by reference to the [Base Case/LOBTA] and will be indexed in accordance with Schedule 6.

The Contractor shall at all times use all endeavours to minimise and mitigate any loss of Revenue and the consequences of any Relevant Event or Loss of Revenue Event which shall include addressing variable costs and making appropriate cost adjustments. For the avoidance of doubt mitigation shall not include a reduction in Loss of Revenue based on an assessment of whether the prescribed rate for each area would have actually been achieved during the closure period in question.

In calculating any Loss of Revenue, the Contractor /[Leisure Operator] shall not be entitled to recover, as Loss of Revenue, any greater amount than the level of Revenue which it is projected to recover calculated by reference to the [Base Case/LOBTA].

The loss of membership revenue shall be equivalent to the price reduction given to the User in lieu of the relevant closures, to be agreed between the Contractor and the Authority in line with sensible commercial practice, plus the loss of membership revenue caused by membership cancellations during the closure period that are not replaced by membership revenue from new sales.

[In the circumstances where the Loss of Revenue is triggered by a Relevant Event and a period of six (6) months has elapsed from the occurrence of such Relevant Event, the amount of daily rate recoverable by the Contractor shall be reduced by [x]% to remove the Contractor's profit from the calculation of the Loss of Revenue.]

Compensation may be paid as follows:

Loss of Revenue Event

The Authority shall (at its discretion) compensate the Contractor in respect of any Loss of Revenue arising from a Loss of Revenue Event by:

lump sum payment

instalments; or

pursuant to Clause 69 (Financial Adjustments).

Relevant Event

The Authority shall compensate the Contractor in respect of any Loss of Revenue arising from a Relevant Event pursuant to Clause 69 (Financial Adjustments).]

SCHEDULE 24

CHANGE PROTOCOL

Part 1 – Definitions

Affordable

means within the revenue resource parameters determined by the Authority and notified in writing by it to the Contractor as available for a proposed High Value Change;

Approval Criteria

has the meaning given to it in paragraph 4.4 of Part 4 of this Schedule 24;

Approved Project

has the meaning given to it in paragraph 4.5.2.1 of Part 4 of this Schedule 24;

Authority Change

means, as the case may be, a Small Value Change, Medium Value Change or High Value Change;

Authority Notice of Change

means, as the case may be, a Small Value Change Notice, a Medium Value Change Notice or a High Value Change Notice;

Calculation Date

means the relevant date for the purposes of calculating the Incurred Change Management Fee in accordance with Part 4 of this Schedule 24;

Capital Cost

means in relation to any High Value Change the cost of carrying out the design, construction and commissioning of that High Value Change;

Catalogue of Small Works and Services and Catalogue

means the schedule setting out the prices and time periods for Small Value Changes and the Small Works Rates as is set out in Appendix 1 Part 1 to this Schedule 24, as shall be amended from time to time in accordance with paragraph 6 of Part 2 of this Schedule 24;

Catalogue Price

means the total cost (excluding VAT) of carrying out a Small Value Change as set out in the Catalogue;

Change

means a change in the Works, the Facilities and/or Services or additional Works and/or Services or a change in the Authority's Policies [or the removal of a Facility pursuant to clause 18.3B.5 (Judicial Review Proceedings)] [or a partial termination pursuant to Part 6 of this Schedule 24] that may be made under clause 57 (Authority and Contractor Changes) or this Schedule 24;

Change Management Fee

means the fee calculated in accordance with paragraph 9 of Part 4 of this Schedule 24;

Contractor Change

means a Change that is initiated by the Contractor by submitting a Contractor Notice of Change to the Authority;

Contractor Notice of Change

has the meaning given to it in paragraph 1 of Part 5 of this Schedule 24;

Estimate

has the meaning given to it in paragraph 2.5.1 of Part 3 of this Schedule 24;

High Value Change

means a Change requested by the Authority that, in the reasonable opinion of the Authority, is likely either to cost in excess of £[100,000] (Indexed) or to require an adjustment to the Annual Payment that is [2]% or more of the Annual Payment in the relevant Contract Year provided that the parties may agree that such a Change should instead be processed as a Medium Value Change;

High Value Change Notice

has the meaning given to it in paragraph 1 of Part 4 of this Schedule 24;

High Value Change Proposal

has the meaning given to it in paragraph 2.1.1 of Part 4 of this Schedule 24;

High Value Change Requirements

has the meaning given to it in paragraph 2.1.2 of Part 4 of this Schedule 24;

High Value Change Stage 2 Submission

has the meaning given to it in paragraph 4.1.1 of Part 4 of this Schedule 24;

Incurred Change Management Fee

means the amounts actually incurred or payable by or on behalf of the Contractor up to the Calculation Date in respect of matters identified by the Contractor pursuant to paragraphs 3.2.3 and/or 4.3.7 of Part 4 of this Schedule as falling within the Change Management Fee (and not already reimbursed by the Authority);

Medium Value Change

means a Change requested by the Authority which is not a Small Value Change or a High Value Change provided that the parties may agree that such a Change should instead be processed as either a Small Value Change or as a High Value Change;

Medium Value Change Notice

has the meaning given to it in paragraph 1 of Part 3 of this Schedule 24;

Resubmission Longstop Date

has the meaning given to it in paragraph 4.5.3.1 of Part 4 of this Schedule 24;

Small Value Change

means a Change which is either:

(a)	listed in the Catalogue of Small Works and Services; or

(b)	not so listed, but has an individual cost not exceeding [five thousand pounds (£5,000)] (Indexed), or as otherwise agreed from time to time, except for any request that would (if implemented) increase the likelihood of the Contractor failing to meet the Authority's Requirements or materially and adversely affect the Contractor's ability to perform its obligations under this Agreement,

provided that the parties may agree that such a Change should instead be processed as either a Medium Value Change;

Small Value Change Notice

means a request for a Small Value Change in the form set out in Appendix 1 Part 2 to this Schedule;

Small Works Rates

means the rates to be applied in respect of any request from the Authority for a Small Value Change set out in limb (b) of that definition;

Stage 1 Approval

has the meaning given to it in paragraph 3.5 of Part 4 of this Schedule 24

Stage 1 Approved Project

has the meaning given to it in paragraph 3.5 of Part 4 of this Schedule 24;

Stage 2 Approval

has the meaning given to it in paragraph 4.5.2.1 of Part 4 of this Schedule 24;

Stage 2 Approved Project

has the meaning given to it in paragraph 4.5.2.1 of Part 4 of this Schedule 24;

Target Cost

has the meaning given to it in paragraph 2.1.1 of Part 4 of this Schedule 24; and

Whole Life Cost

means in relation to any High Value Change, the estimated and (to the extent that such information is available) the actual cost of operating and maintaining that High Value Change over its intended design life (consistent with the Contractor's Proposals).

Part 2 – Small Value Changes

- Small Value Change Notice

Where a Small Value Change is required by the Authority during the Services Period, it shall submit to the Contractor a Small Value Change Notice. Prior to the Services Period any Small Value Changes shall be addressed as part of the Works and accommodated through the Review Procedure.

Contractor Response and Authority Confirmation

Within five (5) Business Days of receipt of the Small Value Change Notice, the Contractor shall confirm in writing and in accordance with this Part 2 of this Schedule 24:

the cost of implementing the required Small Value Change;

the time period for implementing the Small Value Change; and

when it is proposed the Small Value Change is to be carried out.

Where the Small Value Change is listed in the Catalogue, the cost of carrying out that Small Value Change shall not exceed the Catalogue Price and the time period for implementing the Small Value Change shall not exceed the time specified in the Catalogue.

Where the Small Value Change is not listed in the Catalogue, the cost of implementing the required Small Value Change shall be calculated by reference to paragraph 3 of this Part 2.

Other than the costs referred to in paragraphs 2.2 and 2.3 of this Part 2 of this Schedule 24 the Contractor shall make no charge to the Authority for processing, implementing or managing a Small Value Change.

The Authority may object in writing within five (5) Business Days of receipt of the Contractor's confirmation pursuant to paragraph 2.1 of this Part 2 of this Schedule 24 to any part of that confirmation and in such circumstances the parties shall act reasonably to agree as soon as practicable how the Small Value Change is to be implemented. In the absence of any such notification, the Contractor shall proceed with the Small Value Change in question in accordance with the terms of its confirmation.

Small Value Changes not contained in the Catalogue

For the purposes of paragraph 2.3 of this Part 2 of this Schedule 24, the cost of implementing any Small Value Change which is not set out in the Catalogue shall be calculated on the basis that:

wherever practicable the Contractor shall procure that such works are carried out by an existing on-site and suitably qualified Contractor or Contractor Related Party employee and no labour element shall be charged to the Authority in respect of such works. Where such Small Value Change is not carried out by an existing on-site and suitably qualified Contractor or Contractor Related Party employee, the cost of the labour element shall be calculated in accordance with the Small Works Rates or, where such rates are not applicable, in accordance with rates which are fair and reasonable; and

the materials element shall be charged at the cost of materials to the Contractor or to the contractor carrying out the work (net of all discounts) and there shall be no management fee, margin, overhead, contingency or other cost applied in relation thereto.

Implementation

The Contractor shall implement the required Small Value Change so as to minimise any inconvenience to the Authority and within the timescales specified in the confirmation provided pursuant to paragraph 2.1 of this Part 2 of this Schedule 24 (or agreed by the parties pursuant to paragraph 2.5 of this Part 2 of this Schedule 24).

The Contractor shall notify the Authority when it believes the Small Value Change has been completed.

Where the Contractor has either:

failed to provide a response pursuant to paragraph 2.1 of this Part 2 of this Schedule 24 within fifteen (15) Business Days of the date of the Small Value Change Notice; or

has provided a response pursuant to paragraph 2.1 of this Part 2 of this Schedule 24 but has failed to fully implement the Small Value Change within ten (10) Business Days of the date that has been determined or agreed in accordance with paragraph 4.1 of this Part 2 of this Schedule 24 as being the date on which the Small Value Change should have been implemented,

then the Authority may notify the Contractor that the Small Value Change Notice is withdrawn and, following such notification, may procure the implementation of the Small Value Change without further recourse to the Contractor.

Payment

Where the Small Value Change has been implemented to the satisfaction of the Authority acting reasonably:

prior to the Service Period, the Authority shall make a payment to the Contractor within twenty (20) Business Days of an invoice presented to the Authority in respect of the costs of the Small Value Change following completion or implementation of the relevant Small Value Change; and

during the Service Period, the Contractor shall include the costs of the Small Value Change in the next report submitted pursuant to clause 37.2 (Report and Invoice) of this Agreement following completion or implementation of the relevant Small Value Change.

All amounts payable for Small Value Changes shall be invoiced and paid in accordance with the procedure described in clause 37 (Payment during the Services Period) of this Agreement.

Update of Catalogue

From the Commencement Date the Catalogue shall be that set out in Part 1 of Appendix 1 to this Schedule 24 and, subject to paragraph 6.2 of this Part 2 of this Schedule 24, the rates set out therein (including the Small Works Rates referred to in paragraph 6.2.4 of this Part 2 of this Schedule 24) shall be Indexed on each anniversary of the Commencement Date.

On the date which is twenty (20) Business Days before each third anniversary of the Commencement Date, the Contractor shall provide the Authority with a revised and updated Catalogue which:

includes in the Catalogue unit prices for any Small Value Change or any Medium Value Change which has occurred and which is not already included in the Catalogue or any other Change which does not affect the risk profile of the Project which the parties anticipate could occur during the life of the Project;

includes time periods for the carrying out of any works or implementation of any Change for the matters referred to in paragraph 6.2.1 of this Part 2 of this Schedule 24;

reviews the unit pricing for the works and services in the Catalogue to ensure that unit rates continue to provide value for money with reference to prices prevailing for similar items in the market at the time; and

updates the schedule of Small Works Rates to ensure that unit rates continue to provide value for money with reference to rates prevailing for similar services in the market at the time.

Within ten (10) Business Days of the submission by the Contractor of the updated Catalogue pursuant to paragraph 6.2 of this Part 2 of this Schedule 24, the Authority shall confirm in writing whether or not it agrees that the updated Catalogue shall constitute the Catalogue for the purposes of this Agreement.

If the Authority does not agree with the Contractor's proposed amendments to the Catalogue pursuant to paragraph 6.2 of this Part 2 of this Schedule 24, the parties shall meet and endeavour, in good faith, to agree any amendments to the Catalogue. Any dispute shall be referred to the Dispute Resolution Procedure. Twenty (20) Business Days following the submission by the Contractor pursuant to paragraph 6.2 of this Part 2 of this Schedule 24 or, if applicable, ten (10) Business Days following resolution of any dispute in respect of that submission, the Contractor shall issue to the Authority an updated Catalogue which shall set out the agreed or determined amendments and shall constitute the Catalogue for the purposes of this Agreement.

Following the completion of a Small Value Change that is not listed in the Catalogue, the Parties, acting reasonably, shall discuss whether it is appropriate for the Catalogue to be updated to include such Small Value Change and on what terms.

Documentation and Monitoring

No due diligence (whether legal, technical, insurance or financial) shall be required in relation to Small Value Changes unless otherwise agreed between the parties.

No changes shall be made to this Agreement or any Project Document as a result of a Small Value Change, unless otherwise agreed between the parties.

Where it is agreed that an adjustment of the Annual Payment is required, the Base Case shall be adjusted to give effect to such Small Value Changes once each Contract Year on a date to be agreed between the parties and all relevant Small Value Changes that have occurred in the preceding Contract Year shall be aggregated together into a single cumulative adjustment in accordance with clause 69 of this Agreement (Financial Adjustments).

The Contractor shall keep a record of all Small Value Changes processed, completed and outstanding and shall provide the Authority with a copy of that record whenever reasonably required by the Authority.

Disputes

Any dispute may be referred by either party to the Dispute Resolution Procedure, but the Contractor shall, nevertheless, be required to carry out or implement the Small Value Change within the prescribed timescales notwithstanding the dispute, where such dispute concerns the cost of the Small Value Change.

Part 3 – Medium Value Changes

- Medium Value Changes

The Authority has the right to propose Medium Value Changes in accordance with this Part 3 of this Schedule 24. If the Authority requires a Medium Value Change, it must serve a notice (a Medium Value Change Notice) on the Contractor in accordance with paragraph 2 of this Part 3 of this Schedule 24. The Contractor shall be entitled to refuse a Medium Value Change that:

requires the Works and/or the Services to be performed in a way that infringes any Legislation or is inconsistent with Good Industry Practice;

would cause any Necessary Consent to be revoked (or would require a new consent to be obtained to implement the relevant change in the Works and/or the Services which, after using reasonable efforts, the Contractor has been unable to obtain);

would materially and adversely affect the Contractor's ability to deliver the Works and /or Services (except those Works and/or Services which have been specified as requiring to be amended in the Medium Value Change Notice) in a manner not compensated for pursuant to this Part 3 of this Schedule 24;

would materially and adversely affect the health and safety of any person;

would, if implemented, materially and adversely change the nature of the Project (including its risk profile);

the Authority does not have the legal power or capacity to require implementation of; or

is the subject of a Medium Value Change Notice that cannot reasonably be complied with.

Medium Value Change Notice

The Medium Value Change Notice shall:

set out the change in the Works or Services required in sufficient detail to enable the Contractor to calculate and provide the estimated Change in Costs and estimated Change in Revenue in accordance with paragraph 3 of this Part 3 of this Schedule 24;

set out whether, in respect of any additional works, the Contractor is expected to provide soft services, facilities management services and lifecycle maintenance services in respect of such additional works;

set out the timing of the additional works or services required by the Authority;

set out details of the Authority's budgetary constraints and/or affordability thresholds; and

require the Contractor to provide to the Authority within fifteen (15) Business Days of receipt of the Medium Value Change Notice:

an estimate of the likely effects of the proposed variation (the Estimate);

confirmation as to when the Estimate is to be provided to the Authority (provided that the Contractor shall use all reasonable endeavours to obtain such information as is required expeditiously) provided that if the Authority does not believe the proposal from the Contractor is reasonable, the parties shall seek to agree the time period, failing which any dispute as to what is an appropriate period for submission of the Estimate may be referred to the Dispute Resolution Procedure; or

notification in writing if the Contractor believes that any of the circumstances outlined in paragraph 1 of this Part 3 of this Schedule 24 apply.

Contractor's Estimate

Other than where a notice is served under paragraph 2.5.3 of this Part 3 of this Schedule 24 the Contractor shall as soon as practicable and in any event within the time period agreed or determined pursuant to paragraph 2.5 of this Part 3 of this Schedule 24, the Contractor shall deliver to the Authority the Estimate. The Estimate shall include the opinion of the Contractor on:

a detailed timetable for implementation of the Medium Value Change;

whether relief from compliance with obligations is required, including the obligations of the Contractor to achieve the Start on Site Date, each Planned Services Availability Date, to complete the Post Completion Works before the relevant Planned Post Completion Works Acceptance Date and to meet the requirements set out in the Authority's Requirements during the implementation of the Medium Value Change;

an outline of the proposed design solution and design, including an appropriate analysis/risk appraisal and, to the extent relevant, the impact on whole life costings;

any impact on the provision of the Works and/or the Services including whether the proposed change is in contravention of paragraph 1 of this Part 3 of this Schedule 24;

any amendment required to this Agreement and/or any Project Document or Ancillary Document as a result of the Medium Value Change;

any estimated Change in Costs and estimated Change in Revenue that results from the Medium Value Change;

any Capital Expenditure that is required or no longer required as a result of the Medium Value Change;

any Necessary Consents that are required;

its suggested payment schedule for the Change based on milestones where relevant;

costs and details of (i) any other approvals required and/or due diligence permitted pursuant to paragraph 12 of this Part 3 of this Schedule 24 and (ii) any third party costs (that is, external costs of the Contractor and its sub-contractors, including but without limitation the costs of consultants and advisers);

the method of implementation and the proposed method of certification of any construction or operational aspects of the Works or the Services required by the proposed Medium Value Change if not covered by the procedures specified in clause 20 (Notification of Services Availability); and

any other information requested by the Authority in the Medium Value Change Notice.

Costing of the Estimate

In computing the estimated Change in Costs and/or the Capital Expenditure and/or the estimated Change in Revenue, the Contractor shall apply the following principles wherever applicable:

the unit cost of any construction or installation works or associated preliminaries (excluding any temporary or demolition works, professional fees, contingencies, overheads and profit margins) required to implement the Medium Value Change shall be the equivalent unit rates set out in Part 1 of Appendix 2 of this Schedule 24, uplifted using the [DTI Pubsec] index for construction cost inflation in the period between the Commencement Date and the date the Medium Value Change is to be commenced. If the Contractor can demonstrate to the satisfaction of the Authority, acting reasonably, that any such works are specified to a higher quality as compared to the Works, then the unit rates may be increased to reflect such increase in quality;

any lifecycle replacement and maintenance associated with additional works (or changes to the Works) shall be consistent with the lifecycle and maintenance profile of the Facilities envisaged in Schedule 2 (Contractor's Proposals) including (without limitation) in terms of the replacement cycles for equipment provided that the Contractor shall reflect improvements in technology that can optimise whole life costs for the Authority. The unit costs to be applied to the pricing of the lifecycle maintenance shall be the equivalent unit rates set out in Part 2 of Appendix 2 of this Schedule 24 (Indexed). If any such additional works are specified to a higher quality as compared to the Works, then the unit lifecycle replacement and maintenance costs shall be (in real terms) lower;

any professional fees, contingencies, overheads and/or profit margins charged by any consultant, sub-contractor or supplier in respect of construction and/or installation and/or lifecycle and/or service provision shall be the equivalent rates set out in Part 3 of Appendix 2 of this Schedule 24. If the Contractor can demonstrate to the satisfaction of the Authority, acting reasonably, that the professional fees, contingencies, overheads and profit margins being charged by consultants, sub-contractors and/or suppliers in current market conditions have changed significantly from those set out in Part 3 of Appendix 2 of this Schedule 24, then the Authority shall agree to amend the rates set out in Part 3 of Appendix 2 of this Schedule 24 to reflect current market rates;

the unit cost of any extension of, or change to, any Service (either in scope or area), taking into account the capacity of existing labour resources, shall be consistent with the equivalent unit rates set out in Part 4 of Appendix 2 to this Schedule 24 (Indexed). If the Contractor can demonstrate, to the satisfaction of the Authority, acting reasonably, that as a result of the Medium Value Change, the relevant Service will be of a higher quality than required by the relevant Service Specification then the Authority shall agree to increase such rates to reflect any increase in quality;

any Loss of Revenue shall be calculated by applying Schedule 23 (Loss of Revenue);

other than as referred to in paragraphs 4.1 to 4.4 of this Part 3 of this Schedule 24 no charge shall be made in respect of the Contractor's time, or that of any Contractor Related Party spent processing, managing or monitoring the Medium Value Change (or proposed Medium Value Change) (and no additional mark up or management fee shall be applied by the Contractor); and

where elements of the Medium Value Change are not addressed by paragraphs 4.1 to 4.6 of this Part 3 of this Schedule 24, they shall be costed on a fair and reasonable basis reflecting the then current market rates.

Standards of provision of the Estimate

In providing the Estimate the Contractor shall:

use reasonable endeavours to oblige its Sub-Contractors to minimise any increase in costs and maximise any reduction in costs;

demonstrate how any Capital Expenditure to be incurred or avoided is being measured in a cost effective manner, including showing that when such expenditure is incurred, reasonably foreseeable Changes in Law at that time have been taken into account by the Contractor; and

demonstrate that any expenditure that has been avoided, which was anticipated to be incurred to replace or maintain assets that have been affected by the Medium Value Change concerned, has been taken into account in the amount which in its opinion has resulted or is required under paragraphs 3.6 (Contractor's Estimate) and/or 3.7 (Contractor's Estimate) of this Part 3 of this Schedule 24; and

provide written evidence of the Contractor's compliance with paragraphs 4 and 5.1 of this Part 3 of this Schedule 24.

Determination of the Estimate

As soon as practicable after the Authority receives the Estimate, the parties shall discuss and agree the issues set out in the Estimate. If the parties cannot agree on the contents of the Estimate, the matter may be referred to the Dispute Resolution Procedure to determine if the Estimate represents a fair and reasonable approach to implementing the Medium Value Change in all respects.

Confirmation or Withdrawal of the Medium Value Change Notice

As soon as practicable after the contents of the Estimate have been agreed or otherwise determined pursuant to the Dispute Resolution Procedure, the Authority shall:

confirm in writing to the Contractor the Estimate (as modified); or

withdraw the Medium Value Change Notice.

If, in any Contract Year, the Authority has either not confirmed an Estimate (as modified) within twenty (20) Business Days of the contents of the Estimate having been agreed or determined in accordance with the foregoing provisions of this Part 3 of this Schedule 24 or has withdrawn a Medium Value Change Notice on an aggregate of three or more occasions then the Authority shall pay to the Contractor on the third and each subsequent such occasion in that Contract Year the reasonable additional third party costs incurred by the Contractor in preparing the Estimate provided that:

the Contractor has used all reasonable endeavours to submit a reasonably priced Estimate;

the Contractor made available, with the Estimate, to the Authority a cost breakdown of the Estimate including and in accordance with paragraph 3.10 of this Part 3 of this Schedule 24 an estimate of third party costs to be incurred by the Authority in the event the Medium Value Change Notice is withdrawn or deemed to be withdrawn; and

the Authority has:

approved the estimate of third party costs referred to in paragraph 7.2.2 of this Part 3 of this Schedule 24 and the type of third party prior to any third party costs being incurred; and

agreed that, given the nature of the proposed Medium Value Change, it is reasonable to expect the relevant third party to incur costs in preparing the Estimate on the basis of the extent of the proposed change to the Services or the Works and the work required in submitting an accurate Estimate in compliance with this paragraph 7.2 of this Part 3 of this Schedule 24.

Implementation of the Medium Value Change

Where the Authority has confirmed the Estimate in accordance with paragraph 7.1 of this Part 3 of this Schedule 24 the Contractor shall implement the required Medium Value Change in accordance with the Estimate and so as to minimise any inconvenience to the Authority and to the provision of the Services.

The Contractor shall notify the Authority when it believes the Medium Value Change has been completed.

Where the Contractor has either:

failed to provide a response pursuant to paragraph 3 of this Part 3 of this Schedule 24 within fifteen (15) Business Days of the date of the Medium Value Change Notice;

provided an Estimate in accordance with paragraph 3 of this Part 3 of this Schedule 24 but failed to fully implement the Medium Value Change within ten (10) Business Days of the date set out in the Estimate as confirmed in accordance with paragraph 7.1 of this Part 3 of this Schedule 24 being the date on which the Medium Value Change should have been implemented; or

where it is determined pursuant to paragraph 6 of this Part 3 of this Schedule 24 that the Contractor has failed to submit a fair and reasonable Estimate,

then the Authority may notify the Contractor that the Medium Value Change Notice is withdrawn and, following such notification, may procure the implementation of the Medium Value Change without further recourse to the Contractor.

Certification of the Medium Value Change

Where the Medium Value Change is implemented at a Facility before the Services Availability Date for that Facility, the procedure set out at clause 20 of this Agreement (Notification of Services Availability) shall apply to the Works which are the subject of the Medium Value Change at the same time as the Facility in question is subject to that procedure.

Where the Medium Value Change is implemented at a Facility after the Services Availability Date for that Facility, and constitutes additional or varied Works, the procedure set out and agreed in the Estimate for certifying the completion of the Medium Value Change shall apply to determine whether the Medium Value Change has been completed appropriately.

Where the Medium Value Change constitutes additional or varied Services, the Payment and Performance Monitoring System shall apply to determine whether the Medium Value Change has been properly implemented.

Method of Payment of Authority Contribution

The Authority and the Contractor shall agree:

a payment schedule in respect of the payment of a sum reflecting the amount and timing of the costs to be incurred by the Contractor in carrying out the Medium Value Change to the extent borne by the Authority; and

where payment for part of a Medium Value Change reflects the carrying out of, or specific progress towards, an element within the Medium Value Change, an objective means of providing evidence confirming that the part of the Medium Value Change corresponding to each occasion when payment is due under the payment schedule appears to have been duly carried out,

(such payment and evidence to be determined in accordance with the Dispute Resolution Procedure in the event of the Authority and the Contractor failing to agree its terms).

The Authority shall make a payment to the Contractor within fifteen (15) Business Days of receipt by the Authority of invoices presented to the Authority (complete in all material respects) in accordance with the agreed payment schedule (as the case may be, varied by agreement from time to time) accompanied by the relevant evidence (where applicable) that the relevant part of the Medium Value Change has been carried out.

If payment is not made in accordance with paragraph 10.2 of this Part 3 of this Schedule 24, the Authority shall pay interest to the Contractor on the amount unpaid from the date fifteen (15) Business Days after receipt of the relevant invoice until paid at the Prescribed Rate.

Adjustment to Annual Payment

Any adjustment to the Annual Payment that is necessary due to the implementation of a Medium Value Change shall be calculated in accordance with clause 69 (Financial Adjustments), together with any adjustment that is necessary pursuant to any Small Value Changes made under Part 2 of this Schedule 24 that have not already been taken account of.

Due Diligence

It is acknowledged that Changes (particularly where they involve a change to the Works or the Facilities) may require authorisation from the insurers under the Required Insurances. The Contractor shall notify the relevant insurance broker immediately upon any material Medium Value Change being agreed (materiality being judged in relation to the size and nature of the scope of the Medium Value Change).

Project Documentation

Unless the parties otherwise agree, no changes to the Project Documents or Ancillary Documents shall be made as a result of a Medium Value Change.

The Contractor shall, no later than one (1) month following completion of the Change, update the As-built Drawings and the operating and maintenance manuals as necessary to reflect the Change.

Part 4 – High Value Changes

- High Value Changes

The Authority has the right to propose High Value Changes in accordance with this Part 4. If the Authority requires a High Value Change, it must serve a notice (a High Value Change Notice) on the Contractor in accordance with paragraph 2 of this Part 4 of this Schedule 24. The Contractor shall be entitled to refuse a High Value Change that:

requires the Works and/or the Services to be performed in a way that infringes any Legislation or is inconsistent with Good Industry Practice;

would cause any Necessary Consent to be revoked (or would require a new consent to be obtained to implement the relevant change in the Works and/or the Services which, after using reasonable efforts, the Contractor has been unable to obtain);

would materially and adversely affect the Contractor's ability to deliver the Works and /or Services (except those Works and/or Services which have been specified as requiring to be amended in the High Value Change Notice) in a manner not compensated pursuant to this Part 4 of this Schedule 24;

would materially and adversely affect the health and safety of any person;

would, if implemented, materially and adversely change the nature of the Project (including its risk profile);

is the subject of a High Value Change Notice that cannot reasonably be complied with; or

the Authority does not have the legal power or capacity to require implementation of.

High Value Change Notice

Where the Authority wishes to propose a High Value Change, the Authority shall:

submit a written request for the Contractor to produce outline proposals for any High Value Change (a High Value Change Proposal), including indicative funding proposals, setting out the maximum available capital and/or revenue the Authority is able to commit to that High Value Change (the Target Cost).

identify any requirements in relation to the High Value Change that must be satisfied as part of the High Value Change Proposal (the High Value Change Requirements); and

identify how the Authority shall assess whether the High Value Change Stage 2 Submission offers it value for money.

The parties may agree written protocols with express reference to this Part 4 of this Schedule 24 which explain or clarify any aspects of the High Value Change approval procedure set out in this Part 4 of this Schedule 24 and such protocols shall be read as if incorporated into this Part 4 of this Schedule 24 (including accelerated procedures with reduced requirements for High Value Changes of relatively low values).

Without prejudice to the generality of paragraph 2.2 of this Part 4 of this Schedule 24, the parties shall:

within five (5) Business Days of receipt by the Contractor of any High Value Change Notice, discuss and review the nature of the High Value Change, including a discussion as to which of the items set out in paragraph 3.2 of this Part 4 of this Schedule 24 are appropriate to be included within the High Value Change Proposal; and

within five (5) Business Days of a High Value Change Proposal becoming a Stage 1 Approved Project, discuss and review the nature of the Stage 1 Approved Project, including a discussion as to which of the items set out in paragraph 4.3 of this Part 4 of this Schedule 24 are appropriate to be included within the High Value Change Stage 2 Submission.

High Value Change Proposal

The Contractor shall notify the Authority in writing as soon as practicable and in any event within fifteen (15) Business Days after having received the High Value Change Notice if any of the circumstances outlined in paragraph 1 of this Part 4 of this Schedule 24 apply. If no such notice is served, the Contractor shall (within thirty (30) Business Days of its request issued in accordance with paragraph 2 of this Part 4 of this Schedule 24) submit either a High Value Change Proposal to the Authority or shall provide confirmation as to when the High Value Change Proposal will be provided to the Authority (provided that the Contractor shall use all reasonable endeavours to obtain such information as is required expeditiously). If the Authority does not believe the proposed time period from the Contractor is reasonable, the parties shall seek to agree the time period, failing which any dispute as to what is an appropriate period for submission of the High Value Change Proposal may be referred to the Dispute Resolution Procedure.

Save where agreed by the parties to the contrary, all High Value Change Proposals will contain at least the following information in sufficient detail to enable the Authority to make an informed decision under paragraph 3.4 of this Part 4 of this Schedule 24:

a description of the High Value Change, with evidence of how the High Value Change meets the High Value Change Requirements;

an outline of the proposed building solution and design including an appropriate analysis/risk appraisal of, in each case to the extent relevant (if at all), the preferred investment solution contemplated in terms of new build, refurbishment and whole life costings;

a fixed Change Management Fee for the High Value Change;

an estimated programme for submission of the High Value Change Stage 2 Submission together with the implementation of the High Value Change;

whether relief from compliance with obligations is required, including the obligations of the Contractor to achieve the Start on Site Date, each Planned Services Availability Date [to complete the Post Completion Works before the relevant Planned Post Completion Works Acceptance Date] and meet the requirements set out in the Authority's Requirements during the implementation of the High Value Change;

any impact on the provision of the Works and/or the Services;

any amendment required to this Agreement and/or any Project Document or Ancillary Document as a result of the High Value Change;

any estimated Change in Costs and estimated Change in Revenue that results from the High Value Change;

an outline of how the Contractor proposes to finance the High Value Change;

the Contractor's suggested payment schedule for the Change, based on milestones where relevant;

any Necessary Consents which are required;

costs and details of any other approvals required or due diligence permitted pursuant to paragraph 13 of this Part 4 of this Schedule 24;

the proposed method of certification of any construction or operational aspects of the Works or the Services required by the proposed High Value Change if not covered by the procedures specified in clause 20 (Notification of Services Availability);

a value for money assessment explaining why the Contractor's proposals represent value for money taking into account both the proposed Capital Cost and Whole Life Cost; and

if the Contractor reasonably believes that there is a substantial risk that it will not be able to obtain any Necessary Consent the High Value Change Proposal shall contain a statement to that effect along with evidence to support this belief.

Liaison between the Contractor, the Authority and relevant Users

In developing a High Value Change Proposal the Contractor shall liaise with the Authority and relevant Users (being such persons or organisations as the Contractor in consultation with the Authority considers appropriate). The Authority shall provide to the Contractor such information as to its requirements as the Contractor may reasonably require and shall assist the Contractor in the review of any draft designs in relation to the High Value Change Proposal. Any and all information and other input or feedback provided by the Authority to the Contractor shall, unless expressly stated otherwise by the Authority, be provided without warranty and shall be without prejudice to the Authority's rights under this Part 4 of this Schedule 24.

Consideration of a High Value Change Proposal by the Authority

The Authority will consider in good faith each High Value Change Proposal put forward by the Contractor and the Authority will not unreasonably withhold or delay its consent to a High Value Change Proposal. If, acting reasonably, the Authority finds that any material aspects of the High Value Change Proposal are unsatisfactory to it, it shall notify the Contractor of the same and offer reasonable assistance to the Contractor to enable it to address such deficiencies and resubmit the High Value Change Proposal as soon as reasonably practicable. If the Contractor addresses such deficiencies to the Authority's satisfaction, acting reasonably, paragraph 3.5 of this Part 4 of this Schedule 24 shall apply.

Authority response to a High Value Change Proposal

If the Authority approves a High Value Change Proposal (subject to any amendments to it agreed with the Contractor), then it shall be a Stage 1 Approved Project or be referred to as having received Stage 1 Approval, as the context requires.

Contractor's costs in relation to a High Value Change Proposal that is not approved

If a High Value Change Proposal submitted in accordance with this paragraph 3 of this Part 4 of this Schedule 24 does not become a Stage 1 Approved Project then the Contractor's costs in relation to the proposal shall be borne by the Contractor unless the Authority has either not responded to the High Value Change Proposal pursuant to paragraph 3.4 of this Part 4 of this Schedule 24 and/or is in material breach of its obligations under paragraph 3.4 of this Part 4 of this Schedule 24, in which case the Authority shall reimburse the Contractor's reasonable and proper costs.

Stage 2 Approval

Development of a High Value Change Stage 2 Submission

Within ten (10) Business Days of a High Value Change Proposal having become a Stage 1 Approved Project, the parties shall seek to agree the time period within which the Contractor shall develop the Stage 1 Approved Project into a detailed submission (the High Value Change Stage 2 Submission). If the parties are unable to agree a reasonable time period for such submission any dispute may be referred to the Dispute Resolution Procedure.

Following agreement or determination of what is an appropriate time period for submission by the Contractor of the High Value Change Stage 2 Submission pursuant to paragraph 4.1.1 of this Part 4 of this Schedule 24, the Contractor shall proceed regularly and diligently to produce and submit the same to the Authority in accordance with the agreed or determined time period.

Liaison between the Contractor, the Authority and relevant Users

In developing a High Value Change Stage 2 Submission the Contractor shall continue to liaise with the Authority and relevant Users (being such persons or organisations as the Authority in consultation with the Contractor considers appropriate). The Authority shall provide to the Contractor such information as to its requirements necessary to enable the Contractor to submit a full and complete High Value Change Stage 2 Submission and any such other information as the Contractor may reasonably require and shall assist the Contractor in the review of any draft designs in relation to the Stage 1 Approved Project and in the development of other aspects of the High Value Change Stage 2 Submission (but not where this would involve the Authority incurring additional material expense). Any and all information and other input or feedback provided by the Authority to the Contractor shall be provided without warranty and shall be without prejudice to the Authority's rights under this Part 4 of this Schedule 24.

Content requirements in relation to a High Value Change Stage 2 Submission

Save where the parties agree otherwise, in relation to the relevant Stage 1 Approved Project, the Contractor shall procure that a High Value Change Stage 2 Submission shall include (but not be limited to):

draft(s) of the relevant Project Document(s) identifying (if relevant) any material changes or amendments proposed in respect of the relevant Stage 1 Approved Project, together with the reasons for any such changes or amendments proposed. This shall include full details of which provisions of the relevant Project Documents shall apply to the High Value Change so that it is implemented in equivalent manner and to an equivalent standard as required in respect of the Works and/or Services as appropriate;

detailed design solutions (to RIBA Level D);

appropriate plans and drawings;

relevant detailed planning permissions and any other relevant planning approvals and Necessary Consents (or such lesser confirmation or information in relation to planning as may be agreed with the Authority);

a proposed revised Base Case including the detailed price estimates for the Stage 1 Approved Project;

an explanation (together with appropriate supporting evidence) as to why the High Value Change Stage 2 Submission meets the Approval Criteria (as defined in paragraph 4.4 of this Part 4 of this Schedule 24);

confirmation (or details of any requested variations to (with supporting justification)) of the Change Management Fee referred to in paragraph 3.2.3 of this Part 4 of this Schedule 24;

the proposed method of certification of any construction or operational aspects of the Works or the Services required by the proposed High Value Change if not covered by the procedures specified in clause 20 (Notification of Services Availability);

a value for money assessment explaining why the Contractor's proposals represent value for money taking into account both the proposed Capital Cost and Whole Life Cost;

a timetable and method statement setting out how the relevant High Value Change will be delivered which shall include (but not be limited to):

proposals for the effective management of the building programme;

an assessment as to the savings to be generated across the High Value Change, particularly on staff costs and lifecycle replacement and maintenance and operation of services;

details of the Sub-Contractors together with evidence and explanation of the value testing undertaken by the Contractor in relation to the High Value Change;

a completed risk register showing the potential risks identified in relation to the delivery of the High Value Change the occurrence of which are capable of adversely affecting the time for completion, cost and/or quality of the project, the probability of such risks occurring and a financial estimate of the most likely consequences of each risk occurring together with the prioritisation of all continuing risks and an action plan in respect of, and risk owners for, all risks prioritised as serious risks;

any surveys and investigations and associated reports that are reasonably necessary to ascertain (in relation to Changes involving the construction of additional buildings) information as to the nature, location and condition of the relevant land (including hydrological, geological, geotechnical and sub-surface conditions) together with information relating to archaeological finds, areas of archaeological, scientific or natural interest and (in relation to the refurbishment of any existing buildings) information on the condition and quality of existing structures and, in particular, the presence of any latent defects.

Approval Criteria

For the purposes of this Part 4 of this Schedule 24, Approval Criteria means the criteria against which any Stage 1 Approved Project is to be judged by the Authority in determining whether it achieves Stage 2 Approval. The criteria are:

whether the costs of the Stage 1 Approved Project are within the Target Cost notified to the Contractor by the Authority;

whether it has been demonstrated that the Stage 1 Approved Project provides value for money assessed in accordance with the measures identified by the Authority in accordance with paragraph 2.1.3 of this Part 4 of this Schedule 24;

whether the Authority, acting reasonably, is satisfied that the High Value Change Stage 2 Submission meets the Authority Requirements;

whether any material changes or amendments to the relevant Project Document(s) as detailed pursuant to paragraph 4.3.1 of this Part 4 of this Schedule 24 are acceptable to the Authority, acting reasonably; and

whether the High Value Change Stage 2 Submission contains all the information required pursuant to paragraph 4.3 of this Part 4 of this Schedule 24 (or as otherwise agreed by the parties).

Submission of the High Value Change Stage 2 Submission to the Authority and consideration of that submission by the Authority

The Contractor shall submit its High Value Change Stage 2 Submission to the Authority. The Authority will consider in good faith High Value Change Stage 2 Submissions put forward by the Contractor and the Authority will not unreasonably withhold or delay its consent to a High Value Change Stage 2 Submission. The Authority shall be entitled to call for such reasonable information as it considers appropriate to enable it to decide whether the High Value Change Stage 2 Submission meets the Approval Criteria. The Contractor shall reply promptly to all such requests for further information and assistance. If, acting reasonably, the Authority finds that any material aspects of the High Value Change Stage 2 Submission are unsatisfactory to it, it shall notify the Contractor of the same and offer reasonable assistance to the Contractor to address such deficiencies. If the Contractor addresses such deficiencies to the Authority's satisfaction, acting reasonably, paragraph 4.5.2.1 of this Part 4 of this Schedule 24 shall apply. If the Contractor is unable to resolve such deficiencies to the satisfaction of the Authority (acting reasonably) paragraph 4.5.2.2 of this Part 4 of this Schedule 24 shall apply.

As soon as reasonably practicable after the submission to it of a High Value Change Stage 2 Submission the Authority shall give written notice of whether it:

approves the relevant Stage 1 Approved Project (in which case the Stage 1 Approved Project shall be referred to as having received Stage 2 Approval or as being a Stage 2 Approved Project or an Approved Project as the context requires); or

rejects the Stage 1 Approved Project:

subject to paragraph 4.5.2.2.2 of this Part 4 of this Schedule 24, on the grounds that the High Value Change Stage 2 Submission in relation to the relevant Stage 1 Approved Project has failed to meet one or more of the Approval Criteria in which case (subject to resubmission under paragraph 4.5.3 of this Part 4 of this Schedule 24) paragraph 4.6 of this Part 4 of this Schedule 24 shall apply;

because, as a result of any change to the Target Cost referred to in paragraph 2 of this Part 4 of this Schedule 24, the Stage 1 Approved Project is not in fact Affordable despite the High Value Change Stage 2 Submission being within the Target Cost referred to in paragraph 2.1.1 of this Part 4 of this Schedule 24; or

otherwise on grounds other than those set out in paragraph 4.5.2.2.1 or 4.5.2.2.2 of this Part 4 of this Schedule 24,

in which case paragraph 4.7 of this Part 4 of this Schedule 24 shall apply.

If the Authority rejects the High Value Change Stage 2 Submission on the grounds set out in paragraph 4.5.2.2.1 of this Part 4 of this Schedule 24:

the Authority and the Contractor will work together to address the reasons for such failure and attempt in good faith to produce a revised High Value Change Stage 2 Submission which the Contractor shall re-submit to the Authority as soon as reasonably practicable after the rejection of the original submission and in any event within thirty (30) Business Days of the rejection (the Resubmission Longstop Date);

the re-submission pursuant to paragraph 4.5.3.1 of this Part 4 of this Schedule 24 shall be treated as a High Value Change Stage 2 Submission. If:

the resubmitted High Value Change Stage 2 Submission is rejected by the Authority on the grounds set out in paragraph 4.5.2.2.1 of this Part 4 of this Schedule 24 (subject to having been through the Dispute Resolution Procedure under paragraphs 4.8 and 4.9 (if applicable) of this Part 4 of this Schedule 24); or

no resubmission of the High Value Change Stage 2 Submission is made on or before the Resubmission Longstop Date,

then the relevant Stage 1 Approved Project shall be treated as having been properly rejected and the provisions of paragraph 4.6 of this Part 4 of this Schedule 24 shall apply and neither the Authority nor the Contractor shall have any further obligations in relation to the relevant High Value Change referred to in the High Value Change Stage 2 Submission; and

for the avoidance of doubt if the Authority rejects the Stage 1 Approved Project pursuant to paragraph 4.5.2.2.1 because the Contractor has failed to meet one or more of the Approval Criteria and the sole reason for that failure is that any planning consent identified by the Contractor (in compliance with paragraph 3.2.15 of this Part 4 of this Schedule 24) has not been obtained then the provisions of paragraph 4.7 of this Part 4 of this Schedule 24 shall apply, provided that the Contractor has used all reasonable endeavours to obtain the planning consent.

If a High Value Change Stage 2 Submission is properly rejected by the Authority

Where this paragraph 4.6 of this Part 4 of this Schedule 24 applies (as set out in paragraph 4.5.2.2.1, paragraph 4.5.3.2 and paragraph 4.9 of this Part 4 of this Schedule 24):

the Authority shall not be required to reimburse or compensate the Contractor in respect of any costs relating to the High Value Change including the Change Management Fee; and

the Authority shall be entitled to procure the High Value Change required under the relevant High Value Change Stage 2 Submission outside the terms of this Agreement.

If a High Value Change Stage 2 Submission is improperly rejected by the Authority

Where this paragraph 4.7 of this Part 4 of this Schedule 24 applies (as set out in paragraph 4.5.2.2.2, paragraph 4.8.2 and paragraph 5.2.1.2 and paragraph 5.2.2 of this Part 4 of this Schedule 24)):

subject to paragraph 4.7.1.2 of this Part 4 of this Schedule 24, the Incurred Change Management Fee in relation to the relevant High Value Change will be paid by the Authority within ten (10) Business Days of the date on which the Contractor receives written notice of the rejection or the date of the deemed rejection (as the case may be) with the date of the rejection or the deemed rejection (as the case may be) being the Calculation Date for the purposes of calculating the amount of the Incurred Change Management Fee (unless a different Calculation Date is expressly stated in this Part 4 of this Schedule 24 in relation to the circumstances giving rise to the entitlement of the Contractor to be paid the Incurred Change Management Fee);and

if the parties are unable to agree the amount of the Incurred Change Management Fee for the purposes of paragraph 4.7.1.1 of this Part 4 of this Schedule 24 the matter shall be resolved by reference to the Dispute Resolution Procedure; and

the Authority shall be entitled to procure the High Value Change required under the relevant High Value Change Stage 2 Submission outside the terms of this Agreement.

Dispute resolution

If the Authority rejects a High Value Change pursuant to the provisions of paragraph 4.5.3.2.1 of this Part 4 of this Schedule 24, the Contractor shall be entitled to refer the matter for consideration under the Dispute Resolution Procedure within ten (10) Business Days after receiving written notice of the Authority's decision. If, following a referral to the Dispute Resolution Procedure, it is agreed or determined that the High Value Change rejected by the Authority pursuant to paragraph 4.5.3.2.1 of this Part 4 of this Schedule 24 met the Approval Criteria the Authority shall either:

declare that the relevant High Value Change has received Stage 2 Approval and that High Value Change shall proceed; or

declare that its rejection of the relevant High Value Change be treated as an improper rejection and that the provisions of paragraph 4.7 of this Part 4 of this Schedule 24 shall apply.

If, following a referral to the Dispute Resolution Procedure under paragraph 4.8 of this Part 4 of this Schedule 24, it is agreed or determined that the High Value Change did not meet the Approval Criteria, the provisions of paragraph 4.6 of this Part 4 of this Schedule 24 shall apply.

If the Authority rejects a High Value Change Proposal either party may refer the matter to the Dispute Resolution Procedure to determine whether the High Value Change Proposal comprised a fair and reasonable response to the High Value Change Notice. If it is agreed or determined that the High Value Change Proposal was not a fair and reasonable response, paragraph 4.6 of this Part 4 of this Schedule 24 shall apply. [If it is agreed or determined that the High Value Change Proposal was a fair and reasonable response no Performance Adjustment Points and Performance Adjustments shall be applied under Schedule 6 (Payment and Performance Monitoring System) in relation to the High Value Change Proposal but, for the avoidance of doubt, the Authority shall not be obliged to accept the High Value Change Proposal and paragraph 3.6 of this Part 4 of this Schedule 24 shall still apply.]

Time periods for approval

Each High Value Change Proposal and each High Value Change Stage 2 Submission shall be valid for a period of three (3) months from the date of its submission by the Contractor.

If by the end of the three (3) month period referred to in paragraph 5.1 of this Part 4 of this Schedule 24 the Authority has not:

in relation to a High Value Change Proposal, approved or rejected that High Value Change Proposal in accordance with the procedures set out in this Part 4 of this Schedule 24:

the Contractor shall be entitled to withdraw the High Value Change Proposal at the end of that period; and

the Contractor shall not be entitled to any costs relating to the High Value Change Proposal unless the Authority has either not responded to the High Value Change Proposal and/or is in material breach of its obligations in paragraph 3.4 of this Part 4 of this Schedule 24 in which case paragraph 4.7 of this Part 4 of this Schedule 24 shall apply;

in relation to a High Value Change Stage 2 Submission, approved or rejected that High Value Change Stage 2 Submission in accordance with the procedures set out in this Part 4 of this Schedule 24 (has not given any notification of the Authority's response to the High Value Change Stage 2 Submission or has given written notice to the Contractor withdrawing or cancelling the High Value Change to which the High Value Change Stage 2 Submission relates) then the High Value Change Stage 2 Submission shall be deemed to have been improperly rejected by the Authority and paragraph 4.7 of this Part 4 of this Schedule 24 shall apply.

Co-operation of the Authority

The Authority will co-operate with the Contractor in relation to any High Value Change Stage 2 Submission being developed by the Contractor, including (without limitation) promptly providing:

written confirmation of the Target Cost and/or High Value Change Requirements or any change to such Target Cost and/or High Value Change Requirements; and

any information reasonably required by the Contractor to enable it to satisfy the requirements of paragraph 4.3 of this Part 4 of this Schedule 24.

Changes to the High Value Change Requirements

If the High Value Change Requirements or Approval Criteria are subject to any material variation in relation to a High Value Change by the Authority after the High Value Change Proposal has been submitted then:

the Contractor and the Authority shall negotiate in good faith as to the implications on the High Value Change Proposal or High Value Change Stage 2 Submission (as the case may be) and shall seek to agree changes thereto to accommodate the variation (including any change to the Target Cost and/or to the Change Management Fee);

if agreement has not been reached pursuant to paragraph 7.1.1 of this Part 4 of this Schedule 24 within twenty (20) Business Days (or such longer period as the parties may agree) then:

the Contractor shall be entitled by notice in writing to the Authority to withdraw the High Value Change Proposal or the High Value Change Stage 2 Submission (as the case may be) and to be paid the Incurred Change Management Fee with the Calculation Date being the date of the change notified by the Authority; and

the Authority shall not be entitled to procure the High Value Change without recommencing and complying with the procedure in this Part 4 of this Schedule 24 in relation to that High Value Change.

The Authority may, at any time, give notice in writing to the Contractor that it proposes to cancel a High Value Change without completing the process set out in paragraphs 3 to 5 of this Part 4 of this Schedule 24 in which case the Authority shall pay the Contractor the Incurred Change Management Fee in respect of the cancelled High Value Change with the Calculation Date being the date of such notice.

Information and notifications by the Authority to the Contractor and co-operation of the Authority

The Authority shall notify the Contractor as soon as it becomes aware of any matter which may have a reasonably foreseeable material adverse effect on the viability of any High Value Change including any:

planning issues likely to cause a material delay in the anticipated programme for the High Value Change or material cost increases; and

changes to funding which the Authority receives or to the way in which funding may be applied, either or both of which may affect whether a High Value Change is affordable.

The Authority shall provide reasonable assistance to the Contractor in relation to the procurement by the Contractor of all relevant Necessary Consents,

provided that this paragraph 8 of this Part 4 of this Schedule 24 shall not apply to the Authority to the extent it is exercising its functions as a Local Planning Authority or Highways Authority.

Change Management Fee

A proposed fixed management fee for each High Value Change must be submitted by the Contractor as part of the High Value Change Proposal and, once agreed, shall be the Change Management Fee for the High Value Change. The Change Management Fee submitted pursuant to paragraph 3.2.3 of this Part 4 of this Schedule 24 shall include a breakdown of the proposed amount by reference to the following categories of costs (without any double counting between the amounts under paragraphs 9.1 to 9.8 of this Part 4 of this Schedule 24):

the time incurred by or on behalf of the Contractor in project managing the development and procurement of the High Value Change Proposal and High Value Stage 2 Submission, which shall:

be based on actual time spent (validated by timesheet records);

be calculated at the daily rates as set out in Part 3 of Appendix 2 of this Schedule 24; and

not include any mark-up or profit cost or additional overheads;

design costs;

legal advice;

financial advice;

technical advice;

surveys;

fees in connection with obtaining any relevant Necessary Contracts; and

other costs the Contractor shall be required to incur, acting reasonably, to finalise its High Value Change Stage 2 Submission,

in each case applying the Small Works Rates where appropriate and otherwise applying current market rates on a fair and reasonable basis.

Implementation of the High Value Change

The Contractor shall implement any High Value Change approved by the Authority so as to minimise any inconvenience to the Authority and to the provision of the Services and in accordance with:

the High Value Change Stage 2 Submission (subject to any amendments to it agreed by the parties);

subject to paragraph 10.1 of this Part 4, the provisions of Part 3 (Transitional Arrangements) of this Agreement (to the extent the High Value Change involves design and construction), amended as appropriate to apply to the High Value Change; and

subject to paragraph 10.1 of this Part 4, the provisions of clause 22 (Principal Obligations) of this Agreement (to the extent the High Value Change involves provision of Services).

Method of Payment of Authority Contribution

This paragraph 11 of this Part 4 of this Schedule 24 shall apply where an Approved Project provides that the High Value Change shall be funded in whole or part other than by adjustment of the Annual Payment.

The Authority and the Contractor shall agree:

a payment schedule in respect of the payment of such sum reflecting the amount and timing of the costs to be incurred by the Contractor in carrying out the High Value Change to the extent borne by the Authority; and

where payment for part of a High Value Change reflects the carrying out of, or specific progress towards, an element within the High Value Change, an objective means of providing evidence confirming that the part of the High Value Change corresponding to each occasion when payment is due under the payment schedule appears to have been duly carried out,

(such payment and evidence to be determined in accordance with the Dispute Resolution Procedure in the event of the Authority and the Contractor failing to agree as to its terms).

The Authority shall make a payment to the Contractor within fifteen (15) Business Days of receipt by the Authority of invoices presented to the Authority (complete in all material respects) in accordance with the agreed payment schedule (as the case may be, varied by agreement from time to time) accompanied by the relevant evidence (where applicable) that the relevant part of the High Value Change has been carried out.

If payment is not made in accordance with paragraph 11.3 of this Part 4 of this Schedule 24, the Authority shall pay interest to the Contractor on the amount unpaid from the date fifteen (15) Business Days after receipt of the relevant invoice until paid at the Prescribed Rate.

Adjustment to Annual Payment

Any adjustment to the Annual Payment which is necessary as a result of the implementation of a High Value Change shall be calculated in accordance with clause 69 (Financial Adjustments), together with any adjustment that is necessary pursuant to any Small Value Changes made under Part 2 of this Schedule 24 and/or any Medium Value Changes made under Part 3 of this Schedule 24 that have not already been taken account of.

Due Diligence

It is acknowledged that High Value Changes (particularly where they involve a change to the Works or the Facilities) may require authorisation from the insurers under the Required Insurances. The Contractor shall notify the relevant insurance broker immediately upon any material High Value Change being agreed (materiality being judged in relation to the size and nature of the scope of the High Value Change).

Project Documentation

The only changes to the Project Documents or Ancillary Documents to be made as a result of a High Value Change shall be those identified in the High Value Change Stage 2 Submission (subject to any amendments to it agreed by the parties).

The Contractor shall, on completion of the Change, update the As-built Drawings and the operating and maintenance manuals as necessary to reflect the Change.

Part 5 – Contractor Changes

- If the Contractor wishes to introduce a Contractor Change, it shall serve a notice containing the information required pursuant to paragraph 2 of this Part 5 of this Schedule 24 (a Contractor Notice of Change) on the Authority.

The Contractor Notice of Change shall:

set out the proposed Contractor Change in sufficient detail to enable the Authority to evaluate it in full;

specify the Contractor's reasons for proposing the Contractor Change;

indicate any implications of the Contractor Change;

indicate what savings, if any, will be generated by the Contractor Change, including:

whether a revision of the Annual Payment is proposed (and, if so, give details of such proposed revision, taking account of paragraph 8 of this Part 5 of this Schedule 24); or

whether such savings will be paid by a lump sum;

if the Contractor Change is required as a result of a Qualifying Change in Law:

indicate what sums, if any, will be payable by the Authority; and

contain the information required by clause 56.2 (Qualifying Change in Law) of this Agreement;

indicate whether there are any critical dates by which a decision by the Authority is required; and

request the Authority to consult with the Contractor with a view to deciding whether to agree to the Contractor Change and, if so, what consequential changes the Authority requires as a result.

The Authority shall evaluate the Contractor Notice of Change in good faith, taking into account all relevant issues, including whether:

a revision of the Annual Payment will occur;

the Contractor Change may affect the quality of the Services and/or the Works or the likelihood of successful completion of the Works and/or delivery of the Services (or any of them);

the Contractor Change will interfere with the relationship of the Authority with third parties;

the financial strength of the Contractor is sufficient to perform the Works and/or Services after implementation of the Contractor Change;

the value and/or life expectancy of any of the Facilities and/or Assets is reduced; or

the Contractor Change materially affects the risks or costs to which the Authority is exposed.

As soon as practicable after receiving the Contractor Notice of Change, the parties shall meet and discuss the matters referred to in it, including in the case of a Qualifying Change in Law those matters referred to in clause 56.3 (Parties to Discuss) of this Agreement. During discussions, subject to paragraph 9 of this Part 5 of this Schedule 24, the Authority may propose modifications to, or accept or reject, the Contractor Notice of Change.

If the Authority accepts the Contractor Notice of Change (with or without modification) the parties shall consult and agree the remaining details as soon as practicable and upon agreement the Authority shall issue a notice confirming the Contractor Change which shall set out the agreed Contractor Change and:

shall enter into any documents to amend this Agreement or any relevant Project Document which are necessary to give effect to the Contractor Change;

subject to paragraph 7 of this Part 5 of this Schedule 24, the Annual Payment shall be revised in accordance with clause 69 (Financial Adjustments); and

the Contractor Change shall be implemented within the period specified by the Authority in its notice of acceptance.

If the Authority rejects the Contractor Notice of Change, it shall not be obliged to give its reasons for such a rejection and the Contractor shall not be entitled to reimbursement by the Authority of any of its costs involved in the preparation of the Contractor Notice of Change.

Unless the Authority's written acceptance expressly agrees to an increase in the Annual Payment or that the Contractor should be entitled to relief from any of its obligations, there shall be no increase in the Annual Payment or relief granted from any obligations as a result of a Contractor Change.

If the Contractor Change causes, or will cause, the Contractor's costs or those of a sub-contractor to decrease, there shall be a decrease in the Annual Payment where it is a Deficit Annual Payment such that any cost savings (following deduction of costs reasonably incurred by the Contractor in implementing such Contractor Change) shall be shared on the basis of [50] per cent ([50%]) of the saving being retained by the Contractor and [50] per cent ([50%])  of the saving being paid to the Authority as a lump sum within ten (10) Business Days of agreement or determination or by way of revision of the Annual Payment pursuant to clause 69 (Financial Adjustments). Where it is a Surplus Annual Payment, any cost savings shall be for the account of the Contractor.

The Authority shall not reject a Contractor Change that is required in order to conform to a Change in Law. The costs of introducing a Contractor Change resulting from a Qualifying Change in Law (including any resulting revision of the Annual Payment) shall be dealt with in accordance with clause 56 (Change in Law) and, to the extent not dealt with therein, all costs shall be borne by the Contractor.

Part 6 – Partial Termination

- [[Provided that the Authority's right under this paragraph 1 of this Part 6 of this Schedule 24 shall not be exercised more than [x] times during the Contract Period], at any time [following the date that falls [            ] years after the final Services Availability Date] the Authority may serve notice of its intention to remove a Facility from this Agreement by way of a High Value Change Notice (a Partial Termination Authority Notice of Change) in accordance with this paragraph 1 of this Part 6 of this Schedule 24.

Subject to paragraphs 3 and 4 of this Part 6 of this Schedule 24, where the Authority has served a Partial Termination Authority Notice of Change, the provisions of paragraphs 2 to 14 of Part 4 of this Schedule 24 shall apply. The Contractor shall not be entitled to serve a notice under paragraph 3.1 of Part 4 of this Schedule 24 in respect of any Partial Termination Authority Notice of Change.

Proposals delivered by the Contractor under paragraph 3.1 of Part 4 of this Schedule 24 relating to a Partial Termination Authority Notice of Change shall be calculated on the basis that the partial termination shall be carried out on the basis that the Annual Payment shall be adjusted so as to leave the Contractor in a "no better and no worse" position in accordance with clause 69.4.

In the event that a High Value Change Proposal pursuant to a Partial Termination Authority Notice of Change is confirmed by the Authority in accordance with paragraph 4.5.2 of Part 4 of this Schedule 24 the adjustment to the Annual Payment under paragraph 12 of Part 4 of this Schedule 24 shall be carried out so as to leave the Contractor in a "no better no and worse" position in accordance with clause 69.4.]

APPENDIX 1

Part 1 – Catalogue of Small Works and Services

Part 2 - Small Value Change Notice

APPENDIX 2

Part 1 - Unit Cost for Construction or Installation Costs

Part 2 - Unit Costs for Lifecycle Maintenance

Part 3 - Consultant, Sub-Contractor or Supplier Fees

Part 4 - Unit Costs for Labour Rates

SCHEDULE 25

BASE CASE

SCHEDULE 26

LOBTA

SCHEDULE 27

NNDR

- Definitions

Billing Authority

has the meaning given to the term "billing authority" in the Local Government Finance Act 1988;

National Non Domestic Rates or NNDR

means the National Non Domestic Rates as contained in the Local Government Finance Act 1988 (or any rates or tax that replaces it) payable in relation to the Site[s] and/or the [Facility/Facilities];

NNDR Failure

means:

- a failure by (or on behalf of) the Contractor [or Leisure Operator] to submit, or do anything reasonably required by the Authority (acting in its capacity as Billing Authority) in support of, an application for NNDR Relief;

- any act or omission of any Contractor Related Party (excluding the Building Contractor and its servants, agents or employees) and any of their servants, agents or employees which is calculated or intended to cause loss of or unavailability of NNDR Relief;

- any failure by the Contractor [or the Leisure Operator] to exercise reasonable skill and care and use all reasonable endeavours to obtain NNDR Relief; or

- a failure by the Contractor [or the Leisure Operator] to achieve the NNDR Relief status of [            ];

NNDR Pre-Application Information

shall have the meaning given in paragraph 2.2.1 (Eligibility for NNDR Relief);

NNDR Pre-Application Rate

shall have the meaning given in paragraph 2.2.2 (Eligibility for NNDR Relief);

NNDR Relief

means relief from the obligation to pay NNDR applicable to the Site[s] and/or the [Facility/Facilities] pursuant to the provisions of:

- sections 47 to 50 of the Local Government Finance Act 1988 (and/or any such similar scheme making provision for relief or exemption from or reduction of the payment of any part of NNDR); and/or

- the NNDR Relief Policy;

NNDR Relief Policy

means the Authority's (acting in its capacity as Billing Authority) policy [include reference to the policy] for the application of NNDR Relief in the Authority's rating area and the exercise of its discretion to award NNDR Relief in respect of the [Facility/Facilities] pursuant to such policy;

NNDR Report

shall have the meaning given in paragraph 5.3 (Alternative Structures);

Updated NNDR Rate

shall have the meaning given in paragraph 3.4 (Initial Application for NNDR Relief);

Eligibility for NNDR Relief

The Contractor acknowledges and agrees that, subject to the following provisions of this Schedule 27 (NNDR), the Contractor shall [or shall procure that the Leisure Operator shall] be responsible for the payment of NNDR applicable to the [Facility/Facilities] from the [relevant] Services Availability Date (or, if earlier, the date on which NNDR is payable in respect of the Site[s] and/or the [Facility/Facilities]), until the Expiry Date or, if earlier, the Termination Date.

The parties acknowledge and agree that:

the Contractor has, prior to the Commencement Date, submitted to the Authority information relating to the contractual arrangements and the Project and corporate structure proposed by the Contractor for the purposes of the Project to assist the Authority to assess the eligibility of the Contractor [and/or Leisure Operator] to claim NNDR Relief in connection with the [Facility/Facilities] on and from the [relevant] Services Availability Date (or, if earlier, the date on which NNDR is payable in respect of the Site[s] and/or the [Facility/Facilities]), such information being in the Agreed Form or as set our in the Contractor's tender documents (the NNDR Pre-Application Information); and

having relied upon the information contained in the NNDR Pre-Application Information, the Authority has indicated to the Contractor that the contractual arrangements and Project and corporate structure proposed by the Contractor would, on the date of such indication, entitle the Contractor to claim NNDR Relief in connection with the [Facility/Facilities] on and from the [relevant] Services Availability Date (or, if earlier, the date on which NNDR is payable in respect of the Site[s] and/or the [Facility/Facilities]), at a particular rate (the NNDR Pre-Application Rate) the parties acknowledging that for the purposes of the NNDR Pre-Application Rate, NNDR Relief will [include][not include] mandatory rate relief [only] and [no NNDR Policy] will apply in respect of discretionary rate relief].

Initial Application for NNDR Relief

The Contractor shall [or shall procure that the Leisure Operator shall] inform the [Financial Services Department] of the Authority in relation to the occupation of the [Facility/Facilities] by the [Contractor/Leisure Operator].

The Contractor shall [or shall procure that the Leisure Operator shall] submit an application for NNDR Relief to the [Financial Services Department] of the Authority [on or before the [relevant] Services Availability Date, or following the issue of the first NNDR demand note by the Authority in respect of the [Facility/Facilities] (whichever is the earlier)]. Such application will confirm whether the contractual arrangements and project and corporate structure vary from the NNDR Pre-Application Information.

Where, following the application referred to in paragraph 3.2 (Initial Application for NNDR Relief), the Authority (acting in its capacity as Billing Authority) determines that the contractual arrangements contemplated by this Agreement (and (where applicable) the Sub-Contracts) will entitle the Contractor [or Leisure Operator] to claim NNDR Relief in connection with the [Facility/Facilities] at the NNDR Pre-Application Rate, then the Contractor shall apply (and continue to apply) the full benefit of such NNDR Relief to the Project and the Contractor warrants and confirms that in calculating the Annual Payment it has taken into account NNDR Relief at the NNDR Pre-Application Rate in respect of the Site[s] and/or the [Facility/Facilities] (as the case may be), as contemplated in row [       ] of the Base Case.

Where, following the application referred to in paragraph 3.2 (Initial Application for NNDR Relief), the Authority (acting in its capacity as Billing Authority) determines that the contractual arrangements contemplated by this Agreement (and (where applicable) the Sub-Contracts) will not entitle the Contractor [or Leisure Operator] to claim NNDR Relief at the NNDR Pre-Application Rate and instead claim it at a different rate (including for the avoidance of doubt, a nil rate) (the Updated NNDR Rate) in connection with the [Facility/Facilities] so that the NNDR liability for the Project increases, then:

where the information on which such determination is made is:

consistent (in all relevant respects) with the information submitted in the NNDR Pre-Application Information; and

the reason for such determination does not arise as a result of an NNDR Failure; and

the reason for such determination does not arise as a result of a General Change in Law which was foreseeable at the date of this Agreement,

then, subject to the following provisions of this Schedule 27 (NNDR), the Authority shall be responsible for the payment of additional NNDR in respect of the [Facility/Facilities] and the Annual Payment shall be adjusted in accordance with clause 69 (Financial Adjustments) so as to put the Contractor in no better and no worse a position than it would have been in had the relevant determination not been made;

where the information on which such determination is made is inconsistent (in any relevant respect) with the information submitted in the NNDR Pre-Application Information and/or the reason for such determination arises as a result of an NNDR Failure and/or the reason for such determination arises because of a General Change in Law which was foreseeable at the date of this Agreement, then, subject to the following provisions of this Schedule 27 (NNDR), the Contractor shall be responsible for meeting the additional costs of NNDR in respect of the [Facility/Facilities].

Subsequent Applications for NNDR Relief

Following the Contractor's [or Leisure Operator's] initial application for NNDR Relief pursuant to paragraph 3.2 (Initial Application for NNDR Relief), the Contractor shall [or shall procure that the Leisure Operator shall] submit an application for NNDR Relief to the [Financial Services Department] of the Authority whenever thereafter so required by the relevant rules and procedures of the Authority (acting in its capacity as Billing Authority). Such applications will confirm whether the contractual arrangements and project and corporate structure vary from the NNDR Pre-Application Information.

Where, following an application referred to in paragraph 4.1 (Subsequent Applications for NNDR Relief), the Authority (acting in its capacity as Billing Authority) determines that the contractual arrangements contemplated by this Agreement (and (where applicable) the Sub-Contracts) will entitle the Contractor [or Leisure Operator] to claim NNDR Relief in connection with the [Facility/Facilities] at the NNDR Pre-Application Rate or the Updated NNDR Rate (as applicable), then the Contractor shall apply (and continue to apply) the full benefit of such NNDR Relief to the Project and the Contractor will warrant and confirm that in calculating the Annual Payment it has taken into account NNDR Relief at the NNDR Pre-Application Rate or the Updated NNDR Rate (as applicable) in respect of the Site[s] and/or the [Facility/Facilities] (as the case may be), as contemplated in row [       ] of the Base Case.

Where, following an application referred to in paragraph 4.1 (Subsequent Applications for NNDR Relief), the Authority (acting in its capacity as Billing Authority) determines that the contractual arrangements contemplated by this Agreement (and (where applicable) the Sub-Contracts) will not entitle the Contractor [or Leisure Operator] to claim NNDR Relief at the NNDR Pre-Application Rate or the Updated NNDR Rate (as applicable) and instead claim it at a different rate in connection with the [Facility/Facilities] so that the NNDR liability for the Project increases, then:

where the information on which such determination is made is:

consistent (in all relevant respects) with the information submitted in the NNDR Pre-Application Information;

the reason for such determination does not arise as a result of an NNDR Failure; and

the reason for such determination does not arise as a result of a General Change in Law which was  foreseeable at the date of this Agreement,

then, subject to the following provisions of this Schedule 27 (NNDR), the Authority shall be responsible for the payment of additional NNDR in respect of the [Facility/Facilities] and the Annual Payment shall be adjusted in accordance with clause 69 (Financial Adjustments) so as to put the Contractor in no better and no worse a position than it would have been in had the relevant determination not been made;

where the information on which such determination is made is inconsistent (in any relevant respect) with the information submitted in the NNDR Pre-Application Information and/or the reason for such determination arises as a result of an NNDR Failure and/or the reason for such determination arose because of a General Change in Law which was foreseeable at the date of this Agreement, then, subject to the following provisions of this Schedule 27 (NNDR), the Contractor shall be responsible for meeting the additional costs of NNDR in respect of the [Facility/Facilities].

For the avoidance of doubt, references in this paragraph 4 to "Updated NNDR Rate" shall include both any updated rate pursuant to paragraph 3.4 and also any subsequent updates pursuant to this paragraph 4.

Alternative Structures

Where the Contractor [or Leisure Operator] is refused NNDR Relief at the NNDR Pre-Application Rate or the Updated NNDR Rate (as applicable) or has reason to believe that the Contractor [or Leisure Operator] will or is likely to lose all or any NNDR Relief (whether as a result of a General Change in Law or a change in the NNDR Relief Policy or otherwise), it shall notify the Authority as soon as reasonably practicable with full details of the implications of this and shall keep the Authority informed of any developments in relation to such occurrence or likely occurrence and the following provisions shall apply.

The parties shall, within ten (10) Business Days of the Contractor's notification under paragraph 5.1 (Alternative Structures), meet to discuss the implications of the lack or loss of NNDR Relief and how the impact of the lack or loss of NNDR Relief can be mitigated. If either party identifies a way in which the whole or any part of the NNDR Relief can be lawfully obtained by the Authority, the Contractor and/or [the Leisure Operator], the Contractor shall [or shall procure that the Leisure Operator shall] use its reasonable endeavours to obtain such NNDR Relief or assist the Authority in obtaining such NNDR Relief.

If the Authority so requests, the Contractor shall, from the date of such request, investigate what alternative lawful contract structures and/or forms of entity (which are acceptable to the Contractor, acting reasonably) may be available to minimise NNDR applicable to the [Facility/Facilities] and within one (1) month of such request present its findings to the Authority in a report (the NNDR Report), provided that, except in the case of an NNDR Failure, the Authority shall reimburse the Contractor's reasonable expenses in taking the steps required under this paragraph 5.3.

Upon presentation by the Contractor of the NNDR Report to the Authority in accordance with paragraph 5.3 (Alternative Structures), the Authority shall assess the details of the NNDR Report and shall within one (1) month of such presentation notify the Contractor that it:

agrees the alternative structure and/or form of entity proposed in the NNDR Report; or

does not agree the alternative structure and/or form of entity proposed in the NNDR Report; or

requires further information as is reasonable to make an assessment in respect of the NNDR Report, in which case the Contractor shall issue such information as soon as reasonably practicable. Alternatively, the Authority may require (at the Authority's cost) the opinion of a barrister or third party and the Authority will use its reasonable endeavours to not delay obtaining such opinion. The Authority shall within twenty (20) Business Days assess such additional information and/or opinion and shall notify the Contractor of its decision pursuant to paragraph 5.4.1 or 5.4.2 (Alternative Structures) (as applicable).

Where the Authority accepts the alternative structure and/or form of entity proposed in the NNDR Report pursuant to paragraph 5.4.1 (Alternative Structures), with such revisions as may be agreed to by the parties (acting reasonably) the Contractor shall proceed to implement such alternative structure and/or form of entity in accordance with Legislation and as agreed with the Authority, both parties acting reasonably. Such implementation shall be treated as an Authority Change, except where the reason for such Change arises as a result of an NNDR Failure, in which chase it shall be treated as a Contractor Change.

Reductions in NNDR Liability

Where during the Contract Period, the Authority, subsequently becomes entitled to grant (and does so grant) the Contractor additional NNDR Relief in respect of the [Facility/Facilities] and/or where the total amount of NNDR payable in respect of the [Facility/Facilities] decreases for any other reason, then the Annual Payment shall be adjusted in accordance with clause 69 (Financial Adjustments) by the same amount as the amount of relief from NNDR granted and/or the reduction in NNDR liability.

NNDR Failure

Where NNDR Relief is not granted or is lost, or where the percentage of NNDR Relief is changed from or different to that assumed in the Base Case, so as to mean that additional NNDR is payable by the Contractor [or Leisure Operator], or where an alternative structure and/or form of entity is implemented pursuant to paragraph 5 (Alternative Structures), due in each case to any NNDR Failure, the Annual Payment shall not be adjusted in respect of the NNDR Relief not being granted or being lost and the increase in NNDR applicable to the [Facility/Facilities] shall as a result of such lack of or loss of relief be for the account of the Contractor.

NNDR Challenges and Appeals

If the Authority shall require (acting reasonably) the Contractor shall [or shall procure that the Leisure Operator shall] challenge or appeal any decision of the Billing Authority in respect of NNDR in relation to [the Facility] [any of the Facilities] or otherwise seek any rebates, revaluations or other lawful methods of reducing the NNDR payable (other than by way of the Contractor [or Leisure Operator] applying for NNDR Relief in the normal course of events pursuant to paragraphs 3 and 4 of this schedule, to which paragraphs 2 to 7 shall apply), in which case the Contractor shall agree its proposals in advance with the Authority (both parties acting reasonably) and shall use its reasonable endeavours to succeed in any such challenge, appeal, rebate, revaluation or reduction. The Authority shall bear all reasonable and proper third party costs and disbursements properly incurred by the Contractor [or Leisure Operator] provided the Authority gives prior written approval for such costs and disbursements.

If the amount of the NNDR is varied (including for the avoidance of doubt retrospectively) as a result of any challenge, appeal or other action taken pursuant to paragraph 8, then the Annual Payment shall be adjusted in accordance with clause 69 (Financial Adjustments) so as to put the Contractor in no better and no worse a position than if the relevant variation had not been made.

Costs

Where a party is entitled to be reimbursed its reasonable costs pursuant to this Schedule 27 (NNDR), it shall issue an invoice in respect of such costs to the other party with such information that may be reasonably required to verify such costs. The relevant party shall pay the amount of any such invoice submitted to it within twenty (20) Business Days of its receipt.

SCHEDULE 28

SITE PLAN[S]

SCHEDULE 29

HEADLEASE[S]

Dated                         20[ ]

[[          ] COUNCIL]

and

[CONTRACTOR]

Lease of [                      ]

| LR1. Date of lease | [ ] |
| --- | --- |
| LR2. Title Number(s) | LR2.1 Landlord's title number(s) [ ] LR2.2 Other title number(s) None |
| LR3. Parties to this lease | Landlord [ ] Tenant [ ] Other parties None |
| LR4. Property | In the case of a conflict between this clause and the remainder of this lease then, for the purposes of registration, this clause shall prevail. Refer to the definition of Premises in clause 1 of this Lease. |
| LR5. Prescribed statements etc. | LR5.1. Statements prescribed under rules 179 (dispositions in favour of a charity), 180 (dispositions by a charity) or 196 (leases under the Leasehold Reform, Housing and Urban Development Act 1993) of the Land Registration Rules 2003. None LR5.2 This lease is made under, or by reference to, provisions of: None |
| LR6. Term for which the Property is leased | The term as specified in this lease at clause 1 ("the Term") |
| LR7. Premium | None |
| LR8. Prohibitions or restrictions on disposing of this lease | This lease contains a provision that prohibits or restricts dispositions. |
| LR9. Rights of acquisition etc. | LR9.1 Tenant's contractual rights to renew this lease, to acquire the reversion or another lease of the Property, or to acquire an interest in other land None LR9.2 Tenant's covenant to (or offer to) surrender this lease None LR9.3 Landlord's contractual rights to acquire this lease None |
| LR10. Restrictive covenants given in this lease by the Landlord in respect of land other than the Property | None |
| LR11. Easements | LR11.1 Easements granted by this lease for the benefit of the Property The easements as specified in Schedule 2 of this lease. LR11.2 Easements granted or reserved by this lease over the Property for the benefit of other property The easements as specified in Schedule 1 of this lease. |
| LR12. Estate rentcharge burdening the Property | None |
| LR13. Application for standard form of restriction | The parties to this lease apply to enter the following standard form of restriction None |
| LR14. Declaration of trust where there is more than one person comprising the Tenant | None |

date

PARTIES

(1)	[                                            ] of [                                                                      ] (the "Landlord");

(2)	[                                            ] (registered under company registration number [                              whose registered office is at [                                                                                ] (the "Tenant").

IT IS agreed as follows

- DEFINITIONS

The following expressions shall where the context so admits have the following meanings:

"1954 Act"

The Landlord and Tenant Act 1954;

"Authorised Use"

Use for the purposes prescribed under the Leisure Agreement;

"Conducting Media"

All pipes, wires, cables, sewers, tanks, cisterns, pumps, ducts, drains and other service conducting media now or at any time during the Term [in, under, over or on the Retained Land  and] serving the Premises and other adjoining land whether for gas, foul and surface water drainage, water, electricity, telephone, telecommunications or any other service to the Premises;

"this Lease"

This deed as varied or supplemented by any document which is supplemental to this deed;

"Leisure Agreement"

The agreement (and any agreement made supplemental to or in variation thereof from time to time) entered on today's date between (1) the Landlord and (2) the Tenant relating to the provision of [a] leisure centre[s] with ancillary uses at the Premises;

["Leisure Operator"

[insert name and company number];]

"Plan"

The plan annexed;

"Planning Acts"

The Town and Country Planning Act 1990 (as amended), the Planning (Listed Buildings and Conservation Areas) Act 1990, the Planning (Hazardous Substances) Act 1990 and the Planning (Consequential Provisions) Act 1990 and all secondary legislation including but not limited to the Town and Country (General Permitted Development) Order 1995;

"Premises"

The land and buildings at [                  ] shown [edged red] on the Plan together with all buildings, additions, alterations, improvements, and landlord's fixtures and fittings at the same from time to time as the same forms part of the land registered at the Land Registry under title number [                       ];

["Retained Land"]

[The adjoining or neighbouring land of the Landlord being the land registered at the Land Registry under title number [           ] but excluding the Premises and a copy of the title plan to title number [        ] is attached to this Lease];

"Services"

Foul and surface water, drainage, gas, electricity, telephone, telecommunications and other services to or on the Premises [and the Retained Land];

"Term"

The term of years from and including the date hereof and terminating on the [       ] day of [                         ] 20[       ]  being the Expiry Date as defined in the Leisure Agreement;

["Underlease"

the underlease relating to the Premises to be granted by the Tenant to the Leisure Operator in the agreed form;]

"Yearly Rent"

One pound (£1) per annum (if demanded).

INTERPRETATION

The expression "the Landlord" shall include the person for the time being entitled to the reversion immediately expectant on the determination of the Term while the expression "the Tenant" shall include the Tenant's successors in title and assigns.

Subject to and without prejudice to clause [56] (Change in Law) of the Leisure Agreement, in this Lease references to any statute or statutory provision shall be deemed to refer to any statutory modification or re-enactment for the time being in force whether by statute or any directives and regulations (intended to have direct application within the United Kingdom) adopted by the Council of the European Communities.

The headings are inserted for convenience only and shall be ignored in construing the terms and provisions of this Lease.

References in this Lease to any clause or sub-clause, schedule or paragraph of a schedule without further designation shall be construed as a reference to the clause, sub-clause, schedule or paragraph of the schedule to this Lease so numbered.

Where there is any inconsistency between the terms of the Leisure Agreement and this Lease the Leisure Agreement shall prevail.

DEMISE AND RENT

In consideration of the rents and covenants on the part of the Tenant reserved and contained in this Lease the Landlord DEMISES to the Tenant with full title guarantee ALL THOSE the Premises TOGETHER WITH the rights set out in Schedule 2 EXCEPTING AND RESERVING nevertheless unto the Landlord the rights and matters set out in Schedule 1 TO HOLD the same to the Tenant for the Term but determinable as provided later in this Lease YIELDING AND PAYING the Yearly Rent throughout the Term if and when demanded.

TENANT'S COVENANTS

The Tenant covenants with the Landlord as follows:

To Pay Rent

To pay the Yearly Rent reserved in clause 3.

Signs

Save where necessary to comply with its obligations under the Leisure Agreement not to affix, place or exhibit or permit or suffer to be affixed, placed or exhibited to or upon the exterior of any part of the Premises or to or through any windows or to or upon any boundary wall rail or fence at the Premises any sign, placard, poster, signboard or other advertisement save as may have been previously approved in writing by the Landlord such approval not to be unreasonably withheld or delayed.

Planning

Subject to the terms of the Leisure Agreement not to do anything in breach of the Planning Acts and to give as soon as reasonably practicable full particulars to the Landlord of any notice, proposal or order issued under the Planning Acts in respect of or affecting the Premises.

User

Not to use or permit or suffer the Premises to be used otherwise than for the Authorised Use.

Notices

To transmit as soon as reasonably practicable to the Landlord the original or a full and accurate copy of any notice concerning the Premises which is received by the Tenant.

As soon as reasonably practicable to give notice to the Landlord upon becoming aware of any defect or need of repair or renewal arising to the Premises which might result in the Landlord becoming liable to third parties by reason of the provisions of the Defective Premises Act 1972.

Alienation

[Subject to clause 4.6.2:]

not to assign, underlet, charge, part with the possession or share the possession, use or occupation of the whole or any part or parts of the Premises nor enter into a binding agreement to do any of the same;

[the Landlord consents to the Tenant granting the Underlease to the Leisure Operator].

To Yield Up

To yield up the Premises in accordance with the provisions of the Leisure Agreement provided that the Landlord may treat as abandoned by the Tenant any property not removed by the Tenant prior to the expiration of the Term and may as agent of the Tenant (and the Landlord is hereby irrevocably appointed by the Tenant to act in that capacity) arrange for the removal and destruction or sale of the same after having given the Tenant at least 28 days' prior written notice of its intention to carry out such removal and destruction and having given the Tenant reasonable opportunity within such notice period to remove any such property.

LANDLORD'S COVENANT

The Landlord covenants with the Tenant that the Tenant shall and may peaceably and quietly hold and enjoy the Premises during the Term without any interruption by the Landlord or any person rightfully claiming under or in trust for the Landlord.

PROVISOS AGREEMENTS AND DECLARATIONS

PROVIDED ALWAYS and it is hereby expressly agreed as follows:

Remedies

Any breach of the covenants and obligations in this Lease by the Tenant shall be dealt with by way of clause 6.2 and the remedies specified in the Leisure Agreement.

Early Termination of the Term

If the Leisure Agreement is terminated or determines for any reason in accordance with the terms of the Leisure Agreement then this Lease shall automatically determine on the same date without any further notice being served under this Lease but without prejudice to any claim by either party against the other in respect of any antecedent breach of any covenant or condition contained in this Lease and on such determination it shall be lawful for the Landlord at any time thereafter to re-enter the Premises or any part of the Premises in the name of the whole.

No implied Rights

Save for the rights expressly granted nothing in this Lease shall by implication of law or otherwise operate to confer on the Tenant any easement, right or privilege whatsoever over or against [the Retained Land or] any other property of the Landlord which might in any way restrict or prejudicially affect the future rebuilding alteration or development of [the Retained Land or] such other property.

Security of Tenure - Exclusion of sections 24 to 28 of the 1954 Act

The parties confirm that before the Tenant became contractually bound to enter into the tenancy created by this Lease:

the Landlord served a notice on the Tenant, as required by section 38A(3)(a) of the 1954 Act applying to the tenancy created by this Lease; and

[the Tenant] / [name of declarant who was duly authorised by the Tenant to do so] made a [statutory] declaration dated [		] in accordance with the requirements of section 38A(3)(b) of the 1954 Act.

The parties agree that the provisions of sections 24 to 28 of the 1954 Act are excluded in relation to the tenancy created by this Lease.

Notices

The service and receipt of notices shall be undertaken in accordance with the terms of the Leisure Agreement.

Contracts (Rights of Third Parties) Act 1999

A person who is not a party to this Lease shall not have any rights under or in connection with this Lease by virtue of the Contracts (Rights of Third Parties) Act 1999.

Landlord and Tenant (Covenants) Act 1995

This Lease creates a new tenancy for the purposes of the Landlord and Tenant (Covenants) Act 1995.

Warranty on Use

Nothing in this Lease constitutes or shall constitute a representation or warranty that the Premises may lawfully be used for any purpose allowed by this Lease.

Local Authority Landlord's Capacity and Powers

The Landlord enters into this Lease solely in its capacity as a landowner in respect of the Premises and not in any other capacity. Nothing in this Lease shall restrict the Landlord's powers or rights as a local authority, local planning authority or statutory body to perform any of its statutory functions.

This Lease is executed as a deed and is delivered on the date stated at the beginning of this Lease.

SCHEDULE 1

EXCEPTIONS AND RESERVATIONS

- [The free and uninterrupted passage and running of Services to and from the Retained Land in and through the Conducting Media which now are or may at any time hereafter during the Term be in, upon, through, under or over the Premises.]

[The right to maintain in, on, through, under or over the Premises at any time during the Term any easements or services for the benefit of the Retained Land, the right to connect into any Conducting Media on the Premises and the right to install and construct Conducting Media at the Premises to serve any part of the Retained Land.]

The right at any time during the Term in accordance with the conditions for such entry included within the Leisure Agreement or otherwise (if no such conditions apply) at reasonable times and after reasonable prior written notice (except in an emergency when no notice shall be required) to enter upon the Premises to:

[inspect, maintain, relay, repair, replace or renew or execute any works whatever to or in connection with any of the Conducting Media easements or Services referred to in paragraphs 1 and 2 of this Schedule 1;]

[carry out any cleaning and or maintenance of the Landlord's Retained Land; or]

exercise any of the rights granted or reserved to the Landlord by this Lease or the Leisure Agreement,

the Landlord exercising such rights only if such works cannot reasonably be effected without such entry and causing as little inconvenience as possible and remedying any physical damage so caused to the Tenant's reasonable satisfaction.

[All liberties, privileges, easements, quasi-easements, rights and advantages whatsoever now held or enjoyed with or appertaining or reputed to appertain to any other part of the Retained Land provided always that those matters or any of them reserved pursuant to this paragraph do not materially interfere with the Tenant's proper performance and exercise of its obligations and rights contained in the Leisure Agreement.]

[The right to deal in any manner whatsoever with the Retained Land and to erect, maintain, rebuild or alter or suffer to be erected, maintained, rebuilt or altered thereon any buildings whatsoever.]

[The right of support and protection by and from the Premises for adjoining buildings (whether now in existence or erected during the term) situated on the Retained Land.]

The mines and minerals under the Premises and the airspace above the buildings on the Premises.

SCHEDULE 2

RIGHTS GRANTED TO THE TENANT

- [The right of support and protection by and from the Retained Land for the Premises and buildings (whether now in existence or erected during the term) situated on the Premises.]

[The free and uninterrupted passage and running of Services to and from the Premises in and through the Conducting Media which now are or may at any time hereafter during the Term be in, upon, through, under or over the Retained Land.]

[The right at any time during the Term in accordance with the conditions for such entry included within the Leisure Agreement or otherwise (if no such conditions apply) at reasonable times and after reasonable prior written notice (except in an emergency when no notice shall be required) to enter upon the Retained Land to:

inspect, maintain, relay, repair, replace or renew or execute any works whatever to or in connection with any of the Conducting Media, easements or Services referred to in paragraph 2 of this Schedule 2;

carry out any cleaning and or maintenance of the Premises; or

exercise any of the rights granted or reserved to the tenant by this Lease or the Leisure Agreement,

the Tenant exercising such rights only if such works cannot reasonably be effected without such entry and causing as little inconvenience as possible and remedying any physical damage so caused to the Landlord's reasonable satisfaction.]

SCHEDULE 30

HANDBACK

- Without prejudice to the provisions set out in clause 23.1.5 and clause 45 of this Agreement, upon notification of this Agreement terminating, howsoever caused, or twelve months prior to the Expiry Date, the parties will meet to discuss a timetable for drawing up and will draw up a handover plan covering the performance of the obligations of both parties during the handover period. In any event, the Contractor will, at no cost to the Authority, provide such cooperation, information and assistance to the Authority and/or as may be reasonably required by the Authority to transfer and to enable a smooth migration of the Services being supplied by the Contractor including enabling the Authority and/or its New Contractor to perform services the same as or substantially the same as the Services in a similar manner as required under this Agreement.

- The Contractor and the Authority shall use all reasonable endeavours to ensure all appropriate arrangements are put in place to give effect to the transition of the Services to the Authority or a New Contractor.

- The Contractor agrees that if it is requested by the Authority it shall use all reasonable endeavours to assign or novate any then existing contracts which the Contractor has entered into with third parties in connection with the provision of the Services including the leasing of any equipment used in the delivery of the Services to the Authority or to any New Contractor.

- The Contractor shall not [(and shall procure that the Leisure Operator shall not)] in the twelve month period prior to the Expiry Date (or such period remaining where a Termination Notice has been issued) (the "Applicable Period") in relation to the Services except with the prior written consent of the Authority, such consent not to be unreasonably withheld or delayed:

incur any expenditure or enter into any commitments other than in the ordinary course of trading;

dispose of or agree to dispose of or grant any option in respect of any part of the Assets other than stock in the ordinary course of trading;

materially vary the terms of any contracts with any provider of goods and/or services already entered into;

enter into any long-term (being 12 months or longer), unusual or abnormal contract or commitment;

enter into any leasing, hire purchase, contract hire or other agreements or arrangements for payment on deferred terms;

grant or issue or agree to grant or issue any mortgages, charges, debentures or other securities for money or redeem or agree to redeem any such securities or give or agree to give any guarantees or indemnities or, without prejudice to the foregoing generality, create or permit to subsist any other encumbrance over all or any of its present or future incomes or assets affecting this Agreement and/or the provision of the Services;

permit any of its insurances to lapse or do anything which would make any policy of insurance void or voidable;

in any way depart from the ordinary course of its day to day business either as regards the nature or scope or the manner of conducting the same;

pay any fees or commissions to any persons other than fees payable on arm's length terms to third parties who have rendered bona fide service or advice required in the ordinary course of business;

release, waive or modify any warranty or guarantee given by any supplier of goods or services;

cause or permit any item comprised in the records relating to the Services to be removed or destroyed or any programs or data held on the computer systems of the Contractor and relating to the Services to be removed or deleted except for the deletion of Personal Data where required to ensure compliance with the DPA or for the efficient running of the computer system in question after satisfactory back-up copies have been made and securely stored off-site;

terminate the employment of any of the Relevant Employees for any reason whatsoever without first obtaining the consent of the Authority to such termination save where, in the reasonable opinion of the Contractor, termination is justified for cause due to the actions of any such of the Relevant Employees;

alter or change in any way any of the terms and conditions of employment of any of the Relevant Employees whether with or without the consent of the Relevant Employees other than for wage or salary awards which are in line with those offered generally for similar individuals within the Contractor's workforce or as is required by law (for the avoidance of doubt, the Contractor will provide upon request by the Authority evidence that any such wage or salary award is in line with those offered generally for similar individuals);

relocate or assign to new duties any of the Relevant Employees, or assign to the provision of the Services any employee not so assigned at the commencement of the Applicable Period, or increase to any significant degree the proportion of working time spent on the Services by any such employee, without the prior written consent of the Authority, such consent not to be unreasonably withheld or delayed; or

make any other alterations to the structure or composition of the Relevant Employees which are intended to or which may preclude the application of the Regulations upon the resumption of service by the Authority or another service provider.

- In the event that the Authority fails to respond within [five (5)] Business Days of the Contractor's request for consent, the Authority shall be deemed to have given consent.

THIS AGREEMENT is executed as a deed and delivered on the date stated at the beginning of this Agreement.

THE COMMON SEAL of [NAME	)

OF LOCAL AUTHORITY] was 	)

affixed in the presence of:	)

Authorised Signatory

EXECUTED AS A DEED by the Contractor acting by a Director

and its Secretary/two Directors:

Director

Director/Secretary

# Footnotes

This Agreement has been drafted on the basis of an SPV structure with the Contractor contracting with the Authority and then passing on its obligations to a Building Contractor, FM Contractor and Leisure Operator. If a different structure is used the drafting will need to be updated as appropriate and notes have been included accordingly.

This will depend on the frequency of payment of insurance premiums.

Such documents should be annexed to this Agreement.

Depending on the nature of the Site(s), the parties may wish to consider the use of an "Access Protocol".

The Authority may wish to procure Asbestos Survey[s] early in the procurement process to assess the risk profile of the Project and, on the basis of the survey undertaken, to specify the risk to be assumed by the Contractor. In this scenario, it is envisaged that the surveyor will be engaged by the Authority on approved terms and will provide a warranty to each of the Contractor and its Building Contractor. This Agreement has been drafted on this basis.

Include reference to Holdco if relevant.

This threshold will need to be calibrated depending on the level of payments and the nature of the scheme.

This should list the consents that the Contractor cannot obtain but the Authority can obtain. Therefore the Authority should accept an obligation to obtain them.

These are the conditions the Contractor cannot satisfy, but the Authority can satisfy. Therefore the Authority should accept an obligation to satisfy them.

Where on a project specific basis there are particular reasons to do so (for example, where the Authority shares the use of the Site[s]), other persons for whom the Authority is responsible should be added here.

This definition should not be used if the only data in Schedule 11 is employee information. No warranty is to be given in respect of employee information because the cost adjustment mechanism is being used – see clause 29.4 (Employment Costs).

Authorities may wish to consider requiring the provision of a bond if a parent company guarantee is not available from the Contractor. Whether a bond is appropriate should be assessed on a value for money basis, and also in light of the covenant strength of the Contractor/Leisure Operator.

The Authority should procure a Buildings Survey of each Site where buildings are being retained or refurbished at an early stage in the procurement process to enable the Contractor to assess the risk profile of the Project. These surveys should form part of the information issued with the tender documents. The surveyor should be engaged by the Authority on approved terms and should provide a warranty to each of the Contractor and its Building Contractor.

Authorities will need to consider carefully in light of each project's particular ownership structure, including how far up the ownership chain the Authority would require the change of ownership provisions to extend and whether limited partnerships or other non-corporate entities are used in the Contractor's ownership structure.

Any information or classes of information that the parties agree should be treated as Commercially Sensitive Information should be included in Part 2 of Schedule 21 (Commercially Sensitive Material). The Authority should be mindful of guidance on this issue when agreeing which information should be categorised as commercially sensitive. This can cover specific bid information (for specific periods) or other types of generic information but broad blanket categorisations are not appropriate.

This limb of Contractor Default is only relevant where the Start on Site Date is a key date for the Authority.

The levels of the trigger are project-specific and subject to calibration of the Payment and Performance Monitoring System.

The levels of the trigger are project-specific and subject to calibration of the Payment and Performance Monitoring System.

Where there are Post Completion Works, Authorities should consider whether to set a longstop date for those works. This will generally depend on the nature and extent of those works.

Include details of the procurement documents issued.

From 1 October 2012 the treatment of those Eligible Employees who are not members of the LGPS but are eligible to join the Scheme has changed as a result of automatic enrolment legislation. Prior to 1 October 2012, Eligible Employees who were eligible for membership of the LGPS under the terms of an admission agreement were not automatically admitted to the LGPS. If they wanted to join they had to elect to do so. Following the introduction of the automatic enrolment legislation, and as reflected in the LGPS Regulations, all Eligible Employees who transfer to a Contractor or Sub-Contractor will have to be automatically enrolled in the LGPS. So Eligible Employees who are already members of the LGPS will continue to be members and those Eligible Employees who are eligible to join but have not yet done so must also now be automatically enrolled in the LGPS on transfer to their new employer. Contractors should bear this in mind as this latter category of Eligible Employees now has to be included in pricing models as they could choose not to opt out of the LGPS once automatically enrolled following the transfer.

23 Whether or not this is used will depend on whether a "closed" or "open" agreement is intended. This limb will be required if the agreement is to be "open", that is, LGPS access will be offered to eligible individuals who are employed by the Contractor on the Services at a later date.

To be included if the Authority includes such a strategy in the Facilities Requirements (it is not currently a part of the template Facilities Requirements).

Authorities to include the appropriate definition. There is currently no separate list of Handback Requirements in the template Services Specification. If this position is left unchanged the latter suggested definition should be used. If Authorities do create a separate list of "Handback Requirements, care should be taken so as not to create a separate/different standard to the overall obligations set out in the Agreement.

Whether or not this definition is used will depend upon the financial structure which is adopted. If there is no one hundred per cent (100%) holding company used as part of the project structure then this definition should not be used. References to "Holding Company" however must remain.

Authorities may wish to invite proposals from bidders over different review periods and associated costing implications, to assist in determining which review period is likely to deliver best value for money. If there is a different period "Insurance Review Period" will also need to be updated.

Planning permission(s) to be defined on a project-specific basis by reference to the specific detailed/full planning permission(s) only, excluding any revised or replacement planning permissions.

Where a SPV structure is used, it is suggested that the period of lock in is to be one year after the end of the construction period (including demolition and landscaping). Therefore, where demolition and/or landscaping are to occur after the final Services Availability Date, the definition above will need to change to address this.

The period up to the Longstop Date may depend on the complexity of construction and to allow for a sufficient buffer period for the shorter longstop date under the Building Contract.

If there are no Initial Services then this will need to refer to the Services Period as opposed to the Contract Period.

Suggested drafting to be used where there is post Services Availability Works e.g. demolition.

The Authority will need to specify the extent to which it is prepared to accept a phased handover of a particular Facility, including in relation to demolition. If this concept is followed then this defined term will need to be used. Note though that the concept of Post Completion Works will only apply to those phases of the Works other than that which constitutes Services Availability. For Services Availability, the Acceptance Certificate regime will continue to apply.

The Authority should consider whether to specify a separate longstop for any Post Completion Works.

A list of sub-contracted design packages for which a collateral warranty is required will need to be inserted.

Specify other relevant consultants.

This definition may need to be amended on a case by case basis.

In grouped leisure projects with unusually long construction phases this may not be value for money. Authorities to decide on a project specific basis if in such Projects the Contractor should bear the risk on a facility by facility basis.

This is assumed to be covered under fixed price arrangements and so not subject to variation.

If the Required Insurance contains any supplementary (i.e. non-standard) insurances for which insurance premium risk sharing is not being provided, these must also be referred to here. For instance, professional indemnity cover.

Only applicable if phased Service implementation.

Where a Site is known to be in a region of archaeological or historic interest and it may be difficult for the Building Contractor to accept flow down of the risk on a cost effective basis the Authority should consider whether the discovery of fossils and antiquities should be a Relief Event.

This definition will only be required where Initial Services will be provided under the Agreement.

This needs to be considered by Authorities on a project specific basis as it may not be a requirement of the Authority to comply with all Sport England Guidance in this respect. Sport England recognises that full compliance with its guidance may not be appropriate on all Projects. Please contact your local Sport England representative to discuss what is required and/or necessary for your specific Project.

To be defined on a project specific basis.

This may need amendment depending on the structure of the consortium. The FM Contractor will also need to be given rights of access.

This should also include, where appropriate, demolition and landscaping and any other works to be carried on following the Services Availability Date. The optional inclusion of the reference to "Post Completion Works" is intended to pick this up.

Where there are Post Completion Works, then consideration needs to be given to incorporating these within the Works Period if relevant.

Authorities may wish to include a more structured process for notification/discussion/agreement regarding any potential extension.

This wording should be included where there is no Initial Phase or Initial Services being provided.

Additional warranties may be required from other leisure sub-contractors depending on the structure adopted.

This time period has been included in the event that there are consultants providing warranties whose appointments have not been finalised at the date of close. In all other circumstances the warranties should be required to be in place as at the date of close.

See clause 18.7 (Defects and Asbestos) for the recommended approach to the risk allocation in respect of defects and asbestos. These surveys will only be necessary where buildings are being demolished and/or refurbished. It is anticipated that the surveyor will, depending on the timing of the survey, be engaged by the Authority and/or the Contractor but will, if employed by the Authority, provide a warranty to the Contractor and its Building Contractor. If not, clauses 18.7.1.2 and 18.7.4.2 should be deleted.

In the event that any soil survey or similar is commissioned by the Authority, the Authority should try to ensure that warranties will be available for the Contractor and Sub-Contractors.

This warranty will only be relevant if an SPV structure is being used.

The undertakings in clauses 5.2.5, 5.2.6 and 5.2.7 are only to be included if an SPV structure is used.

Schedule 13 to be completed on a Site specific basis.

The value of environmental warranties/indemnities will need to be reviewed on a project specific basis.

This will depend on project specific requirements. The Authority should conduct surveys in advance (see footnote to clause 18.7 (Defects and Asbestos)). If subsurface conditions cannot be investigated below an existing footprint, it may be value for money for the Authority to retain that particular risk.

The term of the leases should be fixed to ensure that they do not extend beyond the Expiry Date.

This obligation is included so as to link the two documents – i.e. Agreement and Head Lease so as to allow breach of this provision by the Authority to be treated as a Compensation Event.

Whether underleases and, indeed, sub-underleases are required will depend on the successful bidder's structure. The structure may also include the granting of licenses to relevant parties.

This provision may be needed where there is a period between execution of the contract and the building contractor taking possession of a site.

If an Authority requires the Contractor to provide Initial Services to the Existing Facilities during construction, it should identify the budget available and service standards required. Authorities should consider whether the Leisure Operator or the FM Contractor ought to be barred from providing Services if performance is sufficiently poor during Initial Services, or whether it only ought to be barred from providing Initial Services. If the Authority requires Initial Services to be provided to parts of the Facilities handed over early, this should be dealt with in the Payment and Performance Monitoring System to allow for phased handover.

Authorities should determine what policies are to be included in Schedule 15 (Authority's Policies).

For instance, if recycled materials are permitted.

See Procurement Toolkit for more details about the CRC Scheme and its reference in this Agreement.

If the Authority has a particular requirement that must be complied with during the Works Period (e.g. if there must always be one of the Existing Facilities open to the public throughout the Works Period), this should be referred to here.

Where it is a Surplus Annual Payment project, Authorities may wish to allow for early completion and commencement of Services

Definition of Authority's Representative to be defined on a Project specific basis. The Authority may wish to refer to an individual by name or make reference to a job title. The Authority's Representative is sometimes different during the Construction and Services periods.

Again, the Contractor may wish to refer to its representative by name or by reference to their position.

Authority to consider whether it would want the Contractor to prepare and update a risk register in relation to the Works.

To the extent it is not practical for the Contractor to investigate areas of the Site(s) (for example, the areas are under existing buildings) then clause 18.2.3 (Site Matters) will provide relief. The Authority should bear any additional costs arising out of the unforeseen conditions in areas which the Contractor cannot investigate and which cannot be reasonably identified by the Contractor. Areas of the Site(s) to which this carve-out applies should be clearly identified in the Agreement. As set out in PF2 "ordinarily, where land is concerned, ground conditions risk should be borne by the Contractor (with the benefit of surveys provided to it which it can rely on). Where however it is not feasible to get surveys done (eg where it is not possible to survey for contamination under the footprint of a building or to check for possible contamination coming onto the Site[s] from an adjoining property not owned by the Authority) it may be better value for money for the Authority to bear or share such risk".

Delete where no such surveys exist.

Authorities to consider whether to extend Compensation Event protection to any Post Completion Works.

The Contractor's responsibility for off-site contamination coming on site is limited to the extent of recovery of damages from the third party causing the contamination on the basis the Contractor is in the same position as the Authority if it was the occupier of the Facility.

The Contractor will be granted relief for a reasonable but limited period but will be required to make good and deal with any such off Site Contamination.

Authority may consider "name-borrowing" provisions in respect of contamination from third party sites, and this has been included here as specimen drafting. Concerns are sometimes raised that the Contractor does not have the necessary right in land to take certain types of action against third party polluters. This drafting is a way of alleviating the problem.

The Authority remains responsible for Contamination coming from Authority owned/occupied land adjacent to/near the Site[s].

Consider each Planning Condition and decide which Party should be responsible for each one. Those that the Authority must discharge are termed Authority Planning Conditions and are listed in a schedule. Where the Authority needs the Contractor's (or a Contractor Related Party's) assistance to discharge an Authority Planning Condition (NB the actual party fulfilling the APC will be the Local Authority), the extra wording in brackets should be added. Where the Parties are aware, during the bid process, that certain Planning Conditions will be imposed, they should agree the drafting prior to contract award.

The time limit must be realistic and must take into account the likely time required for the Judicial Proceedings to be heard and for any appropriate action agreed locally to be taken including for example, challenging the Judicial Proceedings and any Judicial Proceedings Action and to apply for and obtain a new/revised planning permission.

This clause will only be appropriate where buildings are being refurbished and/or if there are existing facilities.

The Authority may identify in its tender documents how it has interpreted the survey results in relation to parts of the Buildings and how they may apply across the remainder of the Buildings forming part of the Project. Alternatively, it may require the Contractor to assume an agreed scope of remediation works given the results of the survey. Discovery of additional remedial works outside the survey or the agreed scope shall be framed as an additional Compensation Event.

The Contractor should take the risk on scope of Buildings Surveys: although one will be provided by the Authority, the Contractor's experience will inform whether it carries out further surveys prior to the bid date, which also become listed "Buildings Surveys". This risk allocation for scope of surveys applies unless the Authority does not allow access for the Contractor to carry out further surveys. This risk allocation does not apply to Asbestos Surveys – the scope of the named asbestos surveys is a matter for the Authority (other than as set out just below). Those surveys will in nearly all cases be the level 2 surveys. It is only where an existing facility is empty prior to close that the Contractor or the Authority may carry out level 3 asbestos surveys prior to close, and then those surveys are listed in the definition of Asbestos Surveys. In those circumstances the Contractor should take scope risk, see footnote 87.

This is included as the term Defect implies Defects which are already present (i.e. latent defects) but this is not explicit. Obviously, the Contractor should not be able to claim a Compensation Event where it has caused the Defect.

This clause will only be appropriate where buildings are being demolished and/or refurbished and/or if there are existing facilities.

Only to be used where the Contractor is responsible for scope of Asbestos Surveys, i.e. where it carries out Level 3 surveys prior to close. See footnote 84.

Where early completion is permitted the parties may decide to allow early Services Availability and payment of the Annual Payment.

On some schemes, subsequent demolition of the old estate is required once the new Facility is constructed. This can be dealt with in several ways and is for the Authority to best determine. On Deficit Annual Payment schemes, one method could be to delay paying the full Annual Payment until such time as the demolition and site clearance have been conducted. On Surplus Annual Payment schemes, there could be rights included for the Authority to step in and do so and recover its costs should there be a failure by the Contractor to demolish existing structures within agreed periods of time. If substantial demolition works are required the Authority may want to agree a programme for demolition works that is aimed at minimising disruption to the provision of the Services. Two alternate forms of drafting are set out above, one for the situation where the demolition works will form part of Post Completion Works and one where the demolition may be more simple and smaller scale.

To be used where no LADs are available.

Authorities may wish to seek LADs but they must be a genuine pre-estimate of loss. Generally, insistence on LADs without a project specific reason is unlikely to offer value for money.

This needs to be considered by Authorities on a project specific basis as it may not be a requirement of the Authority to comply with Sport all England Guidance in this respect.

On the basis surveys are intended to deal with material breach of maintenance obligations it is considered reasonable that there should be a restriction on how often this right may be exercised. For example it would not be considered reasonable for an Authority to require suveys every three months. This does not restrict the Authority from inspecting itself or from exercising rights it has under the Payment and Performance Monitoring System.

The Authority may, in some circumstances, agree to share the cost of any survey where the costs of rectification and/or maintenance work are less than the costs of the survey in which case the cost of the survey could be shared equally between the Authority and the Contractor. This may be appropriate for grouped but not single leisure centre projects.

This maintenance plan is optional.

The lifecycle drafting is prepared on the basis that all lifecycle risk sits with the Contractor. However, there are many different lifecycle options available to Authorities. Please see separate guidance on the different options.

This clause may only relate to part of the Facility.

The Services Specification will need to reflect the preferred order of priority.

The Authority may wish to request proposals from bidders with respect to the sharing of surpluses.

The provisions will need to be amended if Interim Services are being provided.

In contracting with a person for the provision of Services, where those Services are, immediately prior to the Agreement, provided by the Authority, the Authority may if the contract would not amount to a relevant transfer under TUPE, want to ensure that the contract provides that the Contractor is required to offer employment to existing staff on the same terms and conditions as if this were a relevant transfer under TUPE. Existing staff are staff who before the Agreement was entered into, carried out or were engaged in the provision of the Services by the Authority. The clause as drafted does not apply to any existing third party contractor employees who currently provide the services. It is assumed that the risk in such case lies with that existing third party contractor if there is no TUPE transfer. Since the abolition of the Code of Practice on Workforce Matters in local authority contracting, this clause is not mandatory.

This confirms that the pensions obligations will also apply as if there had been a TUPE transfer.

The words in square brackets should only be included where there is an existing sub-contractor and the Authority has power to compel its existing sub-contractors to make these payments under any provision/indemnity or other legal entitlement it has against such sub-contractors.

As above, "Relevant Employees" should only be used where the Authority is able to recover such sums in respect of non-Transferring Employees from any sub-contractor of the Authority under any indemnity or other legal entitlement it has against such sub-contractor.

The list would normally show:

- Staff Reference Number

- Date of Birth

- Age

- Job Title

- Start Date

- Continuous Service Date

- Contracted Hours

- Gender

- Site

- Department

- NI letter (A or D)

- Scale and Point

- Salary

- Superannuation (including type of Scheme, contribution rates, length of reckonable pensionable services scheme membership etc.)

- Allowance/deduction code.

- Holiday entitlement.

- Notice entitlement.

- Enhanced redundancy pay.

- Bonus entitlement(s).

- Contractual remuneration or other benefits.

NB: this is not necessarily an exhaustive list.

The information provided by the Authority prior to financial close is almost certain to be inaccurate by the time Service Transfer occurs, if only because there are likely to be changes to the workforce in the meantime, for example because of staff turnover. The document does not, therefore, focus on the giving of warranties in support of the information given. Authorities should however allow that the Contractor's price can be adjusted in a way  which reflects the differences between the information about the Authority's workforce given to the Contractor when its bid was priced (this can be adjusted prior to financial close to reflect up to date information) and the actual workforce which the Contractor inherits.

Clause 29.4.5 allows for further adjustments to be made where information contained in the final list is incorrect.

This should be reviewed against the bidding assumptions in respect of the project.

These details are taken from the Contractor's final bid. Authorities and their advisors should ensure that sufficient details are included in bids to ensure that all the assumptions made by bidders are transparent. Otherwise, it will be difficult for Authorities to audit the adjustments which are to be made to the Annual Payment to reflect changes in the employee information in the Final Employee List.

In other words, these costs are the allowance made by the Contractor in its bid for continuing payments of salary, NI, pensions contributions, etc. to the workforce it proposes to establish to provide the Services.

These costs are the non-recurring costs of establishing the Contractor's workforce. These might include, for example, possible redundancy costs if the workforce which the Contractor expects to inherit from the Authority does not match the required profile. The drafting is reasonably wide, although it is a requirement that both parties are agreed as to the extent of, and methodology of calculating, the Reorganisation Costs, and Authorities and their advisers may wish to consider carving out some costs on a project specific basis. NB: it is assumed for the purposes of this document that any re-profiling of the workforce is carried out by the Contractor after the Service Transfer Date. If it has been agreed that the Authority will undertake this responsibility, the wording may need review.

This is how the Contractor is compensated for any mismatch between the information it was given about the workforce in the First Employee List and the correct information based on the actual workforce at the time of service transfer (as set out in the Final Employee List). It is therefore important for the Contractor that the information contained in these lists captures all remuneration and benefits that could impact on Remuneration or Reorganisation costs.

If insufficient numbers of staff to establish the Contractor's projected workforce are in place at the time of service transfer, this does not reduce the Contractor's staff costs, because additional staff will have to be recruited to fill the gaps. If there is re-profiling before the transfer at the request of the Contractor or if other changes have been included in pricing assumptions then this clause should be amended to reflect costing assumptions. NOTE: if bids have been invited on the basis that the Authority will assume costs of redundancy this clause will need to be developed to reflect the bid.

The Contractor may have made binding contractual commitments, having relied in good faith on information provided by the Authority.

This could mean that the Contractor will recover the cost of higher salaries due to successful equal pay claims brought by transferring employees. The parties should discuss and agree the risk in this regard.

The list would normally show:

Staff ref no

DoB

Age

Job Title

Start Date

Continuous Service Date

Contracted hours

Sex (M/F)

Site

Department

NI letter (A or D)

Scale and point

Salary

Superannuation (including type of scheme, contribution rates, length of reckonable pensionable service scheme membership etc.)

Allow/deduction code

Holiday entitlement

Notice entitlement

Enhanced redundancy pay

Bonus entitlement(s)

Contractual remuneration or other benefits

NB: this is not necessarily an exhaustive list.

Authorities should ensure that this obligation is passed on to the new service provider by way of contract. Given the abolition of the Code of Practice however there is no obligation to include this sub-clause 29.10.

The level of funding of the relevant pension schemes prior to the Transfer Date will need to be established by bidders. The information made available to bidders, and any assumptions made as to the level of funding of existing schemes, will need to be agreed.

The Authority may also be the Administering Authority.

Authorities to consider whether they would want a separate dispute resolution process for this issue or whether the standard Dispute Resolution provisions should apply.

Under paragraph 6, Part 3 of Schedule 2 of the LGPS Regulations, the admission body must carry out an assessment (to the satisfaction of the Administering Authority), taking account of actuarial advice, of the level of risk arising on premature termination of the provision of the service or assets by reason of the insolvency, winding up or liquidation of the admission body and that where the level of risk identified by the assessment is such as to require it, the admission body must provide an indemnity or bond to meet the level of risk identified. Where for any reason it is not desirable for an admission body to enter into an indemnity or bond the admission body will have to secure a guarantee in a form satisfactory to the Administering Authority.

This clause seeks to mirror the right of set off which must be included in the Contractor Admission Agreement under paragraph 12(c), Part 3 of Schedule 2 of the LGPS Regulations. It also permits set off for monies owed by the sub-contractor, and therefore is more favourable to the Authority.

Footnote 206 should be given consideration here. It may be possible to delete clauses 30.6, 30.7 and 30.8 if they are not applicable to the particular transaction.

The Authority should note that certification by GAD does not take account of any benefits which are payable solely as a result of the member being declared redundant, either compulsorily or voluntarily, where those benefits exceed the normal benefits available to an individual who resigns from employment at the same time. Such benefits are payable under regulation 30(7) of the LGPS Regulations. The Authority may wish to consider whether it wants to include any express provisions about the continuation of such benefits in the Agreement, either through the Contractor's Scheme or by way of compensation. If so, the Authority should consult with its professional advisers about such provisions. If such benefits are contractual, it is likely they will pass under TUPE (where TUPE applies) as clarified by the decisions in Beckmann v Dynamco Whichloe Macfarlane [2002] 64 PBLR and Martin v South Bank University [2003] 85 PBLR.

The Authority may wish to consider the extent it wishes to impose obligations on the Contractor or Sub-Contractors in respect of the discretionary benefits they may award under the LGPS (in particular where employment is terminated by reason of redundancy or in the efficient exercise of the Authority's functions). The suggested wording reflects the starting position for negotiation with the Contractor.

The Contractor may wish to exclude the Relevant Employees who transfer under TUPE from the obligations in clause 31. If the Authority is unwilling to agree to this, the Contractor may seek suitable assurances from the Authority that those Relevant Employees do not have any outstanding convictions, that all necessary checks have already been carried out and are up to date, and that they are not individuals whom the Authority will seek to exclude from the Site[s] or from carrying out the Works or Services. Note that the definition of Relevant Employees includes employees of any existing sub-contractors. Authorities may consider limiting any exclusion it is prepared to give to "Transferring Employees" (i.e. only Authority employees who transfer) unless the Authority has comfort under any provision/indemnity or other legal entitlement it has against such sub-contractors to the effect that the employees of any such sub-contractors who transfer already satisfy the requirements of clause 31.1.

Authorities should identify appropriate Authority Policies which tie in with this requirement.

Authorities may wish to make a retention from payments for the Works/require a retention bond. If so, appropriate drafting will need to be included. If Post Completion Works are to be carried out and payment for such works is also to be made, these provisions will need to be amended to refer to payment for Post Completion Works also.

"Bill in month, pay in month" regarded as providing value for money for Authorities, but it is their discretion whether to adopt this approach.

Prior to financial close this clause 43.3 (Continuing Obligations) should be reviewed and updated as necessary.

The parties may wish to allow a potential relaxation of the Handback Requirements at or around the time of the final survey in line with the principles of PF2. Such a relaxation could be actioned through the Change Protocol. The parties may also wish to consider using a retention bond rather than a retention fund, again to reflect the principles of PF2.

This is to ensure continued service provision beyond expiry or termination.

Loss of profit is specifically excluded from the definition of Sub-Contractor Breakage Costs, therefore a separate item representing profit payable in these termination scenarios has been included.

This limb has been included to allow the Contractor to recoup capital investment it may have made at the Facilities which it has not yet recouped.

This limb has been included to allow the Contractor to recover forward funding that may have been applied in the financial model which it has not yet recouped. For instance to facilitate a smoothed payment profile.

This limb has been included to take into account capital investment the Contractor may have made at the Facilities which it has not yet recouped.

This limb has been included to take into account any forward funding that may have been applied in the financial model which the Contractor has not yet recouped. For instance to facilitate a smoothed payment profile.

This limb has been included to allow the Contractor to recover capital investment it may have made at the Facilities which it has not yet recouped.

This limb has been included to allow the Contractor to recover forward funding that may have applied in the financial model which it has not yet recouped. For instance to facilitate a smoothed payment profile.

This provision has been included to allow for the scenario where the Contractor has invested sums to purchase the Assets but has not yet recouped the cost of such Assets. Whether this will be relevant will depend on the nature of the Assets for each particular project and how/when they are paid for and whether or not included in the Capital Costs.

Payment by instalments may be appropriate in certain circumstances, but bidders may take the view that payment by instalments is not appropriate, particularly for example where termination is due to previous non-payment by the Authority.

For Surplus Annual Payment schemes, the Contractor should be entitled to apply for relief from having to pay Performance Adjustments as the Authority will continue to receive the Monthly Payment and it will reduce the cost of BII cover on the basis no Performance Adjustments are payable. On Deficit Annual Payment schemes Payment Adjustments will continue to apply on the basis the Authority should not pay for a service it is not getting.

Depending on the nature of the Change in Law and level of Capital Expenditure, if the Contractor is not able to obtain funding, the Authority will need to pay against work done.

This drafting assumes that the revenue that the Authority receives is likely to be greater than the Authority's costs of operation and the Surplus Annual Payment for the step in period. If this is not the case, the drafting may need to be amended to place an obligation on the Contractor to pay the Authority the Surplus Annual Payment for the step in period less the revenue received by the Authority and the Authority's costs of operation.

Authorities should keep this exemption limited and should be mindful of FOIA and OGC guidance when agreeing what parts of the documents should be treated as Commercially Sensitive Information.

For example, any planning permission application.

Insert others if appropriate. See also clause 79 (Data Protection).

This should be the same period of time as in clause 59.10.2.1.

If the insurance structure is proposed to be different than set out in this Agreement, the indemnities should be reviewed to check that they are still appropriate with respect to the (revised) insurance structure.

A cap on liability for breach of statutory duty should only be given to a bidder if there are clear value for money benefits or it is demonstrated by the bidder that it is needed in the context of the project and its risk profile.

Advice should be taken from brokers on the insurance structure and the Authority being a co-insured.

Not to be a Required Insurance.

Authority's' insurance advisors to consider appropriate threshold.

This amount should correspond to the amount agreed under clause 61.9 (Notification of Claims).

For example, the Lloyds non marine index.

The Authority may elect to use the following alternative wording: "the Contractor shall notify the Authority of any risk becoming Uninsurable within five (5) Business Days of becoming aware of the same and in any event at least five (5) Business Days before expiry or cancellation of any existing insurance in respect of that risk."

In discussing this issue, each party shall consider the extent to which it may be deemed to be conducting insurance business, and whether it has the necessary powers and authorisations to do so.

Additional clauses 63.3.1.5 and 63.3.1.6 (Consequences) may be added at the Authority's discretion as follows:

63.3.1.5	In respect of any period between the Authority receiving notification in accordance with clause 63.2.1 (Risks Become Uninsurable) that a TPL Risk has become Uninsurable and the Authority's notification to the Contractor in accordance with clause 63.3.1.1 (Consequences) in respect of such risk, then provided it is ultimately agreed or determined that the requirements of clause 63.3.1.2 (Consequences) are satisfied in respect of the Uninsurable TPL Risk and subject to clause 63.3.1.4 (Consequences), clause 63.3.1.2 (Consequences) shall apply in respect of occurrences of the Uninsurable TPL Risk during such period unless the parties otherwise agree how to manage the risk during the period; and

63.3.1.6	clause 63.3.1.5 (Consequences) shall only apply provided the Contractor does not unreasonably materially delay (a) agreement and/or determination in accordance with the Dispute Resolution Procedure as to whether the requirements of clause 63.2.2 (Risks Become Uninsurable) are satisfied in respect of the Uninsurable TPL Risk and/or (b) meeting with the Authority to discuss the means by which the risk should be managed.

TPL Risk should be defined as 'a risk which is required to be insured under the third party liability insurance policy'.

If insurance is no longer available for a term or condition included as a Required Insurance, the parties may agree that the Annual Payment should be reduced to reflect the extent to which the insurance premium payable by the Contractor is lower than it would have been had insurance been effected for the particular term or condition. Whilst the increased risk further to unavailability of a term or condition may reside first and foremost with the Contractor, the Authority's exposure is likely to be increased, as there may be certain circumstances where the Authority bears the risk e.g. where an aggrieved party brings a claim against the Authority for an act committed by the Contractor, but insurance proceeds to cover the claim are no longer available on account of the unavailability of a term or condition. The extent to which the Authority may be exposed will depend in part on the indemnity provisions. In addition, where there is such a loss, then if the Contractor elects not to reinstate the loss then, depending on the size of the loss, it is possible that the Authority would not be able to terminate for Contractor Default, and be forced to accept instead a reduced service. Given that an Authority's potential exposure will depend on contractual provisions, some of which may be project specific, an adjustment to the Annual Payment further to unavailability of a term or condition is not mandatory. It is for the Authority to determine, in conjunction with the insurance and legal advisers, whether the Agreement should contain an Annual Payment adjustment provision.

There may be critical services that are provided by second tier sub-contractors. In these circumstances, the Authority may decide that clauses 67.2 and 67.3 should also apply to such critical services and amendments made to require Authority consent to such providers.

Project specific issue – to be discussed with bidders and financial advisers.

Authorities to consider whether notices may be deliverable by facsimile and/or email.

The Authority may wish to discuss with bidders agreeing a protocol/method statement to confirm what is permissible so as to avoid repeated similar requests for permission.

The Authority may wish to discuss with bidders agreeing a protocol/method statement to confirm what is permissible so as to avoid repeated similar requests for permission.

Sport England is considering the inclusion of drafting in relation to the data standards of the information held by the Contractor.

The template Services Specification at Appendix E of the Procurement Toolkit is intended for use at Schedule 1 Part 3 (Services Specification) of this Agreement. Authorities wishing to have Initial Services will need to prepare an Initial Services Specification reflecting their requirements.

If required.

Consider inserting details of how the daily rate of LADs has been calculated. This may be useful for evidential purposes in the event of a challenge re recoverability of LADs.

To be reviewed and updated as necessary by the Authority's technical advisors.

To be completed on a project specific basis.

This template will need to be developed alongside the payment provisions (Clause 37 (Payment during the services period)) within the Agreement and the Services Specification.

It is important to note that this template provides what is considered a best practice Payment and Performance Monitoring System. It has direct links to the template Services Specification and Agreement. Although it will require a level of on-going monitoring by the Authority, it is largely a self-monitoring system that provides the Authority with an enforceable level of control and protection in the scenario whereby there is continued poor performance by the Contractor.

There are however a number of more high level monitoring mechanisms that the Authority may choose to consider. An alternative approach replaces performance monitoring with a simple reliance on a persistent breach type mechanism coupled with a more structured service improvement plan procedure. This process relies on the issue of "Remedy Notices" “Default Notices” and “Warning Notices” by the Authority which, if enough are collected, can lead to termination. An example Default Performance Monitoring System is included in the template DBOM document – Option B of Scheule 6.

If the Authority would prefer to adopt an alternative monitoring mechanism appropriate drafting will need to be prepared and considered alongside the Services Specification and Agreement to ensure appropriate inter-relationships and cross-references between these key contractual documents

A bedding-in period should be considered where the Contractor will be responsible for providing Services at a new build or refurbished facility.

Level of multiplier to be applied to the identified critical Zones in accordance with paragraph 6.4 to be considered by the Authority

"Contract Period" is the appropriate reference if there are existing facilities and "Services Period" is the appropriate reference if facilities are being built pursuant to this Agreement.

"Commencement Date" is the appropriate reference if there are existing facilities. "Services Availability" is the appropriate reference for new facilities being built pursuant to this Agreement.

If the scheme is a deficit scheme, the Annual Payment should be expressed as a negative number. If the scheme is a surplus scheme, the Annual Payment should be expressed as a positive number.

"Commencement Date" is the appropriate reference if there are existing facilities. "Services Availability" is the appropriate reference for new facilities being built pursuant to this Agreement.

Figure to be inserted at financial close.

"Contract Period" is the appropriate reference if there are existing facilities and "Services Period" is the appropriate reference if facilities are being built pursuant to this Agreement.

Profiled figures to be inserted at financial close, where appropriate. This additional drafting is only required where a profiled Annual Payment has been agreed over the (for instance) first 1-3 years of the [Services Period/Contract Period] prior to a fixed Annual Payment for the remainder of the [Services Period/Contract Period] rather than a fixed Annual Payment, subject to indexation. For some projects a profiled Annual Payment throughout the [Services Period/Contract Period] may be more appropriate and the table should be amended to reflect the agreed payment each Contract Year.

Where the Annual Payment is linked to an assumed Services Availability Date this should be clearly set out.

Figure to be inserted by the Authority based on circa [10-50%] of the Monthly Payment. This figure will need to be reviewed in the context of the anticipated level of the Contractor's profit.

The Authority may prefer to adopt different indexation measures which reflect to a degree increases in wage inflation. Paragraph 3 would therefore need to be amended to reflect any alternative indexation approaches.

To be reviewed by the Authority, as appropriate

To be reviewed by the Authority with bidders, as appropriate. To note, the level of Performance Adjustment Points awarded should remain the same in both deficit and surplus schemes. Although Performance Adjustments are capped on a monthly basis, Performance Adjustment Points and Performance Adjustments can accumulate and lead to potential termination.

Authority to consider whether there are any Zones within the [Facility/ Facilities] that are considered critical and should therefore be prioritised from a local authority service delivery perspective so that they would attract a greater level of Performance Adjustment Points. To note, this should only relate to a small number of key Zones such as the Sports Hall and the Pool Hall.

Table to be completed by the Authority to include any Zones that are intrinsically linked, for example, outdoor pitches and external changing facilities may be Related Zones. The Authority may choose that, for certain Zones that are related to several other Zones such as changing facilities, that only a percentage of the Related Zone is accounted for, apportioned in relation to the number of Zones that are related. This will require careful calibration however.

Table to be completed by the Authority to include any Zones that are considered appropriate to be considered as Replacement Zones within the Facility

Authorities may wish to include this drafting intended to incentivise performance against the Authority’s Outcomes. If this concept is not included, the drafting in this Schedule will need to be updated accordingly, to remove reference to it.

To be reviewed by the Authority, as appropriate

In both deficit and surplus schemes the level of Performance Adjustments needs to be reasonable and strike a balance between incentivising and not being too painful for the Contractor. Performance Adjustment levels should be no more than an agreed percentage of the Contractor's profit margin and should not be seen to bite into the cost of the provision of the Services as it is recognised that the Contractor will still be incurring running/ staffing costs during any period of Facility Performance Failure and/ or Service Performance Failure for example while potentially losing revenue. The Performance Monitoring System should not be used by an Authority as a tool for generating revenue, it is intended to be a performance based form of monitoring tool. The Performance Adjustment levels will need to be calibrated appropriately based on the proposed Annual Payment. The adjustment level could be measured against the value of the leisure service to the community ie, the cost of providing the service (irrelevant of the level of income achievable for a particular Facility in a particular condition in a particular catchment) as that is what the Authority has awarded the contract to the successful contractor for.
The payment and performance monitoring system will need to be aligned to ensure that any amounts set out for adjustments in relation to poor performance are calculated in the context of being a reasonable and ascertainable loss incurred by the Authority, otherwise the mechanism may be open to challenge.

To be reviewed by the Authority, as appropriate and calibrated in line with the proposed Annual Payment

The Authority may prefer to break down the points system so that, for example, within the range of 51-100 Performance Adjustment Points the Monthly Performance Adjustment would be £xx per point and lower ranges £xx-xx per point

[Figure to be inserted by the Authority based on a percentage of the Annual Payment, as appropriate. This figure will need to be reviewed in the context of the anticipated level of Contractor's profit and the cost of carrying out the Annual Performance Standards.]

This excusing cause would only usually be relevant for an existing/ refurbished facility and not new build;

Additional project specific excusing causes may be considered appropriate by the Authority

The required timing of the reporting should be considered alongside the payment provisions drafting in the Agreement and the Authority's internal financial processes

"Contract Period" is the appropriate reference if there are existing facilities and "Services Period" is the appropriate reference if facilities are being built pursuant to this Agreement.

Table to be amended by the Authority as appropriate to reflect the Services Specification and relative service priorities from both an appropriate rectification time and financial impact perspective

This template will need to be developed alongside the Services Specification. If the Authority wishes to use this Option B, drafting amendments will need to be made to Clause 37 (Payment during the Services Period) in the main body of this contract to reflect payment of the Annual Payment only, which would need to be defined by reference to the Base Case/LOBTA.

A bedding-in period should be considered where the Contractor will be responsible for providing Services at a new build or refurbished facility.

"Contract Period" is the appropriate reference if there are existing facilities and "Services Period" is the appropriate reference if facilities are being built pursuant to this Agreement.

This excusing cause would only usually be relevant for an existing/refurbished facility and not new build;

Additional project specific excusing causes may be considered appropriate by the Authority

The required timing of the reporting should be considered and monthly reporting may be preferred.

"Contract Period" is the appropriate reference if there are existing facilities and "Services Period" is the appropriate reference if facilities are being built pursuant to this Agreement.

Table to be amended by the Authority as appropriate to reflect the Services Specification and relative service priorities from an appropriate rectification time perspective.

The Authority's legal advisers must review the Building Contract and ensure any defined terms used in this deed are identical to those used in the Building Contract.

Authority to check level of indemnity is sufficient in relation to the Works at each Facility.

If the limit of cover is "in the aggregate", the level of indemnity should be increased proportionately to ensure sufficient cover is available to equate to each and every loss.

This clause can be amended as set out below if it is required by the Building Contractor's PI insurer provided a) a letter from the PI insurer confirming this is a condition (rather than a recommendation) that such a clause is contained in the warranty is provided b) an extract of the relevant policy wording is provided and c) there is a consequential insertion of a new clause 9.2 as set out below.

Acceptable amendment to clause 5.1.5: add to the end of the clause "but only where and to the extent that such subrogated claim relates to any default and/or negligence on the part of the Building Contractor in relation to its responsibilities under the Building Contract".

Clause 9.2: "The Building Contractor acknowledges that under and in accordance with the Agreement, save where otherwise expressly stated in such agreement, the Authority has placed the entire responsibility for the design of the Works upon the Contractor and that neither the giving of any approval, consent, examination, acknowledgement, knowledge of the terms of any agreement or document nor the review of any document or course of action by or on behalf of the Authority under and in accordance with such agreement, nor the failure of the same, shall unless otherwise expressly stated in such agreement, relieve the Contractor of any of its obligations or of any duty which it may have to ensure the correctness, accuracy or suitability of the matter or thing which is the subject of the approval, consent, examination, acknowledgement or knowledge."

A new clause 9.2 (as set out in footnote 171 above) may be inserted where clause 5.1.5 is amended and acceptable evidence from the PI insurers in relation to clause 5.15 is provided.

A template novation deed is included at appendix 1 for Authorities to use if they wish.

The Authority's legal advisers must review the Subcontract and ensure that any defined terms used in this deed are identical to those used in the Subcontract.

Insert details of relevant subcontract package.

Clause 3.4 should only to be included where the Principal Building Sub-Contractor's PI insurer has provided evidence that it is a condition of the Principal Building Sub-Contractor's insurance policy that such a clause is included in the warranty. "The Principal Building Sub-Contractor's liability for losses under this Deed shall be limited to that proportion of losses which it will be just and equitable to require the Principal Building Sub-Contractor to pay having regard to the extent of the Principal Building Sub-Contractor's responsibility for the same and on the basis that the [insert names of other members of the Professional Team (as defined in the Agreement), the other Principal Building Sub-Contractors (as defined in the Agreement) and the Building Contractor] shall be deemed to have provided contractual undertakings on terms no less onerous that this Deed to the Authority in respect of the performance of their services in connection with the Works and shall be deemed to have paid to the Authority such proportion which it would be just and equitable for them to pay having regard to the extent of their responsibility provided always that the Principal Building Sub-Contractor shall not plead or reply when in defence of any claim brought by the Authority that the Building Contractor is responsible for the design carried out by the Principal Building Sub-Contractor."

The Authority's legal advisers are to check that "Project Data" and "Intellectual Property Rights" etc are appropriately dropped down into the subcontract.

Product Liability insurance may in certain circumstances be acceptable instead of Professional Indemnity Insurance. Authority to check limits of cover are appropriate for such insurance and that the necessary changes to clause 5.1.1 are correctly made.

Or such other sum as the Authority acting reasonably considers appropriate having regard to the Principal Building Sub-Contractor's trade and the nature and importance of the Subcontractor's works.

If the limit of cover is "in the aggregate", the limit of cover should be increased proportionately to ensure sufficient cover is available to equate to each and every loss.

Clauses 5.1.5 and 9.1 can be amended as set out below if it is required by the Principal Building Sub-Contractor's PI insurer provided a) a letter from the PI insurer confirming this is a condition (rather than a recommendation) that such a clause is contained in the warranty is provided b) an extract of the relevant policy wording is provided and c) there is a consequential insertion of a new clause 9.2 as set out below.

Acceptable amendment to clause 5.1.5: add to the end of the clause "but only where and to the extent that such subrogated claim relates to any default and/or negligence on the part of the Principal Building Sub-Contractor in relation to its responsibilities under the Subcontract".

New clause 9.2: "The Principal Building Sub-Contractor acknowledges that under and in accordance with the Agreement, save where otherwise expressly stated in such agreement, the Authority has placed the entire responsibility for the design of the Works upon the Contractor and that neither the giving of any approval, consent, examination, acknowledgement, knowledge of the terms of any agreement or document nor the review of any document or course of action by or on behalf of the Authority under and in accordance with such agreement, nor the failure of the same, shall unless otherwise expressly stated in such agreement, relieve the Contractor of any of its obligations or of any duty which it may have to ensure the correctness, accuracy or suitability of the matter or thing which is the subject of the approval, consent, examination, acknowledgement or knowledge."

A new clause 9.2 (as set out in footnote to clause 5.1.5) may be inserted where acceptable evidence from the PI Insurers in relation to clause 5.1.5 is provided.

Note this is a template document only.

The Authority's legal advisers to ensure that this clause 11 is included in the Subcontract.

Insert details of relevant subcontract works package.

The Authority's legal advisers must review the Appointment and ensure any defined terms used in this deed are identical to those used in the Appointment.

The following drafting for clause 3.4 may be included where the Consultant's PI insurer has provided evidence that it is a condition of the  Consultant's insurance policy that such a clause is included in the warranty:

"The Consultant's liability for losses under this Deed shall be limited to that proportion of losses which it will be just and equitable to require the Consultant to pay having regard to the extent of the Consultant's responsibility for the same and on the basis that the [insert names of Professional Team (as defined in the Agreement), the Building Contractor and Principal Building Sub-Contractors (as defined in the Agreement) shall be deemed to have provided contractual undertakings on terms no less onerous than this Deed to the Authority in respect of the performance of their services in connection with the Works and shall be deemed to have paid to the Authority such proportion which it would be just and equitable for them to pay having regard to the extent of their responsibility provided always that the Consultant shall not plead or reply when in defence of any claim brought by the Authority that the Building Contractor is responsible for the design carried out by the Consultant."

Or such other sum as the Authority and its insurance advisers acting reasonably consider appropriate having regard to the nature and importance of the Consultant's services, having checked that the limit of indemnity is sufficient for the Works at each Facility.

If the limit of cover is "in the aggregate", the level of indemnity should be increased proportionately to ensure sufficient cover is available to equate to each and every loss.

Clause 5.1.5 can be amended as set out below if it is required by the Consultant's PI insurer provided a) a letter from the PI insurer confirming this is a condition (rather than a recommendation) that such a clause is contained in the warranty is provided, b) an extract of the relevant policy wording is provided and c) there is a consequential insertion of a new clause 10.2 as set out below.

Acceptable amendment to clause 5.1.5: add to the end of the clause "but only where and to the extent that such subrogated claim relates to any default and/or negligence on the part of the Consultant in relation to its responsibilities under the Appointment".

New clause 10.2: "The Consultant acknowledges that under and in accordance with the Agreement, save where otherwise expressly stated in such agreement, the Authority has placed the entire responsibility for the design of the Works upon the Contractor and that neither the giving of any approval, consent, examination, acknowledgement, knowledge of the terms of any agreement or document nor the review of any document or course of action by or on behalf of the Authority under and in accordance with such agreement, nor the failure of the same, shall unless otherwise expressly stated in such agreement, relieve the Contractor of any of its obligations or of any duty which it may have to ensure the correctness, accuracy or suitability of the matter or thing which is the subject of the approval, consent, examination, acknowledgement or knowledge."

The Authority's legal advisers must review the FM Agreement and ensure any defined terms used in this deed are identical to those used in the FM Agreement.

The Authority's legal advisers must review the Leisure Contract and ensure any defined terms used in this deed are identical to those used in the Leisure Contract.

To be reviewed and added to by technical advisors.

This is optional. The Authority may wish to incorporate the template Partnering Charter or their own exisiting charter if relevant.

The title of "Warranted Data" should only be used for Schedule 11 if information other than employee information is to be provided by the Authority to the Contractor and which the Authority intends to warrant as true, accurate and complete under clause 6.8. If this title is not used, then references elsewhere in the Agreement to Schedule 11 will need to be amended accordingly.

The information referred to in this Schedule 11 is by way of illustration only. Consideration should be given to the employee information to be given on a project specific basis.

Background information to the LGPS Pension Scheme, including members and employers guides and booklets can be found at http://www.lgps.org.uk  if further information is required for the purposes of pricing or obtaining a GAD certificated broadly comparable pension scheme.

Note – this table will not be needed if all relevant employees are currently employed by the Authority.

Background information to the LGPS Pension Scheme, including members and employers guides and booklets can be found at http://www.lgps.org.uk  if further information is required for the purposes of pricing or obtaining a GAD certificated broadly comparable pension scheme.

This schedule should be amended on a project specific basis. The parties are encouraged to seek insurance advice on the content of this schedule.

It is recommended that the ‘summary’ worksheet of the LOBTA referenced in a number of the following definitions provides a summary of the base figures that would be required for any Net Income Benchmarking process. Rows setting out Base Modelled Income, Base Modelled Costs, Base Leisure Management Amount, Base Profit, Base Head Office Costs, Base Profit as a percentage of Income and Base Head Office Costs as a percentage of Income should be clearly identified by the Contractor at financial close based on the agreed LOBTA

Figure to be determined by the Authority

Figure to be determined by the Authority

Figure to be determined by the Authority

Figures and row references to be inserted by the Contractor at financial close based on the agreed LOBTA

"Commencement Date" is the appropriate reference if there are existing facilities. "Services Availability" is the appropriate reference for new facilities being built pursuant to this Agreement.

Figures and row references to be inserted by the Contractor at financial close based on the agreed LOBTA

Figures and row references to be inserted by the Contractor at financial close based on the agreed LOBTA

Figure to be determined by the Authority

The Utility Cost Benchmarking Procedure set out in Part 2 assumes a biennial benchmark of utility costs. The Authority may prefer to propose that a utility benchmark is carried out on an annual or three yearly basis where it is considered that different length utility contracts are available to operators. If a different assessment period is used the drafting of Part 2 of this Schedule and associated definitions will need to be updated accordingly.

"Commencement Date" is the appropriate reference if there are existing facilities. "Services Availability" is the appropriate reference for new facilities being built pursuant to this Agreement.

To be reviewed on a project specific basis

To be reviewed on a project specific basis

Row reference to be inserted by the Contractor at financial close based on the agreed LOBTA

Percentage to be inserted by the Contractor at financial close based on the agreed LOBTA

The Authority may prefer to use a seven (7) year benchmark within the Net Income Benchmarking Process set out at Part 3, however, this is less representative of typical market positions

This Utility Cost Benchmarking Procedure assumes a biennial benchmark of utility costs. The Authority may prefer to propose that a utility benchmark is carried out on an annual basis or every three years. It is recommended that utility benchmarking is based on the utility contract term available. Where possible utility purchasing should seek to be re-aligned so that it is not out of synch with the Leisure Operator’s Base Trading Account.

The Authority to consider the merits of including these additional provisions on a project specific basis

The "Commencement Date" is the appropriate reference if there are existing facilities. "Services Availability" is the appropriate reference for new facilities being built pursuant to this Agreement.

"Contract Period" is the appropriate reference if there are existing facilities and "Services Period" is the appropriate reference if facilities are being built pursuant to this Agreement

Where it is envisaged that capital works will be undertaken relating to energy consumption reducing initiatives during the [Contract Period/Services Period], it may be more appropriate to include a separate worksheet containing the target consumption levels to apply for each year of the [Contract Period/Services Period] OR where the LOBTA demonstrates that the target consumption levels for each year fluctuate across the [Contract Period/ Services Period] Table 1 is to be replaced with the following paragraph; “See the separate spreadsheet containing the target consumption levels entitled ‘Schedule 13, Part 1, Appendix 2. The figures within the spreadsheet shall apply for each year of the [Contract Period/ Services Period] for the [Facility/ Facilities]

Table to be populated by the Contractor prior to financial close

The intention is that the re-basing of the target consumption levels will occur at those new facilities that have been constructed pursuant to this DBOM contract.

The Authority may decide not to include a Net Income Benchmarking Process based on the length of the Agreement and the proposed approach to risk transfer, in which case this Part 3 and all associated definitions will not be required

The Authority may prefer to use a seven (7) year benchmark, however, this is less representative of typical market positions

Percentage to be reviewed by the Authority with Bidders in order to achieve an appropriate balance between pain and protection for both parties. This is not a set percentage but will be project specific and will depend upon the assumed project financials. The percentage figure used in the associated worked example is used for illustrative purposes only. It is important that worked examples are tested using the Contractor’s bid figures to ensure that the proposed risk share between the Authority and the Contractor is considered appropriate. The application of c(i) or c(ii) will depend on the Bidders financial model and how any increase in costs or decrease in revenue impacts on the net position in the model

See Footnote 25

See Footnote 25

Percentage to be reviewed by the Authority with Bidders, as appropriate. The percentage applied will need to take account of the percentages applied at paragraph 1.1 and having regard to the premise that any adjustment should be on a no better and no worse position as set out in clause 69. A full pass through position may not be  appropriate; as the intention is to ensure that there is an appropriate share of future income risk and that a balance between pain and protection for both parties is achieved.

See Footnote 28

"Commencement Date" is the appropriate reference for existing facilities. "Services Availability" is the appropriate reference for new facilities being built pursuant to this Agreement

It is important to note that the template worked examples are based on percentages used for illustrative purposes where the figures are to be determined on a project specific basis. The worked examples will therefore need to be amended accordingly in order to reflect the project specific figures in square brackets as amended following review by the Authority or determined by the Authority, as appropriate

The Special Benchmarking Process and all associated definitions should ONLY be included where a specific User such as a club or NGB has a rental agreement in place for dedicated use of certain Zones(s) within the Facility (or a high percentage of utilisation) and it is felt that the income associated with that club and/ or NGB (the “Key User”) represents a significant part of the total income for the Facility that would be difficult to replace

Percentage to be reviewed by the Authority with Bidders, as appropriate, and any amended percentage to be referenced throughout this Part 4

Profile of compensation to be reviewed by the Authority with Bidders, as appropriate

Percentage to be reviewed by the Authority with Bidders, as appropriate

Percentage to be determined by the Authority in order to achieve an appropriate balance between pain and protection for both parties. This is not a set percentage but will be project specific and will depend upon the assumed project financials

Percentage to be reviewed by the Authority with Bidders, as appropriate having regard to paragraph 1.7 of Part 5

Reference to either the LOBTA or Base Case to be included here and throughout the schedule

This template determines an average excess surplus based on a three year rolling look back period. The Authority may prefer to amend the look back period to allow for a longer lead in to the calculation of any average excess surplus in order to take into account any proposed capital developments and associated phasing. Alternatively a different approach could be adopted based on an annual review and share of any excess surplus. Although this has been agreed on a number of contracts it is considered less attractive by contractors who believe that an average position over a period of time provides a more accurate representation of any excess surplus, allows for annual fluctuations and does not dis-incentivise against the implementation of any initiatives that may take a number of years to stabilise.

The "Commencement Date" is the appropriate term where there are existing facilities. "Services Availability" is the appropriate term where new Facilities are being built pursuant to this Agreement

Percentage share to be determined by the Contractor as a bid back item unless a restricted procurement process is being followed in which case the percentage share is to be determined by the Authority, as appropriate. In such circumstances it is recommended that a [50/50 share] is applied. In order to encourage a proactive and positive partnership the Authority may also wish to consider the potential inclusion of additional provisions whereby the Contractor receives a greater percentage share of the Excess Surplus linked to the achievement of specific over performance standards.

Figures and row references to be inserted by the Contractor at financial close based on the agreed LOBTA or Base Case (whichever is applicable)

Figures and row references to be inserted by the Contractor at financial close based on the agreed LOBTA or Base Case (whichever is applicable)

Figures and row references to be inserted by the Contractor at financial close based on the agreed LOBTA or Base Case (whichever is applicable)

Percentage to be inserted by the Contractor at financial close based on the agreed LOBTA or Base Case (whichever is applicable)

Part A or B to be deleted by the Contractor at financial close based on the agreed LOBTA or Base Case (whichever is applicable). Part A relates to a deficit scheme where an Annual Payment is made to the Contractor and Part B relates to a surplus scheme where a Surplus Annual Payment is made to the Authority

Part A or B to be deleted by the Contractor at financial close based on the agreed LOBTA or Base Case (whichever is applicable). Part A relates to a deficit scheme where an Annual Payment is made to the Contractor and Part B relates to a surplus scheme where a Surplus Annual Payment is made to the Authority

The Authority may require this as an additional obligation where it wishes to ensure compliance with its own discrimination and employment policies and codes of practice.

The new Fair Deal issued in October 2013 states that all private sector entities have the right to participate in the relevant public sector scheme. It is thought that the Pensions Direction 2007 which applies directly to best value authorities will be amended to reflect the new Fair Deal but this has not occurred yet. Whilst the Fair Deal guidance is aimed at central government departments and therefore is not directly applicable to best value authorities and LGPS contracts, the principles reflect what is understood to be good practice for LGPS contracts. Clauses 30.6-30.8 and Schedule 22 are therefore to be used only where there are exceptional circumstances in which it would be appropriate for the Contractor to use a broadly comparable scheme. Requirements relating to bulk transfer provisions were contained in HM Treasury Guidance "Staff Transfers From Central Government: A Fair Deal for Staff Pensions" (June 1999) and HM Treasury Guidance "A Fair Deal for Staff Pensions: Procurement of Bulk Transfer Agreements and Related Issues" (June 2004) but are now set out in "Fair Deal for staff pensions: staff transfer from central government" (October 2013). This Schedule is provided as a specimen only and Authorities are advised to liaise with the Administering Authority of the relevant LGPS fund (where different from the Authority) and its own advisers as early as possible to agree the provisions of the Schedule. The Administering Authority may have a preferred form of Schedule it would prefer to use or may have specific amendments it would wish to make to this specimen Schedule. It may be possible to delete this Schedule if it is not applicable in any particular transaction.

The Actuary's Letter should set out fully and clearly the bulk transfer assumptions and adjustments and be made available to all qualified bidders at the earliest possible stage in the process. The Actuary's Letter should represent a reasonable final position rather than an opening position for further negotiation. Compliant bids should be on the basis that the Contractor's Scheme will accept the bulk transfer terms set out in the Actuary's Letter and any costs or benefits conferred by the acceptance of those terms should be dealt with by way of a price adjustment set out in the bid documentation and supported by a reasoned statement of need. Where there is uncertainty regarding the size of the bulk transfer, for example where large numbers of staff are potentially involved, the historic HM Treasury Guidance "A Fair Deal for Staff Pensions: Procurement of Bulk Transfer Agreements and Related Issues" suggested that bids could be made which are contingent on the size of the bulk transfer value which is eventually calculated. In such cases, it may be necessary to agree a mechanism in the Agreement by which the contract price can be adjusted to reflect the value of the transfer amount which results from the level of take up by staff. The new HM Treasury Guidance "Fair Deal for staff pensions: staff transfer from central government" has not subsequently addressed this point.

This Schedule 22 (Bulk Transfer Terms) is drafted on the assumption that the bulk transfer takes place following a Relevant Transfer Date. The Schedule does not provide for a bulk transfer following a Cessation Date (when the Contractor or the relevant Sub-Contractor ceases to be an Admission Body in the LGPS and provides a broadly comparable pension scheme as an alternative pension provision) because of the uncertain nature of a Cessation Date. If the Authority wishes the Schedule to apply in the event of a Cessation Date when appropriate amendments to the Schedule will be required and consideration will need to be given regarding the open-ended nature of the Actuary's Letter.

Three months is the decision period referred to in HM Treasury Guidance "A Fair Deal for staff pensions and transfer from central government".

The Authority may wish to consider whether it wants to seek to ring-fence any Transfer Amount within the Contractor's Scheme. The Authority should consult with its professional advisers regarding this option.

The form of payment and discount for cash needs to be discussed with the Administering Authority. If this is to be covered in the Actuary's Letter, this clause can be deleted.

It may be necessary to refer to the Actuary's Letter to determine what "actuarial equivalence" means. "Actuarial equivalence" is the term used in HM Treasury Guidance "A Fair Deal for staff pensions:staff transfer from central government".

The exit provisions aim to reflect as far as possible the exit requirements in HM Treasury Guidance "Fair Deal for staff pensions and staff transfer from central government". The Authority should consult with its professional advisers regarding these provisions and the Guidance and the requirements it wishes to impose.

The Authority will need to consider whether, in light of the direction that was provided in the historic HM Treasury Guidance "A Fair Deal for Staff Pensions: Procurement of Bulk Transfer Agreements and Related Issues", it wants the exit provisions to cover the Transferring Members, the Eligible Employees or wider still the Returning Employees who are members of the Contractor's Scheme. The new HM Treasury Guidance "Fair Deal for staff pensions: staff transfer from central government" has not subsequently provided detailed direction on this point in its section on Exit Provisions in Annex B.

HM Treasury indicated that the exit provisions detailed in HM Treasury Guidance "A Fair Deal for Staff Pensions: Procurement of Bulk Transfer Agreements" covered not only Transferring Members but also Eligible Employees who did not transfer their benefits from the LGPS under the initial bulk transfer but did join the Contractor's Scheme for future service only. The Authority should consult with its professional advisers regarding the scope of the employees it wishes to protect under this paragraph.

Bidders to submit proposals for paragraphs 4 and 5 and the table at paragraphs 11 and 12 of this Schedule 23 (Loss of Revenue) based on the agreed LOBTA. A table to be completed for [each/ the] Facility.

If considered more appropriate the following alternative approach (to include the alternative amends proposed in the notes at the end of this Schedule 23 (Loss of Revenue)) could be used.

"The Anticipated Daily Revenue for each activity shall vary between months and is set out in respect of each year of the Contract Period in Appendix A to this Schedule 23 (Loss of Revenue). The Anticipated Daily Revenue rates for [each/ the] Facility shall be calculated by dividing the monthly Revenue for the relevant activity (as set out in Appendix A) by the number of calendar days in the relevant month and shall be Indexed. The Contractor shall not be entitled to recover as a Loss of Revenue, any greater amount than the level of Revenue which it is projected to recover as set out in Appendix A and divided by the relevant number of calendar days." Appendix A – Anticipated Monthly Revenue Rates to be inserted.

The different seasons for different activities should be set out here.

The different seasons for different activities should be set out here.

Authorities may wish to include clarificatory drafting along these lines.

Figure to be inserted by the Contractor at financial close based on the agreed LOBTA if agreed. Bidders will want to be kept in a no better and no worse position in the LOBTA.

Table to be amended to reflect relevant income lines at [the/each] Facility based on the agreed LOBTA.

Table to be amended to reflect relevant income lines at [the/each] Facility based on the agreed LOBTA.

Figure to be inserted by the Contractor at financial close based on the agreed LOBTA if agreed. Bidders will want to be kept in a no better and no worse position in the LOBTA.

Authorities may wish to consider only including certain Parts of this Change Protocol (as amended, if necessary and appropriate) depending on the likely nature/scope of the Changes under their Project. A simple form is included at [Appendix C of this toolkit, published online on Sport England's website: "Drafting Riders aof legal and contractual issues"].

The Catalogue should contain prices for the initial implementation works only and not pricing of an ongoing lifecycle requirement.

This is because a Change may be more straightforward in nature but, due to its volume, be prima facie classed as a High Value Change. It may be more appropriate to agree to deal with it as a Medium Value Change.

As above, a Change may be a very straightforward, but high-volume, Change: it may be more appropriate to deal with it as a Small Value Change. On the other hand, a Medium Value Change might (if particularly complex) merit being processed as a High Value Change.

At the three year reviews the Contractor should review pricing to ensure the rates continue to provide value for money with reference to prices prevailing in the market. The Contractor must produce evidence of value testing of the revised pricing.

Note this is on the basis that costs savings will be applied through the Surplus Share schedule.

Whether the right to partially terminate should be included must be considered and determined on a project specific basis. If such a right is included, the Parties may also wish to include certain "pre-agreed" partial terminations if it is anticipated that a particular Facility may need to be removed from the Agreement. Bidders should be asked to put forward their proposals for the consequences for such pre-agreed partial terminations during the bidding process.

The number of Facilities that may be removed from a project is to be agreed on a project-specific basis.

Whether this schedule will be relevant will depend upon the Contractor's project structure and whether it/another party in its structure is seeking to claim NNDR Relief.

If the Contractor/Leisure Operator is relying on a particular type of entity being established for the project in order for it to achieve a certain level of NNDR Relief that status should be listed here.

Parties to confirm the position agreed at tender stage in relation to NNDR relief. If the Contractor has tendered on and priced on the basis that mandatory and/or discretionary rate relief will be applied, for clarity, this can be captured in paragraph 2.2.2.

These provisions may need to be amended to reflect the processes for making applications for NNDR Relief at the Authority in question.

A suggested form of "bare bones" lease has been included for use with this Agreement. It does not contain substantive separate obligations so as not to conflict with the main Agreement.

# Text boxes

Appendix A: template Design Build Operate and Maintain Contract

Please read the note below before using this template documentation

This template documentation has been produced by Sport England, in consultation with local authorities, leisure operators and leisure, technical and legal advisors in the market to provide assistance to local authorities in the procurement of sports and leisure projects.

The template documentation has been published in good faith by Sport England with the help of its advisors, FMG Consulting and Nabarro LLP, and neither Sport England nor its advisors shall incur any liability for any action or omission arising out of any reliance being placed on the template documentation by any local authority or organisation or other person. Any local authority or organisation or other person in receipt of this template documentation should take their own legal, financial and other relevant professional advice when considering what action (if any) to take in respect of any initiative, proposal, or other involvement with any contractual partnership, or before placing any reliance on anything contained herein.

Drafting notes and footnotes are included within this Agreement to assist with its interpretation. These should be removed prior to completing the Agreement. Please also see the accompanying Procurement Toolkit for more information. Please also:

- Select either Option A or Option B in respect of Schedule 6 (Payment and Performance Monitoring System) prior to issuing this template document; and

- Select either Option A or Option B in respect of Schedule 23 (Loss of Revenue) prior to issuing this template document.

Quarterly PERFORMANCE MONITORING REPORT providing

- Outcomes Report (including Outcomes Scorecard update)

- Other reporting requirement quarterly updates as set out in paragraph 1.19 of the Services Specification

- Help Desk performance summary of performance failures and level of Performance Adjustments calculated in accordance with the Payment and Performance Monitoring System

- Key Performance Indicator assessment to be included as an appendix to the report, providing service and facility performance, utilisation and financial performance. This quarterly assessment is for information only, to be used as a performance monitoring tool to support the process of continuous improvement

Monitored in accordance with the PAYMENT AND PERFORMANCE MONITORING SYSTEM (SCHEDULE 6)

SERVICES SPECIFICATION (SCHEDULE 1) sets out

- Annual Performance Standards (including Authority’s Outcomes)

- Service Performance Standards

- Facility Performance Standards

-      KPIs

Quarterly PERFORMANCE MONITORING REPORT providing

- Outcomes Report (including Outcomes Scorecard update)

- Other reporting requirement quarterly updates as set out in paragraph 1.19 of the Services Specification

- Help Desk performance summary of performance failures

- Key Performance Indicator assessment to be included as an appendix to the report, providing service and facility performance, utilisation and financial performance. This quarterly assessment is for information only, to be used as a performance monitoring tool to support the process of continuous improvement

Monitored in accordance with the PERFORMANCE MONITORING SYSTEM (SCHEDULE 6)

SERVICES SPECIFICATION (SCHEDULE 1) sets out

- Annual Performance Standards (including Authority’s Outcomes)

- Service Performance Standards

- Facility Performance Standards

- KPIs

A utilities benchmark can be carried out no sooner than the date which is [one/two] years after the Commencement Date. Any subsequent benchmarking of utilities can only be carried out again when another [1/2] years have passed since the previous date that the utilities were previously benchmarked.

A benchmark can be called be either the Contractor or the Authority as long as the above timeframes have been observed and that 5 days written notice is given before the Cost Benchmarking Date.

Within 2 months of the Cost Benchmarking Date, whoever requested the benchmark (the Contractor or the Authority) must produce a report (called the Cost Benchmarking Proposal) setting out what it believes the actual cost of utilities has been over the last [1/2] years. The required contents of this report are listed in Para 2.2 of Part 1 of this Schedule (in reality, the Authority will need the Contractor to produce the information for the report however the Authority must meet the Contractor’s costs for this work if it is the Authority that has requested the benchmark).

Only the tariff (price per unit) should be benchmarked. The consumption figures are entirely at the Contractor’s own risk (subject to a once only consumption review at 2 years in respect of a new or substantially refurbished facility) as they can control the amount consumed through their day to day operational management of the [Facility/ Facilities].

To ensure that the consumption figures do not untowardly influence the outcome, reference should be made to the level of utilities that the Contractor predicted that it would consume per Facility for every year of the Agreement as set out in Appendix 1 of Part 1 of this Schedule. These figures shall be reviewed on an annual basis and can be amended in agreement between the Contractor and the Authority if they are found to not be appropriate. An example of why they might be amended is that capital works are undertaken or energy reducing initiatives might mean that the Contractor is consuming much less energy and thus the target consumption levels should be lower. To amend the target consumption levels, the Contractor must provide that it is operating in line with Good Industry Practice. This is not intended to be a mechanism for the Contractor to increase the target consumption levels every year because it has performed poorly in terms of energy conservation.

The consumption figures to be applied (as determined above) should be multiplied by the actual tariff rate that the Contractor is being charged to identify the Actual Utility Cost. The difference between this figure and the predicted cost of the utility as contained in Appendix 1 (the Base Utility Cost), is the Cost Figure.

If the Contractor’s actual consumption levels are higher than the figures it predicted it would consume in Appendix 1, it is the target consumption levels set out in Appendix 1 that should be the consumption figures applied in the calculation of the Cost Figure (and not the actual consumption figures that have turned out to be higher). If the actual consumption figures are lower than the figures it predicted it would consume in Appendix 1, then the lower actual figures are the ones that should be applied to the calculation.

For the avoidance of doubt, it is intention that all four utility types should be benchmarked at the same time and the sum of the four net utility position is added up to work out the overall Cost Figure. This Schedule 18 is worded so that the utility types can be benchmarked separately or on their own if required however this would only be done if both parties agreed. In reality, if one side wanted to benchmark the gas only (for example), the other side has the right to call for a benchmark on the other utility types at the same time (thus resulting in a net position being taken.

Within 1 month of receiving the Cost Benchmarking Proposal, the Contractor and the Authority must meet to discuss the Cost Benchmarking Proposal.

Within 2 months after receipt, the party (Authority or Contractor) that received the report must let the party who requested the benchmark know whether it agrees the contents of the report, specifically the proposed variation to the Annual Payment, contained within the report (called the ‘Cost Figure’). If the two parties cannot agree the proposed variation to the Annual Payment, the Dispute Resolution Procedure contained in the Agreement will apply. It is crucial that the party that receives the report must respond within the 2 month period discussed above. If it fails to do so, the report and the variation to the Annual Payment will automatically be deemed to be accepted.

When the Cost Figure is agreed, the increase or deduction to the Annual Payment is applied and backdated to the date of the benchmark. Where it is a surplus scheme, the Surplus Annual Payment shall be decreased where the Cost Figure is positive or increased where it is negative. Where it is a deficit scheme, the Deficit Annual Payment shall be increased where the Cost Figure is positive or decreased where it is negative.

Once the Actual Utility Cost has been determined as described above, this figure becomes the Base Utility Cost for the next Cost Benchmarking Procedure.

The Authority is within its rights to compel the Contractor to contract with a different utility supplier when the Contractor’s existing contract with its utility supplier expires if the Authority can prove that the utilities can be obtained at a cheaper rate and the contract with the identified supplier is not on any materially more onerous terms. If the Contractor does not wish to contract with this new utility supplier, it must ensure that the cheaper tariff which is available fro the new utility supplier shall be unit cost applied in the next utilities benchmarking process.

[Five] years must have passed since the Commencement Date or the last Income Benchmarking Date. A number of financial triggers must all be passed before the Contractor is entitled to call for a benchmark. These are set out in paragraph 1.1 (c).

If either party is entitled to and wishes to call a Net Income Benchmark, it shall serve written notice within one month of the Net Income Benchmarking Date.

Within two months of informing the other party that it wishes to call a Net Income Benchmark (called the Net Income Benchmarking Date), the Contractor must provide an Income Proposal to the Authority.

The exact details of what is required in the Income Proposal are set out in paragraph 1.3 of Part 2 of this Schedule. In summary, this must contain a detailed breakdown of all income and expenditure over the previous [five] years (called the Tested Period) together with details of any Performance Adjustment Points received under the Performance Monitoring System, all assumptions and the proposed revised Surplus/ Deficit Annual Payment. To note, the cost of utilities, NNDR, [insurance], [Hard FM] (i.e. lifecycle maintenance) and Performance Adjustments payable in accordance with the Payment and Performance Monitoring System should be excluded from the calculations of expenditure that are used in the benchmark. The Contractor has a duty to mitigate losses where possible.

Within two months (unless agreed otherwise by the two parties) after receiving the Income Proposal, the Authority must either:
i) Request more information (to be received within 15 business days and responded to in accordance with ii) or iii) by the Authority within a further 20 business days); or
ii) Accept the Income Proposal and amend the Annual Payment; or
iii) Do not accept the Income Proposal and enter into consultation with the Contractor in good faith for a further 20 business days.

If agreement still cannot be reached following the 20 days consultation, the Authority shall notify the Contractor that it does not accept the Income Proposal and the parties shall appoint a Benchmark Consultant. 
It is important to note that the Authority’s failure to respond within the timescales set out here will mean that the Income Proposal is accepted and the Annual Payment will be adjusted accordingly. Likewise, if the Contractor fails to respond within the timescales, the Annual Payment will not be amended.

The Benchmark Consultant shall be jointly appointed between the two parties and the cost shall be shared. The criteria for who can act as a Benchmark Consultant is included within the definitions in Part 3 of this Schedule.

The Benchmark Consultant shall produce a report within 3 months taking into account the criteria listed in paragraph 2.3 of Part 2 with the end result of benchmarking the income and expenditure on a like for like comparison basis with other similar leisure facilities to recommend what the Net Income Figure or Compensatory Amount should be and therefore the proposed change to the Annual Payment.

Each party has 20 days to agree the Net Income Figure or Compensatory Amount and the resultant new Annual Payment recommended in the Benchmark Report. If either party disagrees, both parties shall negotiate for a further 15 days. If agreement still cannot be reached, both parties have up to 30 days to discuss and agree an amended specification to mitigate the adverse impact of the implementation of the Net Income Figure or Compensatory Amount on the Annual Payment. If agreement still cannot be reached, the final recourse is Dispute Resolution.

Once the Net Income Figure or Compensatory Amount has been agreed, the adjustment shall be made as follows and backdated to the Income Benchmarking Date:

For a surplus scheme;

- X% of the Net Income Figure shall be applied in full to decrease the Annual Payment to the Authority (‘Surplus Payment Decrease’)

- X% of the Compensatory Amount shall be applied in full to increase the Annual Payment to the Authority (‘Compensatory Amount Increase’)

For a deficit scheme;

-X% of the Net Income Figure shall be applied in full to increase the Annual Payment to the Contractor (‘Deficit Payment Increase’)

X% of the Compensatory Amount shall be applied in full to decrease the Annual Payment to the Contractor (‘Compensatory Amount Decrease’)

The Leisure Operator’s Base Trading Account (LOBTA) shall not be amended by the Net Income Figure or Compensatory Amount after the benchmarking process is complete. The figures in the LOBTA remain as originally drafted.