| Meeting | 19 March 2014, The Stadium/Terraces, Sport England, Victoria House, London WC1B 4SE |
| --- | --- |
| Chair Person Members DCMS Chief Executive Sport England Officers Secretariat | Nick Bitel (NB) Kate Bosomworth (KB), Clare Connor (CC), Ian Drake (ID), David Goldstone (DG), Sally Gunnell (SG), Deborah Jevans (DJ), Hanif Malik (HM), Charles Reed (CR), Peter Rowley (PR) & Mark Spelman (MS) Nick Pontefract Jennie Price (JP) Rona Chester (RC), Mike Diaper (MD), Charles Johnston (CJ), Tanya Joseph (TJ), Lisa O’Keefe (LOK), Phil Smith (PS), Simon Macqueen (SM – part only), Greg Clements (GC – part only), Emyr Roberts (ER – part only), Simon Wergan (SW – part only) & Melissa Bennett (MB - part only) Andrew Norman (AN) |

|  | Item | Action |
| --- | --- | --- |

|  | Welcome Apologies There were no apologies. Declarations of Interest ID declared an interest in item 2, Manchester City Council: Waterfall Capital Investment Strategy, arising from British Cycling’s use of the ‘Etihad Campus’. CC declared an interest in item 4, Payment for Results, by virtue of her role as Head of Women’s Cricket at the ECB. DJ also declared an interest in item 4, Payment for Results, by virtue of her position as Chief Executive of England Rugby 2015. Minutes of the Board Meeting on 21 January 2014 The minutes of the Board Meeting on 21 January 2014 were approved as a correct record. Matters Arising from the Board Meeting on 21 January 2014 The Board NOTED the Matters Arising from the Board Meeting held on 21 January 2014 and earlier meetings. It was noted that the Board would receive an update on Sport England’s information strategy, including SPOGO, at the May Board Meeting. It was requested that the High Performing NGB Model be added to the Sport England website as soon as possible. All other actions had been completed, carried forward or dealt with elsewhere on the Board’s agenda. | RC/CJ/ TJ PS |
| --- | --- | --- |
|  | Chief Executive’s Report JP presented her Chief Executive’s Report and highlighted the following matters: Manchester City Council: Waterfall Capital Investment Strategy CJ updated the Board with regard to the operation of the ‘Waterfall’ Fund, which had been set up to utilise the income derived from the rental and naming rights of the City of Manchester Stadium, and the partnership between Sport England and Manchester City Council. Priorities for capital investment had been agreed and would straddle a range of elite sports and community facilities that would consolidate and enhance Manchester’s sports culture in terms of performance and participation. It was reported that Manchester City Council had proposed an extension to the initial 10 year period of borrowing against the fund to 15 years, in order to generate sufficient funds to cover identified shortfalls across the range of projects. The largest of these projects was the Manchester Institute of Health and Performance (‘MIHP’) which was designed to be a multidisciplinary diagnostic, education, research and development organisation. The Board were asked to endorse the extension of the borrowing arrangements. In response to a question from the Board, CJ confirmed his belief that the Institute would be a ‘world class’ facility and that the community would benefit from its establishment. He agreed to circulate details of the community benefit to the Board. The Board APPROVED the proposal as submitted. Women’s Sport & Fitness Foundation (‘WSFF’) It was reported that WSFF had submitted a revised Commercial Business Plan which had been reviewed by both the Head of Equality & Diversity and members of the grants management team. The Plan covered the period 2014-2017 and demonstrated an intention to reduce its reliance on Sport England funding by diversifying its income and delivering operational efficiency savings. The review of the Plan had been positive, particularly on the inclusion of greater detail on what WSFF wished to achieve, how and when. The new leadership team had also demonstrated a commitment to address WSFF’s over-reliance on Sport England funding. Following discussion, the Board AGREED to convert WSFF’s National Partner Funding of £849,605 for 2014-15. Advertising Campaign – ‘Speaking to Women’ JP outlined proposals for Sport England to develop and undertake an advertising campaign aimed at encouraging more women and girls to play sport and to exercise. It would attempt to narrow the significant gender gap in terms of participation in sport. The campaign would draw heavily on the insight and work already undertaken on the Bury Project and would include a simple call to action with narrative and images that could be adapted for every sport, sports facility and sports provider. It was confirmed that the idea had Ministerial interest and support and that Sport England had lottery funds available to finance it. The Board discussed the proposed campaign and agreed that the mere fact that an advertising campaign had Ministerial support indicated the importance with which the subject was viewed. ID commented that there was capacity in the system to accommodate an influx of women and girls and that there should be a focus on areas where the supply was plentiful, such as dance, gym, and swimming. With regard to timing, it was noted that the campaign would not be activated around a major sporting event, but would be launched in the summer months when people were most inclined to be active. In response to a question from HM on the measurement of the success of the campaign, JP highlighted the experience and techniques that had been developed within Sport England from the Bury Project and, more recently, the Youth Review. Full details for the campaign and a firm budget would be submitted to the Board at its May Meeting. Any developments in the meantime would be communicated promptly. Active People Survey (‘APS’) It was noted that the introduction of mobile phone data collection to the design of the APS was proceeding as planned. The Sport England Executive was confident this would progress smoothly, but was monitoring its implementation closely. Youth Review The Insight Forum, chaired by DJ, had held two very useful sessions to help bring together the work being undertaken across the business to deepen the understanding of the changing behaviours, expectations and motivations of young people in relation to sporting activity. The Board would be further updated as to progress at its meeting in May, with a full recommendation being presented at the June meeting. Primary Spaces JP updated the Board on Sport England’s new Lottery Funded capital investment programme ‘Primary Spaces’ which had gone live on 24 February 2014. The budget for the programme totalled around £18m with grants of £30k being made to around 600 primary schools to help establish or enhance their outdoor sporting facilities. The programme was being run along the lines of the highly successful ‘Inspired Facilities’ scheme and had been funded through a commensurate increase in Sport England’s lottery income. Good progress had been made, with awards expected to be finalised by the end of May 2014 and facilities installation beginning in summer 2014. Business Partnerships Update The Board noted the Business Partnerships Update, in particular the extensive coverage received around the six one-year-funded national sports announcement and the launch of the Flood Relief Fund. The Board NOTED the Chief Executive’s report and the updates contained therein. | CJ JP JP |
|  | Chief Operating Officer’s Report RC presented her Chief Operating Officer’s Report and highlighted the following matters: Medium Term Plan and Lottery Cashflow RC briefly summarised the Medium Term Plan projections, the lottery cashflow numbers and Sport England’s performance against its cost targets. HM asked whether there had been any impact on revenue following the introduction of the £2 lottery ticket. RC commented that it was too early to reach any firm conclusions. PR noted that Sport England had missed its 8.0% lottery cost target and asked if there were any sanctions for this. JP commented that missing by 0.7% was within acceptable boundaries, but that the business remained focussed on controlling costs. 2014/15 Business Plan The 2014/15 Sport England Business Plan was submitted and reviewed. The Plan described the priorities for the year, as well as key activities to be undertaken, the resources available and desired outcomes. Following discussion, The Board APPROVED the 2014/15 Business Plan. 2014/15 Financial Budget The Exchequer and Lottery budgets for 2014/15, together with detail of the budgeting process and a review of the key issues involved, was submitted and reviewed. It was noted that significant time had been spent driving down costs to meet operational targets. Following discussion, the Board APPROVED the 2014/15 Financial Budget. Defined Benefit Pension Plan - Funding RC outlined the progress made in negotiations with the London Pension Fund Authority (‘LPFA’) regarding the basis of valuation of Sport England’s defined benefit pension fund and reported that the LPFA had agreed to revert back to an ‘ongoing basis’. This significantly decreased the deficit payments required over the next three years and took into account the sums paid up to 31 March 2014. It was AGREED that a detailed paper would be presented to the Audit, Risk and Governance Committee for approval of the annual payments involved. Management Accounts as at 31 January 2014 RC summarised the key issues highlighted in the most recent management accounts: The projected under-spend had fallen to £0.55m, however a number of projects were still in progress and all was expected to be spent by 31 March 2014; After including unanticipated deductions from the NLDF sanctioned by the Gambling Commission, the revised income projection from DCMS for 2013/14 was £217.0m. Lottery income for January was higher at £24.3m. Administration costs were forecast to exceed full year budget by £0.5m. Unbudgeted costs had arisen from the move to new offices at 21 Bloomsbury Street (£0.5m), higher than expected recruitment fees due to increased staff turnover (£0.1m), relocatable pools expenditure of (£0.2m) and a small increase in T&S costs (£0.1m) mainly due to the number of staff now working from home. These costs had been partially offset by the release of a £0.5m contingency. Project Committee Minutes The minutes of the Project Committee Meeting held on 20 January 2014 were submitted and noted. The Board noted the COO Report and the updates contained therein. | RC |
|  | SM & GC joined the meeting. |  |
| a | Payment for Results (‘PfR’) – Review of NGB Performance PS presented a paper detailing Sport England’s PfR recommendations for those NGBs that had failed to achieve one or more of their Whole Sport Plan strategic outcomes in 2013-14. It was noted that this was the first time that Sport England had proposed to de-commit funding in the current funding cycle. A systematic review of NGB performance had taken place and the recommendations submitted were the culmination of a 12 month process. It was further noted that core funding was not subject to PfR and that only up to 20% of the amount relating to each failed outcome was subject to potential decommitment. PS emphasised that the process had been open and proactive with each affected NGB being given several opportunities to discuss the strategic outcome failures and address the specific areas raised by Sport England. Sport England had sought to present a consistent approach that reflected the scale of failure and the level of engagement from each affected NGB. The recommendations were aimed at achieving PfR’s objectives of: demonstrating that Sport England was an intelligent investor and ensuring the responsible use of public money; identifying where public funds were not having the desired impact and finding new routes to support community sport; and creating a fair, transparent performance management system which penalised poor performers, stimulated the ‘flat-lining’ middle and rewarded the high performers for the benefit of grassroots sport PS, SM and GC then briefly summarised the PfR recommendations for each of the 13 NGBs that had failed to achieve one or more strategic outcome targets for 2013-14: UK Athletics (‘UKA’) & England Athletics (‘EA’) The decision around athletics was a complicated one. UKA/EA had missed their track & field, running 16-25 and running 26+ outcomes despite the upward trend in the running market. Both NGBs had responded appropriately during the process, but they still needed to prove their capability to capitalise on the growth in the running market. While athletics was seen as a potential candidate for a mixed economy approach, EA’s efforts in establishing its ‘Run Group’ and the acknowledgement that a strategy for running (rather than track and field) was required, meant that Sport England Officers recommended no de-commitment of funds at this stage. ID commented that, having attended the Panel presentation from UKA/EA, the respective NGBs appeared to need more understanding of the size and scale of the challenge facing them. Following discussion, the Board CONFIRMED the recommendation not to de-commit funds from UKA/EA. Badminton England (‘BE’) BE had missed its 14-25 participation outcome by 25%, but had fairly accurately predicted this reduction at the start of the process and had subsequently undertaken a restructuring of its organisation to facilitate a better focus on participation. New programmes targeting the informal market had been introduced and BE had fully engaged with Sport England Officers to understand the changes suggested to its approach and model for delivery. It was recommended that no de-commitment be made at this stage, but that the NGB be put ‘on notice’ that a 20% funding de-commitment from the final 2 years of 14-25 investment could be imposed in future, dependent on the December 2014 APS target being met. Following discussion, the Board CONFIRMED its agreement to the recommendation as submitted. CC withdrew from the Meeting for the next item. England and Wales Cricket Board (‘ECB’) The decline in participation numbers for cricket that was revealed by APS7 came as a surprise to everyone, including the ECB and Sport England. The poor summer of 2012 had contributed to a decline in that year, but the summer of 2013 had provided ideal playing conditions. It was noted that the ECB had responded to the numbers with appropriate vigour and was using its growing insight capability to find answers. This positive response and the good work being done by ECB in its programmes had prompted Sport England officers to recommend that no de-commitment be made at this stage, but that they be put on notice that a 20% funding de-commitment from the final 2 years of 14-25 and 26+ investment could be imposed dependent on the December 2014 APS target being met. HM commented that the ECB might be ‘missing a trick’ in concentrating too much on the traditional formats of the game and not looking to develop a more innovative and flexible approach. Following discussion, the Board CONFIRMED its agreement to the recommendation as submitted. CC rejoined the meeting British Equestrian Federation (‘BEF’) The BEF had missed its 26+ participation outcome by 10% and this, despite an improvement since the June 2013 APS, maintained a downward trend. Equestrianism was seen as particularly important in the delivery of Sport England’s outcomes due to the high proportion of female participants and its strong appeal to disabled participants. The BEF had improved its understanding of its role and position in the market and improved its insight capability, but the nature of the general ‘horse riding community’ meant that much of the activity in the sport remained beyond its control. Sport England officers recommended no de-commitment at this time, but recommended that the BEF trial a different delivery model using 20% of their remaining 26+ participation money to be invested directly in the British Horse Society. Following discussion, the Board CONFIRMED its agreement to the recommendation as submitted. The Football Association (‘FA’) The December 2013 APS numbers were the third consecutive set of disappointing results for football. The 14-25 outcome was missed by 14% and the 26+ outcome by 16%. The scale of the most recent reductions came as a surprise to the FA and Sport England alike and was viewed with concern. Football was the country’s largest team sport and therefore of strategic importance to Sport England. Although the FA had concluded that its strategy was sufficient to reverse the trend, Sport England remained unconvinced the programmes in place had the scale or the reach to achieve this. Sport England officers therefore recommended a 10% de-commitment (£1,594,085) of the total revenue remaining to the 14-25 and 26+ outcomes. PR commented that, having sat in on the FA’s panel presentation, he remained unconvinced that the FA recognised the pressure to deliver. ID queried as to whether a de-commitment would be seen as sending mixed messages following the £6m awarded to the football skills programme. PS believed that this could easily be explained as the two programmes were pursuing differing aims. The fact that de-committed funds would remain within football should be emphasised strongly when the decision was communicated. The Board CONFIRMED its agreement to the recommendation as submitted. England Golf Partnership (‘EGP’) EGP missed its 26+ outcome by 12% despite the dry summer period, a continuation of the steady decline in participation seen over recent years. While some progress was being made, especially in shortened formats of the game such as pitch and putt and par three, the golfing authorities remained largely unable to tackle the challenges affecting the sport. The time demanded by the traditional format of the game together with the unenlightened approach of many clubs was driving away participants. Sport England officers recommended a de-commitment of 10% (£495,652) of the remaining investment available to the 26+ participation outcome. Following discussion, the Board CONFIRMED its agreement to the recommendation as submitted. England Hockey Board (‘EHB’) The EHB missed its 14-25 strategic outcome by the considerable margin of 32%. The 14-25 age group was a strategically crucial one for the future of any sport and a decline of such magnitude, although explicable to some extent by bad weather in the winter of 2012/13, was concerning. The EHB had responded positively to the PfR process and was committed to a participation agenda and this had prompted Sport England officers to recommend only a 5% de-commitment (£137,201) from the remaining investment available to the 14-25 participation outcome. Following discussion, the Board CONFIRMED its agreement to the recommendation as submitted. British Mountaineering Council (‘BMC’) The BMC had missed its 16-25 strategic outcome by 45% and its 26+ strategic outcome by 13%. Whilst these declines were of concern, the BMC’s proxy measures of monthly activity suggested a healthy market. The BMC had engaged positively with the PfR process, had credible market insight and had recently hired three regional managers to help improve the coordination of its strategy. However, given the scale of the failure, a de-commitment was felt necessary and Sport England Officers recommended a 5% (£96,508) de-commitment from the remaining investment available to the 14-25 and 26+ participation outcomes. In response to a question as to whether 5% was too little, PS commented on the small size of the overall investment and the positive response of the BMC to the process. Following discussion, the Board CONFIRMED its agreement to the recommendation as submitted. England Netball (‘EN’) EN had also missed its 14-25 strategic outcome by a significant 38%, although all the factors contributing to the failure had yet to be clarified. EN’s excellent track record and understanding of its market needed to be recognised, however the scale of the failure required some action. Rather than de-commit revenue funding, Sport England officers recommended a 3.8% de-commitment of capital funding (£275,000) with a further 10% funding de-commitment dependent on the December 2014 APS target being met. Following discussion, the Board CONFIRMED its agreement to the recommendation as submitted. British Rowing (‘BR’) BR had missed its 14-25 outcome by 26% and 26+ outcome by 20%. Weather conditions affecting outdoor rowing offered some mitigation, but did not explain the fall in indoor rowing numbers. BR remained an organisation that was not maximising the sport’s potential, despite the significant investment it was receiving. The recent change in CEO offered an opportunity to make changes and Sport England officers believed that a 5% de-commitment (£235,611) from the remaining investment available to the 14-25 and 26+ participation outcomes. Following discussion, the Board CONFIRMED its agreement to the recommendation as submitted. DJ withdrew from the Meeting for the next item. Rugby Football Union (‘RFU’) The RFU missed its 14-25 outcome by 12% and 26+ outcome by 19%. However, the RFU was not lacking either in focus, nor determination, to drive participation. APS targets had been published both within their corporate plan and in the Rugby World Cup legacy plans and the organisation had undertaken an extensive restructuring over the past two years. The RFU was therefore doing all the right things, but needed to see this translated into improved APS numbers. Sport England officers therefore recommended no immediate de-commitment, but to put the RFU on notice that a 20% funding de-commitment could be made, dependent on the December 2014 APS results. The Board discussed the proposed course of action and AGREED that, in light of the RFU’s strong performance and willingness to embrace change, the on notice indication should be 10% rather than the proposed 20%. DJ rejoined the Meeting. British Shooting (‘BS’) While BS missed its disability outcome by 38%, it was noted that BS had only been created in March 2011 and its plans for disability participation were only a year old. It had not experienced the previous funding cycle and much of its efforts had been committed to establishing a robust governance structure and recruiting a small team of staff. Given these factors and the fact that BS had already reacted positively to the missed targets, Sport England officers recommended no de-commitment at this stage, although they should be put on notice of a 20% (£22,000) funding de-commitment dependent on the December 2014 APS target being met. Following discussion, the Board CONFIRMED its agreement to the recommendation as submitted. Volleyball England (‘VE’) There had been significant organisational change within VE over the previous 12 months, including a new talent team, much initiated at the behest of Sport England. Therefore, although VE missed three of its five talent strategic outcomes, Sport England officers recommended no de-commitment at this stage. Following discussion, the Board CONFIRMED its agreement to the recommendation as submitted. |  |
|  | SM & GC left the meeting. MB, ER and SW joined the meeting for the next item. |  |
|  | Talent Strategy PS introduced the team behind Sport England’s Talent Strategy and invited them to present their strategic framework for talent investment and a work programme through to 2017. It was reported that within the overall Sport England Strategy, the development of talent was a key strategic outcome. Of the 46 NGBs in receipt of Whole Sport Plan funding for the 2013-17 cycle, 43 had been allocated funding for talent, totalling £76.3m. The Plan called for ‘a minimum of 30 sports to have enhanced England Talent Pathways to ensure that young people and others fulfil their potential’. The Talent Strategy sought a sharper definition of Sport England’s talent aims, objectives and rationale to enable a clearer external position, particularly in relation to NGBs and UK Sport. The Board noted a schematic representation of the proposed Talent Strategy which laid out the vision, mission, objectives, strategies and tactics (‘VMOST’) involved. It was emphasised that, while continued medal success at future Olympic and Paralympic Games and improved performances of English athletes at Commonwealth Games and other competitions continued to be important, Sport England’s investment in NGB talent pathways was not only about preparing and developing future Olympic, Paralympic and international medallists. Sport England’s talent investment provided NGBs with a real opportunity to build an effective and sustainable talent system with an emphasis on creating inspiring environments and providing a high quality talent workforce to support as broad and diverse a talent pool as possible. Sport England’s investment should aim to produce broader access, equality of opportunity and a more inclusive talent pathway for a greater number of athletes in a wide range of sports. The Board discussed the Talent Strategy as submitted and agreed that talent investment had been a massive success for Sport England over recent years. While not receiving the public acknowledgement that UK Sport’s elite focussed approach received, Sport England’s Talent Strategy attempted to do more than just prepare athletes and teams for success on the world stage. It sought to integrate a talent system into the existing sporting landscape and ensure that all athletes and players had the opportunity to fulfil their potential and develop a sporting habit for life. The Board ENDORSED Sport England’s Talent Strategy. Talented Athlete Scholarship Scheme (‘TASS’) A paper seeking Board approval for Sport England to invest in TASS from October 2014 as an integral part of its Talent Strategy was submitted and reviewed. It was noted that TASS had made a significant contribution towards supporting NGB talent and performance efforts in recent years, but that its funding from UK Sport had been declining and would cease from September 2014. It was believed that UK Sport’s focus on elite programmes meant that TASS was better supported at a home country level. It was proposed that Sport England invest a sum of around £2m per year for the next three years to allow TASS to continue to operate with a number of core sports where it was firmly embedded in the England Talent Pathway. The Board discussed the proposed investment in TASS and the potential for branding the subsequent activity as a Sport England project. It was AGREED to support the proposal and that the precise level of funding be delegated to Project Committee. Sport England would revert to the Board with ideas for branding TASS activity with a view to raising the profile of the organisation’s talent strategy. | PS |
|  | MB, ER and SW left the meeting. |  |
|  | Inclusive Sport Funding Programme – Round 2 LOK updated the Board on the applications submitted to Round 2 of the Inclusive Sport Funding Programme. It was noted that Round 2 had attracted 217 applications requesting grants totalling £42.2m. It was further noted that the Inclusive Sport budget for 2013-14 was £7.0m, with a further £1.5m budgeted for 2014-15. Project Committee recommended that the budget for 2013-14 of £7.0m be increased to £8,060,784, by bringing forward £1,060,784 of 2014-15’s budget, and that this amount be allocated to 44 applications approved in the assessment process. The Board APPROVED the Project Committee recommendations. |  |
|  | DJ left the meeting. |  |
|  | Ratification of Project Committee Recommendations MD reported that following the Project Committee held on 18 March 2014, two recommendations from that Committee required ratification by the main Board: School Games – Transfer of Funds to Ecorys It was recommended that the Board approve an award to Ecorys of £10,710,000 for the April 2014 payments to 450 School Games Organisers via hosts. Hosts would receive a payment of £23,800 for each School Games Organiser. Youth Sport Trust – School Sport Award It was recommended that the Board approve the conversion of an in principle award of £3,000,000 to the Youth Sport Trust to deliver their 2014-15 school sport programme, into a full award. In addition, to award a lottery grant of £155,000 for development support to schools in relation to the Primary Spaces Fund. DG, Chairman of the Project Committee, briefly summarised the Committee’s discussions on the subject and endorsed the recommendations. The Board RATIFIED the Project Committee’s recommendations. |  |
| 8. | Sport England Governance Statement JP reported that the preparation of Sport England’s 2013-14 Governance Statement was underway and that a draft would be reviewed by the Audit, Risk and Governance Committee at its April meeting, before being presented to the Board in May. It was noted that the Governance Statement was included within the Annual Report & Accounts and was the crucial document in laying out the structure and governance of Sport England. A copy of the 2012-13 Statement was included for reference purposes. |  |
| 9. | Equality and Diversity Update RC and HM reported on the work of Sport England’s Equality Group, which provided advice and reports to the Executive on the formulation and operation the organisation’s equality and diversity work. The Group met at least four times per year and reported to the main Board via HM. Sport England aimed to ensure that equality ran through everything it did as an employer and that it was a truly inclusive organisation. In January 2013 Sport England had achieved the Intermediate Level of the UK Equality Standard. It was with some concern therefore, that the results of the 2013 Investors in Diversity Survey were received, which had indicated some concerns around fairness and some incidents of inappropriate behaviour. The Executive had thoroughly reviewed the results of the survey and the comments that were included and taken action to change behaviour and learn lessons from it. Further work was required and was being given a high priority. Updates would be provided to the Board as progress was made. | RC/JP |
| 10. | Any Other Business There was no further business and the Chairman declared the meeting closed. |  |
|  | The Meeting finished at 14.49 |  |

# Text boxes

Main Board Meeting Minutes